## Documents
Project Title & Location: |  |  |  |  | Test Title
Project Review Phase: |  |  |  |  | Reconnaissance Level Alternatives & AFB Parametric Estimates
Project Report Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
[5 empty] | KEY DOCUMENTS SUPPORTING ATR AND COMMENTS | COMMENTS
ER 1105-2-100, Planning Guidance Notebook.
ER 1110-2-1150, Engineering and Design for Civil Works Projects.
ER 1110-1-1300, Cost Engineering Policy and General Requirements.
ER 1110-2-1302, Civil Works Cost Engineering.
EM 1110-2-1304, Civil Works Construction Cost Index System (CWCCIS).
ETL 1110-2-573, Construction Cost Estimating Guide for Civil Works.
EC 1105-2-410, Review of Decision Documents.
Cost Dx Website: http://www.nww.usace.army.mil/html/OFFICES/Ed/C/csra.asp
Y | N | N/P | N/A |  | REVIEW CATEGORIES
|  |  |  | DOC | DOCUMENTS PROVIDED FOR ATR
|  |  |  | DOC 1 | Report: As a minimum, the Main Report, the Engineering Appendix, Cost Appendix.
|  |  |  | DOC 2 | Scoping documents such as drawings, presentations, photos for each alternative under serious study.
|  |  |  | DOC 3 | Record of DQC - District Quality Control form.
|  |  |  | DOC 4 | Quantity Take-offs.
N/P | not provided
N/A | not applicable

## Estimate
Project Title & Location: |  |  |  |  | Test Title
Project Review Phase: |  |  |  |  | Reconnaissance Level & AFB Parametric Estimates
Project Report Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES | COMMENTS
|  |  |  | NOTE | PROJECT NOTES - (General Construction Details and Narrative)
|  |  |  | NOTE | Basis of Cost Estimate Notes
|  |  |  | NOTE 1 | Project notes provide a clear presentation of the alternative and scope.
|  |  |  | NOTE 2 | Estimate products clearly depict author and estimate date.
|  |  |  | NOTE 3 | Each alternative is dated to the same point in time and date.
|  |  |  | NOTE 4 | Notes and element titles are adequate to convey project scope and estimate assumptions.
|  |  |  | NOTE 5 | Costs include any potential Hazardous, Toxic, and Radioactive Waste (HTRW) concerns.
|  |  |  | NOTE 6 | Cost Basis notes provided for significant project costs (>1% of construction value)
|  |  |  | EST | GENERAL ESTIMATE LAYOUT
|  |  |  | EST 1 | Alternative estimates developed in accordance with guidelines established in ETL 1110-2-573.
|  |  |  | EST 2 | The alternative estimates reflect a reasonable consistency in development related to estimate software, methodolgy, assumptions, processes and cost date.
|  |  |  | EST 3 | WBS adequately reflects all project scope and makes distinction of major construction elements.
|  |  |  | EST 4 | Major Folder quantity units and unit prices appear reasonable.
|  |  |  | EST 5 | Unit priced titles clearly indicate the scope of the unit price (labor, equipment, materials, delivery, mobilization, sub and prime contractor, haul, placement, discposal, etc.)
|  |  |  | EST 6 | Major construction features supported by quantity take-offs and appear reasonable.
|  |  |  | EST 7 | Total mobilization and demobilization costs applied and reasonable.
|  |  |  | EST 8 | Overuse of Cost Book unit prices for critical cost items that could undermine the total cost accuracy.
|  |  |  | EST 9 | Overuse of Lump Sum, Each or Allowance items that do not accurately convey scope or pricing.
Construction Estimate Details - Class 4 Estimate Data
|  |  |  | EST 11 | Current labor database used that match the location where the work is occurring.
|  |  |  | EST 12 | Current equipment manual and fuel prices utilized.
|  |  |  | EST 13 | Adequate crews and productivities that reflect the work being performed.
|  |  |  | EST 14 | Unit prices appear reasonable based on crew assembly and productivity.
|  |  |  | EST 15 | Clarification of unit price and what it includes: direct & indirect costs, sub and prime contractors, markups.
|  |  |  | EST 16 | Markups appear reasonable.
|  |  |  | EST 17 | Handling methods adequately considered related to demolition or excavation, load and transport, placement or disposal.
|  |  |  | EST 18 | Earthwork quantities make reasonable adjustments between BCY, LCY and ECY.
Parametric or Unit Priced Items - Class 5 Estimate Data
|  |  |  | EST 19 | Unit prices appear reasonable based upon the element title.
|  |  |  | EST 20 | Major cost elements include note of cost bases, such as historical, trends, bid data, etc.
|  |  |  | EST 21 | Handling methods adequately considered related to demolition or excavation, load and transport, placement or disposal.
|  |  |  | EST 22 | Earthwork quantities make reasonable adjustments between BCY, LCY and ECY.
|  |  |  | EST 23 | Cost basis provided for special systems and equipment such as pumping stations, navlock gates, etc.
|  |  |  | EST 24 | Dredging – Unit price appears reasonable based on historical costs, locale, type of dredge, fuel prices, productivity.
|  |  |  | EST 25 | Cost basis provided for estimated allowances.
|  |  |  | MAT | Materials
|  |  |  | MAT 1 | Major quantities supported by a quantity take-off document.
|  |  |  | MAT 2 | Estimate correctly includes State Sales Tax or Gross Receipts Tax to materials and supplies purchased for the contract.
|  |  |  | MAT 3 | Line item note description for material purchase indicates if shipping is included for major items.

## Schedule
Project Title & Location: |  |  |  |  | Test Title
Project Review Phase: |  |  |  |  | Reconnaissance Level & AFB Parametric Estimates
Project Report Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES | COMMENTS
SCHEDULES
|  |  |  | SCH | Construction Schedule
|  |  |  | SCH 1 | Construction schedule adequate to reflect the estimate of each alternative.
|  |  |  | SCH 2 | Schedule used to establish constant dollar basis as needed.
|  |  |  | SCH 3 | Construction schedule used to calculate the construction escalation based on current OMB rates.

## Contingency
Project Title & Location: |  |  |  |  | Test Title
Project Review Phase: |  |  |  |  | Reconnaissance Level & AFB Parametric Estimates
Project Report Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES | COMMENTS
RISK-BASED CONTINGENCY
|  |  |  | CONT | Contingency Value
|  |  |  | CONT 1 | Contingency values reasonable for each alternative.
|  |  |  | CONT 2 | Contingency development basis provided for determining values.
|  |  |  | CONT 3 | Considers other factors other than just technical design and construction.
|  |  |  | CONT 4 | Considers external risk potentials.

## AFB - TPCS
Project Title & Location: |  |  |  |  | Test Title
Project Review Phase: |  |  |  |  | Reconnaissance Level & AFB Parametric Estimates
Project Report Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES | COMMENTS
|  |  |  | TPCS | PROJECT COST SUMMARY in Current Dollars (first column set)
|  |  |  | TPCS 1 | Price level date shown is consistent with the estimate preparation date.
|  |  |  | TPCS 2 | All project-related Civil Works WBS Features depicted.
|  |  |  | TPCS 3 | Base costs reflects the esitmate development in current dollars.
|  |  |  | TPCS 4 | Costs reasonable for PED (30 Feature). Note: percentages are sometimes used to develop these costs.
|  |  |  | TPCS 5 | Costs reasonable for Construction Management (31 Feature Code). Note: percentages are sometimes used to develop these costs.
|  |  |  | TPCS 6 | Contingency application reasonable for each alternative.

## Reports
Project Title & Location: |  |  |  |  | Test Title
Project Review Phase: |  |  |  |  | Reconnaissance Level & AFB Parametric Estimates
Project Report Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES | COMMENTS
REPORTS - Basic Information for Reviewer – Scope and Form
|  |  |  | MR | Draft Main Report, General
|  |  |  | MR 1 | Complete report document provided for ATR. As a minimum: Main Report, Engineering Appendix, Cost Appendix, cost tables and project schedule.
|  |  |  | MR 2 | Package meets the requirements within ER 1105-2-100, Exhibit G of the Planning Guidance Notebook?
|  |  |  | MR 3 | Presents the various estimate scopes, technical/design data, method of construction, and assumptions used for developing the comparative estimates included and described (ER 1110-2-1302).
|  |  |  | MR 4 | Comparative cost estimates developed at the same price level.
|  |  |  | MR 5 | TPC of each comparative estimate accurately used in the economic analysis comparisons, such as costs and benefits at the same price level (ER 1105-2-100).