## Input %
DISTRICT | NPD North Pacific Division
PROJECT NAME | Project X Major Rehabilitation
PROJECT NUMBER | P2 311759
PROJECT LOCATION | Somewhere WA
PROGRAM YEAR | 2015
DATE TPCS PREPARED | 2014-04-02
ENGINEERING REPORT AS BASIS | Project X Major Rehabilitation Report June 2014
ENGINEERING & DESIGN PHASE -> 30 ACCOUNT |  |  | Overide
PROJECT MANAGER, xxx | Program Management: | 2.5% | 2.5% | 30 | 23% | Sum per % of 30 Account
CHIEF, DPM, xxx |  |  |  | 30
CHIEF, PLANNING,xxx | Planning & Environmental Compliance: | 1% | 2% | 30
CHIEF, ENGINEERING, xxx | Engineering & Design: | 15% | 8.5% | 30
CHIEF, COST ENGINEERING, xxx
CHIEF, ENGINEERING, xxx | Reviews, ATRs, IEPRs, VE: | 1% | 0.5% | 30
| Life Cycle Updates (cost, schedule, risks): | 1% | 0.5% | 30
CHIEF, CONTRACTING,xxx | Contracting & Reprographics: | 1% | 2% | 30
CHIEF, ENGINEERING, xxx | Engineering During Construction: | 3% | 3% | 30 |  | Escalate to Mid Point Construction
CHIEF, PLANNING,xxx | Planning During Construction | 2% | 2% | 30
CHIEF, OPERATIONS, xxx | Project Operation: | 1% | 2% | 30
CONSTRUCTION PHASE -> 31 ACCOUNT
CHIEF, CONSTRUCTION, xxx | Supervision & Assurance: | 10% | 10% | 31 | 14.5% | Sum per % of 31 Account
CHIEF, OPERATIONS, xxx | Project Operation: | 2% | 2% | 30
CHIEF, DPM, xxx | Program Management: | 2.5% | 2.5% | 31
[5 empty] | 37.5% | Sum per % of 30 & 31 Accounts
REAL ESTATE -> 01 ACCOUNT
CHIEF, REAL ESTATE, xxx
CULTURAL RESOURCES -> 18 ACCOUNT
CHIEF, PLANNING,xxx
SPENT THRU FYXX COSTS
CHIEF, PM-PB, xxxx
1980-10-01 | 1981 | 1981Q1
1981-10-01 | 1982 | 1982Q1
1982-10-01 | 1983 | 1983Q1
1983-10-01 | 1984 | 1984Q1
1984-10-01 | 1985 | 1985Q1
1985-10-01 | 1986 | 1986Q1
1986-10-01 | 1987 | 1987Q1
1987-10-01 | 1988 | 1988Q1
1988-10-01 | 1989 | 1989Q1
1989-10-01 | 1990 | 1990Q1
1990-10-01 | 1991 | 1991Q1
1991-10-01 | 1992 | 1992Q1
1992-10-01 | 1993 | 1993Q1
1993-10-01 | 1994 | 1994Q1
1994-10-01 | 1995 | 1995Q1
1995-10-01 | 1996 | 1996Q1
1996-10-01 | 1997 | 1997Q1
1997-10-01 | 1998 | 1998Q1
1998-10-01 | 1999 | 1999Q1
1999-10-01 | 2000 | 2000Q1
2000-10-01 | 2001 | 2001Q1
2001-10-01 | 2002 | 2002Q1
2002-10-01 | 2003 | 2003Q1
2003-10-01 | 2004 | 2004Q1
2004-10-01 | 2005 | 2005Q1
2005-10-01 | 2006 | 2006Q1
2006-10-01 | 2007 | 2007Q1
2007-10-01 | 2008 | 2008Q1
2008-10-01 | 2009 | 2009Q1
2009-10-01 | 2010 | 2010Q1
2010-10-01 | 2011 | 2011Q1
2011-10-01 | 2012 | 2012Q1
2012-10-01 | 2013 | 2013Q1
2013-10-01 | 2014 | 2014Q1
2014-10-01 | 2015 | 2015Q1
2015-10-01 | 2016 | 2016Q1
2016-10-01 | 2017 | 2017Q1
2017-10-01 | 2018 | 2018Q1
2018-10-01 | 2019 | 2019Q1
2019-10-01 | 2020 | 2020Q1
2020-10-01 | 2021 | 2021Q1
2021-10-01 | 2022 | 2022Q1
2022-10-01 | 2023 | 2023Q1
2023-10-01 | 2024 | 2024Q1
2024-10-01 | 2025 | 2025Q1
2025-10-01 | 2026 | 2026Q1
2026-10-01 | 2027 | 2027Q1
2027-10-01 | 2028 | 2028Q1
2028-10-01 | 2029 | 2029Q1
2029-10-01 | 2030 | 2030Q1
2030-10-01 | 2031 | 2031Q1
2031-10-01 | 2032 | 2032Q1
2032-10-01 | 2033 | 2033Q1
2033-10-01 | 2034 | 2034Q1
2034-10-01 | 2035 | 2035Q1
2035-10-01 | 2036 | 2036Q1
2036-10-01 | 2037 | 2037Q1
2037-10-01 | 2038 | 2038Q1
2038-10-01 | 2039 | 2039Q1
2039-10-01 | 2040 | 2040Q1
2040-10-01 | 2041 | 2041Q1
2041-10-01 | 2042 | 2042Q1
2042-10-01 | 2043 | 2043Q1
2043-10-01 | 2044 | 2044Q1
2044-10-01 | 2045 | 2045Q1
2045-10-01 | 2046 | 2046Q1
2046-10-01 | 2047 | 2047Q1
2047-10-01 | 2048 | 2048Q1
2048-10-01 | 2049 | 2049Q1
2049-10-01 | 2050 | 2050Q1
2050-10-01 | 2051 | 2051Q1
2051-10-01 | 2052 | 2052Q1
2052-10-01 | 2053 | 2053Q1
2053-10-01 | 2054 | 2054Q1
2054-10-01 | 2055 | 2055Q1
2055-10-01 | 2056 | 2056Q1
2056-10-01 | 2057 | 2057Q1
2057-10-01 | 2058 | 2058Q1
2058-10-01 | 2059 | 2059Q1
2059-10-01 | 2060 | 2060Q1
2060-10-01 | 2061 | 2061Q1
2061-10-01 | 2062 | 2062Q1
2062-10-01 | 2063 | 2063Q1
2063-10-01 | 2064 | 2064Q1
2064-10-01 | 2065 | 2065Q1
2065-10-01 | 2066 | 2066Q1
2066-10-01 | 2067 | 2067Q1
2067-10-01 | 2068 | 2068Q1
2068-10-01 | 2069 | 2069Q1
2069-10-01 | 2070 | 2070Q1
2070-10-01 | 2071 | 2071Q1
2071-10-01 | 2072 | 2072Q1
2072-10-01 | 2073 | 2073Q1
2073-10-01 | 2074 | 2074Q1
2074-10-01 | 2075 | 2075Q1
2075-10-01 | 2076 | 2076Q1
2076-10-01 | 2077 | 2077Q1
2077-10-01 | 2078 | 2078Q1
2078-10-01 | 2079 | 2079Q1
2079-10-01 | 2080 | 2080Q1
2080-10-01 | 2081 | 2081Q1
2081-10-01 | 2082 | 2082Q1
2082-10-01 | 2083 | 2083Q1
2083-10-01 | 2084 | 2084Q1
2084-10-01 | 2085 | 2085Q1
2085-10-01 | 2086 | 2086Q1
2086-10-01 | 2087 | 2087Q1
2087-10-01 | 2088 | 2088Q1
2088-10-01 | 2089 | 2089Q1
2089-10-01 | 2090 | 2090Q1
2090-10-01 | 2091 | 2091Q1
2091-10-01 | 2092 | 2092Q1
2092-10-01 | 2093 | 2093Q1
2093-10-01 | 2094 | 2094Q1
2094-10-01 | 2095 | 2095Q1
2095-10-01 | 2096 | 2096Q1
2096-10-01 | 2097 | 2097Q1
2097-10-01 | 2098 | 2098Q1
2098-10-01 | 2099 | 2099Q1
2099-10-01 | 2100 | 2100Q1
2100-10-01 | 2101 | 2101Q1

## TPCS
|  | Legend |  | Represents Formula's | 0 | Cell Entry | [19 empty] | 0 |  | 2438 | 2438 | Check
Schedule
Estimate PL INDEX | Prog Year Index | MidPoint Index | Time Period | CWCCIS CAT USED |  | Quarter
Column to check for math errors ( Adds up three ways.)
[8 empty] | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | Numbers show up three times
[8 empty] | 1: PROJECT:; 2: Project X Major Rehabilitation; 13: DISTRICT:; 14: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 1: PROJECT NO:; 2: P2 311759 | POC: | CHIEF, COST ENGINEERING, xxx
[9 empty] | LOCATION: | Somewhere WA
[9 empty] | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
[8 empty] | 1: Civil Works Work Breakdown Structure; 3: ESTIMATED COST; 8: PROJECT FIRST COST (Constant Dollar Basis) | TOTAL PROJECT COST (FULLY FUNDED)
[19 empty] | Program Year (Budget EC): |  | 2015
[19 empty] | Effective Price Level Date: |  | 1 OCT 14
[21 empty] | Spent Thru: | TOTAL FIRST COST
[9 empty] | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | 2013-10-01 |  | ESC | COST | CNTG | FULL
[9 empty] | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | ($K) | ($K) | (%) | ($K) | ($K) | ($K)
[9 empty] | A | B | C | D | E | F |  | G | H | I | J |  |  |  |  | M | N | O
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 03 | RESERVOIRS | 100 | 10 | 10% | 110 |  | 1.554% | 101.5543 | 10.1554 | 111.7097 |  | 0 | 111.7097 | 3.871% | 105.4854 | 10.5485 | 116.0339
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 04 | DAMS | 100 | 20 | 20% | 120 |  | 1.555% | 101.5552 | 20.311 | 121.8663 |  | 0 | 121.8663 | 3.87% | 105.4857 | 21.0971 | 126.5828
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 05 | LOCKS | 100 | 24 | 24% | 124 |  | 1.555% | 101.555 | 24.3732 | 125.9282 |  | 0 | 125.9282 | 3.87% | 105.485 | 25.3164 | 130.8014
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 06 | FISH & WILDLIFE FACILITIES | 100 | 10 | 10% | 110 |  | 1.555% | 101.5548 | 10.1555 | 111.7103 |  | 0 | 111.7103 | 3.87% | 105.485 | 10.5485 | 116.0335
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 07 | POWER PLANT | 100 | 10 | 10% | 110 |  | 1.554% | 101.5536 | 10.1554 | 111.709 |  | 0 | 111.709 | 3.871% | 105.4845 | 10.5484 | 116.0329
[24 empty] | _ | _ | _ | bar: 3 to 4; 6; 9 to 11; 13
[10 empty] | CONSTRUCTION ESTIMATE TOTALS: | 500 | 74 |  | 574 |  | 1.555% | 507.7729 | 75.1505 | 582.9235 |  | 0 | 582.9235 | 3.87% | 527.4256 | 78.059 | 605.4847 |  | 605.4847 | 1188.4468 | Estimate Check
Program yr check
[9 empty] | 01 | LANDS AND DAMAGES | 5 | 1.55 | 31% | 6.55 |  | 1.555% | 5.0777 | 1.5741 | 6.6518 |  | 0 | 6.6518 | 1.873% | 5.1728 | 1.6036 | 6.7764 |  |  |  | FF Check | 1562.4449
[5 empty] | PED % of Construction Contract (w/o Cont) | 23.4% |  |  | 30 | PLANNING, ENGINEERING & DESIGN | 117 | 17.316 | 14.8% | 134.316 |  | 2.16% | 119.5267 | 17.69 | 137.2167 |  | 750 | 887.2167 | 1.973% | 121.8846 | 18.0389 | 889.9235
COLUMN TO CHECK SPREAD SHEET
[5 empty] | % CM of Construction Contract (w/o Cont) | 14.6% |  |  | 31 | CONSTRUCTION MANAGEMENT | 73 | 10.804 | 14.8% | 83.804 |  | 2.16% | 74.5765 | 11.0373 | 85.6138 |  | 0 | 85.6138 | 7.452% | 80.134 | 11.8598 | 91.9938 |  |  | Below spreadsheets numbers show (SUM) up three times THEN DIVIDED BY 3. (SEE Cell W85)
[10 empty] | PROJECT COST TOTALS: | 695 | 103.67 | 14.92% | 798.67 |  |  | 706.9539 | 105.4519 | 812.4058 |  | 750 | 1562.4058 | 3.911% | 734.617 | 109.5614 | 1594.1783 |  | 1594.1783 | 1594.1783
[8 empty] | 2: Mandatory by Regulation; 3: CHIEF, COST ENGINEERING, xxx | [5 empty] | 0 | DIFFERENCE
[8 empty] | 2: Mandatory by Regulation |  | ESTIMATED FEDERAL COST: | 50% | 797.0892 |  | 1594.1783 | CHECK COST
[8 empty] | 3: PROJECT MANAGER, xxx |  | ESTIMATED NON-FEDERAL COST: | 50% | 797.0892 |  | ======
[8 empty] | 2: Mandatory by Regulation | [5 empty] | 750 | COMPLETED COST
[8 empty] | 3: CHIEF, REAL ESTATE, xxx |  | ESTIMATED TOTAL PROJECT COST: |  | 1594.1783 |  |  | COST NOT IN BELOW SHEET
CHIEF, PLANNING,xxx
SUMMED COST IN BELOW SHEETS
[8 empty] | 3: CHIEF, ENGINEERING, xxx | [5 empty] | 844.1783 | FUTURE COST |  | 844.1783
CHIEF, OPERATIONS, xxx
CHIEF, CONSTRUCTION, xxx
CHIEF, CONTRACTING,xxx
CHIEF, PM-PB, xxxx
CHIEF, DPM, xxx
| Pg Brk |  |  |  |  | 1 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  | Program Year (Budget EC): |  |  | 2015
[8 empty] | 9 |  |  | Effective Price Level: |  |  | 2013-10-01 |  | Effective Price Level Date: |  |  | 1 OCT 14
[8 empty] | 10 |  |  |  |  | RISK BASED
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 1 or CONTRACT 1
871.77 | 885.32 | 919.59 | 2016(Oct - Dec) | 03 | Midpoint 03 | 2017Q1 |  | 15 | 03 | RESERVOIRS | 100 | 10 | 10% | 110 |  | 1.554% | 101.5543 | 10.1554 | 111.7097 |  | 2017Q1 | 3.871% |  | 105.4854 | 10.5485 | 116.0339
790.24 | 802.53 | 833.59 | 2016(Oct - Dec) | 04 | Midpoint 04 | 2017Q1 |  | 16 | 04 | DAMS | 100 | 20 | 20% | 120 |  | 1.555% | 101.5552 | 20.311 | 121.8663 |  | 2017Q1 | 3.87% |  | 105.4857 | 21.0971 | 126.5828
787.78 | 800.03 | 830.99 | 2016(Oct - Dec) | 05 | Midpoint 05 | 2017Q1 |  | 17 | 05 | LOCKS | 100 | 24 | 24% | 124 |  | 1.555% | 101.555 | 24.3732 | 125.9282 |  | 2017Q1 | 3.87% |  | 105.485 | 25.3164 | 130.8014
775.02 | 787.07 | 817.53 | 2016(Oct - Dec) | 06 | Midpoint 06 | 2017Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 100 | 10 | 10% | 110 |  | 1.555% | 101.5548 | 10.1555 | 111.7103 |  | 2017Q1 | 3.87% |  | 105.485 | 10.5485 | 116.0335
735.71 | 747.14 | 776.06 | 2016(Oct - Dec) | 07 | Midpoint 07 | 2017Q1 |  | 19 | 07 | POWER PLANT | 100 | 10 | 10% | 110 |  | 1.554% | 101.5536 | 10.1554 | 111.709 |  | 2017Q1 | 3.871% |  | 105.4845 | 10.5484 | 116.0329
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 500 | 74 | 14.8% | 574 |  |  | 507.7729 | 75.1505 | 582.9235 |  |  |  |  | 527.4256 | 78.059 | 605.4847 |  | 605.4847
23
798.14 | 810.55 | 825.73 | 2015(Oct - Dec) | All | Lands And Damages Midpoint | 2016Q1 |  | 24 | 01 | LANDS AND DAMAGES | 5 | 1.55 | 31% | 6.55 |  | 1.555% | 5.0777 | 1.5741 | 6.6518 |  | 2016Q1 | 1.873% |  | 5.1728 | 1.6036 | 6.7764 |  | 6.7764
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | Design mid point period | 2015Q2 |  | 28 | 2.5% | Project Management | 13 | 1.924 | 14.8% | 14.924 |  | 2.16% | 13.2807 | 1.9656 | 15.2463 |  | 2015Q2 | 0.4837% |  | 13.345 | 1.9751 | 15.32 |  | 15.32
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 29 | 2% | Planning & Environmental Compliance | 10 | 1.48 | 14.8% | 11.48 |  | 2.16% | 10.216 | 1.512 | 11.7279 |  | 2015Q2 | 0.4837% |  | 10.2654 | 1.5193 | 11.7846 |  | 11.7846
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 30 | 8.5% | Engineering & Design | 43 | 6.364 | 14.8% | 49.364 |  | 2.16% | 43.9286 | 6.5014 | 50.4301 |  | 2015Q2 | 0.4837% |  | 44.1411 | 6.5329 | 50.674 |  | 50.674
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 3 | 0.444 | 14.8% | 3.444 |  | 2.16% | 3.0648 | 0.45359 | 3.5184 |  | 2015Q2 | 0.4837% |  | 3.0796 | 0.45578 | 3.5354 |  | 3.5354
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From From Design mid point period | 2015Q2 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 3 | 0.444 | 14.8% | 3.444 |  | 2.16% | 3.0648 | 0.45359 | 3.5184 |  | 2015Q2 | 0.4837% |  | 3.0796 | 0.45578 | 3.5354 |  | 3.5354
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 33 | 2% | Contracting & Reprographics | 10 | 1.48 | 14.8% | 11.48 |  | 2.16% | 10.216 | 1.512 | 11.7279 |  | 2015Q2 | 0.4837% |  | 10.2654 | 1.5193 | 11.7846 |  | 11.7846
1.0286 | 1.0508 | 1.1291 | 2016(Oct - Dec) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2017Q1 |  | 34 | 3% | Engineering During Construction | 15 | 2.22 | 14.8% | 17.22 |  | 2.16% | 15.3239 | 2.2679 | 17.5919 |  | 2017Q1 | 7.452% |  | 16.4659 | 2.437 | 18.9028 |  | 18.9028
1.0286 | 1.0508 | 1.1291 | 2016(Oct - Dec) | 30 | From Aggreagate Constrction Midpoint | 2017Q1 |  | 35 | 2% | Planning During Construction | 10 | 1.48 | 14.8% | 11.48 |  | 2.16% | 10.216 | 1.512 | 11.7279 |  | 2017Q1 | 7.452% |  | 10.9773 | 1.6246 | 12.6019 |  | 12.6019
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 36 | 2% | Project Operations | 10 | 1.48 | 14.8% | 11.48 |  | 2.16% | 10.216 | 1.512 | 11.7279 |  | 2015Q2 | 0.4837% |  | 10.2654 | 1.5193 | 11.7846 |  | 11.7846
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.1291 | 2016(Oct - Dec) | 31 | From Aggreagate Constrction Midpoint | 2017Q1 |  | 39 | 10% | Construction Management | 50 | 7.4 | 14.8% | 57.4 |  | 2.16% | 51.0798 | 7.5598 | 58.6396 |  | 2017Q1 | 7.452% |  | 54.8863 | 8.1232 | 63.0094 |  | 63.0094
1.0286 | 1.0508 | 1.1291 | 2016(Oct - Dec) | 31 | From Aggreagate Constrction Midpoint | 2017Q1 |  | 40 | 2% | Project Operation: | 10 | 1.48 | 14.8% | 11.48 |  | 2.16% | 10.216 | 1.512 | 11.7279 |  | 2017Q1 | 7.452% |  | 10.9773 | 1.6246 | 12.6019 |  | 12.6019
1.0286 | 1.0508 | 1.1291 | 2016(Oct - Dec) | 31 | From Aggreagate Constrction Midpoint | 2017Q1 |  | 41 | 2.5% | Project Management | 13 | 1.924 | 14.8% | 14.924 |  | 2.16% | 13.2807 | 1.9656 | 15.2463 |  | 2017Q1 | 7.452% |  | 14.2704 | 2.112 | 16.3825 |  | 16.3825
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 695; 4: 103.67; 6: 798.67; 9: 706.9539; 10: 105.4519; 11: 812.4058 |  | 734.617 | 109.5614 | 844.1783 |  | 844.1783 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 844.1783
| Pg Brk |  |  |  |  | 2 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  | Program Year (Budget EC): |  |  | 2015
[8 empty] | 9 |  |  | Effective Price Level: |  |  | 2013-10-01 |  | Effective Price Level Date: |  |  | 1 OCT 14
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 2 or CONTRACT 2
871.77 | 885.32 | 910.53 | 2016(Apr - Jun) | 03 | Midpoint 03 | 2016Q3 | No del | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 825.37 | 2016(Apr - Jun) | 04 | Midpoint 04 | 2016Q3 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 822.81 | 2016(Apr - Jun) | 05 | Midpoint 05 | 2016Q3 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 809.48 | 2016(Apr - Jun) | 06 | Midpoint 06 | 2016Q3 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 768.42 | 2016(Apr - Jun) | 07 | Midpoint 07 | 2016Q3 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 792.07 | 2013(Jul - Sep) | All | Lands And Damages Midpoint | 2013Q4 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | Design mid point period | 2015Q2 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From From Design mid point period | 2015Q2 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2016Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0559 | 2015(Jan - Mar) | 30 | From Design mid point period | 2015Q2 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
| Pg Brk |  |  |  |  | 3 |  | 1: 44 | [5 empty] | 0
[8 empty] | 1 | [5 empty] | **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  | Program Year (Budget EC): |  |  | 2015
[8 empty] | 9 |  |  | Effective Price Level: |  |  | 2013-10-01 |  | Effective Price Level Date: |  |  | 1 OCT 14
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 3 or CONTRACT 3
871.77 | 885.32 | 928.86 | 2017(Apr - Jun) | 03 | Midpoint 03 | 2017Q3 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 841.99 | 2017(Apr - Jun) | 04 | Midpoint 04 | 2017Q3 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 839.37 | 2017(Apr - Jun) | 05 | Midpoint 05 | 2017Q3 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 825.77 | 2017(Apr - Jun) | 06 | Midpoint 06 | 2017Q3 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 783.88 | 2017(Apr - Jun) | 07 | Midpoint 07 | 2017Q3 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 792.07 | 2013(Jul - Sep) | All | Lands And Damages Midpoint | 2013Q4 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.0972 | 2016(Jan - Mar) | 30 | Design mid point period | 2016Q2 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0972 | 2016(Jan - Mar) | 30 | From Design mid point period | 2016Q2 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0972 | 2016(Jan - Mar) | 30 | From Design mid point period | 2016Q2 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0972 | 2016(Jan - Mar) | 30 | From Design mid point period | 2016Q2 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0972 | 2016(Jan - Mar) | 30 | From From Design mid point period | 2016Q2 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0972 | 2016(Jan - Mar) | 30 | From Design mid point period | 2016Q2 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2017Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0972 | 2016(Jan - Mar) | 30 | From Design mid point period | 2016Q2 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
| Pg Brk |  |  |  |  | 4 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  |  |  | Program Year (Budget EC): | 2015
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2013-10-01; 10: Effective Price Level Date:; 11: 1 OCT 14 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 4 or CONTRACT 4
871.77 | 885.32 | 849.84 | 2012(Oct - Dec) | 03 | Midpoint 03 | 2013Q1 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 790.24 | 2013(Oct - Dec) | 04 | Midpoint 04 | 2014Q1 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 800.03 | 2014(Oct - Dec) | 05 | Midpoint 05 | 2015Q1 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 801.81 | 2015(Oct - Dec) | 06 | Midpoint 06 | 2016Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 764.77 | 2016(Jan - Mar) | 07 | Midpoint 07 | 2016Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 782.27 | 2012(Oct - Dec) | All | Lands And Damages Midpoint | 2013Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.0662 | 2015(Apr - Jun) | 30 | Design mid point period | 2015Q3 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0662 | 2015(Apr - Jun) | 30 | From Design mid point period | 2015Q3 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0662 | 2015(Apr - Jun) | 30 | From Design mid point period | 2015Q3 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0662 | 2015(Apr - Jun) | 30 | From Design mid point period | 2015Q3 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0662 | 2015(Apr - Jun) | 30 | From From Design mid point period | 2015Q3 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0662 | 2015(Apr - Jun) | 30 | From Design mid point period | 2015Q3 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2016Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.0662 | 2015(Apr - Jun) | 30 | From Design mid point period | 2015Q3 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2016Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
| Pg Brk |  |  |  |  | 5 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  |  |  | Program Year (Budget EC): | 2015
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2013-10-01; 10: Effective Price Level Date:; 11: 1 OCT 14 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 5 or CONTRACT 5
871.77 | 885.32 | 849.84 | 2012(Oct - Dec) | 03 | Midpoint 03 | 2013Q1 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 790.24 | 2013(Oct - Dec) | 04 | Midpoint 04 | 2014Q1 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 800.03 | 2014(Oct - Dec) | 05 | Midpoint 05 | 2015Q1 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 801.81 | 2015(Oct - Dec) | 06 | Midpoint 06 | 2016Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 764.77 | 2016(Jan - Mar) | 07 | Midpoint 07 | 2016Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 782.27 | 2012(Oct - Dec) | All | Lands And Damages Midpoint | 2013Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | Design mid point period | 2016Q3 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From Design mid point period | 2016Q3 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From Design mid point period | 2016Q3 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From Design mid point period | 2016Q3 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From From Design mid point period | 2016Q3 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From Design mid point period | 2016Q3 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2017Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1078 | 2016(Apr - Jun) | 30 | From Design mid point period | 2016Q3 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2017Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
| Pg Brk |  |  |  |  | 6 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  |  |  | Program Year (Budget EC): | 2015
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2013-10-01; 10: Effective Price Level Date:; 11: 1 OCT 14 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 6 or CONTRACT 6
871.77 | 885.32 | 849.84 | 2012(Oct - Dec) | 03 | Midpoint 03 | 2013Q1 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 790.24 | 2013(Oct - Dec) | 04 | Midpoint 04 | 2014Q1 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 800.03 | 2014(Oct - Dec) | 05 | Midpoint 05 | 2015Q1 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 801.81 | 2015(Oct - Dec) | 06 | Midpoint 06 | 2016Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 764.77 | 2016(Jan - Mar) | 07 | Midpoint 07 | 2016Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 782.27 | 2012(Oct - Dec) | All | Lands And Damages Midpoint | 2013Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | Design mid point period | 2017Q3 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From Design mid point period | 2017Q3 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From Design mid point period | 2017Q3 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From Design mid point period | 2017Q3 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From From Design mid point period | 2017Q3 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From Design mid point period | 2017Q3 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2018Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2018Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1508 | 2017(Apr - Jun) | 30 | From Design mid point period | 2017Q3 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2018Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2018Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2018Q3 |  | 1: 41; 1: 2.5%; 3: 0; 4: 0; 5: 0% | [5 empty] | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
| Pg Brk |  |  |  |  | 7 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  |  |  | Program Year (Budget EC): | 2015
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2013-10-01; 10: Effective Price Level Date:; 11: 1 OCT 14 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 7 or CONTRACT 7
871.77 | 885.32 | 849.84 | 2012(Oct - Dec) | 03 | Midpoint 03 | 2013Q1 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 790.24 | 2013(Oct - Dec) | 04 | Midpoint 04 | 2014Q1 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 800.03 | 2014(Oct - Dec) | 05 | Midpoint 05 | 2015Q1 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 801.81 | 2015(Oct - Dec) | 06 | Midpoint 06 | 2016Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 764.77 | 2016(Jan - Mar) | 07 | Midpoint 07 | 2016Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 782.27 | 2012(Oct - Dec) | All | Lands And Damages Midpoint | 2013Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | Design mid point period | 2018Q3 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | From Design mid point period | 2018Q3 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | From Design mid point period | 2018Q3 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | From Design mid point period | 2018Q3 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | From From Design mid point period | 2018Q3 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | From Design mid point period | 2018Q3 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2019Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2019Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.1959 | 2018(Apr - Jun) | 30 | From Design mid point period | 2018Q3 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2019Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2019Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2019Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
| Pg Brk |  |  |  |  | 8 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  |  |  | Program Year (Budget EC): | 2015
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2013-10-01; 10: Effective Price Level Date:; 11: 1 OCT 14 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 8 or CONTRACT 8
871.77 | 885.32 | 849.84 | 2012(Oct - Dec) | 03 | Midpoint 03 | 2013Q1 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 790.24 | 2013(Oct - Dec) | 04 | Midpoint 04 | 2014Q1 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 800.03 | 2014(Oct - Dec) | 05 | Midpoint 05 | 2015Q1 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 801.81 | 2015(Oct - Dec) | 06 | Midpoint 06 | 2016Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 764.77 | 2016(Jan - Mar) | 07 | Midpoint 07 | 2016Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 782.27 | 2012(Oct - Dec) | All | Lands And Damages Midpoint | 2013Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | Design mid point period | 2019Q3 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | From Design mid point period | 2019Q3 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | From Design mid point period | 2019Q3 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | From Design mid point period | 2019Q3 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | From From Design mid point period | 2019Q3 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | From Design mid point period | 2019Q3 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2020Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2431 | 2019(Apr - Jun) | 30 | From Design mid point period | 2019Q3 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2020Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2020Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2020Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
| Pg Brk |  |  |  |  | 9 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
| CWCCIS |  | Time Period |  |  | Schedule |  | 1: 6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  |  |  | Program Year (Budget EC): | 2015
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2013-10-01; 10: Effective Price Level Date:; 11: 1 OCT 14 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 9 or CONTRACT 9
871.77 | 885.32 | 849.84 | 2012(Oct - Dec) | 03 | Midpoint 03 | 2013Q1 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 790.24 | 2013(Oct - Dec) | 04 | Midpoint 04 | 2014Q1 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 800.03 | 2014(Oct - Dec) | 05 | Midpoint 05 | 2015Q1 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 801.81 | 2015(Oct - Dec) | 06 | Midpoint 06 | 2016Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 764.77 | 2016(Jan - Mar) | 07 | Midpoint 07 | 2016Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 782.27 | 2012(Oct - Dec) | All | Lands And Damages Midpoint | 2013Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | Design mid point period | 2020Q3 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From From Design mid point period | 2020Q3 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2021Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
| Pg Brk |  |  |  |  | 9 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: NPD North Pacific Division |  |  | PREPARED: | 2014-04-02
[8 empty] | 4 | LOCATION: | Somewhere WA | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2014
| CWCCIS |  | Time Period |  |  | Schedule |  | 1: 6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2014-03-15 |  |  |  | Program Year (Budget EC): | 2015
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2013-10-01; 10: Effective Price Level Date:; 11: 1 OCT 14 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2013(Oct - Dec) |  | Price Level of Estimate ==> | 2014Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
| Program Year Price Level |  | 2014(Oct - Dec) |  | Program Year Price Level ==> | 2015Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 10 or CONTRACT 10
871.77 | 885.32 | 849.84 | 2012(Oct - Dec) | 03 | Midpoint 03 | 2013Q1 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
790.24 | 802.53 | 790.24 | 2013(Oct - Dec) | 04 | Midpoint 04 | 2014Q1 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
787.78 | 800.03 | 800.03 | 2014(Oct - Dec) | 05 | Midpoint 05 | 2015Q1 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
775.02 | 787.07 | 801.81 | 2015(Oct - Dec) | 06 | Midpoint 06 | 2016Q1 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
735.71 | 747.14 | 764.77 | 2016(Jan - Mar) | 07 | Midpoint 07 | 2016Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
798.14 | 810.55 | 782.27 | 2012(Oct - Dec) | All | Lands And Damages Midpoint | 2013Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | Design mid point period | 2020Q3 |  | 28 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 29 | 2% | Planning & Environmental Compliance | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 30 | 8.5% | Engineering & Design | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 31 | 0.5% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From From Design mid point period | 2020Q3 |  | 32 | 0.5% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 33 | 2% | Contracting & Reprographics | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2021Q3 |  | 34 | 3% | Engineering During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 30 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 35 | 2% | Planning During Construction | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.2925 | 2020(Apr - Jun) | 30 | From Design mid point period | 2020Q3 |  | 36 | 2% | Project Operations | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
37
[8 empty] | 38 | 31 | CONSTRUCTION MANAGEMENT
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 39 | 10% | Construction Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 40 | 2% | Project Operation: | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0286 | 1.0508 | 1.3441 | 2021(Apr - Jun) | 31 | From Aggreagate Constrction Midpoint | 2021Q3 |  | 41 | 2.5% | Project Management | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
42
[8 empty] | 1: 43; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 44 | [5 empty] | 0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
Note on F1: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V19: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V20: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V21: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V22: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V23: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V27: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V29: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V31: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on N36: USACE: Three signatures mandatory...

## TPCS Rules
Estimated Cost (Price Level) is the initially developed cost estimate which includes contingencies. The effective price level date for Estimated Cost (shown in MONTH YYYY format) is usually the date of preparation of the cost estimate.
Project First Cost (Constant Dollar Cost) (Price Level) is the Estimated Cost BROUGHT TO THE EFFECTIVE PRICE LEVEL. The effective price level for Constant Dollar Cost (shown in MONTH YYYY format) is the date of the common point in time of the pricing used in the cost estimate. Constant Dollar Cost does not include inflation. Constant Dollar Cost at current price levels is the cost estimate used in feasibility reports and Chief's Reports (see paragraphs 5(a) and 5(b) below). THE CONSTANT DOLLAR COST SHOULD BE EXPRESSED AS THE FY OF THE CHIEF'S REPORT TO ENSURE THAT THE CW PROGRAM TOTALS IN ONE FY DOLLAR TO ASA AND CONGRESS.
Total Project Cost is the Constant Dollar Cost FULLY FUNDED WITH ESCALATION to the estimated midpoint of construction. Total Project Cost (or Total Cost of Construction of GNFs when discussing navigation projects) is the cost estimate used in Project Partnership Agreements and Integral Determination Reports. Total Project Cost is the cost estimate provided non-Federal sponsors for their use in financial planning as it provides information regarding the overall non-Federal cost sharing obligation. See the enclosed tables for more detail of what is or is not included in the Total Project Cost.
Type of Program | CWBS* | Project Cost Component** | Brief Definition | For Chief's Report |  | For PPA's
|  |  |  | Project First Cost | Economic Cost for BCR | Total Project Cost
|  |  |  | Constant Cost Estimate "Oct (YYYY) Price Level" |  | Fully Funded Cost Estimate
Flood Risk Management | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Flood Risk Management | 02 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Flood Risk Management | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Flood Risk Management | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Flood Risk Management |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Flood Risk Management | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Flood Risk Management | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Flood Risk Management | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Flood Risk Management | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Flood Risk Management | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Flood Risk Management | By project element | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within cost shared project cost. | N | Y | Y
Ecosystem Restoration | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Ecosystem Restoration | 03 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Ecosystem Restoration | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Ecosystem Restoration | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Ecosystem Restoration |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Ecosystem Restoration | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Ecosystem Restoration | By project element | Monitoring and Adaptive Management | This represents the estimated costs of monitoring and or adaptive management to be cost shared for the project. | Y | Y | Y
Ecosystem Restoration | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Ecosystem Restoration | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Ecosystem Restoration | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Ecosystem Restoration | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Ecosystem Restoration |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Navigation and Harbors | 01,02 | Lands, Easements, Rights of Way, Relocations (LERR). This includes related Federal costs. | Estimated value/costs of LERR (to include breakout of related Federal administrative costs). | Y | Y | Y
Navigation and Harbors | 03 - 20 | Construction Elements (General Navigation Features) | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Navigation and Harbors | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Navigation and Harbors | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Navigation and Harbors |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Navigation and Harbors | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Navigation and Harbors | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Navigation and Harbors | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Navigation and Harbors | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Navigation and Harbors | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Navigation and Harbors | By project element | Local Service Facilities (LSF) | For Navigation Only: This represents the estimated cost of Local Service Facilities as defined in the Planning Guidance Notebook Appendix E. These are the responsibility of the non-Federal entity and are required as part of the PCA if they are necessary for project benefits to accrue. | N | Y | Y
Navigation and Harbors |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Inland Navigation | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Inland Navigation | 03 - 20 | Construction Elements (General Navigation Features) | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Inland Navigation | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Inland Navigation | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Inland Navigation |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Inland Navigation | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Inland Navigation | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Inland Navigation | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Inland Navigation | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Inland Navigation | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Inland Navigation | By project element | Local Service Facilities (LSF) | For Navigation Only: This represents the estimated cost of Local Service Facilities as defined in the Planning Guidance Notebook Appendix E. These are the responsibility of the non-Federal entity and are required as part of the PCA if they are necessary for project benefits to accrue. | N | Y | Y
Inland Navigation |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
COASTAL STORM | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
COASTAL STORM | 03 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
COASTAL STORM | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
COASTAL STORM | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
COASTAL STORM |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
COASTAL STORM | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
COASTAL STORM | By project element | Monitoring and Adaptive Management | This represents the estimated costs of monitoring and or adaptive management to be cost shared for the project. | Y | Y | Y
COASTAL STORM | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
COASTAL STORM | By project element | Continued Construction (periodic nourishment) | For Hurricane and Storm Damage Reduction Only: Estimate of Allowable Periodic Average future construction cost submitted for authorization. | Y | Y | Y
COASTAL STORM | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
COASTAL STORM | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
COASTAL STORM |  | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
COASTAL STORM |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Feature Code Definitions
CWBS | Definitions
01 Lands and Damages | This feature includes all costs of acquiring for the project (by purchase or condemnation) real property or permanent interests therein, including Government costs, damages, and costs of disposal of real estate. Government costs include planning expenses for the real estate portion of the General Design Memo and for the detailed Real Estate Memo; and project real estate office administration, surveys, and marking for land acquisition purposes and appraisals. For projects which require that costs be incurred on real estate activities, i.e., for records search, appraisals, and field inspection to assure compliance by local interests in the provision of local requirements on projects where no Federal land acquisition is involved, a memorandum statement will be provided with the PB-3 indicating the estimated costs of such real estate activities. These costs will be charged to feature 30, Engineering and Design and that feature will be properly footnoted to show the amount of such costs. A similar footnote will be shown on the PB-1's and PB-2a's for all such projects. This feature is credited with disposal receipts from sale of such items as standing crops, standing timber, structures, and improvements in place and acquired with the land. Disposal receipts from sale of excess land not turned in to the U.S. Treasury as miscellaneous receipts are credited to this feature. Lands or interests purchased for relocations and conveyed to others are included in the feature "Relocations.” Temporary interests such as leases are included in the feature or distributive item benefited thereby.
02 Relocations | This feature includes removing and relocating, or reconstructing property of others, such as roads, railroads, cemeteries, utilities, buildings, and other structures; and lands or interests purchased for such relocations and conveyed to others, including real estate planning and acquisition expenses. The cost of removal of improvements from the reservoir area for disposal is included in the feature “Reservoirs.” All alterations of railroad bridges in accordance with Section 3 of the 1946 Flood Control Act (22 USC 701p) are also included in this feature.
03 Reservoirs | This feature includes clearing lands in reservoirs and pools of debris, brush, trees, improvements, and structures. Any salvage, obtained by sale or disposal by the Government, of material removed in clearing operations is credited to this feature. This feature also includes bank stabilization, shoreline improvement, firebreaks, fencing, boundary line survey and marking of land which has been acquired or is to be acquired, rehabilitation of natural resources, erosion control, drainage, and rim grouting and mine sealing, etc., to prevent leakage. Site clearing, grouting, etc., incidental to and required for specific construction features is included as part of the construction features.
04 Dams | This feature includes dams and all other water collecting and storage facilities, whether man-made or natural, together with appurtenant diversion, regulation, and delivery facilities and spillways, outlet works, and power intake works, whether separate from the dam or not. In the case where the powerhouse is an integral part of the intake dam, the cost of the power intake dam is included in the feature "Power Plant." Any auxiliary dams or spillways detached from the main structures and floating trash and drift booms and barriers are included in this feature. The power intake works include such power items as forebay, penstocks, tunnels, surge tank, gates, operating equipment, and appurtenances. Service roads and service railroads on the dam are included in this feature. The additional cost of relocating highways and railroads across the dam is included in the feature "Relocations."
05 Locks | This feature includes facilities to provide for passage of waterborne traffic, including gates, valves, operating mechanisms, cribs, fills, lock walls, guide and guard walls, operating buildings, and excavation therefore. The lock structure is considered that part of the work within the limit lines extending from the upper end of the upper guide or guard walls to the lower end of the lower guide or guard walls, including dolphins within the lock approaches for tie up, guard, or guide purposes. Excavation or dredging• required in approaches outside of the limits defined above for the lock structure is included in the feature "Channels and Canals." The cost of a cofferdam or the properly allocable amount thereof, if required, is charged to this feature. Locks provided in connection with facilities for the prevention of encroachment of salt water are included in this feature. Locks in connection with fish facilities are included in the feature "Fish and Wildlife Facilities."
06 Fish and Wildlife Facilities | This feature includes items such as ladders, elevators, locks and related facilities for passage of fish at dams and navigation locks and maintenance of fish runs; and provision for wildlife preservation.
07 Power Plant | This feature includes those facilities specifically required for the production of power other than those included in the feature “Dams,” and consists of the following: powerhouse, turbines and governors, generators, accessory electrical equipment, miscellaneous power plant equipment, switchyard, and tailrace improvement for power. In the case where the powerhouse is an integral part of the power intake dam, the cost of the power intake dam is included in this feature. Where the structure of a dam also forms the foundation of the powerhouse, such foundation is considered a part of the dam. Units for production of power for the operation only of power for the operation only of navigation, flood control, or other purpose projects (excluding those projects with power as a feature) are included in other than this feature. The cost of a cofferdam or appropriate part is charged to this feature.
08 Roads, Railroads and Bridges | This feature includes permanent roads, railroads, and bridges required for access and other purposes in connection with the construction and operation of the project. This feature does not include roads, railroads, and bridges chargeable to the feature "Relocations," access roads to recreation facilities and areas, which will be charged to the feature "14. Recreation Facilities," and service roads and service railroads on structures.
09 Channels and Canals | This feature includes all forms of excavation (including dredging, preparation of spoil disposal area, and attendant facilities) necessary for the development and construction of channels, harbors, and canals for navigation purposes; and deepening, providing new, or improving existing watercourses for flood control and major drainage. Excavation of natural watercourse to provide adequate depths for navigation is included. Excavation for specific structures, such as dams and locks used in the development of waterways and conservation of water resources, is included with such structures. The removal of trees, brush, accumulated snags, drift, debris, water hyacinths and other aquatic growths from canals, harbors, and channels in navigable streams and tributaries thereof for navigational included in this feature. Excavation, clearing, and removal of accumulated snags, drifts, debris, and vegetable growth from streams for flood control and major drainage purposes also is included. Included in this feature are revetments, linings, dikes, and bulkheads constructed as channel improvement works for flood control or navigation, as against such items constructed for bank stabilization only. Also included are jetties constructed in connection with flood control channel improvements.
10 Breakwaters and Seawalls | This feature includes breakwaters, seawalls, piers, and like improvements constructed in connection with the protection of beaches, harbors, shores•, and port facilities against the force of waves and encroachment of seas or lakes by direct wave action. Jetties, groins, and like structures provided in seas, lakes, tidewater reaches of rivers and canals, and harbors to control water flow and current, to maintain depth of channels, and to provide protection, are included in this feature.
11 Levees and Floodwalls | This feature includes embankments and walls constructed to protect areas from inundation by overflow from creeks, rivers, lakes, canals, and other bodies of water. This feature consists of such items as: service roads on levee crown or landside berms, road ramps, closure structures, seepage control measures, erosion protection measures on levee slopes and on berms and bank slops when an integral part of the levees or floodwalls; and drainage facilities, constructed to provide means for the passage of accumulated drainage and seepage water and sewage from the protected area over or through levees and floodwalls, comprising such items as interceptor and collection sewers and ditches, and pressurized sewers and drainage structures, including outfalls through levees or floodwalls. Pumping plants are included in the feature "Pumping Plants." Levees locally called dikes are included in this feature.
13 Pumping Plants | This feature includes pumping plants construction to pass accumulated drainage and seepage water and sewage from the protected area over or through levees and floodwalls.
14 Recreation Facilities | This feature includes access roads; parking areas; public camping and picnicking areas, including tables and fireplaces; water supply; sanitary facilities; boat launching ramps; directional signs; and other facilities constructed primarily for public recreational use, including essential safety measures in connection therewith. The latter includes, as appropriate, sheltered anchorage areas for small craft, bathing areas readily accessible and reasonably safe, and safety provisions for visitors and fishermen in the project area. (Boat launching ramps, anchorage areas and beaches should be provided during construction to the extent they will definitely be needed and can be accomplished more economically than at a later date.)
15 Floodway Control and Diversion Structures | This feature includes floodway control and diversion structures to provide for the release of flood waters from streams where discharges exceed flood capacity of the stream, including items such as diversion dams, gated or ungated discharge structures, training walls, stilling basin, and those adjacent embankment sections forming part of the control structure. Construction of channels and levees not forming part of the main control structure, but necessary for operation of such structures is included in the appropriate feature "Channels and Canals" or "Levees and Floodwalls."
16 Bank Stabilization | This feature includes revetments, linings, training dikes, and bulkheads for stabilization of banks of watercourses to prevent erosion, sloughing, or meandering. Bank stabilization constructed in navigation channels or in connection with flood control channel improvement is included in• the feature "Channels and Canals."
17 Beach Replenishment | This feature includes replacement of eroded beaches, for purposes of recreation and shore protection, by direct deposit of materials obtained by dredging or land excavation.
19 Buildings, Grounds and Utilities | This feature includes permanent facilities such as operators' quarters, administration and shop buildings, storage buildings and areas, garage buildings and areas, community buildings, local streets and sidewalks, landscaping, and electric, gas, water, and sewage facilities. Where space in a dam, powerhouse, or other basic structure is used in lieu of construction of any of the above-mentioned buildings, such allocated space is not separated from the basic structure. Communication systems are• included in the feature "Permanent Operating Equipment."
20 Permanent Operating Equipment | This feature includes all project-owned operation and maintenance tools and equipment, such as laboratory, shop, warehousing, communications, and transportation equipment, and office furniture and equipment. The cost of installing sedimentation and degradation measuring facilities, including the surveys requisite to locating and monumenting range layouts, is charged to this feature. •The cost of planning the installation of sedimentation and degradation ranges is charged to the feature "Engineering and Design."
30 Engineering and Design | This feature includes all engineering, design, surveys, preparation of detailed plans and specifications, and related work required for the construction of the project, including relocations. Surveys and planning required in connection with land acquisition are charged to the features "Lands and Damages" or "Relocations," as applicable. Engineering and design performed by hired labor or as a pay item under a contract is included in this feature.
31 Supervision and Administration | This feature includes such functions as inspection, supervision, project office administration, and distributive costs of area office and general overhead charged to the project. Costs for OCE and Division Office Executive Direction and Management are not charged to Construction, General but to the General Expenses appropriation title.
Note on B6: *Civil Works Breakdown Structure
Note on F15: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F26: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F38: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F50: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F62: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on A73: *Civil Works Breakdown Structure

## CWCCIS
| Date of Index Factors: | 2014-03-31 |  |  |  |  | Table A-1 Quarterly Indexes |  |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS
| CWCCIS ESCALATION CALCULATION |  |  |  |  | 1 |  | 1 |  |  | 1980Q1 | 1980Q2 | 1980Q3 | 1980Q4 | 1981Q1 | 1981Q2 | 1981Q3 | 1981Q4 | 1982Q1 | 1982Q2 | 1982Q3 | 1982Q4 | 1983Q1 | 1983Q2 | 1983Q3 | 1983Q4 | 1984Q1 | 1984Q2 | 1984Q3 | 1984Q4 | 1985Q1 | 1985Q2 | 1985Q3 | 1985Q4 | 1986Q1 | 1986Q2 | 1986Q3 | 1986Q4 | 1987Q1 | 1987Q2 | 1987Q3 | 1987Q4 | 1988Q1 | 1988Q2 | 1988Q3 | 1988Q4 | 1989Q1 | 1989Q2 | 1989Q3 | 1989Q4 | 1990Q1 | 1990Q2 | 1990Q3 | 1990Q4 | 1991Q1 | 1991Q2 | 1991Q3 | 1991Q4 | 1992Q1 | 1992Q2 | 1992Q3 | 1992Q4 | 1993Q1 | 1993Q2 | 1993Q3 | 1993Q4 | 1994Q1 | 1994Q2 | 1994Q3 | 1994Q4 | 1995Q1 | 1995Q2 | 1995Q3 | 1995Q4 | 1996Q1 | 1996Q2 | 1996Q3 | 1996Q4 | 1997Q1 | 1997Q2 | 1997Q3 | 1997Q4 | 1998Q1 | 1998Q2 | 1998Q3 | 1998Q4 | 1999Q1 | 1999Q2 | 1999Q3 | 1999Q4 | 2000Q1 | 2000Q2 | 2000Q3 | 2000Q4 | 2001Q1 | 2001Q2 | 2001Q3 | 2001Q4 | 2002Q1 | 2002Q2 | 2002Q3 | 2002Q4 | 2003Q1 | 2003Q2 | 2003Q3 | 2003Q4 | 2004Q1 | 2004Q2 | 2004Q3 | 2004Q4 | 2005Q1 | 2005Q2 | 2005Q3 | 2005Q4 | 2006Q1 | 2006Q2 | 2006Q3 | 2006Q4 | 2007Q1 | 2007Q2 | 2007Q3 | 2007Q4 | 2008Q1 | 2008Q2 | 2008Q3 | 2008Q4 | 2009Q1 | 2009Q2 | 2009Q3 | 2009Q4 | 2010Q1 | 2010Q2 | 2010Q3 | 2010Q4 | 2011Q1 | 2011Q2 | 2011Q3 | 2011Q4 | 2012Q1 | 2012Q2 | 2012Q3 | 2012Q4 | 2013Q1 | 2013Q2 | 2013Q3 | 2013Q4 | 2014Q1 | 2014Q2 | 2014Q3 | 2014Q4 | 2015Q1 | 2015Q2 | 2015Q3 | 2015Q4 | 2016Q1 | 2016Q2 | 2016Q3 | 2016Q4 | 2017Q1 | 2017Q2 | 2017Q3 | 2017Q4 | 2018Q1 | 2018Q2 | 2018Q3 | 2018Q4 | 2019Q1 | 2019Q2 | 2019Q3 | 2019Q4 | 2020Q1 | 2020Q2 | 2020Q3 | 2020Q4 | 2021Q1 | 2021Q2 | 2021Q3 | 2021Q4 | 2022Q1 | 2022Q2 | 2022Q3 | 2022Q4 | 2023Q1 | 2023Q2 | 2023Q3 | 2023Q4 | 2024Q1 | 2024Q2 | 2024Q3 | 2024Q4 | 2025Q1 | 2025Q2 | 2025Q3 | 2025Q4 | 2026Q1 | 2026Q2 | 2026Q3 | 2026Q4 | 2027Q1 | 2027Q2 | 2027Q3 | 2027Q4 | 2028Q1 | 2028Q2 | 2028Q3 | 2028Q4 | 2029Q1 | 2029Q2 | 2029Q3 | 2029Q4 | 2030Q1 | 2030Q2 | 2030Q3 | 2030Q4 | 2031Q1 | 2031Q2 | 2031Q3 | 2031Q4 | 2032Q1 | 2032Q2 | 2032Q3 | 2032Q4 | 2033Q1 | 2033Q2 | 2033Q3 | 2033Q4 | 2034Q1 | 2034Q2 | 2034Q3 | 2034Q4 | 2035Q1 | 2035Q2 | 2035Q3 | 2035Q4 | 2036Q1 | 2036Q2 | 2036Q3 | 2036Q4 | 2037Q1 | 2037Q2 | 2037Q3 | 2037Q4 | 2038Q1 | 2038Q2 | 2038Q3 | 2038Q4 | 2039Q1 | 2039Q2 | 2039Q3 | 2039Q4 | 2040Q1 | 2040Q2 | 2040Q3 | 2040Q4 | 2041Q1 | 2041Q2 | 2041Q3 | 2041Q4 | 2042Q1 | 2042Q2 | 2042Q3 | 2042Q4 | 2043Q1 | 2043Q2 | 2043Q3 | 2043Q4 | 2044Q1 | 2044Q2 | 2044Q3 | 2044Q4 | 2045Q1 | 2045Q2 | 2045Q3 | 2045Q4 | 2046Q1 | 2046Q2 | 2046Q3 | 2046Q4 | 2047Q1 | 2047Q2 | 2047Q3 | 2047Q4 | 2048Q1 | 2048Q2 | 2048Q3 | 2048Q4 | 2049Q1 | 2049Q2 | 2049Q3 | 2049Q4 | 2050Q1 | 2050Q2 | 2050Q3 | 2050Q4 | 2051Q1 | 2051Q2 | 2051Q3 | 2051Q4 | 2052Q1 | 2052Q2 | 2052Q3 | 2052Q4 | 2053Q1 | 2053Q2 | 2053Q3 | 2053Q4 | 2054Q1 | 2054Q2 | 2054Q3 | 2054Q4 | 2055Q1 | 2055Q2 | 2055Q3 | 2055Q4 | 2056Q1 | 2056Q2 | 2056Q3 | 2056Q4 | 2057Q1 | 2057Q2 | 2057Q3 | 2057Q4 | 2058Q1 | 2058Q2 | 2058Q3 | 2058Q4 | 2059Q1 | 2059Q2 | 2059Q3 | 2059Q4 | 2060Q1 | 2060Q2 | 2060Q3 | 2060Q4 | 2061Q1 | 2061Q2 | 2061Q3 | 2061Q4 | 2062Q1 | 2062Q2 | 2062Q3 | 2062Q4 | 2063Q1 | 2063Q2 | 2063Q3 | 2063Q4 | 2064Q1 | 2064Q2 | 2064Q3 | 2064Q4 | 2065Q1 | 2065Q2 | 2065Q3 | 2065Q4 | 2066Q1 | 2066Q2 | 2066Q3 | 2066Q4 | 2067Q1 | 2067Q2 | 2067Q3 | 2067Q4 | 2068Q1 | 2068Q2 | 2068Q3 | 2068Q4 | 2069Q1 | 2069Q2 | 2069Q3 | 2069Q4 | 2070Q1 | 2070Q2 | 2070Q3 | 2070Q4 | 2071Q1 | 2071Q2 | 2071Q3 | 2071Q4 | 2072Q1 | 2072Q2 | 2072Q3 | 2072Q4 | 2073Q1 | 2073Q2 | 2073Q3 | 2073Q4 | 2074Q1 | 2074Q2 | 2074Q3 | 2074Q4 | 2075Q1 | 2075Q2 | 2075Q3 | 2075Q4 | 2076Q1 | 2076Q2 | 2076Q3 | 2076Q4 | 2077Q1 | 2077Q2 | 2077Q3 | 2077Q4 | 2078Q1 | 2078Q2 | 2078Q3 | 2078Q4 | 2079Q1 | 2079Q2 | 2079Q3 | 2079Q4 | 2080Q1 | 2080Q2 | 2080Q3 | 2080Q4 | 2081Q1 | 2081Q2 | 2081Q3 | 2081Q4 | 2082Q1 | 2082Q2 | 2082Q3 | 2082Q4 | 2083Q1 | 2083Q2 | 2083Q3 | 2083Q4 | 2084Q1 | 2084Q2 | 2084Q3 | 2084Q4 | 2085Q1 | 2085Q2 | 2085Q3 | 2085Q4 | 2086Q1 | 2086Q2 | 2086Q3 | 2086Q4 | 2087Q1 | 2087Q2 | 2087Q3 | 2087Q4 | 2088Q1 | 2088Q2 | 2088Q3 | 2088Q4 | 2089Q1 | 2089Q2 | 2089Q3 | 2089Q4 | 2090Q1 | 2090Q2 | 2090Q3 | 2090Q4 | 2091Q1 | 2091Q2 | 2091Q3 | 2091Q4 | 2092Q1 | 2092Q2 | 2092Q3 | 2092Q4 | 2093Q1 | 2093Q2 | 2093Q3 | 2093Q4 | 2094Q1 | 2094Q2 | 2094Q3 | 2094Q4 | 2095Q1 | 2095Q2 | 2095Q3 | 2095Q4 | 2096Q1 | 2096Q2 | 2096Q3 | 2096Q4 | 2097Q1 | 2097Q2 | 2097Q3 | 2097Q4 | 2098Q1 | 2098Q2 | 2098Q3 | 2098Q4 | 2099Q1 | 2099Q2 | 2099Q3 | 2099Q4 | 2100Q1 | 2100Q2 | 2100Q3 | 2100Q4
Enter Code below | [5 empty] | 2 |  | 2 |  |  | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00 | 1Q01 | 2Q01 | 3Q01 | 4Q01 | 1Q02 | 2Q02 | 3Q02 | 4Q02 | 1Q03 | 2Q03 | 3Q03 | 4Q03 | 1Q04 | 2Q04 | 3Q04 | 4Q04 | 1Q05 | 2Q05 | 3Q05 | 4Q05 | 1Q06 | 2Q06 | 3Q06 | 4Q06 | 1Q07 | 2Q07 | 3Q07 | 4Q07 | 1Q08 | 2Q08 | 3Q08 | 4Q08 | 1Q09 | 2Q09 | 3Q09 | 4Q09 | 1Q10 | 2Q10 | 3Q10 | 4Q10 | 1Q11 | 2Q11 | 3Q11 | 4Q11 | 1Q12 | 2Q12 | 3Q12 | 4Q12 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | 1Q20 | 2Q20 | 3Q20 | 4Q20 | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22 | 2Q22 | 3Q22 | 4Q22 | 1Q23 | 2Q23 | 3Q23 | 4Q23 | 1Q24 | 2Q24 | 3Q24 | 4Q24 | 1Q25 | 2Q25 | 3Q25 | 4Q25 | 1Q26 | 2Q26 | 3Q26 | 4Q26 | 1Q27 | 2Q27 | 3Q27 | 4Q27 | 1Q28 | 2Q28 | 3Q28 | 4Q28 | 1Q29 | 2Q29 | 3Q29 | 4Q29 | 1Q30 | 2Q30 | 3Q30 | 4Q30 | 1Q31 | 2Q31 | 3Q31 | 4Q31 | 1Q32 | 2Q32 | 3Q32 | 4Q32 | 1Q33 | 2Q33 | 3Q33 | 4Q33 | 1Q34 | 2Q34 | 3Q34 | 4Q34 | 1Q35 | 2Q35 | 3Q35 | 4Q35 | 1Q36 | 2Q36 | 3Q36 | 4Q36 | 1Q37 | 2Q37 | 3Q37 | 4Q37 | 1Q38 | 2Q38 | 3Q38 | 4Q38 | 1Q39 | 2Q39 | 3Q39 | 4Q39 | 1Q40 | 2Q40 | 3Q40 | 4Q40 | 1Q41 | 2Q41 | 3Q41 | 4Q41 | 1Q42 | 2Q42 | 3Q42 | 4Q42 | 1Q43 | 2Q43 | 3Q43 | 4Q43 | 1Q44 | 2Q44 | 3Q44 | 4Q44 | 1Q45 | 2Q45 | 3Q45 | 4Q45 | 1Q46 | 2Q46 | 3Q46 | 4Q46 | 1Q47 | 2Q47 | 3Q47 | 4Q47 | 1Q48 | 2Q48 | 3Q48 | 4Q48 | 1Q49 | 2Q49 | 3Q49 | 4Q49 | 1Q50 | 2Q50 | 3Q50 | 4Q50 | 1Q51 | 2Q51 | 3Q51 | 4Q51 | 1Q52 | 2Q52 | 3Q52 | 4Q52 | 1Q53 | 2Q53 | 3Q53 | 4Q53 | 1Q54 | 2Q54 | 3Q54 | 4Q54 | 1Q55 | 2Q55 | 3Q55 | 4Q55 | 1Q56 | 2Q56 | 3Q56 | 4Q56 | 1Q57 | 2Q57 | 3Q57 | 4Q57 | 1Q58 | 2Q58 | 3Q58 | 4Q58 | 1Q59 | 2Q59 | 3Q59 | 4Q59 | 1Q60 | 2Q60 | 3Q60 | 4Q60 | 1Q61 | 2Q61 | 3Q61 | 4Q61 | 1Q62 | 2Q62 | 3Q62 | 4Q62 | 1Q63 | 2Q63 | 3Q63 | 4Q63 | 1Q64 | 2Q64 | 3Q64 | 4Q64 | 1Q65 | 2Q65 | 3Q65 | 4Q65 | 1Q66 | 2Q66 | 3Q66 | 4Q66 | 1Q67 | 2Q67 | 3Q67 | 4Q67 | 1Q68 | 2Q68 | 3Q68 | 4Q68 | 1Q69 | 2Q69 | 3Q69 | 4Q69 | 1Q70 | 2Q70 | 3Q70 | 4Q70 | 1Q71 | 2Q71 | 3Q71 | 4Q71 | 1Q72 | 2Q72 | 3Q72 | 4Q72 | 1Q73 | 2Q73 | 3Q73 | 4Q73 | 1Q74 | 2Q74 | 3Q74 | 4Q74 | 1Q75 | 2Q75 | 3Q75 | 4Q75 | 1Q76 | 2Q76 | 3Q76 | 4Q76 | 1Q77 | 2Q77 | 3Q77 | 4Q77 | 1Q78 | 2Q78 | 3Q78 | 4Q78 | 1Q79 | 2Q79 | 3Q79 | 4Q79 | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00
11 | LEVEES & FLOODWALLS |  | 15 | th row |  | 3 |  | 3 |  |  | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00 | 1Q01 | 2Q01 | 3Q01 | 4Q01 | 1Q02 | 2Q02 | 3Q02 | 4Q02 | 1Q03 | 2Q03 | 3Q03 | 4Q03 | 1Q04 | 2Q04 | 3Q04 | 4Q04 | 1Q05 | 2Q05 | 3Q05 | 4Q05 | 1Q06 | 2Q06 | 3Q06 | 4Q06 | 1Q07 | 2Q07 | 3Q07 | 4Q07 | 1Q08 | 2Q08 | 3Q08 | 4Q08 | 1Q09 | 2Q09 | 3Q09 | 4Q09 | 1Q10 | 2Q10 | 3Q10 | 4Q10 | 1Q11 | 2Q11 | 3Q11 | 4Q11 | 1Q12 | 2Q12 | 3Q12 | 4Q12 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14* | 2Q14* | 3Q14* | 4Q14* | 1Q15* | 2Q15* | 3Q15* | 4Q15* | 1Q16* | 2Q16* | 3Q16* | 4Q16* | 1Q17* | 2Q17* | 3Q17* | 4Q17* | 1Q18* | 2Q18* | 3Q18* | 4Q18* | 1Q19* | 2Q19* | 3Q19* | 4Q19* | 1Q20* | 2Q20* | 3Q20* | 4Q20* | 1Q21* | 2Q21* | 3Q21* | 4Q21* | 1Q22* | 2Q22* | 3Q22* | 4Q22* | 1Q23* | 2Q23* | 3Q23* | 4Q23* | 1Q24* | 2Q24* | 3Q24* | 4Q24* | 1Q25* | 2Q25* | 3Q25* | 4Q25* | 1Q26* | 2Q26* | 3Q26* | 4Q26* | 1Q27* | 2Q27* | 3Q27* | 4Q27* | 1Q28* | 2Q28* | 3Q28* | 4Q28* | 1Q29* | 2Q29* | 3Q29* | 4Q29* | 1Q30* | 2Q30* | 3Q30* | 4Q30* | 1Q31* | 2Q31* | 3Q31* | 4Q31* | 1Q32* | 2Q32* | 3Q32* | 4Q32* | 1Q33* | 2Q33* | 3Q33* | 4Q33* | 1Q34* | 2Q34* | 3Q34* | 4Q34* | 1Q35* | 2Q35* | 3Q35* | 4Q35* | 1Q36* | 2Q36* | 3Q36* | 4Q36* | 1Q37* | 2Q37* | 3Q37* | 4Q37* | 1Q38* | 2Q38* | 3Q38* | 4Q38* | 1Q39* | 2Q39* | 3Q39* | 4Q39* | 1Q40* | 2Q40* | 3Q40* | 4Q40* | 1Q41* | 2Q41* | 3Q41* | 4Q41* | 1Q42* | 2Q42* | 3Q42* | 4Q42* | 1Q43* | 2Q43* | 3Q43* | 4Q43* | 1Q44* | 2Q44* | 3Q44* | 4Q44* | 1Q45* | 2Q45* | 3Q45* | 4Q45* | 1Q46* | 2Q46* | 3Q46* | 4Q46* | 1Q47* | 2Q47* | 3Q47* | 4Q47* | 1Q48* | 2Q48* | 3Q48* | 4Q48* | 1Q49* | 2Q49* | 3Q49* | 4Q49* | 1Q50* | 2Q50* | 3Q50* | 4Q50* | 1Q51* | 2Q51* | 3Q51* | 4Q51* | 1Q52* | 2Q52* | 3Q52* | 4Q52* | 1Q53* | 2Q53* | 3Q53* | 4Q53* | 1Q54* | 2Q54* | 3Q54* | 4Q54* | 1Q55* | 2Q55* | 3Q55* | 4Q55* | 1Q56* | 2Q56* | 3Q56* | 4Q56* | 1Q57* | 2Q57* | 3Q57* | 4Q57* | 1Q58* | 2Q58* | 3Q58* | 4Q58* | 1Q59* | 2Q59* | 3Q59* | 4Q59* | 1Q60* | 2Q60* | 3Q60* | 4Q60* | 1Q61* | 2Q61* | 3Q61* | 4Q61* | 1Q62* | 2Q62* | 3Q62* | 4Q62* | 1Q63* | 2Q63* | 3Q63* | 4Q63* | 1Q64* | 2Q64* | 3Q64* | 4Q64* | 1Q65* | 2Q65* | 3Q65* | 4Q65* | 1Q66* | 2Q66* | 3Q66* | 4Q66* | 1Q67* | 2Q67* | 3Q67* | 4Q67* | 1Q68* | 2Q68* | 3Q68* | 4Q68* | 1Q69* | 2Q69* | 3Q69* | 4Q69* | 1Q70* | 2Q70* | 3Q70* | 4Q70* | 1Q71* | 2Q71* | 3Q71* | 4Q71* | 1Q72* | 2Q72* | 3Q72* | 4Q72* | 1Q73* | 2Q73* | 3Q73* | 4Q73* | 1Q74* | 2Q74* | 3Q74* | 4Q74* | 1Q75* | 2Q75* | 3Q75* | 4Q75* | 1Q76* | 2Q76* | 3Q76* | 4Q76* | 1Q77* | 2Q77* | 3Q77* | 4Q77* | 1Q78* | 2Q78* | 3Q78* | 4Q78* | 1Q79* | 2Q79* | 3Q79* | 4Q79* | 1Q80* | 2Q80* | 3Q80* | 4Q80* | 1Q81* | 2Q81* | 3Q81* | 4Q81* | 1Q82* | 2Q82* | 3Q82* | 4Q82* | 1Q83* | 2Q83* | 3Q83* | 4Q83* | 1Q84* | 2Q84* | 3Q84* | 4Q84* | 1Q85* | 2Q85* | 3Q85* | 4Q85* | 1Q86* | 2Q86* | 3Q86* | 4Q86* | 1Q87* | 2Q87* | 3Q87* | 4Q87* | 1Q88* | 2Q88* | 3Q88* | 4Q88* | 1Q89* | 2Q89* | 3Q89* | 4Q89* | 1Q90* | 2Q90* | 3Q90* | 4Q90* | 1Q91* | 2Q91* | 3Q91* | 4Q91* | 1Q92* | 2Q92* | 3Q92* | 4Q92* | 1Q93* | 2Q93* | 3Q93* | 4Q93* | 1Q94* | 2Q94* | 3Q94* | 4Q94* | 1Q95* | 2Q95* | 3Q95* | 4Q95* | 1Q96* | 2Q96* | 3Q96* | 4Q96* | 1Q97* | 2Q97* | 3Q97* | 4Q97* | 1Q98* | 2Q98* | 3Q98* | 4Q98* | 1Q99* | 2Q99* | 3Q99* | 4Q99* | 1Q00* | 2Q00* | 3Q00* | 4Q00*
[6 empty] | 4 |  | 4 |  |  | 1979 | 1980 | 1980 | 1980 | 1980 | 1981 | 1981 | 1981 | 1981 | 1982 | 1982 | 1982 | 1982 | 1983 | 1983 | 1983 | 1983 | 1984 | 1984 | 1984 | 1984 | 1985 | 1985 | 1985 | 1985 | 1986 | 1986 | 1986 | 1986 | 1987 | 1987 | 1987 | 1987 | 1988 | 1988 | 1988 | 1988 | 1989 | 1989 | 1989 | 1989 | 1990 | 1990 | 1990 | 1990 | 1991 | 1991 | 1991 | 1991 | 1992 | 1992 | 1992 | 1992 | 1993 | 1993 | 1993 | 1993 | 1994 | 1994 | 1994 | 1994 | 1995 | 1995 | 1995 | 1995 | 1996 | 1996 | 1996 | 1996 | 1997 | 1997 | 1997 | 1997 | 1998 | 1998 | 1998 | 1998 | 1999 | 1999 | 1999 | 1999 | 2000 | 2000 | 2000 | 2000 | 2001 | 2001 | 2001 | 2001 | 2002 | 2002 | 2002 | 2002 | 2003 | 2003 | 2003 | 2003 | 2004 | 2004 | 2004 | 2004 | 2005 | 2005 | 2005 | 2005 | 2006 | 2006 | 2006 | 2006 | 2007 | 2007 | 2007 | 2007 | 2008 | 2008 | 2008 | 2008 | 2009 | 2009 | 2009 | 2009 | 2010 | 2010 | 2010 | 2010 | 2011 | 2011 | 2011 | 2011 | 2012 | 2012 | 2012 | 2012 | 2013 | 2013 | 2013 | 2013 | 2014 | 2014 | 2014 | 2014 | 2015 | 2015 | 2015 | 2015 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031 | 2031 | 2031 | 2032 | 2032 | 2032 | 2032 | 2033 | 2033 | 2033 | 2033 | 2034 | 2034 | 2034 | 2034 | 2035 | 2035 | 2035 | 2035 | 2036 | 2036 | 2036 | 2036 | 2037 | 2037 | 2037 | 2037 | 2038 | 2038 | 2038 | 2038 | 2039 | 2039 | 2039 | 2039 | 2040 | 2040 | 2040 | 2040 | 2041 | 2041 | 2041 | 2041 | 2042 | 2042 | 2042 | 2042 | 2043 | 2043 | 2043 | 2043 | 2044 | 2044 | 2044 | 2044 | 2045 | 2045 | 2045 | 2045 | 2046 | 2046 | 2046 | 2046 | 2047 | 2047 | 2047 | 2047 | 2048 | 2048 | 2048 | 2048 | 2049 | 2049 | 2049 | 2049 | 2050 | 2050 | 2050 | 2050 | 2051 | 2051 | 2051 | 2051 | 2052 | 2052 | 2052 | 2052 | 2053 | 2053 | 2053 | 2053 | 2054 | 2054 | 2054 | 2054 | 2055 | 2055 | 2055 | 2055 | 2056 | 2056 | 2056 | 2056 | 2057 | 2057 | 2057 | 2057 | 2058 | 2058 | 2058 | 2058 | 2059 | 2059 | 2059 | 2059 | 2060 | 2060 | 2060 | 2060 | 2061 | 2061 | 2061 | 2061 | 2062 | 2062 | 2062 | 2062 | 2063 | 2063 | 2063 | 2063 | 2064 | 2064 | 2064 | 2064 | 2065 | 2065 | 2065 | 2065 | 2066 | 2066 | 2066 | 2066 | 2067 | 2067 | 2067 | 2067 | 2068 | 2068 | 2068 | 2068 | 2069 | 2069 | 2069 | 2069 | 2070 | 2070 | 2070 | 2070 | 2071 | 2071 | 2071 | 2071 | 2072 | 2072 | 2072 | 2072 | 2073 | 2073 | 2073 | 2073 | 2074 | 2074 | 2074 | 2074 | 2075 | 2075 | 2075 | 2075 | 2076 | 2076 | 2076 | 2076 | 2077 | 2077 | 2077 | 2077 | 2078 | 2078 | 2078 | 2078 | 2079 | 2079 | 2079 | 2079 | 2080 | 2080 | 2080 | 2080 | 2081 | 2081 | 2081 | 2081 | 2082 | 2082 | 2082 | 2082 | 2083 | 2083 | 2083 | 2083 | 2084 | 2084 | 2084 | 2084 | 2085 | 2085 | 2085 | 2085 | 2086 | 2086 | 2086 | 2086 | 2087 | 2087 | 2087 | 2087 | 2088 | 2088 | 2088 | 2088 | 2089 | 2089 | 2089 | 2089 | 2090 | 2090 | 2090 | 2090 | 2091 | 2091 | 2091 | 2091 | 2092 | 2092 | 2092 | 2092 | 2093 | 2093 | 2093 | 2093 | 2094 | 2094 | 2094 | 2094 | 2095 | 2095 | 2095 | 2095 | 2096 | 2096 | 2096 | 2096 | 2097 | 2097 | 2097 | 2097 | 2098 | 2098 | 2098 | 2098 | 2099 | 2099 | 2099 | 2099 | 2100 | 2100 | 2100
| Pick FY Quarter - Check Dates | FY Quarter | Dates | Index |  | 5 | CWBS | 5 | - FEATURE CODES | Wt % | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep)
| Estimate Pricing Level Date: | 1980Q1 |  | 270.52 | / | 6 | 02 | 6 | RELOCATIONS | 5% | 271.87 | 274.31 | 285.26 | 289.3 | 295.1 | 301.18 | 312.75 | 315.63 | 320.53 | 322.08 | 333.33 | 333.67 | 335.14 | 338.18 | 345.35 | 344.78 | 345.52 | 348.83 | 352.68 | 351.02 | 353.13 | 354.92 | 357.91 | 355.77 | 355.59 | 359.01 | 359.28 | 359.55 | 361.04 | 363.87 | 368.87 | 371.5 | 374.44 | 379.38 | 383.85 | 384.02 | 388.26 | 393.87 | 398.1 | 398.06 | 397.7 | 402.35 | 406.27 | 405.48 | 407.61 | 409.79 | 415.17 | 412.51 | 416.6 | 423.9 | 424.33 | 424.64 | 432.27 | 444.84 | 440.26 | 444.4 | 453.13 | 453.19 | 455.09 | 455.63 | 459.16 | 463.37 | 466.65 | 466.2 | 466.08 | 471.21 | 477.34 | 478.46 | 481.69 | 487.33 | 488.95 | 487 | 488.93 | 492.32 | 491.1 | 488.69 | 492.81 | 499.56 | 509.16 | 503.04 | 506.82 | 508.77 | 508.18 | 508.11 | 508.75 | 510.79 | 516.87 | 516.78 | 519.56 | 530.58 | 535.25 | 534.41 | 535.7 | 538.79 | 543.21 | 549.21 | 559.04 | 583.39 | 595.63 | 608.05 | 612.78 | 617.37 | 619.16 | 625.19 | 639.51 | 643.94 | 647.71 | 655.73 | 660.22 | 678.49 | 685.41 | 681.9 | 685.16 | 701.29 | 728.77 | 727.11 | 708.97 | 699.5 | 706.43 | 707.53 | 715.45 | 727.79 | 733.68 | 732.86 | 741.6 | 754.5 | 762.57 | 763.99 | 768.33 | 774.53 | 776.41 | 776.53 | 787.84 | 795.56 | 794.68 | 797.33 | 805.49 | 808.51 | 811.53 | 814.55 | 818.01 | 822.04 | 825.54 | 829.04 | 833.33 | 837.32 | 841.3 | 845.29 | 849.67 | 853.96 | 858.24 | 862.52 | 866.67 | 871.03 | 875.4 | 879.77 | 884 | 888.46 | 892.91 | 897.36 | 901.68 | 906.22 | 910.77 | 915.31 | 919.72 | 924.35 | 928.98 | 933.62 | 938.11 | 942.84 | 947.56 | 952.29 | 956.87 | 961.69 | 966.51 | 971.33 | 976.01 | 980.93 | 985.84 | 990.76 | 995.53 | 1000.54 | 1005.56 | 1010.58 | 1015.44 | 1020.56 | 1025.67 | 1030.79 | 1035.75 | 1040.97 | 1046.18 | 1051.4 | 1056.46 | 1061.79 | 1067.11 | 1072.43 | 1077.59 | 1083.02 | 1088.45 | 1093.88 | 1099.14 | 1104.68 | 1110.22 | 1115.76 | 1121.13 | 1126.78 | 1132.42 | 1138.07 | 1143.55 | 1149.31 | 1155.07 | 1160.83 | 1166.42 | 1172.3 | 1178.17 | 1184.05 | 1189.75 | 1195.74 | 1201.74 | 1207.73 | 1213.54 | 1219.66 | 1225.77 | 1231.89 | 1237.82 | 1244.05 | 1250.29 | 1256.52 | 1262.57 | 1268.93 | 1275.29 | 1281.65 | 1287.82 | 1294.31 | 1300.8 | 1307.29 | 1313.58 | 1320.2 | 1326.81 | 1333.43 | 1339.85 | 1346.6 | 1353.35 | 1360.1 | 1366.65 | 1373.53 | 1380.42 | 1387.3 | 1393.98 | 1401 | 1408.03 | 1415.05 | 1421.86 | 1429.02 | 1436.19 | 1443.35 | 1450.3 | 1457.6 | 1464.91 | 1472.22 | 1479.3 | 1486.76 | 1494.21 | 1501.66 | 1508.89 | 1516.49 | 1524.09 | 1531.69 | 1539.07 | 1546.82 | 1554.58 | 1562.33 | 1569.85 | 1577.76 | 1585.67 | 1593.58 | 1601.25 | 1609.31 | 1617.38 | 1625.45 | 1633.27 | 1641.5 | 1649.73 | 1657.96 | 1665.94 | 1674.33 | 1682.72 | 1691.11 | 1699.26 | 1707.82 | 1716.38 | 1724.94 | 1733.24 | 1741.97 | 1750.7 | 1759.44 | 1767.91 | 1776.81 | 1785.72 | 1794.62 | 1803.26 | 1812.35 | 1821.43 | 1830.52 | 1839.33 | 1848.6 | 1857.86 | 1867.13 | 1876.12 | 1885.57 | 1895.02 | 1904.47 | 1913.64 | 1923.28 | 1932.92 | 1942.56 | 1951.91 | 1961.74 | 1971.58 | 1981.41 | 1990.95 | 2000.98 | 2011.01 | 2021.04 | 2030.77 | 2041 | 2051.23 | 2061.46 | 2071.38 | 2081.82 | 2092.25 | 2102.69 | 2112.81 | 2123.45 | 2134.1 | 2144.74 | 2155.07 | 2165.92 | 2176.78 | 2187.64 | 2198.17 | 2209.24 | 2220.32 | 2231.39 | 2242.13 | 2253.43 | 2264.72 | 2276.02 | 2286.97 | 2298.5 | 2310.02 | 2321.54 | 2332.71 | 2344.47 | 2356.22 | 2367.97 | 2379.37 | 2391.35 | 2403.34 | 2415.33 | 2426.96 | 2439.18 | 2451.41 | 2463.63 | 2475.49 | 2487.97 | 2500.44 | 2512.91 | 2525 | 2537.72 | 2550.45 | 2563.17 | 2575.5 | 2588.48 | 2601.45 | 2614.43 | 2627.01 | 2640.25 | 2653.48 | 2666.72 | 2679.55 | 2693.05 | 2706.55 | 2720.05 | 2733.15 | 2746.92 | 2760.68 | 2774.45 | 2787.81 | 2801.85 | 2815.9 | 2829.94 | 2843.57 | 2857.89 | 2872.22 | 2886.54 | 2900.44 | 2915.05 | 2929.66 | 2944.27 | 2958.45 | 2973.35 | 2988.25 | 3003.16 | 3017.61 | 3032.82 | 3048.02 | 3063.22 | 3077.97 | 3093.47 | 3108.98 | 3124.48 | 3139.53 | 3155.34 | 3171.16 | 3186.97 | 3202.32 | 3218.45 | 3234.58 | 3250.71 | 3266.36 | 3282.82 | 3299.27 | 3315.73 | 3331.69 | 3348.47 | 3365.26 | 3382.04 | 3398.32 | 3415.44 | 3432.56 | 3449.68 | 3466.29 | 3483.75 | 3501.21 | 3518.68 | 3535.62 | 3553.43 | 3571.24 | 3589.05 | 3606.33 | 3624.5 | 3642.66 | 3660.83 | 3678.45 | 3696.99 | 3715.52 | 3734.05 | 3752.02 | 3770.93 | 3789.83 | 3808.73 | 3827.06 | 3846.34 | 3865.62 | 3884.9 | 3903.61 | 3923.27 | 3942.94 | 3962.6 | 3981.68 | 4001.74 | 4021.8 | 4041.85 | 4061.31 | 4081.77 | 4102.23 | 4122.69 | 4142.54 | 4163.41 | 4184.28 | 4205.15 | 4225.39 | 4246.67 | 4267.96 | 4289.25 | 4309.9 | 4331.61 | 4353.32 | 4375.03 | 4396.09 | 4418.24 | 4440.39 | 4462.53
| Middle Point of Construction Date: | 2012Q1 |  | 785.64 | = | 7 | 03 | 7 | RESERVOIRS | 5% | 274.7 | 276.51 | 293.22 | 297.8 | 300.01 | 305.39 | 325.04 | 330.69 | 335.73 | 336.83 | 356.25 | 357.68 | 359.13 | 360.28 | 370.01 | 370.86 | 371.61 | 372.33 | 379.08 | 378.13 | 379.31 | 381.22 | 383.57 | 383.71 | 384.37 | 386.05 | 387.94 | 388.09 | 389.18 | 390.97 | 398.32 | 399.74 | 402.12 | 405.81 | 410.03 | 411.79 | 414.93 | 418.28 | 423.45 | 424.66 | 426.62 | 432.72 | 440.03 | 441.87 | 443.75 | 445.96 | 448.72 | 449.9 | 452.29 | 455.74 | 459.63 | 460.86 | 463.31 | 466.47 | 468.97 | 469.52 | 471.63 | 476.39 | 481 | 481.85 | 483.22 | 489.04 | 494.52 | 495.36 | 497.21 | 501.71 | 505.9 | 506.27 | 507.4 | 510.01 | 512.1 | 514.82 | 517.4 | 520.17 | 522.7 | 525.43 | 532.68 | 539.36 | 544.82 | 545.17 | 546.17 | 549.66 | 554.69 | 558.99 | 563.32 | 563.43 | 570.76 | 574.83 | 578.45 | 588.04 | 596.92 | 597.44 | 599.3 | 601.96 | 608.05 | 612.58 | 618.26 | 622.07 | 631.33 | 636.79 | 643.64 | 648.68 | 655.31 | 659.06 | 666.12 | 668.01 | 669.42 | 686.51 | 694.1 | 706.17 | 718.54 | 718.99 | 720.94 | 725.82 | 737.53 | 744.72 | 754.07 | 755.1 | 766.33 | 770.44 | 778.06 | 780.49 | 798.39 | 799.72 | 802.29 | 811.14 | 821.33 | 824.47 | 828.38 | 833.59 | 844.93 | 845.07 | 849.84 | 853.83 | 869.35 | 869.57 | 871.77 | 875.04 | 878.31 | 881.58 | 885.32 | 889.68 | 893.47 | 897.26 | 901.9 | 906.21 | 910.53 | 914.84 | 919.59 | 924.22 | 928.86 | 933.49 | 937.98 | 942.71 | 947.43 | 952.16 | 956.74 | 961.56 | 966.38 | 971.2 | 975.88 | 980.79 | 985.71 | 990.63 | 995.39 | 1000.41 | 1005.42 | 1010.44 | 1015.3 | 1020.42 | 1025.53 | 1030.65 | 1035.61 | 1040.83 | 1046.04 | 1051.26 | 1056.32 | 1061.64 | 1066.96 | 1072.28 | 1077.45 | 1082.87 | 1088.3 | 1093.73 | 1099 | 1104.53 | 1110.07 | 1115.61 | 1120.98 | 1126.62 | 1132.27 | 1137.92 | 1143.4 | 1149.16 | 1154.92 | 1160.68 | 1166.26 | 1172.14 | 1178.01 | 1183.89 | 1189.59 | 1195.58 | 1201.57 | 1207.57 | 1213.38 | 1219.49 | 1225.61 | 1231.72 | 1237.65 | 1243.88 | 1250.12 | 1256.35 | 1262.4 | 1268.76 | 1275.12 | 1281.48 | 1287.65 | 1294.14 | 1300.62 | 1307.11 | 1313.4 | 1320.02 | 1326.63 | 1333.25 | 1339.67 | 1346.42 | 1353.17 | 1359.92 | 1366.46 | 1373.35 | 1380.23 | 1387.11 | 1393.79 | 1400.81 | 1407.84 | 1414.86 | 1421.67 | 1428.83 | 1435.99 | 1443.15 | 1450.1 | 1457.41 | 1464.71 | 1472.02 | 1479.1 | 1486.56 | 1494.01 | 1501.46 | 1508.69 | 1516.29 | 1523.89 | 1531.49 | 1538.86 | 1546.61 | 1554.36 | 1562.12 | 1569.64 | 1577.54 | 1585.45 | 1593.36 | 1601.03 | 1609.09 | 1617.16 | 1625.23 | 1633.05 | 1641.28 | 1649.5 | 1657.73 | 1665.71 | 1674.1 | 1682.49 | 1690.89 | 1699.03 | 1707.58 | 1716.14 | 1724.7 | 1733.01 | 1741.74 | 1750.47 | 1759.2 | 1767.67 | 1776.57 | 1785.48 | 1794.38 | 1803.02 | 1812.1 | 1821.19 | 1830.27 | 1839.08 | 1848.34 | 1857.61 | 1866.87 | 1875.86 | 1885.31 | 1894.76 | 1904.21 | 1913.38 | 1923.02 | 1932.66 | 1942.3 | 1951.65 | 1961.48 | 1971.31 | 1981.14 | 1990.68 | 2000.71 | 2010.74 | 2020.76 | 2030.49 | 2040.72 | 2050.95 | 2061.18 | 2071.1 | 2081.54 | 2091.97 | 2102.4 | 2112.52 | 2123.17 | 2133.81 | 2144.45 | 2154.77 | 2165.63 | 2176.49 | 2187.34 | 2197.87 | 2208.94 | 2220.01 | 2231.09 | 2241.83 | 2253.12 | 2264.42 | 2275.71 | 2286.66 | 2298.18 | 2309.7 | 2321.22 | 2332.4 | 2344.15 | 2355.9 | 2367.65 | 2379.05 | 2391.03 | 2403.02 | 2415 | 2426.63 | 2438.85 | 2451.08 | 2463.3 | 2475.16 | 2487.63 | 2500.1 | 2512.57 | 2524.66 | 2537.38 | 2550.1 | 2562.82 | 2575.16 | 2588.13 | 2601.1 | 2614.07 | 2626.66 | 2639.89 | 2653.12 | 2666.36 | 2679.19 | 2692.69 | 2706.19 | 2719.68 | 2732.78 | 2746.54 | 2760.31 | 2774.08 | 2787.43 | 2801.47 | 2815.52 | 2829.56 | 2843.18 | 2857.5 | 2871.83 | 2886.15 | 2900.04 | 2914.65 | 2929.26 | 2943.87 | 2958.04 | 2972.95 | 2987.85 | 3002.75 | 3017.2 | 3032.4 | 3047.6 | 3062.8 | 3077.55 | 3093.05 | 3108.56 | 3124.06 | 3139.1 | 3154.91 | 3170.73 | 3186.54 | 3201.88 | 3218.01 | 3234.14 | 3250.27 | 3265.92 | 3282.37 | 3298.83 | 3315.28 | 3331.24 | 3348.02 | 3364.8 | 3381.58 | 3397.86 | 3414.98 | 3432.1 | 3449.22 | 3465.82 | 3483.28 | 3500.74 | 3518.2 | 3535.14 | 3552.95 | 3570.75 | 3588.56 | 3605.84 | 3624 | 3642.17 | 3660.34 | 3677.96 | 3696.48 | 3715.01 | 3733.54 | 3751.51 | 3770.41 | 3789.31 | 3808.21 | 3826.55 | 3845.82 | 3865.1 | 3884.38 | 3903.08 | 3922.74 | 3942.4 | 3962.06 | 3981.14 | 4001.19 | 4021.25 | 4041.31 | 4060.76 | 4081.22 | 4101.67 | 4122.13 | 4141.98 | 4162.84 | 4183.71 | 4204.57 | 4224.82 | 4246.1 | 4267.38 | 4288.67 | 4309.31 | 4331.02 | 4352.73 | 4374.44 | 4395.5 | 4417.64 | 4439.78 | 4461.93 | 4483.41 | 4505.99 | 4528.58 | 4551.17 | 4573.08 | 4596.11 | 4619.15 | 4642.19 | 4664.54 | 4688.04 | 4711.54 | 4735.03 | 4757.83 | 4781.8 | 4805.77 | 4829.73
[6 empty] | 8 | 04 | 8 | DAMS | 15% | 268.61 | 272.52 | 281.67 | 285.68 | 291.27 | 297.99 | 308.49 | 311.94 | 317.12 | 318.98 | 328.96 | 329.62 | 329.81 | 331.82 | 337.99 | 339.43 | 339.85 | 343.07 | 347.13 | 346.95 | 348.18 | 350.26 | 351.95 | 351.5 | 351.32 | 353.16 | 353.43 | 353.83 | 355.05 | 356.86 | 360.95 | 363.11 | 366.73 | 370.67 | 374.28 | 375.6 | 380.19 | 383.99 | 387.52 | 388.29 | 389.13 | 392.24 | 396.69 | 397.57 | 400.37 | 402.16 | 404.98 | 404.39 | 406.6 | 409.86 | 412.2 | 412.6 | 416.86 | 423.16 | 424.3 | 426.5 | 430.77 | 434.22 | 437.46 | 439.04 | 443.1 | 449.75 | 453.64 | 453.85 | 455.02 | 458.98 | 462.87 | 463.99 | 465.98 | 470.03 | 472.01 | 473.15 | 475.97 | 479.55 | 480.64 | 480.07 | 482.4 | 487.32 | 492.58 | 491.25 | 494.04 | 496.25 | 498.01 | 498.82 | 500.65 | 501.87 | 505.85 | 507.48 | 509.54 | 517.86 | 523.54 | 523.71 | 524.83 | 527.44 | 530.53 | 535 | 543.14 | 561.95 | 574.06 | 587.47 | 594.9 | 598.72 | 603.91 | 611.03 | 625.48 | 631.2 | 637.92 | 647.39 | 651.74 | 668.81 | 674.55 | 673.9 | 678.85 | 694.86 | 719.14 | 720.13 | 705.76 | 697.72 | 701.88 | 701.98 | 708.05 | 715.18 | 723.36 | 723.26 | 729.81 | 742.73 | 751.52 | 752.53 | 758.31 | 763.62 | 764.46 | 765.52 | 772.81 | 776.78 | 781.78 | 782.77 | 790.24 | 793.2 | 796.17 | 799.13 | 802.53 | 806.48 | 809.91 | 813.35 | 817.55 | 821.46 | 825.37 | 829.29 | 833.59 | 837.79 | 841.99 | 846.19 | 850.26 | 854.54 | 858.83 | 863.11 | 867.27 | 871.63 | 876 | 880.37 | 884.61 | 889.07 | 893.52 | 897.98 | 902.3 | 906.85 | 911.39 | 915.94 | 920.35 | 924.99 | 929.62 | 934.26 | 938.76 | 943.48 | 948.21 | 952.94 | 957.53 | 962.35 | 967.18 | 972 | 976.68 | 981.6 | 986.52 | 991.44 | 996.22 | 1001.23 | 1006.25 | 1011.27 | 1016.14 | 1021.26 | 1026.38 | 1031.5 | 1036.46 | 1041.68 | 1046.91 | 1052.13 | 1057.19 | 1062.52 | 1067.84 | 1073.17 | 1078.34 | 1083.77 | 1089.2 | 1094.63 | 1099.9 | 1105.44 | 1110.98 | 1116.53 | 1121.9 | 1127.55 | 1133.2 | 1138.86 | 1144.34 | 1150.1 | 1155.87 | 1161.63 | 1167.22 | 1173.1 | 1178.99 | 1184.87 | 1190.57 | 1196.57 | 1202.56 | 1208.56 | 1214.38 | 1220.5 | 1226.62 | 1232.73 | 1238.67 | 1244.91 | 1251.15 | 1257.39 | 1263.44 | 1269.81 | 1276.17 | 1282.54 | 1288.71 | 1295.2 | 1301.69 | 1308.19 | 1314.48 | 1321.11 | 1327.73 | 1334.35 | 1340.77 | 1347.53 | 1354.28 | 1361.04 | 1367.59 | 1374.48 | 1381.37 | 1388.26 | 1394.94 | 1401.97 | 1409 | 1416.02 | 1422.84 | 1430.01 | 1437.18 | 1444.34 | 1451.3 | 1458.61 | 1465.92 | 1473.23 | 1480.32 | 1487.78 | 1495.24 | 1502.7 | 1509.93 | 1517.54 | 1525.14 | 1532.75 | 1540.13 | 1547.89 | 1555.65 | 1563.4 | 1570.93 | 1578.84 | 1586.76 | 1594.67 | 1602.35 | 1610.42 | 1618.49 | 1626.57 | 1634.4 | 1642.63 | 1650.86 | 1659.1 | 1667.08 | 1675.48 | 1683.88 | 1692.28 | 1700.43 | 1708.99 | 1717.56 | 1726.13 | 1734.43 | 1743.17 | 1751.91 | 1760.65 | 1769.12 | 1778.04 | 1786.95 | 1795.86 | 1804.51 | 1813.6 | 1822.69 | 1831.78 | 1840.6 | 1849.87 | 1859.14 | 1868.41 | 1877.41 | 1886.87 | 1896.32 | 1905.78 | 1914.96 | 1924.6 | 1934.25 | 1943.9 | 1953.26 | 1963.1 | 1972.94 | 1982.78 | 1992.32 | 2002.36 | 2012.39 | 2022.43 | 2032.17 | 2042.4 | 2052.64 | 2062.88 | 2072.81 | 2083.25 | 2093.69 | 2104.14 | 2114.27 | 2124.92 | 2135.57 | 2146.22 | 2156.55 | 2167.42 | 2178.28 | 2189.14 | 2199.68 | 2210.76 | 2221.85 | 2232.93 | 2243.68 | 2254.98 | 2266.28 | 2277.59 | 2288.55 | 2300.08 | 2311.61 | 2323.14 | 2334.32 | 2346.08 | 2357.84 | 2369.6 | 2381.01 | 2393 | 2405 | 2416.99 | 2428.63 | 2440.86 | 2453.1 | 2465.33 | 2477.2 | 2489.68 | 2502.16 | 2514.64 | 2526.74 | 2539.47 | 2552.2 | 2564.93 | 2577.28 | 2590.26 | 2603.25 | 2616.23 | 2628.82 | 2642.07 | 2655.31 | 2668.55 | 2681.4 | 2694.91 | 2708.42 | 2721.93 | 2735.03 | 2748.81 | 2762.59 | 2776.36 | 2789.73 | 2803.78 | 2817.84 | 2831.89 | 2845.52 | 2859.86 | 2874.19 | 2888.53 | 2902.43 | 2917.06 | 2931.68 | 2946.3 | 2960.48 | 2975.4 | 2990.31 | 3005.23 | 3019.69 | 3034.91 | 3050.12 | 3065.33 | 3080.09 | 3095.6 | 3111.12 | 3126.64 | 3141.69 | 3157.52 | 3173.34 | 3189.17 | 3204.52 | 3220.67 | 3236.81 | 3252.95 | 3268.61 | 3285.08 | 3301.55 | 3318.01 | 3333.98 | 3350.78 | 3367.58 | 3384.37 | 3400.66 | 3417.8 | 3434.93 | 3452.06 | 3468.68 | 3486.15 | 3503.63 | 3521.1 | 3538.05 | 3555.88 | 3573.7 | 3591.52 | 3608.81 | 3626.99 | 3645.17 | 3663.35 | 3680.99 | 3699.53 | 3718.08 | 3736.62 | 3754.61 | 3773.52 | 3792.44 | 3811.35 | 3829.7 | 3848.99 | 3868.29 | 3887.58 | 3906.29 | 3925.97 | 3945.65 | 3965.33 | 3984.42 | 4004.49 | 4024.57 | 4044.64 | 4064.11 | 4084.58 | 4105.06 | 4125.53 | 4145.39 | 4166.27 | 4187.16 | 4208.04 | 4228.3 | 4249.6 | 4270.9 | 4292.2 | 4312.86 | 4334.59 | 4356.32 | 4378.05
|  |  | Escalation Percentage: -> | 290.4% |  | 9 | 05 | 9 | LOCKS | 2% | 267.29 | 271.45 | 280.61 | 285.09 | 290.51 | 297.43 | 307.88 | 311.66 | 316.52 | 318.59 | 328.44 | 329.3 | 329.66 | 332.24 | 338.19 | 339.29 | 339.75 | 342.69 | 346.67 | 346.19 | 345.85 | 348 | 349.9 | 349.39 | 348.48 | 350.45 | 351.03 | 351.44 | 352.56 | 354.8 | 358.68 | 361.3 | 365.49 | 370.09 | 373.68 | 374.96 | 378.98 | 383.12 | 385.9 | 386.53 | 386.61 | 389.75 | 393.42 | 393.88 | 396.33 | 398.06 | 400.61 | 399.93 | 402.01 | 405.84 | 407.64 | 407.9 | 411.78 | 418.65 | 419.5 | 422.06 | 426.64 | 429.83 | 432.86 | 434.57 | 438.73 | 445.29 | 449.25 | 449.32 | 449.94 | 453.54 | 457.63 | 458.66 | 460.32 | 464.19 | 466.28 | 467.21 | 469.68 | 473.13 | 474.11 | 472.96 | 474.43 | 478.77 | 484.44 | 482.76 | 485.77 | 488.74 | 490.22 | 490.8 | 492.11 | 493.23 | 497.55 | 498.84 | 500.92 | 510.32 | 516.3 | 516.21 | 517.34 | 520.67 | 523.36 | 528.58 | 537.81 | 560.55 | 572.89 | 588.45 | 595.76 | 599.22 | 602.17 | 610.26 | 624.39 | 630.3 | 638.4 | 648.48 | 652.21 | 671.85 | 677.88 | 676.32 | 682.18 | 701.14 | 730.54 | 728.97 | 708.16 | 696.16 | 699.79 | 701.92 | 708.17 | 718.31 | 725.64 | 725.88 | 733.84 | 748.48 | 756.76 | 756.73 | 760.93 | 765.02 | 765.35 | 764.34 | 771.04 | 775.23 | 778.58 | 780.15 | 787.78 | 790.73 | 793.69 | 796.64 | 800.03 | 803.97 | 807.39 | 810.82 | 815.01 | 818.91 | 822.81 | 826.7 | 830.99 | 835.18 | 839.37 | 843.55 | 847.61 | 851.88 | 856.15 | 860.42 | 864.57 | 868.92 | 873.28 | 877.63 | 881.86 | 886.3 | 890.74 | 895.18 | 899.49 | 904.03 | 908.56 | 913.09 | 917.48 | 922.11 | 926.73 | 931.35 | 935.83 | 940.55 | 945.26 | 949.98 | 954.55 | 959.36 | 964.17 | 968.98 | 973.64 | 978.55 | 983.45 | 988.36 | 993.11 | 998.12 | 1003.12 | 1008.12 | 1012.98 | 1018.08 | 1023.18 | 1028.29 | 1033.24 | 1038.44 | 1043.65 | 1048.85 | 1053.9 | 1059.21 | 1064.52 | 1069.83 | 1074.98 | 1080.39 | 1085.81 | 1091.22 | 1096.48 | 1102 | 1107.53 | 1113.05 | 1118.41 | 1124.04 | 1129.68 | 1135.31 | 1140.78 | 1146.52 | 1152.27 | 1158.02 | 1163.59 | 1169.45 | 1175.32 | 1181.18 | 1186.86 | 1192.84 | 1198.82 | 1204.8 | 1210.6 | 1216.7 | 1222.8 | 1228.9 | 1234.81 | 1241.03 | 1247.25 | 1253.47 | 1259.51 | 1265.85 | 1272.2 | 1278.54 | 1284.7 | 1291.17 | 1297.64 | 1304.11 | 1310.39 | 1316.99 | 1323.6 | 1330.2 | 1336.6 | 1343.33 | 1350.07 | 1356.8 | 1363.33 | 1370.2 | 1377.07 | 1383.94 | 1390.6 | 1397.6 | 1404.61 | 1411.62 | 1418.41 | 1425.56 | 1432.7 | 1439.85 | 1446.78 | 1454.07 | 1461.36 | 1468.65 | 1475.72 | 1483.15 | 1490.58 | 1498.02 | 1505.23 | 1512.81 | 1520.4 | 1527.98 | 1535.33 | 1543.07 | 1550.8 | 1558.54 | 1566.04 | 1573.93 | 1581.82 | 1589.71 | 1597.36 | 1605.41 | 1613.46 | 1621.5 | 1629.31 | 1637.52 | 1645.72 | 1653.93 | 1661.89 | 1670.27 | 1678.64 | 1687.01 | 1695.13 | 1703.67 | 1712.21 | 1720.75 | 1729.04 | 1737.75 | 1746.46 | 1755.17 | 1763.62 | 1772.5 | 1781.39 | 1790.27 | 1798.89 | 1807.95 | 1817.01 | 1826.08 | 1834.87 | 1844.11 | 1853.35 | 1862.6 | 1871.56 | 1880.99 | 1890.42 | 1899.85 | 1908.99 | 1918.61 | 1928.23 | 1937.85 | 1947.17 | 1956.98 | 1966.79 | 1976.6 | 1986.12 | 1996.12 | 2006.13 | 2016.13 | 2025.84 | 2036.05 | 2046.25 | 2056.46 | 2066.36 | 2076.77 | 2087.18 | 2097.59 | 2107.68 | 2118.3 | 2128.92 | 2139.54 | 2149.84 | 2160.67 | 2171.5 | 2182.33 | 2192.83 | 2203.88 | 2214.93 | 2225.98 | 2236.69 | 2247.96 | 2259.23 | 2270.5 | 2281.43 | 2292.92 | 2304.41 | 2315.91 | 2327.05 | 2338.78 | 2350.5 | 2362.22 | 2373.59 | 2385.55 | 2397.51 | 2409.47 | 2421.07 | 2433.26 | 2445.46 | 2457.66 | 2469.49 | 2481.93 | 2494.37 | 2506.81 | 2518.88 | 2531.57 | 2544.26 | 2556.95 | 2569.26 | 2582.2 | 2595.14 | 2608.09 | 2620.64 | 2633.84 | 2647.05 | 2660.25 | 2673.05 | 2686.52 | 2699.99 | 2713.45 | 2726.51 | 2740.25 | 2753.99 | 2767.72 | 2781.04 | 2795.06 | 2809.07 | 2823.08 | 2836.67 | 2850.96 | 2865.25 | 2879.54 | 2893.4 | 2907.98 | 2922.55 | 2937.13 | 2951.27 | 2966.13 | 2981 | 2995.87 | 3010.29 | 3025.46 | 3040.62 | 3055.79 | 3070.5 | 3085.97 | 3101.44 | 3116.9 | 3131.91 | 3147.69 | 3163.46 | 3179.24 | 3194.55 | 3210.64 | 3226.73 | 3242.83 | 3258.44 | 3274.85 | 3291.27 | 3307.68 | 3323.61 | 3340.35 | 3357.09 | 3373.84 | 3390.08 | 3407.16 | 3424.24 | 3441.31 | 3457.88 | 3475.3 | 3492.72 | 3510.14 | 3527.04 | 3544.81 | 3562.57 | 3580.34 | 3597.58 | 3615.7 | 3633.83 | 3651.95 | 3669.53 | 3688.02 | 3706.5 | 3724.99 | 3742.92 | 3761.78 | 3780.63 | 3799.49 | 3817.78 | 3837.01 | 3856.24 | 3875.48 | 3894.13 | 3913.75 | 3933.37 | 3952.99 | 3972.02 | 3992.03 | 4012.04 | 4032.05 | 4051.46 | 4071.87 | 4092.28 | 4112.69 | 4132.49 | 4153.3 | 4174.12 | 4194.94 | 4215.14 | 4236.37 | 4257.61 | 4278.84 | 4299.44 | 4321.1 | 4342.76 | 4364.42
[6 empty] | 10 | 06 | 10 | FISH & WILDLIFE FACILITIES | 5% | 272.96 | 276.04 | 284.61 | 287.69 | 293.79 | 300 | 309.83 | 312.44 | 317.17 | 318.26 | 327.74 | 327.83 | 327.53 | 329.77 | 336.78 | 337.58 | 337.59 | 341.9 | 345.41 | 344.61 | 344.74 | 346.93 | 349.22 | 347.84 | 347.27 | 349.61 | 349.34 | 349.75 | 350.28 | 352.65 | 356.54 | 359.07 | 362.38 | 367.09 | 370.86 | 371.49 | 374.97 | 379.49 | 382.47 | 382.81 | 382.1 | 385.48 | 388.93 | 389.01 | 391.31 | 393.28 | 396.94 | 395.33 | 398.09 | 402.68 | 403.56 | 403.94 | 409.21 | 419.09 | 417.86 | 421.18 | 427.15 | 429.69 | 432.59 | 434.12 | 438.14 | 444.64 | 447.98 | 447.96 | 447.8 | 452.65 | 457.78 | 459.09 | 461.23 | 466.4 | 468.57 | 468.4 | 469.97 | 474.07 | 474.38 | 472.57 | 474.86 | 480.31 | 487.47 | 483.86 | 487.08 | 489.21 | 489.75 | 489.55 | 490.33 | 491.91 | 496.69 | 497.31 | 499.28 | 508.67 | 514.07 | 513.82 | 514.15 | 516.87 | 520.35 | 525.69 | 534.75 | 558.9 | 571.55 | 586.56 | 593.35 | 597.76 | 600.97 | 608.18 | 624.32 | 630.14 | 636.39 | 645.47 | 649.01 | 668.79 | 674.11 | 671.55 | 675.58 | 693.72 | 722.13 | 719.86 | 698.29 | 686.42 | 689.95 | 691.34 | 696.93 | 707.21 | 712.33 | 711.42 | 718.73 | 732.94 | 740.7 | 740.08 | 744.72 | 749.69 | 749.6 | 749.46 | 758.43 | 764.29 | 764.9 | 766.75 | 775.02 | 777.93 | 780.83 | 783.74 | 787.07 | 790.94 | 794.31 | 797.68 | 801.81 | 805.64 | 809.48 | 813.31 | 817.53 | 821.65 | 825.77 | 829.89 | 833.88 | 838.08 | 842.29 | 846.49 | 850.56 | 854.85 | 859.13 | 863.42 | 867.57 | 871.94 | 876.31 | 880.68 | 884.92 | 889.38 | 893.84 | 898.3 | 902.62 | 907.17 | 911.72 | 916.26 | 920.68 | 925.31 | 929.95 | 934.59 | 939.09 | 943.82 | 948.55 | 953.28 | 957.87 | 962.7 | 967.52 | 972.35 | 977.03 | 981.95 | 986.87 | 991.79 | 996.57 | 1001.59 | 1006.61 | 1011.63 | 1016.5 | 1021.62 | 1026.74 | 1031.86 | 1036.83 | 1042.05 | 1047.28 | 1052.5 | 1057.57 | 1062.89 | 1068.22 | 1073.55 | 1078.72 | 1084.15 | 1089.59 | 1095.02 | 1100.29 | 1105.84 | 1111.38 | 1116.92 | 1122.3 | 1127.95 | 1133.61 | 1139.26 | 1144.74 | 1150.51 | 1156.28 | 1162.04 | 1167.64 | 1173.52 | 1179.4 | 1185.29 | 1190.99 | 1196.99 | 1202.99 | 1208.99 | 1214.81 | 1220.93 | 1227.05 | 1233.17 | 1239.11 | 1245.35 | 1251.59 | 1257.83 | 1263.89 | 1270.26 | 1276.62 | 1282.99 | 1289.17 | 1295.66 | 1302.16 | 1308.65 | 1314.95 | 1321.58 | 1328.2 | 1334.82 | 1341.25 | 1348.01 | 1354.76 | 1361.52 | 1368.08 | 1374.97 | 1381.86 | 1388.75 | 1395.44 | 1402.47 | 1409.5 | 1416.53 | 1423.35 | 1430.52 | 1437.69 | 1444.86 | 1451.81 | 1459.13 | 1466.44 | 1473.75 | 1480.85 | 1488.31 | 1495.77 | 1503.23 | 1510.47 | 1518.07 | 1525.68 | 1533.29 | 1540.67 | 1548.44 | 1556.2 | 1563.96 | 1571.49 | 1579.41 | 1587.32 | 1595.24 | 1602.92 | 1610.99 | 1619.07 | 1627.14 | 1634.98 | 1643.21 | 1651.45 | 1659.69 | 1667.68 | 1676.08 | 1684.48 | 1692.88 | 1701.03 | 1709.6 | 1718.17 | 1726.74 | 1735.05 | 1743.79 | 1752.53 | 1761.27 | 1769.75 | 1778.67 | 1787.58 | 1796.5 | 1805.15 | 1814.24 | 1823.33 | 1832.43 | 1841.25 | 1850.52 | 1859.8 | 1869.08 | 1878.07 | 1887.54 | 1897 | 1906.46 | 1915.64 | 1925.29 | 1934.94 | 1944.59 | 1953.95 | 1963.79 | 1973.64 | 1983.48 | 1993.03 | 2003.07 | 2013.11 | 2023.15 | 2032.89 | 2043.13 | 2053.37 | 2063.61 | 2073.55 | 2083.99 | 2094.44 | 2104.88 | 2115.02 | 2125.67 | 2136.33 | 2146.98 | 2157.32 | 2168.18 | 2179.05 | 2189.92 | 2200.46 | 2211.55 | 2222.63 | 2233.72 | 2244.47 | 2255.78 | 2267.09 | 2278.39 | 2289.36 | 2300.89 | 2312.43 | 2323.96 | 2335.15 | 2346.91 | 2358.68 | 2370.44 | 2381.85 | 2393.85 | 2405.85 | 2417.85 | 2429.49 | 2441.73 | 2453.97 | 2466.21 | 2478.08 | 2490.56 | 2503.05 | 2515.53 | 2527.64 | 2540.37 | 2553.11 | 2565.84 | 2578.19 | 2591.18 | 2604.17 | 2617.16 | 2629.76 | 2643.01 | 2656.25 | 2669.5 | 2682.35 | 2695.87 | 2709.38 | 2722.89 | 2736 | 2749.78 | 2763.57 | 2777.35 | 2790.72 | 2804.78 | 2818.84 | 2832.9 | 2846.53 | 2860.87 | 2875.21 | 2889.55 | 2903.46 | 2918.09 | 2932.72 | 2947.35 | 2961.53 | 2976.45 | 2991.37 | 3006.29 | 3020.76 | 3035.98 | 3051.2 | 3066.42 | 3081.18 | 3096.7 | 3112.22 | 3127.75 | 3142.8 | 3158.64 | 3174.47 | 3190.3 | 3205.66 | 3221.81 | 3237.96 | 3254.11 | 3269.77 | 3286.24 | 3302.72 | 3319.19 | 3335.17 | 3351.97 | 3368.77 | 3385.57 | 3401.87 | 3419.01 | 3436.15 | 3453.28 | 3469.91 | 3487.39 | 3504.87 | 3522.35 | 3539.31 | 3557.14 | 3574.97 | 3592.8 | 3610.09 | 3628.28 | 3646.47 | 3664.65 | 3682.29 | 3700.85 | 3719.4 | 3737.95 | 3755.94 | 3774.86 | 3793.78 | 3812.71 | 3831.06 | 3850.36 | 3869.66 | 3888.96 | 3907.68 | 3927.37 | 3947.05 | 3966.74 | 3985.83 | 4005.91 | 4025.99 | 4046.07 | 4065.55 | 4086.03 | 4106.51 | 4126.99 | 4146.86 | 4167.75 | 4188.64 | 4209.53 | 4229.8 | 4251.11 | 4272.42 | 4293.73
| Paste the Web Address into browser for downloadable (.pdf) source of factors: |  |  |  |  | 11 | 07 | 11 | POWER PLANT | 10% | 254.91 | 261.92 | 271.8 | 276.78 | 282.49 | 290.3 | 299.66 | 305.47 | 309.82 | 312.2 | 318.6 | 318.44 | 319.76 | 322.14 | 326.42 | 328.13 | 329.23 | 331.22 | 336.05 | 336.13 | 335.55 | 336.98 | 338.59 | 338.98 | 339.42 | 341.68 | 342.4 | 343.89 | 344.84 | 346.64 | 350.24 | 352.88 | 355.43 | 359.77 | 362.57 | 365.95 | 370.58 | 375.63 | 379.26 | 380.68 | 382.72 | 385.98 | 390.04 | 392.37 | 395.96 | 398.37 | 400.46 | 401.16 | 403.39 | 406.1 | 407.68 | 408.81 | 411.75 | 415.92 | 417.3 | 419.18 | 422.2 | 424.51 | 426.7 | 429.08 | 432.79 | 437.55 | 440.85 | 442.1 | 441.89 | 444.43 | 446.64 | 447.38 | 447.1 | 450.74 | 453.52 | 455.29 | 457.05 | 458.84 | 460.27 | 459.69 | 461.41 | 464.12 | 467.99 | 467.98 | 469.5 | 472.63 | 473.85 | 474.95 | 476.65 | 478.03 | 481.14 | 482.73 | 483.76 | 489.01 | 493.68 | 493.88 | 494.64 | 496.8 | 499.15 | 502.53 | 508.32 | 524.12 | 534.82 | 545 | 550.58 | 555.21 | 557.62 | 565.16 | 578.01 | 583.39 | 591.74 | 602.27 | 605.88 | 621.78 | 628.04 | 628.54 | 635.04 | 648.1 | 672.38 | 676.86 | 660.73 | 657.37 | 660.93 | 664.75 | 670.51 | 677.22 | 683.75 | 684.61 | 690.66 | 702.31 | 709.32 | 709.88 | 713.57 | 717.4 | 717.04 | 718.99 | 722.83 | 725.97 | 728.72 | 730.08 | 735.71 | 738.47 | 741.22 | 743.98 | 747.14 | 750.82 | 754.02 | 757.22 | 761.13 | 764.77 | 768.42 | 772.06 | 776.06 | 779.97 | 783.88 | 787.79 | 791.58 | 795.57 | 799.56 | 803.55 | 807.42 | 811.48 | 815.55 | 819.62 | 823.56 | 827.71 | 831.86 | 836.01 | 840.04 | 844.27 | 848.5 | 852.73 | 856.84 | 861.15 | 865.47 | 869.79 | 873.97 | 878.38 | 882.78 | 887.18 | 891.45 | 895.94 | 900.43 | 904.93 | 909.28 | 913.86 | 918.44 | 923.02 | 927.47 | 932.14 | 936.81 | 941.48 | 946.02 | 950.78 | 955.55 | 960.31 | 964.94 | 969.8 | 974.66 | 979.52 | 984.24 | 989.19 | 994.15 | 999.11 | 1003.92 | 1008.98 | 1014.04 | 1019.09 | 1024 | 1029.16 | 1034.32 | 1039.47 | 1044.48 | 1049.74 | 1055 | 1060.26 | 1065.37 | 1070.74 | 1076.1 | 1081.47 | 1086.68 | 1092.15 | 1097.62 | 1103.1 | 1108.41 | 1113.99 | 1119.58 | 1125.16 | 1130.58 | 1136.27 | 1141.97 | 1147.66 | 1153.19 | 1159 | 1164.81 | 1170.62 | 1176.25 | 1182.18 | 1188.1 | 1194.03 | 1199.78 | 1205.82 | 1211.87 | 1217.91 | 1223.77 | 1229.94 | 1236.1 | 1242.27 | 1248.25 | 1254.54 | 1260.83 | 1267.11 | 1273.21 | 1279.63 | 1286.04 | 1292.46 | 1298.68 | 1305.22 | 1311.76 | 1318.31 | 1324.65 | 1331.32 | 1338 | 1344.67 | 1351.14 | 1357.95 | 1364.76 | 1371.56 | 1378.17 | 1385.11 | 1392.05 | 1399 | 1405.73 | 1412.81 | 1419.89 | 1426.98 | 1433.85 | 1441.07 | 1448.29 | 1455.52 | 1462.52 | 1469.89 | 1477.26 | 1484.63 | 1491.77 | 1499.29 | 1506.8 | 1514.32 | 1521.61 | 1529.27 | 1536.94 | 1544.6 | 1552.04 | 1559.86 | 1567.68 | 1575.5 | 1583.08 | 1591.06 | 1599.03 | 1607.01 | 1614.74 | 1622.88 | 1631.01 | 1639.15 | 1647.04 | 1655.33 | 1663.63 | 1671.93 | 1679.98 | 1688.44 | 1696.9 | 1705.37 | 1713.58 | 1722.21 | 1730.84 | 1739.48 | 1747.85 | 1756.65 | 1765.46 | 1774.27 | 1782.81 | 1791.79 | 1800.77 | 1809.75 | 1818.46 | 1827.62 | 1836.78 | 1845.95 | 1854.83 | 1864.18 | 1873.52 | 1882.86 | 1891.93 | 1901.46 | 1910.99 | 1920.52 | 1929.77 | 1939.49 | 1949.21 | 1958.93 | 1968.36 | 1978.28 | 1988.19 | 1998.11 | 2007.73 | 2017.84 | 2027.96 | 2038.07 | 2047.88 | 2058.2 | 2068.52 | 2078.83 | 2088.84 | 2099.36 | 2109.89 | 2120.41 | 2130.62 | 2141.35 | 2152.09 | 2162.82 | 2173.23 | 2184.18 | 2195.13 | 2206.08 | 2216.7 | 2227.86 | 2239.03 | 2250.2 | 2261.03 | 2272.42 | 2283.81 | 2295.2 | 2306.25 | 2317.87 | 2329.49 | 2341.11 | 2352.38 | 2364.23 | 2376.08 | 2387.93 | 2399.42 | 2411.51 | 2423.6 | 2435.69 | 2447.41 | 2459.74 | 2472.07 | 2484.4 | 2496.36 | 2508.94 | 2521.51 | 2534.09 | 2546.29 | 2559.11 | 2571.94 | 2584.77 | 2597.21 | 2610.3 | 2623.38 | 2636.46 | 2649.16 | 2662.5 | 2675.85 | 2689.19 | 2702.14 | 2715.75 | 2729.37 | 2742.98 | 2756.18 | 2770.07 | 2783.95 | 2797.84 | 2811.31 | 2825.47 | 2839.63 | 2853.79 | 2867.53 | 2881.98 | 2896.42 | 2910.87 | 2924.88 | 2939.62 | 2954.35 | 2969.09 | 2983.38 | 2998.41 | 3013.44 | 3028.47 | 3043.05 | 3058.38 | 3073.71 | 3089.04 | 3103.91 | 3119.55 | 3135.18 | 3150.82 | 3165.99 | 3181.94 | 3197.89 | 3213.84 | 3229.31 | 3245.58 | 3261.84 | 3278.11 | 3293.89 | 3310.49 | 3327.08 | 3343.67 | 3359.77 | 3376.7 | 3393.62 | 3410.55 | 3426.97 | 3444.23 | 3461.49 | 3478.76 | 3495.51 | 3513.12 | 3530.72 | 3548.33 | 3565.42 | 3583.38 | 3601.34 | 3619.3 | 3636.72 | 3655.05 | 3673.37 | 3691.69 | 3709.46 | 3728.15 | 3746.83 | 3765.52 | 3783.65 | 3802.71 | 3821.77 | 3840.83 | 3859.32 | 3878.76 | 3898.21 | 3917.65 | 3936.51 | 3956.34 | 3976.17 | 3996 | 4015.24 | 4035.47 | 4055.69 | 4075.92
| EM 1110-2-1304 CWCCIS | http://publications.usace.army.mil/publications/eng-manuals/EM_1110-2-1304/toc.htm |  |  |  | 12 | 08 | 12 | ROADS, RAILROADS & BRIDGES | 10% | 271.87 | 274.31 | 285.26 | 289.3 | 295.1 | 301.18 | 312.75 | 315.63 | 320.53 | 322.08 | 333.33 | 333.67 | 335.14 | 338.18 | 345.35 | 344.78 | 345.52 | 348.83 | 352.68 | 351.02 | 353.13 | 354.92 | 357.91 | 355.77 | 355.59 | 359.01 | 359.28 | 359.55 | 361.04 | 363.87 | 368.87 | 371.5 | 374.44 | 379.38 | 383.85 | 384.02 | 388.26 | 393.87 | 398.1 | 398.06 | 397.7 | 402.35 | 406.27 | 405.48 | 407.61 | 409.79 | 415.17 | 412.51 | 416.6 | 423.9 | 424.33 | 424.64 | 432.27 | 444.84 | 440.26 | 444.4 | 453.13 | 453.19 | 455.09 | 455.63 | 459.16 | 463.37 | 466.65 | 466.2 | 466.08 | 471.21 | 477.34 | 478.46 | 481.69 | 487.33 | 488.95 | 487 | 488.93 | 492.32 | 491.1 | 488.69 | 492.81 | 499.56 | 509.16 | 503.04 | 506.82 | 508.77 | 508.18 | 508.11 | 508.75 | 510.79 | 516.87 | 516.78 | 519.56 | 530.58 | 535.25 | 534.41 | 535.7 | 538.79 | 543.21 | 549.21 | 559.04 | 583.39 | 595.63 | 608.05 | 612.78 | 617.37 | 619.16 | 625.19 | 639.51 | 643.94 | 647.71 | 655.73 | 660.22 | 678.49 | 685.41 | 681.9 | 685.16 | 701.29 | 728.77 | 727.11 | 708.97 | 699.5 | 706.43 | 707.53 | 715.45 | 727.79 | 733.68 | 732.86 | 741.6 | 754.5 | 762.57 | 763.99 | 768.33 | 774.53 | 776.41 | 776.53 | 787.84 | 795.56 | 794.68 | 797.33 | 805.49 | 808.51 | 811.53 | 814.55 | 818.01 | 822.04 | 825.54 | 829.04 | 833.33 | 837.32 | 841.3 | 845.29 | 849.67 | 853.96 | 858.24 | 862.52 | 866.67 | 871.03 | 875.4 | 879.77 | 884 | 888.46 | 892.91 | 897.36 | 901.68 | 906.22 | 910.77 | 915.31 | 919.72 | 924.35 | 928.98 | 933.62 | 938.11 | 942.84 | 947.56 | 952.29 | 956.87 | 961.69 | 966.51 | 971.33 | 976.01 | 980.93 | 985.84 | 990.76 | 995.53 | 1000.54 | 1005.56 | 1010.58 | 1015.44 | 1020.56 | 1025.67 | 1030.79 | 1035.75 | 1040.97 | 1046.18 | 1051.4 | 1056.46 | 1061.79 | 1067.11 | 1072.43 | 1077.59 | 1083.02 | 1088.45 | 1093.88 | 1099.14 | 1104.68 | 1110.22 | 1115.76 | 1121.13 | 1126.78 | 1132.42 | 1138.07 | 1143.55 | 1149.31 | 1155.07 | 1160.83 | 1166.42 | 1172.3 | 1178.17 | 1184.05 | 1189.75 | 1195.74 | 1201.74 | 1207.73 | 1213.54 | 1219.66 | 1225.77 | 1231.89 | 1237.82 | 1244.05 | 1250.29 | 1256.52 | 1262.57 | 1268.93 | 1275.29 | 1281.65 | 1287.82 | 1294.31 | 1300.8 | 1307.29 | 1313.58 | 1320.2 | 1326.81 | 1333.43 | 1339.85 | 1346.6 | 1353.35 | 1360.1 | 1366.65 | 1373.53 | 1380.42 | 1387.3 | 1393.98 | 1401 | 1408.03 | 1415.05 | 1421.86 | 1429.02 | 1436.19 | 1443.35 | 1450.3 | 1457.6 | 1464.91 | 1472.22 | 1479.3 | 1486.76 | 1494.21 | 1501.66 | 1508.89 | 1516.49 | 1524.09 | 1531.69 | 1539.07 | 1546.82 | 1554.58 | 1562.33 | 1569.85 | 1577.76 | 1585.67 | 1593.58 | 1601.25 | 1609.31 | 1617.38 | 1625.45 | 1633.27 | 1641.5 | 1649.73 | 1657.96 | 1665.94 | 1674.33 | 1682.72 | 1691.11 | 1699.26 | 1707.82 | 1716.38 | 1724.94 | 1733.24 | 1741.97 | 1750.7 | 1759.44 | 1767.91 | 1776.81 | 1785.72 | 1794.62 | 1803.26 | 1812.35 | 1821.43 | 1830.52 | 1839.33 | 1848.6 | 1857.86 | 1867.13 | 1876.12 | 1885.57 | 1895.02 | 1904.47 | 1913.64 | 1923.28 | 1932.92 | 1942.56 | 1951.91 | 1961.74 | 1971.58 | 1981.41 | 1990.95 | 2000.98 | 2011.01 | 2021.04 | 2030.77 | 2041 | 2051.23 | 2061.46 | 2071.38 | 2081.82 | 2092.25 | 2102.69 | 2112.81 | 2123.45 | 2134.1 | 2144.74 | 2155.07 | 2165.92 | 2176.78 | 2187.64 | 2198.17 | 2209.24 | 2220.32 | 2231.39 | 2242.13 | 2253.43 | 2264.72 | 2276.02 | 2286.97 | 2298.5 | 2310.02 | 2321.54 | 2332.71 | 2344.47 | 2356.22 | 2367.97 | 2379.37 | 2391.35 | 2403.34 | 2415.33 | 2426.96 | 2439.18 | 2451.41 | 2463.63 | 2475.49 | 2487.97 | 2500.44 | 2512.91 | 2525 | 2537.72 | 2550.45 | 2563.17 | 2575.5 | 2588.48 | 2601.45 | 2614.43 | 2627.01 | 2640.25 | 2653.48 | 2666.72 | 2679.55 | 2693.05 | 2706.55 | 2720.05 | 2733.15 | 2746.92 | 2760.68 | 2774.45 | 2787.81 | 2801.85 | 2815.9 | 2829.94 | 2843.57 | 2857.89 | 2872.22 | 2886.54 | 2900.44 | 2915.05 | 2929.66 | 2944.27 | 2958.45 | 2973.35 | 2988.25 | 3003.16 | 3017.61 | 3032.82 | 3048.02 | 3063.22 | 3077.97 | 3093.47 | 3108.98 | 3124.48 | 3139.53 | 3155.34 | 3171.16 | 3186.97 | 3202.32 | 3218.45 | 3234.58 | 3250.71 | 3266.36 | 3282.82 | 3299.27 | 3315.73 | 3331.69 | 3348.47 | 3365.26 | 3382.04 | 3398.32 | 3415.44 | 3432.56 | 3449.68 | 3466.29 | 3483.75 | 3501.21 | 3518.68 | 3535.62 | 3553.43 | 3571.24 | 3589.05 | 3606.33 | 3624.5 | 3642.66 | 3660.83 | 3678.45 | 3696.99 | 3715.52 | 3734.05 | 3752.02 | 3770.93 | 3789.83 | 3808.73 | 3827.06 | 3846.34 | 3865.62 | 3884.9 | 3903.61 | 3923.27 | 3942.94 | 3962.6 | 3981.68 | 4001.74 | 4021.8 | 4041.85 | 4061.31 | 4081.77 | 4102.23 | 4122.69 | 4142.54 | 4163.41 | 4184.28 | 4205.15 | 4225.39 | 4246.67 | 4267.96 | 4289.25 | 4309.9 | 4331.61 | 4353.32 | 4375.03 | 4396.09 | 4418.24 | 4440.39 | 4462.53
| EC 11-2-206 | http://publications.usace.army.mil/publications/eng-circulars/EC_11-2-206/ |  |  |  | 13 | 09 | 13 | CHANNELS & CANALS | 3% | 265.64 | 270.82 | 281.65 | 287.98 | 293.61 | 301.38 | 313.41 | 317.89 | 325.51 | 328.36 | 339.24 | 340.71 | 342.1 | 343.64 | 348.71 | 349.82 | 350.85 | 352.53 | 357.12 | 357.17 | 356.12 | 357.8 | 359.39 | 359.65 | 360.57 | 362.65 | 364.2 | 364.3 | 367.72 | 369.39 | 374.27 | 375.45 | 378.91 | 381.47 | 386.02 | 387.57 | 394.41 | 397.56 | 404.46 | 406 | 408.91 | 412.18 | 419.85 | 421.37 | 423.64 | 426.24 | 429.12 | 429.87 | 432.46 | 436.45 | 440.83 | 441.51 | 444.91 | 448.13 | 451.04 | 451.92 | 455.98 | 459.44 | 460.96 | 462.02 | 464.74 | 469.56 | 473.89 | 474.38 | 478.3 | 482.06 | 485.4 | 485.86 | 488.99 | 492.02 | 493.05 | 494.6 | 500.35 | 503.18 | 504.72 | 505.95 | 509.67 | 515.79 | 519.24 | 519.75 | 522.7 | 525.67 | 528.21 | 530.31 | 533.17 | 533.64 | 537.32 | 539.98 | 543.14 | 552.98 | 556.82 | 557.3 | 562.22 | 565.12 | 566.01 | 568.24 | 574.07 | 580.55 | 589.71 | 593.18 | 602.74 | 606.87 | 617.59 | 621.31 | 634.12 | 639.7 | 643.34 | 650.07 | 658.19 | 666.22 | 672.31 | 674.92 | 679 | 687.99 | 696.83 | 700.63 | 708.75 | 714.03 | 722.16 | 718.6 | 726.21 | 727.34 | 738.67 | 740.12 | 745.5 | 752.01 | 763.2 | 769.05 | 779.45 | 787.23 | 792.32 | 796.23 | 804.86 | 806.09 | 816.37 | 817.99 | 825.25 | 828.34 | 831.44 | 834.53 | 838.08 | 842.21 | 845.79 | 849.38 | 853.77 | 857.86 | 861.94 | 866.03 | 870.52 | 874.9 | 879.29 | 883.68 | 887.93 | 892.4 | 896.88 | 901.35 | 905.69 | 910.25 | 914.81 | 919.38 | 923.8 | 928.46 | 933.11 | 937.76 | 942.28 | 947.02 | 951.77 | 956.52 | 961.12 | 965.96 | 970.81 | 975.65 | 980.35 | 985.28 | 990.22 | 995.16 | 999.95 | 1004.99 | 1010.03 | 1015.06 | 1019.95 | 1025.09 | 1030.23 | 1035.37 | 1040.35 | 1045.59 | 1050.83 | 1056.07 | 1061.16 | 1066.5 | 1071.85 | 1077.2 | 1082.38 | 1087.83 | 1093.29 | 1098.74 | 1104.03 | 1109.59 | 1115.15 | 1120.71 | 1126.11 | 1131.78 | 1137.45 | 1143.13 | 1148.63 | 1154.42 | 1160.2 | 1165.99 | 1171.6 | 1177.51 | 1183.41 | 1189.31 | 1195.04 | 1201.06 | 1207.08 | 1213.1 | 1218.94 | 1225.08 | 1231.22 | 1237.36 | 1243.32 | 1249.58 | 1255.84 | 1262.11 | 1268.18 | 1274.57 | 1280.96 | 1287.35 | 1293.54 | 1300.06 | 1306.58 | 1313.09 | 1319.42 | 1326.06 | 1332.71 | 1339.36 | 1345.8 | 1352.58 | 1359.36 | 1366.14 | 1372.72 | 1379.64 | 1386.55 | 1393.47 | 1400.17 | 1407.23 | 1414.28 | 1421.34 | 1428.18 | 1435.37 | 1442.57 | 1449.76 | 1456.74 | 1464.08 | 1471.42 | 1478.76 | 1485.88 | 1493.36 | 1500.85 | 1508.33 | 1515.59 | 1523.23 | 1530.86 | 1538.5 | 1545.91 | 1553.69 | 1561.48 | 1569.27 | 1576.82 | 1584.77 | 1592.71 | 1600.66 | 1608.36 | 1616.46 | 1624.57 | 1632.67 | 1640.53 | 1648.79 | 1657.06 | 1665.32 | 1673.34 | 1681.77 | 1690.2 | 1698.63 | 1706.81 | 1715.4 | 1724 | 1732.6 | 1740.94 | 1749.71 | 1758.48 | 1767.25 | 1775.76 | 1784.71 | 1793.65 | 1802.6 | 1811.28 | 1820.4 | 1829.52 | 1838.65 | 1847.5 | 1856.81 | 1866.12 | 1875.42 | 1884.45 | 1893.94 | 1903.44 | 1912.93 | 1922.14 | 1931.82 | 1941.51 | 1951.19 | 1960.58 | 1970.46 | 1980.34 | 1990.21 | 1999.79 | 2009.87 | 2019.94 | 2030.02 | 2039.79 | 2050.07 | 2060.34 | 2070.62 | 2080.59 | 2091.07 | 2101.55 | 2112.03 | 2122.2 | 2132.89 | 2143.58 | 2154.27 | 2164.64 | 2175.55 | 2186.45 | 2197.36 | 2207.93 | 2219.06 | 2230.18 | 2241.3 | 2252.09 | 2263.44 | 2274.78 | 2286.13 | 2297.13 | 2308.71 | 2320.28 | 2331.85 | 2343.08 | 2354.88 | 2366.69 | 2378.49 | 2389.94 | 2401.98 | 2414.02 | 2426.06 | 2437.74 | 2450.02 | 2462.3 | 2474.58 | 2486.49 | 2499.02 | 2511.55 | 2524.07 | 2536.22 | 2549 | 2561.78 | 2574.55 | 2586.95 | 2599.98 | 2613.01 | 2626.04 | 2638.69 | 2651.98 | 2665.27 | 2678.57 | 2691.46 | 2705.02 | 2718.58 | 2732.14 | 2745.29 | 2759.12 | 2772.95 | 2786.78 | 2800.19 | 2814.3 | 2828.41 | 2842.52 | 2856.2 | 2870.59 | 2884.98 | 2899.37 | 2913.32 | 2928 | 2942.68 | 2957.35 | 2971.59 | 2986.56 | 3001.53 | 3016.5 | 3031.02 | 3046.29 | 3061.56 | 3076.83 | 3091.64 | 3107.22 | 3122.79 | 3138.37 | 3153.47 | 3169.36 | 3185.25 | 3201.13 | 3216.54 | 3232.75 | 3248.95 | 3265.16 | 3280.87 | 3297.4 | 3313.93 | 3330.46 | 3346.49 | 3363.35 | 3380.21 | 3397.07 | 3413.42 | 3430.62 | 3447.81 | 3465.01 | 3481.69 | 3499.23 | 3516.77 | 3534.31 | 3551.32 | 3569.21 | 3587.11 | 3605 | 3622.35 | 3640.6 | 3658.85 | 3677.1 | 3694.8 | 3713.41 | 3732.02 | 3750.64 | 3768.69 | 3787.68 | 3806.67 | 3825.65 | 3844.07 | 3863.43 | 3882.8 | 3902.16 | 3920.95 | 3940.7 | 3960.45 | 3980.21 | 3999.37 | 4019.52 | 4039.66 | 4059.81 | 4079.35 | 4099.91 | 4120.46 | 4141.01 | 4160.94 | 4181.9 | 4202.87 | 4223.83 | 4244.16 | 4265.54 | 4286.92 | 4308.3 | 4329.04 | 4350.85 | 4372.66 | 4394.47 | 4415.62 | 4437.87 | 4460.11 | 4482.36 | 4503.94 | 4526.63 | 4549.32 | 4572.01
[6 empty] | 14 | 10 | 14 | BREAKWATER & SEAWALLS | 5% | 268.87 | 275.43 | 284.94 | 291.47 | 297.87 | 307 | 317.48 | 322.03 | 329.54 | 332.77 | 341.4 | 342.84 | 344.42 | 346.28 | 350.15 | 351.06 | 351.96 | 353.84 | 357.66 | 357.81 | 360.2 | 360.88 | 362.49 | 363.08 | 364.15 | 366.12 | 367.26 | 367.48 | 371.39 | 372.87 | 376.57 | 377.7 | 381.39 | 383.48 | 387.91 | 389.42 | 399.19 | 402.23 | 408.93 | 410.56 | 416.23 | 418.83 | 426.15 | 427.58 | 431.75 | 434.02 | 436.95 | 437.42 | 440.32 | 444.65 | 449.52 | 450.14 | 453.92 | 457.1 | 459.86 | 459.59 | 464.97 | 467.37 | 469.13 | 470.36 | 473.69 | 477.42 | 480.99 | 481.23 | 486.3 | 489.3 | 492.45 | 493.39 | 497.41 | 499.61 | 500.41 | 501.47 | 508.28 | 510.27 | 511.29 | 512.16 | 515.93 | 520.56 | 523.14 | 523.68 | 526.04 | 526.7 | 528.42 | 530.28 | 533 | 532.9 | 535.39 | 537.42 | 539.67 | 551.63 | 554.03 | 554.89 | 560.3 | 563.87 | 564.09 | 566.98 | 572.43 | 579.15 | 587.47 | 594.67 | 603.21 | 607.88 | 618.82 | 622.23 | 633.85 | 640.07 | 642.8 | 647.89 | 654.97 | 660.82 | 666.4 | 668.25 | 672.17 | 679.9 | 689.75 | 696.2 | 704.84 | 708.1 | 714.7 | 707.23 | 714.39 | 715.35 | 722.61 | 723.34 | 730.49 | 737.82 | 747.94 | 753.93 | 757.76 | 764.47 | 768.52 | 772.18 | 782 | 784.6 | 792.86 | 792.77 | 800.12 | 803.12 | 806.12 | 809.12 | 812.56 | 816.56 | 820.04 | 823.52 | 827.77 | 831.73 | 835.69 | 839.65 | 844.01 | 848.26 | 852.51 | 856.77 | 860.89 | 865.23 | 869.56 | 873.9 | 878.11 | 882.53 | 886.96 | 891.38 | 895.67 | 900.18 | 904.69 | 909.21 | 913.58 | 918.19 | 922.79 | 927.39 | 931.86 | 936.55 | 941.24 | 945.94 | 950.49 | 955.28 | 960.07 | 964.86 | 969.5 | 974.39 | 979.27 | 984.15 | 988.89 | 993.87 | 998.86 | 1003.84 | 1008.67 | 1013.75 | 1018.83 | 1023.91 | 1028.84 | 1034.03 | 1039.21 | 1044.39 | 1049.42 | 1054.71 | 1059.99 | 1065.28 | 1070.41 | 1075.8 | 1081.19 | 1086.59 | 1091.82 | 1097.32 | 1102.82 | 1108.32 | 1113.65 | 1119.26 | 1124.87 | 1130.48 | 1135.93 | 1141.65 | 1147.37 | 1153.09 | 1158.65 | 1164.48 | 1170.32 | 1176.16 | 1181.82 | 1187.77 | 1193.73 | 1199.68 | 1205.45 | 1211.53 | 1217.6 | 1223.67 | 1229.56 | 1235.76 | 1241.95 | 1248.15 | 1254.15 | 1260.47 | 1266.79 | 1273.11 | 1279.24 | 1285.68 | 1292.13 | 1298.57 | 1304.82 | 1311.4 | 1317.97 | 1324.54 | 1330.92 | 1337.62 | 1344.33 | 1351.03 | 1357.54 | 1364.38 | 1371.22 | 1378.05 | 1384.69 | 1391.66 | 1398.64 | 1405.62 | 1412.38 | 1419.5 | 1426.61 | 1433.73 | 1440.63 | 1447.89 | 1455.14 | 1462.4 | 1469.44 | 1476.84 | 1484.25 | 1491.65 | 1498.83 | 1506.38 | 1513.93 | 1521.48 | 1528.81 | 1536.51 | 1544.21 | 1551.91 | 1559.38 | 1567.24 | 1575.1 | 1582.95 | 1590.57 | 1598.58 | 1606.6 | 1614.61 | 1622.38 | 1630.56 | 1638.73 | 1646.9 | 1654.83 | 1663.17 | 1671.5 | 1679.84 | 1687.93 | 1696.43 | 1704.93 | 1713.44 | 1721.69 | 1730.36 | 1739.03 | 1747.71 | 1756.12 | 1764.97 | 1773.81 | 1782.66 | 1791.24 | 1800.27 | 1809.29 | 1818.31 | 1827.07 | 1836.27 | 1845.48 | 1854.68 | 1863.61 | 1873 | 1882.38 | 1891.77 | 1900.88 | 1910.46 | 1920.03 | 1929.61 | 1938.9 | 1948.67 | 1958.43 | 1968.2 | 1977.68 | 1987.64 | 1997.6 | 2007.56 | 2017.23 | 2027.39 | 2037.55 | 2047.72 | 2057.57 | 2067.94 | 2078.3 | 2088.67 | 2098.73 | 2109.3 | 2119.87 | 2130.44 | 2140.7 | 2151.48 | 2162.27 | 2173.05 | 2183.51 | 2194.51 | 2205.51 | 2216.51 | 2227.18 | 2238.4 | 2249.62 | 2260.84 | 2271.73 | 2283.17 | 2294.62 | 2306.06 | 2317.16 | 2328.84 | 2340.51 | 2352.18 | 2363.51 | 2375.41 | 2387.32 | 2399.23 | 2410.78 | 2422.92 | 2435.07 | 2447.21 | 2458.99 | 2471.38 | 2483.77 | 2496.15 | 2508.17 | 2520.81 | 2533.44 | 2546.08 | 2558.33 | 2571.22 | 2584.11 | 2597 | 2609.5 | 2622.65 | 2635.79 | 2648.94 | 2661.69 | 2675.1 | 2688.51 | 2701.92 | 2714.92 | 2728.6 | 2742.28 | 2755.96 | 2769.22 | 2783.17 | 2797.12 | 2811.08 | 2824.61 | 2838.84 | 2853.07 | 2867.3 | 2881.1 | 2895.61 | 2910.13 | 2924.64 | 2938.72 | 2953.53 | 2968.33 | 2983.14 | 2997.5 | 3012.6 | 3027.7 | 3042.8 | 3057.45 | 3072.85 | 3088.25 | 3103.65 | 3118.6 | 3134.31 | 3150.02 | 3165.73 | 3180.97 | 3196.99 | 3213.02 | 3229.04 | 3244.59 | 3260.93 | 3277.28 | 3293.62 | 3309.48 | 3326.15 | 3342.82 | 3359.5 | 3375.67 | 3392.67 | 3409.68 | 3426.69 | 3443.18 | 3460.53 | 3477.87 | 3495.22 | 3512.04 | 3529.74 | 3547.43 | 3565.12 | 3582.29 | 3600.33 | 3618.38 | 3636.43 | 3653.93 | 3672.34 | 3690.75 | 3709.15 | 3727.01 | 3745.79 | 3764.56 | 3783.34 | 3801.55 | 3820.7 | 3839.85 | 3859 | 3877.58 | 3897.12 | 3916.65 | 3936.18 | 3955.13 | 3975.06 | 3994.98 | 4014.91 | 4034.24 | 4054.56 | 4074.88 | 4095.21 | 4114.92 | 4135.65 | 4156.38 | 4177.11 | 4197.22 | 4218.36 | 4239.51 | 4260.65 | 4281.16 | 4302.73 | 4324.3 | 4345.87 | 4366.79 | 4388.79 | 4410.78 | 4432.78
[6 empty] | 15 | 11 | 15 | LEVEES & FLOODWALLS | 5% | 270.52 | 275.78 | 285.6 | 291.08 | 296.16 | 303.75 | 315.68 | 320.28 | 326.15 | 328.53 | 339.43 | 340.6 | 341.33 | 343.87 | 349.13 | 350.51 | 351.28 | 353.23 | 357.74 | 357.71 | 357.94 | 359.12 | 360.8 | 360.91 | 360.26 | 362.26 | 363.58 | 363.91 | 366.29 | 368.16 | 372.27 | 374.39 | 378.8 | 382.73 | 386.7 | 388.36 | 394.83 | 398.49 | 402.75 | 404 | 405.46 | 408.36 | 414.01 | 415.03 | 417.23 | 419.02 | 421.7 | 422.01 | 424.47 | 428.96 | 433.01 | 433.35 | 436.37 | 441.4 | 444.14 | 445.43 | 449.93 | 453.36 | 455.18 | 456.83 | 460.62 | 466.66 | 471.12 | 471.24 | 473.49 | 476.42 | 480.07 | 480.75 | 482.63 | 485.59 | 487.37 | 489.24 | 493.85 | 496.31 | 497.18 | 496.64 | 497.88 | 502.33 | 506.75 | 506.45 | 509.22 | 512.18 | 514.03 | 515.05 | 516.54 | 516.31 | 519.93 | 521.86 | 523.8 | 536.25 | 541.49 | 541.59 | 545.36 | 549.52 | 550.19 | 554.42 | 563.84 | 582.42 | 594.09 | 607.65 | 615.61 | 618 | 623.58 | 630.33 | 644.64 | 651.23 | 658.68 | 666.93 | 669.92 | 687.06 | 693.47 | 691.82 | 697.52 | 714.17 | 739.43 | 737.4 | 721.64 | 712.69 | 718.95 | 719.93 | 726.98 | 735.23 | 744.32 | 745.35 | 753.7 | 767.06 | 776.75 | 779.51 | 785.64 | 789.19 | 790.48 | 790.25 | 798.03 | 800.91 | 806.93 | 807.9 | 815.35 | 818.41 | 821.47 | 824.52 | 828.03 | 832.1 | 835.65 | 839.19 | 843.53 | 847.57 | 851.6 | 855.64 | 860.08 | 864.41 | 868.74 | 873.07 | 877.28 | 881.7 | 886.12 | 890.54 | 894.82 | 899.33 | 903.84 | 908.35 | 912.72 | 917.32 | 921.92 | 926.51 | 930.97 | 935.66 | 940.35 | 945.04 | 949.59 | 954.38 | 959.16 | 963.94 | 968.58 | 973.46 | 978.34 | 983.22 | 987.96 | 992.93 | 997.91 | 1002.89 | 1007.72 | 1012.79 | 1017.87 | 1022.95 | 1027.87 | 1033.05 | 1038.23 | 1043.4 | 1048.43 | 1053.71 | 1058.99 | 1064.27 | 1069.4 | 1074.78 | 1080.17 | 1085.56 | 1090.78 | 1096.28 | 1101.77 | 1107.27 | 1112.6 | 1118.2 | 1123.81 | 1129.41 | 1134.85 | 1140.57 | 1146.29 | 1152 | 1157.55 | 1163.38 | 1169.21 | 1175.04 | 1180.7 | 1186.65 | 1192.6 | 1198.54 | 1204.31 | 1210.38 | 1216.45 | 1222.51 | 1228.4 | 1234.59 | 1240.78 | 1246.97 | 1252.97 | 1259.28 | 1265.59 | 1271.9 | 1278.03 | 1284.47 | 1290.9 | 1297.34 | 1303.59 | 1310.15 | 1316.72 | 1323.29 | 1329.66 | 1336.36 | 1343.06 | 1349.76 | 1356.25 | 1363.09 | 1369.92 | 1376.75 | 1383.38 | 1390.35 | 1397.32 | 1404.29 | 1411.05 | 1418.15 | 1425.26 | 1432.37 | 1439.27 | 1446.52 | 1453.77 | 1461.02 | 1468.05 | 1475.45 | 1482.84 | 1490.24 | 1497.41 | 1504.96 | 1512.5 | 1520.04 | 1527.36 | 1535.06 | 1542.75 | 1550.44 | 1557.91 | 1565.76 | 1573.6 | 1581.45 | 1589.07 | 1597.07 | 1605.08 | 1613.08 | 1620.85 | 1629.01 | 1637.18 | 1645.34 | 1653.26 | 1661.59 | 1669.92 | 1678.25 | 1686.33 | 1694.83 | 1703.32 | 1711.82 | 1720.06 | 1728.72 | 1737.39 | 1746.05 | 1754.46 | 1763.3 | 1772.13 | 1780.97 | 1789.55 | 1798.56 | 1807.58 | 1816.59 | 1825.34 | 1834.53 | 1843.73 | 1852.92 | 1861.84 | 1871.22 | 1880.6 | 1889.98 | 1899.08 | 1908.65 | 1918.22 | 1927.78 | 1937.06 | 1946.82 | 1956.58 | 1966.34 | 1975.8 | 1985.76 | 1995.71 | 2005.66 | 2015.32 | 2025.47 | 2035.63 | 2045.78 | 2055.63 | 2065.98 | 2076.34 | 2086.69 | 2096.74 | 2107.3 | 2117.86 | 2128.43 | 2138.67 | 2149.45 | 2160.22 | 2171 | 2181.45 | 2192.44 | 2203.43 | 2214.42 | 2225.08 | 2236.29 | 2247.5 | 2258.7 | 2269.58 | 2281.01 | 2292.44 | 2303.88 | 2314.97 | 2326.63 | 2338.29 | 2349.96 | 2361.27 | 2373.16 | 2385.06 | 2396.96 | 2408.49 | 2420.63 | 2432.76 | 2444.89 | 2456.66 | 2469.04 | 2481.42 | 2493.79 | 2505.8 | 2518.42 | 2531.04 | 2543.67 | 2555.91 | 2568.79 | 2581.67 | 2594.54 | 2607.03 | 2620.17 | 2633.3 | 2646.43 | 2659.17 | 2672.57 | 2685.96 | 2699.36 | 2712.36 | 2726.02 | 2739.68 | 2753.35 | 2766.6 | 2780.54 | 2794.48 | 2808.42 | 2821.93 | 2836.15 | 2850.37 | 2864.58 | 2878.37 | 2892.87 | 2907.37 | 2921.88 | 2935.94 | 2950.73 | 2965.52 | 2980.31 | 2994.66 | 3009.75 | 3024.83 | 3039.92 | 3054.55 | 3069.94 | 3085.33 | 3100.72 | 3115.64 | 3131.34 | 3147.04 | 3162.73 | 3177.96 | 3193.97 | 3209.98 | 3225.99 | 3241.52 | 3257.85 | 3274.18 | 3290.51 | 3306.35 | 3323 | 3339.66 | 3356.32 | 3372.47 | 3389.46 | 3406.45 | 3423.44 | 3439.92 | 3457.25 | 3474.58 | 3491.91 | 3508.72 | 3526.4 | 3544.07 | 3561.75 | 3578.9 | 3596.93 | 3614.95 | 3632.98 | 3650.47 | 3668.86 | 3687.25 | 3705.64 | 3723.48 | 3742.24 | 3761 | 3779.76 | 3797.95 | 3817.09 | 3836.22 | 3855.35 | 3873.91 | 3893.43 | 3912.94 | 3932.46 | 3951.39 | 3971.3 | 3991.2 | 4011.11 | 4030.42 | 4050.72 | 4071.03 | 4091.33 | 4111.03 | 4131.74 | 4152.45 | 4173.16 | 4193.25 | 4214.37 | 4235.5 | 4256.62 | 4277.11 | 4298.66 | 4320.21 | 4341.75 | 4362.65 | 4384.63 | 4406.61 | 4428.59 | 4449.91 | 4472.32 | 4494.74 | 4517.16
[6 empty] | 16 | 12 | 16 | NAVIGATION PORTS & HARBORS | 10% | 296.3 | 313.31 | 320.93 | 319.65 | 330.51 | 349.87 | 353.82 | 359.31 | 366.59 | 368.34 | 376.27 | 376.98 | 380.06 | 363.25 | 364.66 | 368.73 | 373.05 | 379.74 | 381.11 | 385.87 | 385.63 | 374.08 | 376.9 | 371.31 | 372.96 | 368.74 | 374.47 | 365.23 | 360.11 | 354.3 | 355.95 | 366.15 | 366.8 | 368.08 | 366.12 | 371.23 | 374.55 | 379.56 | 381.82 | 389.13 | 390.24 | 388.71 | 385.42 | 423.17 | 409.44 | 394.25 | 398.68 | 406.79 | 402.75 | 404.05 | 409.82 | 414.28 | 415.43 | 419.76 | 419.6 | 421.51 | 416.32 | 421.58 | 422.01 | 431 | 429.5 | 437.84 | 436.89 | 434.34 | 439.35 | 449.73 | 446.82 | 469.89 | 465.98 | 463.12 | 458.42 | 465.36 | 459.69 | 457.07 | 454.85 | 458.59 | 455.42 | 459.42 | 466.91 | 480.03 | 485.6 | 495.16 | 501.01 | 519.15 | 512.19 | 502.64 | 505.06 | 499.47 | 491.92 | 502.81 | 509.07 | 521.2 | 525.66 | 527.04 | 524.41 | 529.19 | 537.22 | 562.46 | 569.88 | 608.44 | 592.73 | 617.25 | 632.02 | 688.11 | 649.53 | 675.74 | 683.98 | 688.3 | 692.6 | 696.34 | 706.31 | 713.66 | 738.66 | 791.33 | 844.82 | 767.18 | 693.15 | 698.1 | 700.97 | 721.64 | 735.18 | 744.79 | 739.8 | 759.65 | 775.94 | 824.07 | 820.39 | 813.49 | 818.43 | 834.42 | 811.06 | 847.13 | 827.74 | 829.45 | 829.74 | 843.32 | 838.06 | 841.2 | 844.35 | 847.49 | 851.09 | 855.28 | 858.92 | 862.57 | 867.02 | 871.17 | 875.32 | 879.47 | 884.03 | 888.48 | 892.94 | 897.39 | 901.71 | 906.25 | 910.8 | 915.34 | 919.75 | 924.38 | 929.01 | 933.65 | 938.14 | 942.87 | 947.59 | 952.32 | 956.9 | 961.72 | 966.55 | 971.37 | 976.04 | 980.96 | 985.88 | 990.79 | 995.56 | 1000.58 | 1005.59 | 1010.61 | 1015.47 | 1020.59 | 1025.71 | 1030.82 | 1035.78 | 1041 | 1046.22 | 1051.44 | 1056.5 | 1061.82 | 1067.14 | 1072.47 | 1077.63 | 1083.06 | 1088.49 | 1093.92 | 1099.18 | 1104.72 | 1110.26 | 1115.79 | 1121.17 | 1126.81 | 1132.46 | 1138.11 | 1143.59 | 1149.35 | 1155.11 | 1160.87 | 1166.46 | 1172.34 | 1178.21 | 1184.09 | 1189.79 | 1195.78 | 1201.78 | 1207.77 | 1213.59 | 1219.7 | 1225.81 | 1231.93 | 1237.86 | 1244.09 | 1250.33 | 1256.57 | 1262.61 | 1268.98 | 1275.34 | 1281.7 | 1287.87 | 1294.35 | 1300.84 | 1307.33 | 1313.62 | 1320.24 | 1326.86 | 1333.48 | 1339.9 | 1346.65 | 1353.4 | 1360.15 | 1366.69 | 1373.58 | 1380.46 | 1387.35 | 1394.03 | 1401.05 | 1408.07 | 1415.1 | 1421.91 | 1429.07 | 1436.24 | 1443.4 | 1450.35 | 1457.65 | 1464.96 | 1472.27 | 1479.35 | 1486.81 | 1494.26 | 1501.71 | 1508.94 | 1516.54 | 1524.14 | 1531.75 | 1539.12 | 1546.87 | 1554.63 | 1562.38 | 1569.9 | 1577.81 | 1585.72 | 1593.63 | 1601.3 | 1609.37 | 1617.43 | 1625.5 | 1633.33 | 1641.55 | 1649.78 | 1658.01 | 1665.99 | 1674.39 | 1682.78 | 1691.17 | 1699.31 | 1707.87 | 1716.43 | 1725 | 1733.3 | 1742.03 | 1750.76 | 1759.5 | 1767.97 | 1776.87 | 1785.78 | 1794.68 | 1803.32 | 1812.41 | 1821.49 | 1830.58 | 1839.39 | 1848.66 | 1857.92 | 1867.19 | 1876.18 | 1885.63 | 1895.08 | 1904.53 | 1913.7 | 1923.34 | 1932.98 | 1942.62 | 1951.98 | 1961.81 | 1971.64 | 1981.48 | 1991.02 | 2001.05 | 2011.08 | 2021.11 | 2030.84 | 2041.07 | 2051.3 | 2061.53 | 2071.45 | 2081.89 | 2092.32 | 2102.76 | 2112.88 | 2123.53 | 2134.17 | 2144.81 | 2155.14 | 2166 | 2176.85 | 2187.71 | 2198.24 | 2209.32 | 2220.39 | 2231.47 | 2242.21 | 2253.5 | 2264.8 | 2276.09 | 2287.05 | 2298.57 | 2310.09 | 2321.62 | 2332.79 | 2344.54 | 2356.3 | 2368.05 | 2379.45 | 2391.44 | 2403.42 | 2415.41 | 2427.04 | 2439.26 | 2451.49 | 2463.72 | 2475.58 | 2488.05 | 2500.52 | 2512.99 | 2525.09 | 2537.81 | 2550.53 | 2563.25 | 2575.59 | 2588.57 | 2601.54 | 2614.52 | 2627.1 | 2640.34 | 2653.57 | 2666.81 | 2679.65 | 2693.14 | 2706.64 | 2720.14 | 2733.24 | 2747.01 | 2760.78 | 2774.55 | 2787.9 | 2801.95 | 2815.99 | 2830.04 | 2843.66 | 2857.99 | 2872.31 | 2886.64 | 2900.53 | 2915.15 | 2929.76 | 2944.37 | 2958.54 | 2973.45 | 2988.35 | 3003.26 | 3017.72 | 3032.92 | 3048.12 | 3063.32 | 3078.07 | 3093.58 | 3109.08 | 3124.59 | 3139.63 | 3155.45 | 3171.26 | 3187.08 | 3202.42 | 3218.56 | 3234.69 | 3250.82 | 3266.47 | 3282.93 | 3299.38 | 3315.84 | 3331.8 | 3348.59 | 3365.37 | 3382.16 | 3398.44 | 3415.56 | 3432.68 | 3449.8 | 3466.41 | 3483.87 | 3501.33 | 3518.8 | 3535.73 | 3553.55 | 3571.36 | 3589.17 | 3606.45 | 3624.62 | 3642.79 | 3660.96 | 3678.58 | 3697.11 | 3715.64 | 3734.17 | 3752.15 | 3771.05 | 3789.96 | 3808.86 | 3827.19 | 3846.47 | 3865.75 | 3885.03 | 3903.74 | 3923.4 | 3943.07 | 3962.74 | 3981.81 | 4001.87 | 4021.93 | 4041.99 | 4061.45 | 4081.91 | 4102.37 | 4122.83 | 4142.68 | 4163.55 | 4184.42 | 4205.29 | 4225.53 | 4246.82 | 4268.11 | 4289.39 | 4310.04 | 4331.75 | 4353.47 | 4375.18 | 4396.24 | 4418.39 | 4440.54 | 4462.68 | 4484.17 | 4506.76 | 4529.35 | 4551.94 | 4573.85 | 4596.89 | 4619.93 | 4642.98
[6 empty] | 17 | 13 | 17 | PUMPING PLANT | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 786.1 | 789.05 | 792 | 794.94 | 798.32 | 802.25 | 805.67 | 809.09 | 813.27 | 817.16 | 821.05 | 824.94 | 829.22 | 833.4 | 837.58 | 841.75 | 845.81 | 850.07 | 854.33 | 858.59 | 862.72 | 867.07 | 871.41 | 875.76 | 879.98 | 884.41 | 888.84 | 893.28 | 897.58 | 902.1 | 906.62 | 911.14 | 915.53 | 920.14 | 924.75 | 929.36 | 933.84 | 938.54 | 943.25 | 947.95 | 952.51 | 957.31 | 962.11 | 966.91 | 971.56 | 976.46 | 981.35 | 986.25 | 991 | 995.99 | 1000.98 | 1005.97 | 1010.82 | 1015.91 | 1021 | 1026.09 | 1031.03 | 1036.23 | 1041.42 | 1046.61 | 1051.65 | 1056.95 | 1062.25 | 1067.55 | 1072.69 | 1078.09 | 1083.49 | 1088.9 | 1094.14 | 1099.65 | 1105.16 | 1110.68 | 1116.02 | 1121.64 | 1127.27 | 1132.89 | 1138.34 | 1144.08 | 1149.81 | 1155.55 | 1161.11 | 1166.96 | 1172.81 | 1178.66 | 1184.33 | 1190.3 | 1196.26 | 1202.23 | 1208.02 | 1214.1 | 1220.19 | 1226.28 | 1232.18 | 1238.39 | 1244.59 | 1250.8 | 1256.82 | 1263.15 | 1269.49 | 1275.82 | 1281.96 | 1288.42 | 1294.88 | 1301.33 | 1307.6 | 1314.19 | 1320.77 | 1327.36 | 1333.75 | 1340.47 | 1347.19 | 1353.91 | 1360.43 | 1367.28 | 1374.13 | 1380.99 | 1387.63 | 1394.62 | 1401.61 | 1408.61 | 1415.39 | 1422.52 | 1429.65 | 1436.78 | 1443.69 | 1450.97 | 1458.24 | 1465.51 | 1472.57 | 1479.99 | 1487.4 | 1494.82 | 1502.02 | 1509.59 | 1517.15 | 1524.72 | 1532.06 | 1539.78 | 1547.5 | 1555.21 | 1562.7 | 1570.57 | 1578.45 | 1586.32 | 1593.95 | 1601.98 | 1610.01 | 1618.04 | 1625.83 | 1634.02 | 1642.22 | 1650.41 | 1658.35 | 1666.71 | 1675.06 | 1683.41 | 1691.52 | 1700.04 | 1708.56 | 1717.08 | 1725.35 | 1734.04 | 1742.73 | 1751.42 | 1759.85 | 1768.72 | 1777.59 | 1786.45 | 1795.05 | 1804.1 | 1813.14 | 1822.18 | 1830.95 | 1840.18 | 1849.4 | 1858.62 | 1867.57 | 1876.98 | 1886.39 | 1895.8 | 1904.92 | 1914.52 | 1924.12 | 1933.71 | 1943.02 | 1952.81 | 1962.6 | 1972.39 | 1981.88 | 1991.87 | 2001.85 | 2011.84 | 2021.52 | 2031.7 | 2041.89 | 2052.07 | 2061.95 | 2072.34 | 2082.73 | 2093.11 | 2103.19 | 2113.79 | 2124.38 | 2134.98 | 2145.25 | 2156.06 | 2166.87 | 2177.68 | 2188.16 | 2199.18 | 2210.21 | 2221.23 | 2231.92 | 2243.17 | 2254.41 | 2265.65 | 2276.56 | 2288.03 | 2299.5 | 2310.97 | 2322.09 | 2333.79 | 2345.49 | 2357.19 | 2368.53 | 2380.47 | 2392.4 | 2404.33 | 2415.9 | 2428.07 | 2440.25 | 2452.42 | 2464.22 | 2476.64 | 2489.05 | 2501.46 | 2513.51 | 2526.17 | 2538.83 | 2551.49 | 2563.78 | 2576.69 | 2589.61 | 2602.52 | 2615.05 | 2628.23 | 2641.4 | 2654.57 | 2667.35 | 2680.79 | 2694.23 | 2707.67 | 2720.7 | 2734.41 | 2748.11 | 2761.82 | 2775.11 | 2789.09 | 2803.07 | 2817.06 | 2830.62 | 2844.88 | 2859.14 | 2873.4 | 2887.23 | 2901.77 | 2916.32 | 2930.86 | 2944.97 | 2959.81 | 2974.65 | 2989.48 | 3003.87 | 3019.01 | 3034.14 | 3049.27 | 3063.95 | 3079.39 | 3094.82 | 3110.26 | 3125.23 | 3140.97 | 3156.72 | 3172.46 | 3187.73 | 3203.79 | 3219.85 | 3235.91 | 3251.49 | 3267.87 | 3284.25 | 3300.63 | 3316.52 | 3333.23 | 3349.93 | 3366.64 | 3382.85 | 3399.89 | 3416.93 | 3433.97 | 3450.51 | 3467.89 | 3485.27 | 3502.65 | 3519.52 | 3537.25 | 3554.98 | 3572.71 | 3589.91 | 3607.99 | 3626.08 | 3644.16 | 3661.7 | 3680.15 | 3698.6 | 3717.04 | 3734.94 | 3753.75 | 3772.57 | 3791.39 | 3809.64 | 3828.83 | 3848.02 | 3867.21 | 3885.83 | 3905.41 | 3924.98 | 3944.56 | 3963.55 | 3983.51 | 4003.48 | 4023.45 | 4042.82 | 4063.18 | 4083.55 | 4103.92 | 4123.67 | 4144.45 | 4165.22 | 4186 | 4206.15 | 4227.34 | 4248.53 | 4269.72 | 4290.27 | 4311.88 | 4333.5 | 4355.11
| CWCCIS EM1110-2-1304 updates occur twice yearly on 31 March and 30 September. |  |  |  |  | 18 | 14 | 18 | RECREATION FACILITIES | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 786.1 | 789.05 | 792 | 794.94 | 798.32 | 802.25 | 805.67 | 809.09 | 813.27 | 817.16 | 821.05 | 824.94 | 829.22 | 833.4 | 837.58 | 841.75 | 845.81 | 850.07 | 854.33 | 858.59 | 862.72 | 867.07 | 871.41 | 875.76 | 879.98 | 884.41 | 888.84 | 893.28 | 897.58 | 902.1 | 906.62 | 911.14 | 915.53 | 920.14 | 924.75 | 929.36 | 933.84 | 938.54 | 943.25 | 947.95 | 952.51 | 957.31 | 962.11 | 966.91 | 971.56 | 976.46 | 981.35 | 986.25 | 991 | 995.99 | 1000.98 | 1005.97 | 1010.82 | 1015.91 | 1021 | 1026.09 | 1031.03 | 1036.23 | 1041.42 | 1046.61 | 1051.65 | 1056.95 | 1062.25 | 1067.55 | 1072.69 | 1078.09 | 1083.49 | 1088.9 | 1094.14 | 1099.65 | 1105.16 | 1110.68 | 1116.02 | 1121.64 | 1127.27 | 1132.89 | 1138.34 | 1144.08 | 1149.81 | 1155.55 | 1161.11 | 1166.96 | 1172.81 | 1178.66 | 1184.33 | 1190.3 | 1196.26 | 1202.23 | 1208.02 | 1214.1 | 1220.19 | 1226.28 | 1232.18 | 1238.39 | 1244.59 | 1250.8 | 1256.82 | 1263.15 | 1269.49 | 1275.82 | 1281.96 | 1288.42 | 1294.88 | 1301.33 | 1307.6 | 1314.19 | 1320.77 | 1327.36 | 1333.75 | 1340.47 | 1347.19 | 1353.91 | 1360.43 | 1367.28 | 1374.13 | 1380.99 | 1387.63 | 1394.62 | 1401.61 | 1408.61 | 1415.39 | 1422.52 | 1429.65 | 1436.78 | 1443.69 | 1450.97 | 1458.24 | 1465.51 | 1472.57 | 1479.99 | 1487.4 | 1494.82 | 1502.02 | 1509.59 | 1517.15 | 1524.72 | 1532.06 | 1539.78 | 1547.5 | 1555.21 | 1562.7 | 1570.57 | 1578.45 | 1586.32 | 1593.95 | 1601.98 | 1610.01 | 1618.04 | 1625.83 | 1634.02 | 1642.22 | 1650.41 | 1658.35 | 1666.71 | 1675.06 | 1683.41 | 1691.52 | 1700.04 | 1708.56 | 1717.08 | 1725.35 | 1734.04 | 1742.73 | 1751.42 | 1759.85 | 1768.72 | 1777.59 | 1786.45 | 1795.05 | 1804.1 | 1813.14 | 1822.18 | 1830.95 | 1840.18 | 1849.4 | 1858.62 | 1867.57 | 1876.98 | 1886.39 | 1895.8 | 1904.92 | 1914.52 | 1924.12 | 1933.71 | 1943.02 | 1952.81 | 1962.6 | 1972.39 | 1981.88 | 1991.87 | 2001.85 | 2011.84 | 2021.52 | 2031.7 | 2041.89 | 2052.07 | 2061.95 | 2072.34 | 2082.73 | 2093.11 | 2103.19 | 2113.79 | 2124.38 | 2134.98 | 2145.25 | 2156.06 | 2166.87 | 2177.68 | 2188.16 | 2199.18 | 2210.21 | 2221.23 | 2231.92 | 2243.17 | 2254.41 | 2265.65 | 2276.56 | 2288.03 | 2299.5 | 2310.97 | 2322.09 | 2333.79 | 2345.49 | 2357.19 | 2368.53 | 2380.47 | 2392.4 | 2404.33 | 2415.9 | 2428.07 | 2440.25 | 2452.42 | 2464.22 | 2476.64 | 2489.05 | 2501.46 | 2513.51 | 2526.17 | 2538.83 | 2551.49 | 2563.78 | 2576.69 | 2589.61 | 2602.52 | 2615.05 | 2628.23 | 2641.4 | 2654.57 | 2667.35 | 2680.79 | 2694.23 | 2707.67 | 2720.7 | 2734.41 | 2748.11 | 2761.82 | 2775.11 | 2789.09 | 2803.07 | 2817.06 | 2830.62 | 2844.88 | 2859.14 | 2873.4 | 2887.23 | 2901.77 | 2916.32 | 2930.86 | 2944.97 | 2959.81 | 2974.65 | 2989.48 | 3003.87 | 3019.01 | 3034.14 | 3049.27 | 3063.95 | 3079.39 | 3094.82 | 3110.26 | 3125.23 | 3140.97 | 3156.72 | 3172.46 | 3187.73 | 3203.79 | 3219.85 | 3235.91 | 3251.49 | 3267.87 | 3284.25 | 3300.63 | 3316.52 | 3333.23 | 3349.93 | 3366.64 | 3382.85 | 3399.89 | 3416.93 | 3433.97 | 3450.51 | 3467.89 | 3485.27 | 3502.65 | 3519.52 | 3537.25 | 3554.98 | 3572.71 | 3589.91 | 3607.99 | 3626.08 | 3644.16 | 3661.7 | 3680.15 | 3698.6 | 3717.04 | 3734.94 | 3753.75 | 3772.57 | 3791.39 | 3809.64 | 3828.83 | 3848.02 | 3867.21 | 3885.83 | 3905.41 | 3924.98 | 3944.56 | 3963.55 | 3983.51 | 4003.48 | 4023.45 | 4042.82 | 4063.18 | 4083.55 | 4103.92 | 4123.67 | 4144.45 | 4165.22 | 4186 | 4206.15 | 4227.34 | 4248.53 | 4269.72 | 4290.27 | 4311.88 | 4333.5 | 4355.11
| Feature codes 02 to 20 and Composite index reflect the indices in the 31 March 2014 EM1110-2-1304 CWCCIS |  |  |  |  | 19 | 15 | 19 | FLOODWAY CONTROL & DIVERSION STRUCTURE | 2% | 272.96 | 276.04 | 284.61 | 287.69 | 293.79 | 300 | 309.83 | 312.44 | 317.17 | 318.26 | 327.74 | 327.83 | 327.53 | 329.77 | 336.78 | 337.58 | 337.59 | 341.9 | 345.41 | 344.61 | 344.74 | 346.93 | 349.22 | 347.84 | 347.27 | 349.61 | 349.34 | 349.75 | 350.28 | 352.65 | 356.54 | 359.07 | 362.38 | 367.09 | 370.86 | 371.49 | 374.97 | 379.49 | 382.47 | 382.81 | 382.1 | 385.48 | 388.93 | 389.01 | 391.31 | 393.28 | 396.94 | 395.33 | 398.09 | 402.68 | 403.56 | 403.94 | 409.21 | 419.09 | 417.86 | 421.18 | 427.15 | 429.69 | 432.59 | 434.12 | 438.14 | 444.64 | 447.98 | 447.96 | 447.8 | 452.65 | 457.78 | 459.09 | 461.23 | 466.4 | 468.57 | 468.4 | 469.97 | 474.07 | 474.38 | 472.57 | 474.86 | 480.31 | 487.47 | 483.86 | 487.08 | 489.21 | 489.75 | 489.55 | 490.33 | 491.91 | 496.69 | 497.31 | 499.28 | 508.67 | 514.07 | 513.82 | 514.15 | 516.87 | 520.35 | 525.69 | 534.75 | 558.9 | 571.55 | 586.56 | 593.35 | 597.76 | 600.97 | 608.18 | 624.32 | 630.14 | 636.39 | 645.47 | 649.01 | 668.79 | 674.11 | 671.55 | 675.58 | 693.72 | 722.13 | 719.86 | 698.29 | 686.42 | 689.95 | 691.34 | 696.93 | 707.21 | 712.33 | 711.42 | 718.73 | 732.94 | 740.7 | 740.08 | 744.72 | 749.69 | 749.6 | 749.46 | 758.43 | 764.29 | 764.9 | 766.75 | 775.02 | 777.93 | 780.83 | 783.74 | 787.07 | 790.94 | 794.31 | 797.68 | 801.81 | 805.64 | 809.48 | 813.31 | 817.53 | 821.65 | 825.77 | 829.89 | 833.88 | 838.08 | 842.29 | 846.49 | 850.56 | 854.85 | 859.13 | 863.42 | 867.57 | 871.94 | 876.31 | 880.68 | 884.92 | 889.38 | 893.84 | 898.3 | 902.62 | 907.17 | 911.72 | 916.26 | 920.68 | 925.31 | 929.95 | 934.59 | 939.09 | 943.82 | 948.55 | 953.28 | 957.87 | 962.7 | 967.52 | 972.35 | 977.03 | 981.95 | 986.87 | 991.79 | 996.57 | 1001.59 | 1006.61 | 1011.63 | 1016.5 | 1021.62 | 1026.74 | 1031.86 | 1036.83 | 1042.05 | 1047.28 | 1052.5 | 1057.57 | 1062.89 | 1068.22 | 1073.55 | 1078.72 | 1084.15 | 1089.59 | 1095.02 | 1100.29 | 1105.84 | 1111.38 | 1116.92 | 1122.3 | 1127.95 | 1133.61 | 1139.26 | 1144.74 | 1150.51 | 1156.28 | 1162.04 | 1167.64 | 1173.52 | 1179.4 | 1185.29 | 1190.99 | 1196.99 | 1202.99 | 1208.99 | 1214.81 | 1220.93 | 1227.05 | 1233.17 | 1239.11 | 1245.35 | 1251.59 | 1257.83 | 1263.89 | 1270.26 | 1276.62 | 1282.99 | 1289.17 | 1295.66 | 1302.16 | 1308.65 | 1314.95 | 1321.58 | 1328.2 | 1334.82 | 1341.25 | 1348.01 | 1354.76 | 1361.52 | 1368.08 | 1374.97 | 1381.86 | 1388.75 | 1395.44 | 1402.47 | 1409.5 | 1416.53 | 1423.35 | 1430.52 | 1437.69 | 1444.86 | 1451.81 | 1459.13 | 1466.44 | 1473.75 | 1480.85 | 1488.31 | 1495.77 | 1503.23 | 1510.47 | 1518.07 | 1525.68 | 1533.29 | 1540.67 | 1548.44 | 1556.2 | 1563.96 | 1571.49 | 1579.41 | 1587.32 | 1595.24 | 1602.92 | 1610.99 | 1619.07 | 1627.14 | 1634.98 | 1643.21 | 1651.45 | 1659.69 | 1667.68 | 1676.08 | 1684.48 | 1692.88 | 1701.03 | 1709.6 | 1718.17 | 1726.74 | 1735.05 | 1743.79 | 1752.53 | 1761.27 | 1769.75 | 1778.67 | 1787.58 | 1796.5 | 1805.15 | 1814.24 | 1823.33 | 1832.43 | 1841.25 | 1850.52 | 1859.8 | 1869.08 | 1878.07 | 1887.54 | 1897 | 1906.46 | 1915.64 | 1925.29 | 1934.94 | 1944.59 | 1953.95 | 1963.79 | 1973.64 | 1983.48 | 1993.03 | 2003.07 | 2013.11 | 2023.15 | 2032.89 | 2043.13 | 2053.37 | 2063.61 | 2073.55 | 2083.99 | 2094.44 | 2104.88 | 2115.02 | 2125.67 | 2136.33 | 2146.98 | 2157.32 | 2168.18 | 2179.05 | 2189.92 | 2200.46 | 2211.55 | 2222.63 | 2233.72 | 2244.47 | 2255.78 | 2267.09 | 2278.39 | 2289.36 | 2300.89 | 2312.43 | 2323.96 | 2335.15 | 2346.91 | 2358.68 | 2370.44 | 2381.85 | 2393.85 | 2405.85 | 2417.85 | 2429.49 | 2441.73 | 2453.97 | 2466.21 | 2478.08 | 2490.56 | 2503.05 | 2515.53 | 2527.64 | 2540.37 | 2553.11 | 2565.84 | 2578.19 | 2591.18 | 2604.17 | 2617.16 | 2629.76 | 2643.01 | 2656.25 | 2669.5 | 2682.35 | 2695.87 | 2709.38 | 2722.89 | 2736 | 2749.78 | 2763.57 | 2777.35 | 2790.72 | 2804.78 | 2818.84 | 2832.9 | 2846.53 | 2860.87 | 2875.21 | 2889.55 | 2903.46 | 2918.09 | 2932.72 | 2947.35 | 2961.53 | 2976.45 | 2991.37 | 3006.29 | 3020.76 | 3035.98 | 3051.2 | 3066.42 | 3081.18 | 3096.7 | 3112.22 | 3127.75 | 3142.8 | 3158.64 | 3174.47 | 3190.3 | 3205.66 | 3221.81 | 3237.96 | 3254.11 | 3269.77 | 3286.24 | 3302.72 | 3319.19 | 3335.17 | 3351.97 | 3368.77 | 3385.57 | 3401.87 | 3419.01 | 3436.15 | 3453.28 | 3469.91 | 3487.39 | 3504.87 | 3522.35 | 3539.31 | 3557.14 | 3574.97 | 3592.8 | 3610.09 | 3628.28 | 3646.47 | 3664.65 | 3682.29 | 3700.85 | 3719.4 | 3737.95 | 3755.94 | 3774.86 | 3793.78 | 3812.71 | 3831.06 | 3850.36 | 3869.66 | 3888.96 | 3907.68 | 3927.37 | 3947.05 | 3966.74 | 3985.83 | 4005.91 | 4025.99 | 4046.07 | 4065.55 | 4086.03 | 4106.51 | 4126.99 | 4146.86 | 4167.75 | 4188.64 | 4209.53 | 4229.8 | 4251.11 | 4272.42 | 4293.73
[6 empty] | 20 | 16 | 20 | BANK STABILIZATION | 2% | 252.82 | 257.63 | 266.45 | 273.32 | 279.15 | 286.12 | 295.88 | 299.36 | 305.34 | 308.27 | 318.02 | 320.08 | 321.52 | 322.52 | 327.18 | 327.81 | 329.24 | 331.83 | 336.53 | 336.61 | 339.5 | 342.69 | 344.67 | 344.96 | 346.37 | 349.19 | 351.15 | 351.23 | 354.5 | 357.36 | 360.96 | 362.01 | 365.31 | 368.11 | 370.12 | 371.45 | 376.09 | 379.56 | 383.04 | 384.58 | 386.68 | 391.12 | 394.94 | 396.05 | 398.72 | 402.16 | 404.24 | 405.03 | 406.86 | 411.41 | 414.73 | 415.36 | 419.18 | 423.02 | 424.66 | 427.08 | 430.35 | 433.67 | 435.18 | 436.35 | 439.89 | 444.59 | 449.63 | 450.08 | 453.16 | 456.47 | 459.29 | 459.9 | 462.5 | 464.94 | 466.65 | 467.64 | 472.31 | 476.13 | 478.33 | 479.14 | 483.67 | 488.48 | 492.81 | 493.47 | 496.2 | 500.74 | 503.53 | 505.51 | 508.86 | 511.15 | 515.13 | 516.86 | 519.9 | 530.24 | 534.49 | 534.58 | 538.56 | 542.73 | 544.59 | 547.71 | 553.65 | 561.04 | 568.83 | 574.2 | 584.95 | 591.3 | 599.32 | 603.93 | 619.29 | 627.39 | 632.75 | 642.25 | 654.93 | 666.89 | 672.89 | 678.39 | 685.5 | 693.62 | 705.31 | 710.77 | 718.39 | 722.75 | 726.93 | 725.05 | 731.87 | 734.65 | 743.86 | 745.72 | 751.63 | 757.16 | 765.44 | 765.87 | 771.7 | 779.14 | 784.52 | 784.53 | 790.84 | 793.64 | 801.54 | 805.25 | 811.93 | 814.97 | 818.02 | 821.06 | 824.55 | 828.61 | 832.14 | 835.67 | 839.99 | 844.01 | 848.03 | 852.05 | 856.47 | 860.78 | 865.1 | 869.41 | 873.6 | 878 | 882.4 | 886.8 | 891.07 | 895.56 | 900.05 | 904.54 | 908.89 | 913.47 | 918.05 | 922.63 | 927.07 | 931.74 | 936.41 | 941.08 | 945.61 | 950.37 | 955.14 | 959.9 | 964.52 | 969.38 | 974.24 | 979.1 | 983.81 | 988.77 | 993.73 | 998.68 | 1003.49 | 1008.54 | 1013.6 | 1018.65 | 1023.56 | 1028.72 | 1033.87 | 1039.03 | 1044.03 | 1049.29 | 1054.55 | 1059.81 | 1064.91 | 1070.28 | 1075.64 | 1081 | 1086.21 | 1091.68 | 1097.15 | 1102.62 | 1107.93 | 1113.51 | 1119.1 | 1124.68 | 1130.09 | 1135.78 | 1141.48 | 1147.17 | 1152.69 | 1158.5 | 1164.31 | 1170.11 | 1175.75 | 1181.67 | 1187.59 | 1193.52 | 1199.26 | 1205.3 | 1211.35 | 1217.39 | 1223.25 | 1229.41 | 1235.57 | 1241.73 | 1247.71 | 1254 | 1260.28 | 1266.57 | 1272.67 | 1279.08 | 1285.49 | 1291.9 | 1298.12 | 1304.66 | 1311.2 | 1317.74 | 1324.08 | 1330.75 | 1337.42 | 1344.09 | 1350.56 | 1357.37 | 1364.17 | 1370.98 | 1377.58 | 1384.51 | 1391.45 | 1398.39 | 1405.13 | 1412.21 | 1419.28 | 1426.36 | 1433.23 | 1440.45 | 1447.67 | 1454.89 | 1461.89 | 1469.26 | 1476.62 | 1483.99 | 1491.13 | 1498.64 | 1506.16 | 1513.67 | 1520.95 | 1528.62 | 1536.28 | 1543.94 | 1551.37 | 1559.19 | 1567 | 1574.82 | 1582.4 | 1590.37 | 1598.34 | 1606.32 | 1614.05 | 1622.18 | 1630.31 | 1638.44 | 1646.33 | 1654.62 | 1662.92 | 1671.21 | 1679.26 | 1687.72 | 1696.18 | 1704.64 | 1712.84 | 1721.47 | 1730.1 | 1738.73 | 1747.1 | 1755.9 | 1764.7 | 1773.5 | 1782.04 | 1791.02 | 1800 | 1808.97 | 1817.68 | 1826.84 | 1836 | 1845.15 | 1854.03 | 1863.37 | 1872.72 | 1882.06 | 1891.12 | 1900.64 | 1910.17 | 1919.7 | 1928.94 | 1938.66 | 1948.37 | 1958.09 | 1967.52 | 1977.43 | 1987.34 | 1997.25 | 2006.87 | 2016.98 | 2027.09 | 2037.2 | 2047 | 2057.32 | 2067.63 | 2077.94 | 2087.94 | 2098.46 | 2108.98 | 2119.5 | 2129.7 | 2140.43 | 2151.16 | 2161.89 | 2172.3 | 2183.24 | 2194.18 | 2205.13 | 2215.74 | 2226.91 | 2238.07 | 2249.23 | 2260.06 | 2271.44 | 2282.83 | 2294.21 | 2305.26 | 2316.87 | 2328.49 | 2340.1 | 2351.36 | 2363.21 | 2375.06 | 2386.9 | 2398.39 | 2410.47 | 2422.56 | 2434.64 | 2446.36 | 2458.68 | 2471.01 | 2483.33 | 2495.29 | 2507.86 | 2520.43 | 2533 | 2545.19 | 2558.01 | 2570.84 | 2583.66 | 2596.1 | 2609.17 | 2622.25 | 2635.33 | 2648.02 | 2661.36 | 2674.7 | 2688.04 | 2700.98 | 2714.59 | 2728.19 | 2741.8 | 2755 | 2768.88 | 2782.76 | 2796.64 | 2810.1 | 2824.25 | 2838.41 | 2852.57 | 2866.3 | 2880.74 | 2895.18 | 2909.62 | 2923.63 | 2938.35 | 2953.08 | 2967.81 | 2982.1 | 2997.12 | 3012.14 | 3027.17 | 3041.74 | 3057.06 | 3072.39 | 3087.71 | 3102.58 | 3118.21 | 3133.84 | 3149.47 | 3164.63 | 3180.57 | 3196.51 | 3212.45 | 3227.92 | 3244.18 | 3260.44 | 3276.7 | 3292.48 | 3309.06 | 3325.65 | 3342.24 | 3358.33 | 3375.25 | 3392.16 | 3409.08 | 3425.49 | 3442.75 | 3460.01 | 3477.26 | 3494 | 3511.61 | 3529.21 | 3546.81 | 3563.88 | 3581.84 | 3599.79 | 3617.75 | 3635.16 | 3653.47 | 3671.79 | 3690.1 | 3707.86 | 3726.54 | 3745.22 | 3763.9 | 3782.02 | 3801.07 | 3820.13 | 3839.18 | 3857.66 | 3877.1 | 3896.53 | 3915.96 | 3934.82 | 3954.64 | 3974.46 | 3994.28 | 4013.51 | 4033.73 | 4053.95 | 4074.17 | 4093.78 | 4114.41 | 4135.03 | 4155.65 | 4175.66 | 4196.69 | 4217.73 | 4238.77 | 4259.17 | 4280.63 | 4302.08 | 4323.54 | 4344.35 | 4366.24 | 4388.13 | 4410.01 | 4431.24 | 4453.56 | 4475.89 | 4498.21
[6 empty] | 21 | 17 | 21 | BEACH REPLENISHMENT | 2% | 262.51 | 266.77 | 278.85 | 284.04 | 287.68 | 293.48 | 307.19 | 311.48 | 317.47 | 319.47 | 334.99 | 336.48 | 338.31 | 339.12 | 345.4 | 346.48 | 347.61 | 348.8 | 354.71 | 354.44 | 356.26 | 357.84 | 360.19 | 360.68 | 361.64 | 364.59 | 366.87 | 366.99 | 370.06 | 371.75 | 376.2 | 377.19 | 380.01 | 382.4 | 385.05 | 386.6 | 394.09 | 397.39 | 402.05 | 404.39 | 408.11 | 411.77 | 417.43 | 418.79 | 421.46 | 424.52 | 427.62 | 429.07 | 431.08 | 437.09 | 443.07 | 443.82 | 446.08 | 450.52 | 454.06 | 454.39 | 457.05 | 460.68 | 462.35 | 463.56 | 465.83 | 471.98 | 479.09 | 479.43 | 482.58 | 486.02 | 489.99 | 490.51 | 492.64 | 494.85 | 496.49 | 498.23 | 503.53 | 506.24 | 508.4 | 510.21 | 514.77 | 520.48 | 525.81 | 526.51 | 527.91 | 531.22 | 534.34 | 537.36 | 540.77 | 539.82 | 544.75 | 547.51 | 550.76 | 568.85 | 574.22 | 574.58 | 580.2 | 585.05 | 585.18 | 588.23 | 593.35 | 597.42 | 605.82 | 610.94 | 619.98 | 626.28 | 635.25 | 639.56 | 650.69 | 658.21 | 661.81 | 669.01 | 676.88 | 686.56 | 696 | 698.14 | 700.69 | 705.47 | 713.5 | 717.74 | 727.05 | 730.99 | 740.35 | 741.15 | 747.83 | 748.86 | 765.59 | 766.53 | 771.39 | 778.88 | 787.89 | 789.66 | 795.15 | 798.73 | 806.02 | 807.05 | 812.95 | 815.76 | 828.49 | 829.61 | 834.23 | 837.36 | 840.49 | 843.62 | 847.2 | 851.37 | 855 | 858.62 | 863.06 | 867.19 | 871.32 | 875.45 | 879.99 | 884.42 | 888.86 | 893.29 | 897.59 | 902.11 | 906.63 | 911.16 | 915.54 | 920.16 | 924.77 | 929.38 | 933.85 | 938.56 | 943.26 | 947.97 | 952.53 | 957.33 | 962.13 | 966.93 | 971.58 | 976.48 | 981.37 | 986.27 | 991.01 | 996.01 | 1001 | 1005.99 | 1010.83 | 1015.93 | 1021.02 | 1026.11 | 1031.05 | 1036.24 | 1041.44 | 1046.63 | 1051.67 | 1056.97 | 1062.27 | 1067.57 | 1072.7 | 1078.11 | 1083.51 | 1088.92 | 1094.16 | 1099.67 | 1105.18 | 1110.69 | 1116.04 | 1121.66 | 1127.29 | 1132.91 | 1138.36 | 1144.1 | 1149.83 | 1155.57 | 1161.13 | 1166.98 | 1172.83 | 1178.68 | 1184.35 | 1190.32 | 1196.29 | 1202.25 | 1208.04 | 1214.13 | 1220.21 | 1226.3 | 1232.2 | 1238.41 | 1244.62 | 1250.82 | 1256.84 | 1263.18 | 1269.51 | 1275.84 | 1281.98 | 1288.44 | 1294.9 | 1301.36 | 1307.62 | 1314.21 | 1320.8 | 1327.38 | 1333.77 | 1340.49 | 1347.21 | 1353.93 | 1360.45 | 1367.3 | 1374.16 | 1381.01 | 1387.66 | 1394.65 | 1401.64 | 1408.63 | 1415.41 | 1422.54 | 1429.67 | 1436.8 | 1443.72 | 1450.99 | 1458.27 | 1465.54 | 1472.59 | 1480.01 | 1487.43 | 1494.85 | 1502.05 | 1509.61 | 1517.18 | 1524.75 | 1532.09 | 1539.8 | 1547.52 | 1555.24 | 1562.73 | 1570.6 | 1578.47 | 1586.35 | 1593.98 | 1602.01 | 1610.04 | 1618.07 | 1625.86 | 1634.05 | 1642.24 | 1650.43 | 1658.38 | 1666.73 | 1675.09 | 1683.44 | 1691.55 | 1700.07 | 1708.59 | 1717.11 | 1725.38 | 1734.07 | 1742.76 | 1751.45 | 1759.89 | 1768.75 | 1777.62 | 1786.48 | 1795.08 | 1804.13 | 1813.17 | 1822.21 | 1830.98 | 1840.21 | 1849.43 | 1858.66 | 1867.6 | 1877.01 | 1886.42 | 1895.83 | 1904.96 | 1914.55 | 1924.15 | 1933.75 | 1943.06 | 1952.84 | 1962.63 | 1972.42 | 1981.92 | 1991.9 | 2001.89 | 2011.87 | 2021.56 | 2031.74 | 2041.92 | 2052.11 | 2061.99 | 2072.37 | 2082.76 | 2093.15 | 2103.23 | 2113.82 | 2124.42 | 2135.01 | 2145.29 | 2156.1 | 2166.91 | 2177.71 | 2188.2 | 2199.22 | 2210.24 | 2221.27 | 2231.96 | 2243.2 | 2254.45 | 2265.69 | 2276.6 | 2288.07 | 2299.54 | 2311.01 | 2322.13 | 2333.83 | 2345.53 | 2357.23 | 2368.57 | 2380.51 | 2392.44 | 2404.37 | 2415.95 | 2428.12 | 2440.29 | 2452.46 | 2464.26 | 2476.68 | 2489.09 | 2501.51 | 2513.55 | 2526.21 | 2538.88 | 2551.54 | 2563.82 | 2576.74 | 2589.65 | 2602.57 | 2615.1 | 2628.27 | 2641.45 | 2654.62 | 2667.4 | 2680.84 | 2694.27 | 2707.71 | 2720.75 | 2734.45 | 2748.16 | 2761.87 | 2775.16 | 2789.14 | 2803.12 | 2817.1 | 2830.67 | 2844.93 | 2859.19 | 2873.45 | 2887.28 | 2901.82 | 2916.37 | 2930.91 | 2945.02 | 2959.86 | 2974.7 | 2989.53 | 3003.92 | 3019.06 | 3034.19 | 3049.32 | 3064 | 3079.44 | 3094.87 | 3110.31 | 3125.28 | 3141.03 | 3156.77 | 3172.52 | 3187.79 | 3203.85 | 3219.91 | 3235.97 | 3251.54 | 3267.93 | 3284.31 | 3300.69 | 3316.58 | 3333.28 | 3349.99 | 3366.7 | 3382.91 | 3399.95 | 3416.99 | 3434.03 | 3450.57 | 3467.95 | 3485.33 | 3502.71 | 3519.58 | 3537.31 | 3555.04 | 3572.77 | 3589.97 | 3608.05 | 3626.14 | 3644.22 | 3661.77 | 3680.21 | 3698.66 | 3717.11 | 3735 | 3753.82 | 3772.63 | 3791.45 | 3809.7 | 3828.9 | 3848.09 | 3867.28 | 3885.9 | 3905.47 | 3925.05 | 3944.63 | 3963.61 | 3983.58 | 4003.55 | 4023.52 | 4042.89 | 4063.25 | 4083.62 | 4103.99 | 4123.74 | 4144.52 | 4165.29 | 4186.07 | 4206.22 | 4227.41 | 4248.6 | 4269.79 | 4290.34 | 4311.96 | 4333.57 | 4355.19 | 4376.15 | 4398.2 | 4420.24 | 4442.29 | 4463.67 | 4486.16 | 4508.65 | 4531.13 | 4552.95 | 4575.88 | 4598.82 | 4621.76
| The 30 and 31 feature codes can be based on the updating factors from Table 1 in |  |  |  |  | 22 | 18 | 22 | CULTURAL RESOURCE PRESERVATION | 2% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 786.1 | 789.05 | 792 | 794.94 | 798.32 | 802.25 | 805.67 | 809.09 | 813.27 | 817.16 | 821.05 | 824.94 | 829.22 | 833.4 | 837.58 | 841.75 | 845.81 | 850.07 | 854.33 | 858.59 | 862.72 | 867.07 | 871.41 | 875.76 | 879.98 | 884.41 | 888.84 | 893.28 | 897.58 | 902.1 | 906.62 | 911.14 | 915.53 | 920.14 | 924.75 | 929.36 | 933.84 | 938.54 | 943.25 | 947.95 | 952.51 | 957.31 | 962.11 | 966.91 | 971.56 | 976.46 | 981.35 | 986.25 | 991 | 995.99 | 1000.98 | 1005.97 | 1010.82 | 1015.91 | 1021 | 1026.09 | 1031.03 | 1036.23 | 1041.42 | 1046.61 | 1051.65 | 1056.95 | 1062.25 | 1067.55 | 1072.69 | 1078.09 | 1083.49 | 1088.9 | 1094.14 | 1099.65 | 1105.16 | 1110.68 | 1116.02 | 1121.64 | 1127.27 | 1132.89 | 1138.34 | 1144.08 | 1149.81 | 1155.55 | 1161.11 | 1166.96 | 1172.81 | 1178.66 | 1184.33 | 1190.3 | 1196.26 | 1202.23 | 1208.02 | 1214.1 | 1220.19 | 1226.28 | 1232.18 | 1238.39 | 1244.59 | 1250.8 | 1256.82 | 1263.15 | 1269.49 | 1275.82 | 1281.96 | 1288.42 | 1294.88 | 1301.33 | 1307.6 | 1314.19 | 1320.77 | 1327.36 | 1333.75 | 1340.47 | 1347.19 | 1353.91 | 1360.43 | 1367.28 | 1374.13 | 1380.99 | 1387.63 | 1394.62 | 1401.61 | 1408.61 | 1415.39 | 1422.52 | 1429.65 | 1436.78 | 1443.69 | 1450.97 | 1458.24 | 1465.51 | 1472.57 | 1479.99 | 1487.4 | 1494.82 | 1502.02 | 1509.59 | 1517.15 | 1524.72 | 1532.06 | 1539.78 | 1547.5 | 1555.21 | 1562.7 | 1570.57 | 1578.45 | 1586.32 | 1593.95 | 1601.98 | 1610.01 | 1618.04 | 1625.83 | 1634.02 | 1642.22 | 1650.41 | 1658.35 | 1666.71 | 1675.06 | 1683.41 | 1691.52 | 1700.04 | 1708.56 | 1717.08 | 1725.35 | 1734.04 | 1742.73 | 1751.42 | 1759.85 | 1768.72 | 1777.59 | 1786.45 | 1795.05 | 1804.1 | 1813.14 | 1822.18 | 1830.95 | 1840.18 | 1849.4 | 1858.62 | 1867.57 | 1876.98 | 1886.39 | 1895.8 | 1904.92 | 1914.52 | 1924.12 | 1933.71 | 1943.02 | 1952.81 | 1962.6 | 1972.39 | 1981.88 | 1991.87 | 2001.85 | 2011.84 | 2021.52 | 2031.7 | 2041.89 | 2052.07 | 2061.95 | 2072.34 | 2082.73 | 2093.11 | 2103.19 | 2113.79 | 2124.38 | 2134.98 | 2145.25 | 2156.06 | 2166.87 | 2177.68 | 2188.16 | 2199.18 | 2210.21 | 2221.23 | 2231.92 | 2243.17 | 2254.41 | 2265.65 | 2276.56 | 2288.03 | 2299.5 | 2310.97 | 2322.09 | 2333.79 | 2345.49 | 2357.19 | 2368.53 | 2380.47 | 2392.4 | 2404.33 | 2415.9 | 2428.07 | 2440.25 | 2452.42 | 2464.22 | 2476.64 | 2489.05 | 2501.46 | 2513.51 | 2526.17 | 2538.83 | 2551.49 | 2563.78 | 2576.69 | 2589.61 | 2602.52 | 2615.05 | 2628.23 | 2641.4 | 2654.57 | 2667.35 | 2680.79 | 2694.23 | 2707.67 | 2720.7 | 2734.41 | 2748.11 | 2761.82 | 2775.11 | 2789.09 | 2803.07 | 2817.06 | 2830.62 | 2844.88 | 2859.14 | 2873.4 | 2887.23 | 2901.77 | 2916.32 | 2930.86 | 2944.97 | 2959.81 | 2974.65 | 2989.48 | 3003.87 | 3019.01 | 3034.14 | 3049.27 | 3063.95 | 3079.39 | 3094.82 | 3110.26 | 3125.23 | 3140.97 | 3156.72 | 3172.46 | 3187.73 | 3203.79 | 3219.85 | 3235.91 | 3251.49 | 3267.87 | 3284.25 | 3300.63 | 3316.52 | 3333.23 | 3349.93 | 3366.64 | 3382.85 | 3399.89 | 3416.93 | 3433.97 | 3450.51 | 3467.89 | 3485.27 | 3502.65 | 3519.52 | 3537.25 | 3554.98 | 3572.71 | 3589.91 | 3607.99 | 3626.08 | 3644.16 | 3661.7 | 3680.15 | 3698.6 | 3717.04 | 3734.94 | 3753.75 | 3772.57 | 3791.39 | 3809.64 | 3828.83 | 3848.02 | 3867.21 | 3885.83 | 3905.41 | 3924.98 | 3944.56 | 3963.55 | 3983.51 | 4003.48 | 4023.45 | 4042.82 | 4063.18 | 4083.55 | 4103.92 | 4123.67 | 4144.45 | 4165.22 | 4186 | 4206.15 | 4227.34 | 4248.53 | 4269.72 | 4290.27 | 4311.88 | 4333.5 | 4355.11
| EC 11-2-206 Program Development Guidance Fiscal Year 2016 Dated: 31 March 2014 |  |  |  |  | 23 | 19 | 23 | BUILDINGS, GROUNDS & UTILITIES | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 786.1 | 789.05 | 792 | 794.94 | 798.32 | 802.25 | 805.67 | 809.09 | 813.27 | 817.16 | 821.05 | 824.94 | 829.22 | 833.4 | 837.58 | 841.75 | 845.81 | 850.07 | 854.33 | 858.59 | 862.72 | 867.07 | 871.41 | 875.76 | 879.98 | 884.41 | 888.84 | 893.28 | 897.58 | 902.1 | 906.62 | 911.14 | 915.53 | 920.14 | 924.75 | 929.36 | 933.84 | 938.54 | 943.25 | 947.95 | 952.51 | 957.31 | 962.11 | 966.91 | 971.56 | 976.46 | 981.35 | 986.25 | 991 | 995.99 | 1000.98 | 1005.97 | 1010.82 | 1015.91 | 1021 | 1026.09 | 1031.03 | 1036.23 | 1041.42 | 1046.61 | 1051.65 | 1056.95 | 1062.25 | 1067.55 | 1072.69 | 1078.09 | 1083.49 | 1088.9 | 1094.14 | 1099.65 | 1105.16 | 1110.68 | 1116.02 | 1121.64 | 1127.27 | 1132.89 | 1138.34 | 1144.08 | 1149.81 | 1155.55 | 1161.11 | 1166.96 | 1172.81 | 1178.66 | 1184.33 | 1190.3 | 1196.26 | 1202.23 | 1208.02 | 1214.1 | 1220.19 | 1226.28 | 1232.18 | 1238.39 | 1244.59 | 1250.8 | 1256.82 | 1263.15 | 1269.49 | 1275.82 | 1281.96 | 1288.42 | 1294.88 | 1301.33 | 1307.6 | 1314.19 | 1320.77 | 1327.36 | 1333.75 | 1340.47 | 1347.19 | 1353.91 | 1360.43 | 1367.28 | 1374.13 | 1380.99 | 1387.63 | 1394.62 | 1401.61 | 1408.61 | 1415.39 | 1422.52 | 1429.65 | 1436.78 | 1443.69 | 1450.97 | 1458.24 | 1465.51 | 1472.57 | 1479.99 | 1487.4 | 1494.82 | 1502.02 | 1509.59 | 1517.15 | 1524.72 | 1532.06 | 1539.78 | 1547.5 | 1555.21 | 1562.7 | 1570.57 | 1578.45 | 1586.32 | 1593.95 | 1601.98 | 1610.01 | 1618.04 | 1625.83 | 1634.02 | 1642.22 | 1650.41 | 1658.35 | 1666.71 | 1675.06 | 1683.41 | 1691.52 | 1700.04 | 1708.56 | 1717.08 | 1725.35 | 1734.04 | 1742.73 | 1751.42 | 1759.85 | 1768.72 | 1777.59 | 1786.45 | 1795.05 | 1804.1 | 1813.14 | 1822.18 | 1830.95 | 1840.18 | 1849.4 | 1858.62 | 1867.57 | 1876.98 | 1886.39 | 1895.8 | 1904.92 | 1914.52 | 1924.12 | 1933.71 | 1943.02 | 1952.81 | 1962.6 | 1972.39 | 1981.88 | 1991.87 | 2001.85 | 2011.84 | 2021.52 | 2031.7 | 2041.89 | 2052.07 | 2061.95 | 2072.34 | 2082.73 | 2093.11 | 2103.19 | 2113.79 | 2124.38 | 2134.98 | 2145.25 | 2156.06 | 2166.87 | 2177.68 | 2188.16 | 2199.18 | 2210.21 | 2221.23 | 2231.92 | 2243.17 | 2254.41 | 2265.65 | 2276.56 | 2288.03 | 2299.5 | 2310.97 | 2322.09 | 2333.79 | 2345.49 | 2357.19 | 2368.53 | 2380.47 | 2392.4 | 2404.33 | 2415.9 | 2428.07 | 2440.25 | 2452.42 | 2464.22 | 2476.64 | 2489.05 | 2501.46 | 2513.51 | 2526.17 | 2538.83 | 2551.49 | 2563.78 | 2576.69 | 2589.61 | 2602.52 | 2615.05 | 2628.23 | 2641.4 | 2654.57 | 2667.35 | 2680.79 | 2694.23 | 2707.67 | 2720.7 | 2734.41 | 2748.11 | 2761.82 | 2775.11 | 2789.09 | 2803.07 | 2817.06 | 2830.62 | 2844.88 | 2859.14 | 2873.4 | 2887.23 | 2901.77 | 2916.32 | 2930.86 | 2944.97 | 2959.81 | 2974.65 | 2989.48 | 3003.87 | 3019.01 | 3034.14 | 3049.27 | 3063.95 | 3079.39 | 3094.82 | 3110.26 | 3125.23 | 3140.97 | 3156.72 | 3172.46 | 3187.73 | 3203.79 | 3219.85 | 3235.91 | 3251.49 | 3267.87 | 3284.25 | 3300.63 | 3316.52 | 3333.23 | 3349.93 | 3366.64 | 3382.85 | 3399.89 | 3416.93 | 3433.97 | 3450.51 | 3467.89 | 3485.27 | 3502.65 | 3519.52 | 3537.25 | 3554.98 | 3572.71 | 3589.91 | 3607.99 | 3626.08 | 3644.16 | 3661.7 | 3680.15 | 3698.6 | 3717.04 | 3734.94 | 3753.75 | 3772.57 | 3791.39 | 3809.64 | 3828.83 | 3848.02 | 3867.21 | 3885.83 | 3905.41 | 3924.98 | 3944.56 | 3963.55 | 3983.51 | 4003.48 | 4023.45 | 4042.82 | 4063.18 | 4083.55 | 4103.92 | 4123.67 | 4144.45 | 4165.22 | 4186 | 4206.15 | 4227.34 | 4248.53 | 4269.72 | 4290.27 | 4311.88 | 4333.5 | 4355.11
[5 empty] | Select | 24 | 20 | 24 | PERMANENT OPERATING EQUIPMENT | 2% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 469.97 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 786.1 | 789.05 | 792 | 794.94 | 798.32 | 802.25 | 805.67 | 809.09 | 813.27 | 817.16 | 821.05 | 824.94 | 829.22 | 833.4 | 837.58 | 841.75 | 845.81 | 850.07 | 854.33 | 858.59 | 862.72 | 867.07 | 871.41 | 875.76 | 879.98 | 884.41 | 888.84 | 893.28 | 897.58 | 902.1 | 906.62 | 911.14 | 915.53 | 920.14 | 924.75 | 929.36 | 933.84 | 938.54 | 943.25 | 947.95 | 952.51 | 957.31 | 962.11 | 966.91 | 971.56 | 976.46 | 981.35 | 986.25 | 991 | 995.99 | 1000.98 | 1005.97 | 1010.82 | 1015.91 | 1021 | 1026.09 | 1031.03 | 1036.23 | 1041.42 | 1046.61 | 1051.65 | 1056.95 | 1062.25 | 1067.55 | 1072.69 | 1078.09 | 1083.49 | 1088.9 | 1094.14 | 1099.65 | 1105.16 | 1110.68 | 1116.02 | 1121.64 | 1127.27 | 1132.89 | 1138.34 | 1144.08 | 1149.81 | 1155.55 | 1161.11 | 1166.96 | 1172.81 | 1178.66 | 1184.33 | 1190.3 | 1196.26 | 1202.23 | 1208.02 | 1214.1 | 1220.19 | 1226.28 | 1232.18 | 1238.39 | 1244.59 | 1250.8 | 1256.82 | 1263.15 | 1269.49 | 1275.82 | 1281.96 | 1288.42 | 1294.88 | 1301.33 | 1307.6 | 1314.19 | 1320.77 | 1327.36 | 1333.75 | 1340.47 | 1347.19 | 1353.91 | 1360.43 | 1367.28 | 1374.13 | 1380.99 | 1387.63 | 1394.62 | 1401.61 | 1408.61 | 1415.39 | 1422.52 | 1429.65 | 1436.78 | 1443.69 | 1450.97 | 1458.24 | 1465.51 | 1472.57 | 1479.99 | 1487.4 | 1494.82 | 1502.02 | 1509.59 | 1517.15 | 1524.72 | 1532.06 | 1539.78 | 1547.5 | 1555.21 | 1562.7 | 1570.57 | 1578.45 | 1586.32 | 1593.95 | 1601.98 | 1610.01 | 1618.04 | 1625.83 | 1634.02 | 1642.22 | 1650.41 | 1658.35 | 1666.71 | 1675.06 | 1683.41 | 1691.52 | 1700.04 | 1708.56 | 1717.08 | 1725.35 | 1734.04 | 1742.73 | 1751.42 | 1759.85 | 1768.72 | 1777.59 | 1786.45 | 1795.05 | 1804.1 | 1813.14 | 1822.18 | 1830.95 | 1840.18 | 1849.4 | 1858.62 | 1867.57 | 1876.98 | 1886.39 | 1895.8 | 1904.92 | 1914.52 | 1924.12 | 1933.71 | 1943.02 | 1952.81 | 1962.6 | 1972.39 | 1981.88 | 1991.87 | 2001.85 | 2011.84 | 2021.52 | 2031.7 | 2041.89 | 2052.07 | 2061.95 | 2072.34 | 2082.73 | 2093.11 | 2103.19 | 2113.79 | 2124.38 | 2134.98 | 2145.25 | 2156.06 | 2166.87 | 2177.68 | 2188.16 | 2199.18 | 2210.21 | 2221.23 | 2231.92 | 2243.17 | 2254.41 | 2265.65 | 2276.56 | 2288.03 | 2299.5 | 2310.97 | 2322.09 | 2333.79 | 2345.49 | 2357.19 | 2368.53 | 2380.47 | 2392.4 | 2404.33 | 2415.9 | 2428.07 | 2440.25 | 2452.42 | 2464.22 | 2476.64 | 2489.05 | 2501.46 | 2513.51 | 2526.17 | 2538.83 | 2551.49 | 2563.78 | 2576.69 | 2589.61 | 2602.52 | 2615.05 | 2628.23 | 2641.4 | 2654.57 | 2667.35 | 2680.79 | 2694.23 | 2707.67 | 2720.7 | 2734.41 | 2748.11 | 2761.82 | 2775.11 | 2789.09 | 2803.07 | 2817.06 | 2830.62 | 2844.88 | 2859.14 | 2873.4 | 2887.23 | 2901.77 | 2916.32 | 2930.86 | 2944.97 | 2959.81 | 2974.65 | 2989.48 | 3003.87 | 3019.01 | 3034.14 | 3049.27 | 3063.95 | 3079.39 | 3094.82 | 3110.26 | 3125.23 | 3140.97 | 3156.72 | 3172.46 | 3187.73 | 3203.79 | 3219.85 | 3235.91 | 3251.49 | 3267.87 | 3284.25 | 3300.63 | 3316.52 | 3333.23 | 3349.93 | 3366.64 | 3382.85 | 3399.89 | 3416.93 | 3433.97 | 3450.51 | 3467.89 | 3485.27 | 3502.65 | 3519.52 | 3537.25 | 3554.98 | 3572.71 | 3589.91 | 3607.99 | 3626.08 | 3644.16 | 3661.7 | 3680.15 | 3698.6 | 3717.04 | 3734.94 | 3753.75 | 3772.57 | 3791.39 | 3809.64 | 3828.83 | 3848.02 | 3867.21 | 3885.83 | 3905.41 | 3924.98 | 3944.56 | 3963.55 | 3983.51 | 4003.48 | 4023.45 | 4042.82 | 4063.18 | 4083.55 | 4103.92 | 4123.67 | 4144.45 | 4165.22 | 4186 | 4206.15 | 4227.34 | 4248.53 | 4269.72 | 4290.27 | 4311.88 | 4333.5 | 4355.11
[5 empty] | Class | 25 | ALL | 25 | COMPOSITE INDEX (WEIGHTED AVERAGE) | 100% | 270.89 | 276.33 | 285.85 | 289.76 | 295.87 | 303.91 | 314.31 | 318.24 | 323.45 | 325.24 | 335.09 | 335.72 | 336.75 | 337.22 | 342.77 | 344.12 | 345.25 | 348.43 | 352.39 | 352.45 | 353.23 | 353.64 | 355.73 | 354.66 | 354.6 | 356.25 | 357.4 | 356.91 | 357.75 | 359.01 | 362.94 | 366.08 | 369.3 | 373.44 | 376.76 | 378.56 | 383.22 | 387.78 | 391.19 | 392.55 | 393.28 | 396.19 | 399.75 | 404.15 | 405.07 | 405.25 | 408.48 | 408.68 | 410.77 | 414.89 | 417.22 | 418.01 | 422.05 | 428.85 | 429.04 | 431.4 | 435.65 | 438.47 | 440.77 | 442.92 | 446.34 | 452.21 | 455.44 | 455.24 | 456.46 | 460.75 | 464.13 | 467.28 | 468.6 | 471.96 | 473.39 | 474.74 | 476.72 | 478.83 | 478.86 | 478.01 | 479.74 | 484.42 | 490.61 | 490.05 | 493.28 | 496.38 | 498.13 | 500.48 | 501.17 | 501.33 | 505.47 | 506.11 | 507.18 | 516.82 | 522.4 | 523.44 | 525.26 | 528.3 | 530.64 | 535.59 | 544.89 | 566.51 | 578.67 | 595.09 | 599.22 | 604.49 | 608.79 | 620.94 | 630.43 | 638.08 | 644.95 | 654.19 | 657.49 | 674.89 | 681.29 | 680.42 | 687.9 | 708.36 | 738.89 | 731.03 | 705.87 | 697.73 | 702.67 | 705.72 | 713.39 | 722.89 | 729.23 | 731.19 | 739.86 | 756.92 | 764.34 | 764.82 | 769.23 | 775.01 | 773.35 | 777.41 | 782.27 | 786.67 | 789.56 | 792.07 | 798.14 | 801.14 | 804.13 | 807.12 | 810.55 | 814.54 | 818.01 | 821.48 | 825.73 | 829.68 | 833.63 | 837.58 | 841.93 | 846.17 | 850.41 | 854.65 | 858.77 | 863.09 | 867.42 | 871.74 | 875.94 | 880.35 | 884.77 | 889.18 | 893.46 | 897.96 | 902.46 | 906.96 | 911.33 | 915.92 | 920.51 | 925.1 | 929.56 | 934.24 | 938.92 | 943.6 | 948.15 | 952.92 | 957.7 | 962.48 | 967.11 | 971.98 | 976.85 | 981.73 | 986.45 | 991.42 | 996.39 | 1001.36 | 1006.18 | 1011.25 | 1016.32 | 1021.39 | 1026.3 | 1031.47 | 1036.64 | 1041.81 | 1046.83 | 1052.1 | 1057.38 | 1062.65 | 1067.77 | 1073.15 | 1078.52 | 1083.9 | 1089.12 | 1094.61 | 1100.1 | 1105.58 | 1110.9 | 1116.5 | 1122.1 | 1127.69 | 1133.12 | 1138.83 | 1144.54 | 1150.25 | 1155.78 | 1161.61 | 1167.43 | 1173.25 | 1178.9 | 1184.84 | 1190.78 | 1196.72 | 1202.48 | 1208.54 | 1214.59 | 1220.65 | 1226.53 | 1232.71 | 1238.89 | 1245.07 | 1251.06 | 1257.36 | 1263.66 | 1269.97 | 1276.08 | 1282.51 | 1288.94 | 1295.37 | 1301.6 | 1308.16 | 1314.72 | 1321.27 | 1327.63 | 1334.32 | 1341.01 | 1347.7 | 1354.19 | 1361.01 | 1367.83 | 1374.65 | 1381.27 | 1388.23 | 1395.19 | 1402.15 | 1408.9 | 1415.99 | 1423.09 | 1430.19 | 1437.07 | 1444.31 | 1451.55 | 1458.79 | 1465.81 | 1473.2 | 1480.58 | 1487.97 | 1495.13 | 1502.66 | 1510.2 | 1517.73 | 1525.03 | 1532.72 | 1540.4 | 1548.08 | 1555.53 | 1563.37 | 1571.21 | 1579.04 | 1586.64 | 1594.64 | 1602.63 | 1610.62 | 1618.38 | 1626.53 | 1634.68 | 1642.84 | 1650.75 | 1659.06 | 1667.38 | 1675.69 | 1683.76 | 1692.24 | 1700.73 | 1709.21 | 1717.44 | 1726.09 | 1734.74 | 1743.39 | 1751.78 | 1760.61 | 1769.43 | 1778.26 | 1786.82 | 1795.82 | 1804.82 | 1813.82 | 1822.56 | 1831.74 | 1840.92 | 1850.1 | 1859.01 | 1868.37 | 1877.74 | 1887.1 | 1896.19 | 1905.74 | 1915.29 | 1924.85 | 1934.11 | 1943.85 | 1953.6 | 1963.34 | 1972.79 | 1982.73 | 1992.67 | 2002.61 | 2012.25 | 2022.39 | 2032.52 | 2042.66 | 2052.49 | 2062.83 | 2073.17 | 2083.51 | 2093.54 | 2104.09 | 2114.64 | 2125.18 | 2135.42 | 2146.17 | 2156.93 | 2167.69 | 2178.12 | 2189.1 | 2200.07 | 2211.04 | 2221.69 | 2232.88 | 2244.07 | 2255.26 | 2266.12 | 2277.54 | 2288.95 | 2300.37 | 2311.44 | 2323.09 | 2334.73 | 2346.38 | 2357.67 | 2369.55 | 2381.43 | 2393.3 | 2404.82 | 2416.94 | 2429.05 | 2441.17 | 2452.92 | 2465.28 | 2477.64 | 2489.99 | 2501.98 | 2514.58 | 2527.19 | 2539.79 | 2552.02 | 2564.88 | 2577.73 | 2590.59 | 2603.06 | 2616.17 | 2629.29 | 2642.4 | 2655.12 | 2668.5 | 2681.87 | 2695.25 | 2708.22 | 2721.87 | 2735.51 | 2749.15 | 2762.39 | 2776.3 | 2790.22 | 2804.14 | 2817.64 | 2831.83 | 2846.02 | 2860.22 | 2873.99 | 2888.47 | 2902.94 | 2917.42 | 2931.47 | 2946.24 | 2961 | 2975.77 | 2990.1 | 3005.16 | 3020.22 | 3035.29 | 3049.9 | 3065.26 | 3080.63 | 3095.99 | 3110.9 | 3126.57 | 3142.24 | 3157.91 | 3173.11 | 3189.1 | 3205.09 | 3221.07 | 3236.58 | 3252.88 | 3269.19 | 3285.49 | 3301.31 | 3317.94 | 3334.57 | 3351.2 | 3367.33 | 3384.3 | 3401.26 | 3418.23 | 3434.68 | 3451.98 | 3469.29 | 3486.59 | 3503.37 | 3521.02 | 3538.67 | 3556.32 | 3573.44 | 3591.44 | 3609.45 | 3627.45 | 3644.91 | 3663.27 | 3681.64 | 3700 | 3717.81 | 3736.54 | 3755.27 | 3774 | 3792.17 | 3811.27 | 3830.37 | 3849.48 | 3868.01 | 3887.5 | 3906.98 | 3926.47 | 3945.37 | 3965.25 | 3985.12 | 4005 | 4024.28 | 4044.55 | 4064.82 | 4085.1 | 4104.76 | 4125.44 | 4146.12 | 4166.8 | 4186.86 | 4207.95 | 4229.04 | 4250.13 | 4270.59 | 4292.11 | 4313.62 | 4335.14 | 4356.01 | 4377.95 | 4399.9 | 4421.84
|  |  |  | Government Personnel | 1 | 26 | 30 | 26 | Planning Engineering and Design |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.0019 | 1.0038 | 1.0058 | 1.0077 | 1.0146 | 1.0216 | 1.0286 | 1.0355 | 1.0406 | 1.0457 | 1.0508 | 1.0559 | 1.0662 | 1.0765 | 1.0869 | 1.0972 | 1.1078 | 1.1185 | 1.1291 | 1.1397 | 1.1508 | 1.162 | 1.1731 | 1.1842 | 1.1959 | 1.2076 | 1.2192 | 1.2309 | 1.2431 | 1.2553 | 1.2675 | 1.2797 | 1.2925 | 1.3052 | 1.318 | 1.3308 | 1.3441 | 1.3574 | 1.3706 | 1.3839 | 1.3979 | 1.4119 | 1.4259 | 1.44 | 1.4547 | 1.4695 | 1.4842 | 1.499 | 1.5148 | 1.5306 | 1.5464 | 1.5622 | 1.5789 | 1.5955 | 1.6122 | 1.6288 | 1.6467 | 1.6645 | 1.6823 | 1.7001 | 1.7189 | 1.7376 | 1.7564 | 1.7752 | 1.7952 | 1.8153 | 1.8353 | 1.8553 | 1.8767 | 1.8981 | 1.9195 | 1.9409 | 1.9638 | 1.9866 | 2.0094 | 2.0323 | 2.0566 | 2.0809 | 2.1053 | 2.1296 | 2.1556 | 2.1815 | 2.2075 | 2.2334 | 2.261 | 2.2887 | 2.3163 | 2.3439 | 2.3736 | 2.4034 | 2.4331 | 2.4629 | 2.4941 | 2.5254 | 2.5566 | 2.5878 | 2.6207 | 2.6535 | 2.6863 | 2.7192 | 2.7537 | 2.7882 | 2.8227 | 2.8572 | 2.8934 | 2.9297 | 2.9659 | 3.0022 | 3.0402 | 3.0783 | 3.1164 | 3.1545 | 3.1945 | 3.2345 | 3.2746 | 3.3146 | 3.3566 | 3.3987 | 3.4407 | 3.4828 | 3.527 | 3.5712 | 3.6153 | 3.6595 | 3.706 | 3.7524 | 3.7988 | 3.8452 | 3.894 | 3.9428 | 3.9916 | 4.0404 | 4.0916 | 4.1429 | 4.1942 | 4.2454 | 4.2993 | 4.3531 | 4.407 | 4.4609 | 4.5175 | 4.574 | 4.6306 | 4.6872 | 4.7467 | 4.8062 | 4.8656 | 4.9251 | 4.9876 | 5.0501 | 5.1125 | 5.175 | 5.2407 | 5.3063 | 5.372 | 5.4376 | 5.5066 | 5.5756 | 5.6446 | 5.7136 | 5.7861 | 5.8586 | 5.9311 | 6.0035 | 6.0797 | 6.1559 | 6.232 | 6.3082 | 6.3882 | 6.4683 | 6.5483 | 6.6283 | 6.7124 | 6.7965 | 6.8806 | 6.9647 | 7.0531 | 7.1414 | 7.2298 | 7.3181 | 7.411 | 7.5038 | 7.5967 | 7.6895 | 7.7871 | 7.8846 | 7.9822 | 8.0797 | 8.1822 | 8.2847 | 8.3872 | 8.4898 | 8.5975 | 8.7052 | 8.8129 | 8.9206 | 9.0338 | 9.1469 | 9.2601 | 9.3733 | 9.4922 | 9.6111 | 9.73 | 9.8489 | 9.9739 | 10.0989 | 10.2238 | 10.3488 | 10.48 | 10.6113 | 10.7426 | 10.8739 | 11.0119 | 11.1498 | 11.2878 | 11.4257 | 11.5707 | 11.7157 | 11.8606 | 12.0056 | 12.1579 | 12.3102 | 12.4625 | 12.6148 | 12.7749 | 12.9349 | 13.0949 | 13.255 | 13.4231 | 13.5913 | 13.7595 | 13.9276 | 14.1043 | 14.281 | 14.4577 | 14.6344 | 14.8201 | 15.0058 | 15.1914 | 15.3771 | 15.5722 | 15.7673 | 15.9623 | 16.1574 | 16.3624 | 16.5674 | 16.7724 | 16.9774 | 17.1928 | 17.4081 | 17.6235 | 17.8389 | 18.0652 | 18.2916 | 18.5179 | 18.7442 | 18.982 | 19.2198 | 19.4576 | 19.6954 | 19.9453 | 20.1952 | 20.445 | 20.6949 | 20.9574 | 21.22 | 21.4826 | 21.7451 | 22.021 | 22.2969 | 22.5727 | 22.8486 | 23.1385 | 23.4284 | 23.7182 | 24.0081 | 24.3127 | 24.6173 | 24.9219 | 25.2264 | 25.5465 | 25.8665 | 26.1866 | 26.5066 | 26.8429 | 27.1792 | 27.5155 | 27.8518 | 28.2051 | 28.5585 | 28.9118 | 29.2652 | 29.6364 | 30.0077 | 30.379 | 30.7503 | 31.1404 | 31.5305 | 31.9206 | 32.3108 | 32.7207 | 33.1306 | 33.5405 | 33.9504 | 34.3812 | 34.8119 | 35.2426 | 35.6733 | 36.1259 | 36.5785 | 37.0311 | 37.4837 | 37.9592 | 38.4347 | 38.9103 | 39.3858 | 39.8855 | 40.3852 | 40.8849 | 41.3846 | 41.9096 | 42.4346 | 42.9597 | 43.4847 | 44.0364 | 44.5881 | 45.1398 | 45.6914 | 46.2711 | 46.8508 | 47.4305 | 48.0101 | 48.6192 | 49.2283 | 49.8374 | 50.4465 | 51.0865 | 51.7265 | 52.3665 | 53.0065 | 53.679 | 54.3515 | 55.024 | 55.6965 | 56.4031 | 57.1097 | 57.8163 | 58.5229 | 59.2654 | 60.0078 | 60.7503 | 61.4928 | 46.1196 | 30.7464
| Instructions for Feature Codes 30 and 31: In Cells F27 and F28 Enter the Table 1 class that is going to be used for the 30 and 31 accounts either class 1 or class 2. Inflation factors differ if work is to be performed by Government personnel or AE contractor. Class 1 is for government personnel and Class 2 is for everything else. Class 1 includes salary increases, step increases, health insurance, attrition rates, retirement, etc. Note: the Class 1 factor can be higher than the Class 2 factor, when the FEPCA formula is used by OMB to predict future raises, and this will affect the TPCS. In addition, EC11-2-XXX does not provide a historical index as it is only concerned with future projections. |  |  | Government Personnel | 1 | 27 | 31 | 27 | Construction Management |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.0019 | 1.0038 | 1.0058 | 1.0077 | 1.0146 | 1.0216 | 1.0286 | 1.0355 | 1.0406 | 1.0457 | 1.0508 | 1.0559 | 1.0662 | 1.0765 | 1.0869 | 1.0972 | 1.1078 | 1.1185 | 1.1291 | 1.1397 | 1.1508 | 1.162 | 1.1731 | 1.1842 | 1.1959 | 1.2076 | 1.2192 | 1.2309 | 1.2431 | 1.2553 | 1.2675 | 1.2797 | 1.2925 | 1.3052 | 1.318 | 1.3308 | 1.3441 | 1.3574 | 1.3706 | 1.3839 | 1.3979 | 1.4119 | 1.4259 | 1.44 | 1.4547 | 1.4695 | 1.4842 | 1.499 | 1.5148 | 1.5306 | 1.5464 | 1.5622 | 1.5789 | 1.5955 | 1.6122 | 1.6288 | 1.6467 | 1.6645 | 1.6823 | 1.7001 | 1.7189 | 1.7376 | 1.7564 | 1.7752 | 1.7952 | 1.8153 | 1.8353 | 1.8553 | 1.8767 | 1.8981 | 1.9195 | 1.9409 | 1.9638 | 1.9866 | 2.0094 | 2.0323 | 2.0566 | 2.0809 | 2.1053 | 2.1296 | 2.1556 | 2.1815 | 2.2075 | 2.2334 | 2.261 | 2.2887 | 2.3163 | 2.3439 | 2.3736 | 2.4034 | 2.4331 | 2.4629 | 2.4941 | 2.5254 | 2.5566 | 2.5878 | 2.6207 | 2.6535 | 2.6863 | 2.7192 | 2.7537 | 2.7882 | 2.8227 | 2.8572 | 2.8934 | 2.9297 | 2.9659 | 3.0022 | 3.0402 | 3.0783 | 3.1164 | 3.1545 | 3.1945 | 3.2345 | 3.2746 | 3.3146 | 3.3566 | 3.3987 | 3.4407 | 3.4828 | 3.527 | 3.5712 | 3.6153 | 3.6595 | 3.706 | 3.7524 | 3.7988 | 3.8452 | 3.894 | 3.9428 | 3.9916 | 4.0404 | 4.0916 | 4.1429 | 4.1942 | 4.2454 | 4.2993 | 4.3531 | 4.407 | 4.4609 | 4.5175 | 4.574 | 4.6306 | 4.6872 | 4.7467 | 4.8062 | 4.8656 | 4.9251 | 4.9876 | 5.0501 | 5.1125 | 5.175 | 5.2407 | 5.3063 | 5.372 | 5.4376 | 5.5066 | 5.5756 | 5.6446 | 5.7136 | 5.7861 | 5.8586 | 5.9311 | 6.0035 | 6.0797 | 6.1559 | 6.232 | 6.3082 | 6.3882 | 6.4683 | 6.5483 | 6.6283 | 6.7124 | 6.7965 | 6.8806 | 6.9647 | 7.0531 | 7.1414 | 7.2298 | 7.3181 | 7.411 | 7.5038 | 7.5967 | 7.6895 | 7.7871 | 7.8846 | 7.9822 | 8.0797 | 8.1822 | 8.2847 | 8.3872 | 8.4898 | 8.5975 | 8.7052 | 8.8129 | 8.9206 | 9.0338 | 9.1469 | 9.2601 | 9.3733 | 9.4922 | 9.6111 | 9.73 | 9.8489 | 9.9739 | 10.0989 | 10.2238 | 10.3488 | 10.48 | 10.6113 | 10.7426 | 10.8739 | 11.0119 | 11.1498 | 11.2878 | 11.4257 | 11.5707 | 11.7157 | 11.8606 | 12.0056 | 12.1579 | 12.3102 | 12.4625 | 12.6148 | 12.7749 | 12.9349 | 13.0949 | 13.255 | 13.4231 | 13.5913 | 13.7595 | 13.9276 | 14.1043 | 14.281 | 14.4577 | 14.6344 | 14.8201 | 15.0058 | 15.1914 | 15.3771 | 15.5722 | 15.7673 | 15.9623 | 16.1574 | 16.3624 | 16.5674 | 16.7724 | 16.9774 | 17.1928 | 17.4081 | 17.6235 | 17.8389 | 18.0652 | 18.2916 | 18.5179 | 18.7442 | 18.982 | 19.2198 | 19.4576 | 19.6954 | 19.9453 | 20.1952 | 20.445 | 20.6949 | 20.9574 | 21.22 | 21.4826 | 21.7451 | 22.021 | 22.2969 | 22.5727 | 22.8486 | 23.1385 | 23.4284 | 23.7182 | 24.0081 | 24.3127 | 24.6173 | 24.9219 | 25.2264 | 25.5465 | 25.8665 | 26.1866 | 26.5066 | 26.8429 | 27.1792 | 27.5155 | 27.8518 | 28.2051 | 28.5585 | 28.9118 | 29.2652 | 29.6364 | 30.0077 | 30.379 | 30.7503 | 31.1404 | 31.5305 | 31.9206 | 32.3108 | 32.7207 | 33.1306 | 33.5405 | 33.9504 | 34.3812 | 34.8119 | 35.2426 | 35.6733 | 36.1259 | 36.5785 | 37.0311 | 37.4837 | 37.9592 | 38.4347 | 38.9103 | 39.3858 | 39.8855 | 40.3852 | 40.8849 | 41.3846 | 41.9096 | 42.4346 | 42.9597 | 43.4847 | 44.0364 | 44.5881 | 45.1398 | 45.6914 | 46.2711 | 46.8508 | 47.4305 | 48.0101 | 48.6192 | 49.2283 | 49.8374 | 50.4465 | 51.0865 | 51.7265 | 52.3665 | 53.0065 | 53.679 | 54.3515 | 55.024 | 55.6965 | 56.4031 | 57.1097 | 57.8163 | 58.5229 | 59.2654 | 60.0078 | 60.7503 | 61.4928 | 46.1196 | 30.7464
|  |  |  | 1 | Government Personnel |  |  |  | EC 11-2-206 Table 1 Class 1 Factors | 31 March 2014 | FY QTRS 1980Q2: 1; FY QTRS 1981Q2: 1; FY QTRS 1982Q2: 1; FY QTRS 1983Q2: 1; FY QTRS 1984Q2: 1; FY QTRS 1985Q2: 1; FY QTRS 1986Q2: 1; FY QTRS 1987Q2: 1; FY QTRS 1988Q2: 1; FY QTRS 1989Q2: 1; FY QTRS 1990Q2: 1; FY QTRS 1991Q2: 1; FY QTRS 1992Q2: 1; FY QTRS 1993Q2: 1; FY QTRS 1994Q2: 1; FY QTRS 1995Q2: 1; FY QTRS 1996Q2: 1; FY QTRS 1997Q2: 1; FY QTRS 1998Q2: 1; FY QTRS 1999Q2: 1; FY QTRS 2000Q2: 1; FY QTRS 2001Q2: 1; FY QTRS 2002Q2: 1; FY QTRS 2003Q2: 1; FY QTRS 2004Q2: 1; FY QTRS 2005Q2: 1; FY QTRS 2006Q2: 1; FY QTRS 2007Q2: 1; FY QTRS 2008Q2: 1; FY QTRS 2009Q2: 1; FY QTRS 2010Q2: 1; FY QTRS 2011Q2: 1; FY QTRS 2012Q2: 1; FY QTRS 2013Q2: 0.7669%; FY QTRS 2014Q2: 2.765%; FY QTRS 2015Q2: 1.963%; FY QTRS 2016Q2: 3.914%; FY QTRS 2017Q2: 3.875%; FY QTRS 2018Q2: 3.907%; FY QTRS 2019Q2: 3.937%; FY QTRS 2020Q2: 3.966%; FY QTRS 2021Q2: 3.991%; FY QTRS 2022Q2: 3.996%; FY QTRS 2023Q2: 4.048%; FY QTRS 2024Q2: 4.101%; FY QTRS 2025Q2: 4.217%; FY QTRS 2026Q2: 4.265%; FY QTRS 2027Q2: 4.374%; FY QTRS 2028Q2: 4.416%; FY QTRS 2029Q2: 4.517%; FY QTRS 2030Q2: 4.614%; FY QTRS 2031Q2: 4.705%; FY QTRS 2032Q2: 4.791%; FY QTRS 2033Q2: 4.872%; FY QTRS 2034Q2: 4.948%; FY QTRS 2035Q2: 5.075%; FY QTRS 2036Q2: 5.075%; FY QTRS 2037Q2: 5.075%; FY QTRS 2038Q2: 5.075%; FY QTRS 2039Q2: 5.075%; FY QTRS 2040Q2: 5.075%; FY QTRS 2041Q2: 5.075%; FY QTRS 2042Q2: 5.075%; FY QTRS 2043Q2: 5.075%; FY QTRS 2044Q2: 5.075%; FY QTRS 2045Q2: 5.075%; FY QTRS 2046Q2: 5.075%; FY QTRS 2047Q2: 5.075%; FY QTRS 2048Q2: 5.075%; FY QTRS 2049Q2: 5.075%; FY QTRS 2050Q2: 5.075%; FY QTRS 2051Q2: 5.075%; FY QTRS 2052Q2: 5.075%; FY QTRS 2053Q2: 5.075%; FY QTRS 2054Q2: 5.075%; FY QTRS 2055Q2: 5.075%; FY QTRS 2056Q2: 5.075%; FY QTRS 2057Q2: 5.075%; FY QTRS 2058Q2: 5.075%; FY QTRS 2059Q2: 5.075%; FY QTRS 2060Q2: 5.075%; FY QTRS 2061Q2: 5.075%; FY QTRS 2062Q2: 5.075%; FY QTRS 2063Q2: 5.075%; FY QTRS 2064Q2: 5.075%; FY QTRS 2065Q2: 5.075%; FY QTRS 2066Q2: 5.075%; FY QTRS 2067Q2: 5.075%; FY QTRS 2068Q2: 5.075%; FY QTRS 2069Q2: 5.075%; FY QTRS 2070Q2: 5.075%; FY QTRS 2071Q2: 5.075%; FY QTRS 2072Q2: 5.075%; FY QTRS 2073Q2: 5.075%; FY QTRS 2074Q2: 5.075%; FY QTRS 2075Q2: 5.075%; FY QTRS 2076Q2: 5.075%; FY QTRS 2077Q2: 5.075%; FY QTRS 2078Q2: 5.075%; FY QTRS 2079Q2: 5.075%; FY QTRS 2080Q2: 5.075%; FY QTRS 2081Q2: 5.075%; FY QTRS 2082Q2: 5.075%; FY QTRS 2083Q2: 5.075%; FY QTRS 2084Q2: 5.075%; FY QTRS 2085Q2: 5.075%; FY QTRS 2086Q2: 5.075%; FY QTRS 2087Q2: 5.075%; FY QTRS 2088Q2: 5.075%; FY QTRS 2089Q2: 5.075%; FY QTRS 2090Q2: 5.075%; FY QTRS 2091Q2: 5.075%; FY QTRS 2092Q2: 5.075%; FY QTRS 2093Q2: 5.075%; FY QTRS 2094Q2: 5.075%; FY QTRS 2095Q2: 5.075%; FY QTRS 2096Q2: 5.075%; FY QTRS 2097Q2: 5.075%; FY QTRS 2098Q2: 5.075%; FY QTRS 2099Q2: 5.075%; FY QTRS 2100Q2: 5.075%
|  |  |  | 2 | AE Contractor |  |  |  | EC 11-2-206 Table 1 Class 2 Factors | 31 March 2014 | FY QTRS 1980Q2: 1; FY QTRS 1981Q2: 1; FY QTRS 1982Q2: 1; FY QTRS 1983Q2: 1; FY QTRS 1984Q2: 1; FY QTRS 1985Q2: 1; FY QTRS 1986Q2: 1; FY QTRS 1987Q2: 1; FY QTRS 1988Q2: 1; FY QTRS 1989Q2: 1; FY QTRS 1990Q2: 1; FY QTRS 1991Q2: 1; FY QTRS 1992Q2: 1; FY QTRS 1993Q2: 1; FY QTRS 1994Q2: 1; FY QTRS 1995Q2: 1; FY QTRS 1996Q2: 1; FY QTRS 1997Q2: 1; FY QTRS 1998Q2: 1; FY QTRS 1999Q2: 1; FY QTRS 2000Q2: 1; FY QTRS 2001Q2: 1; FY QTRS 2002Q2: 1; FY QTRS 2003Q2: 1; FY QTRS 2004Q2: 1; FY QTRS 2005Q2: 1; FY QTRS 2006Q2: 1; FY QTRS 2007Q2: 1; FY QTRS 2008Q2: 1; FY QTRS 2009Q2: 1; FY QTRS 2010Q2: 1; FY QTRS 2011Q2: 1; FY QTRS 2012Q2: 1; FY QTRS 2013Q2: 1.5%; FY QTRS 2014Q2: 1.5%; FY QTRS 2015Q2: 1.7%; FY QTRS 2016Q2: 1.9%; FY QTRS 2017Q2: 2%; FY QTRS 2018Q2: 2%; FY QTRS 2019Q2: 2%; FY QTRS 2020Q2: 2%; FY QTRS 2021Q2: 2%; FY QTRS 2022Q2: 2%; FY QTRS 2023Q2: 2%; FY QTRS 2024Q2: 2%; FY QTRS 2025Q2: 2%; FY QTRS 2026Q2: 2%; FY QTRS 2027Q2: 2%; FY QTRS 2028Q2: 2%; FY QTRS 2029Q2: 2%; FY QTRS 2030Q2: 2%; FY QTRS 2031Q2: 2%; FY QTRS 2032Q2: 2%; FY QTRS 2033Q2: 2%; FY QTRS 2034Q2: 2%; FY QTRS 2035Q2: 2%; FY QTRS 2036Q2: 2%; FY QTRS 2037Q2: 2%; FY QTRS 2038Q2: 2%; FY QTRS 2039Q2: 2%; FY QTRS 2040Q2: 2%; FY QTRS 2041Q2: 2%; FY QTRS 2042Q2: 2%; FY QTRS 2043Q2: 2%; FY QTRS 2044Q2: 2%; FY QTRS 2045Q2: 2%; FY QTRS 2046Q2: 2%; FY QTRS 2047Q2: 2%; FY QTRS 2048Q2: 2%; FY QTRS 2049Q2: 2%; FY QTRS 2050Q2: 2%; FY QTRS 2051Q2: 2%; FY QTRS 2052Q2: 2%; FY QTRS 2053Q2: 2%; FY QTRS 2054Q2: 2%; FY QTRS 2055Q2: 2%; FY QTRS 2056Q2: 2%; FY QTRS 2057Q2: 2%; FY QTRS 2058Q2: 2%; FY QTRS 2059Q2: 2%; FY QTRS 2060Q2: 2%; FY QTRS 2061Q2: 2%; FY QTRS 2062Q2: 2%; FY QTRS 2063Q2: 2%; FY QTRS 2064Q2: 2%; FY QTRS 2065Q2: 2%; FY QTRS 2066Q2: 2%; FY QTRS 2067Q2: 2%; FY QTRS 2068Q2: 2%; FY QTRS 2069Q2: 2%; FY QTRS 2070Q2: 2%; FY QTRS 2071Q2: 2%; FY QTRS 2072Q2: 2%; FY QTRS 2073Q2: 2%; FY QTRS 2074Q2: 2%; FY QTRS 2075Q2: 2%; FY QTRS 2076Q2: 2%; FY QTRS 2077Q2: 2%; FY QTRS 2078Q2: 2%; FY QTRS 2079Q2: 2%; FY QTRS 2080Q2: 2%; FY QTRS 2081Q2: 2%; FY QTRS 2082Q2: 2%; FY QTRS 2083Q2: 2%; FY QTRS 2084Q2: 2%; FY QTRS 2085Q2: 2%; FY QTRS 2086Q2: 2%; FY QTRS 2087Q2: 2%; FY QTRS 2088Q2: 2%; FY QTRS 2089Q2: 2%; FY QTRS 2090Q2: 2%; FY QTRS 2091Q2: 2%; FY QTRS 2092Q2: 2%; FY QTRS 2093Q2: 2%; FY QTRS 2094Q2: 2%; FY QTRS 2095Q2: 2%; FY QTRS 2096Q2: 2%; FY QTRS 2097Q2: 2%; FY QTRS 2098Q2: 2%; FY QTRS 2099Q2: 2%; FY QTRS 2100Q2: 2%
[109 empty] | 1 | 1.0334 | 1.0438 | 1.0542 | 1.0647 | 1.0754 | 1.0862 | 1.097 | 1.108 | 1.1191 |  |  |  | 1.167 |  |  |  | 1.219 |  |  |  | 1.273 |  |  |  | 1.331 |  |  |  | 1.391 |  |  |  | 1.453 |  |  |  | 1.519 |  |  |  | 1.588 |  |  |  | 1.662 |  |  |  | 1.739 |  |  |  | 1.821 |  |  |  | 1.907 |  |  |  | 1.998 |  |  |  | 2.094 |  |  |  | 2.196 |  |  |  | 2.281 |  |  |  | 2.361 |  |  |  | 2.443 |  |  |  | 2.529 |  |  |  | 2.617
[136 empty] | 1.0428 | [55 empty] | 1.0487 |  |  |  | 1.0387 |  |  |  | 1.0351 |  |  |  | 1.0347 |  |  |  | 1.0352 |  |  |  | 1.0348
Note on J30: Table 1 Factors are yearly factors for inflating costs to future values and do not include historical rates. Rates will be shown in the first calendar year quarter. Values will be changed to 1.00 for quarters where CWCCIS has a historical basis.
Note on HY30: Due to comments received from the field on compounded rates exponential growth in the PY+50 timeframe several methods were researched:, extending all of the EC11-2-XXX table 1 formulas out to 2099, Using the formula found in EC11-2-XXX notes to extend the future projections and using the last (2034) rate for all future projections. Because all of the methods with the exception of the last resulted in runaway exponential growth due to the magic of compounding the last table 1 factor is used for projected forcasting.
Note on J31: Table 1 Factors are yearly factors for inflating costs to future values and do not include historical rates. Rates will be shown in the first calendar year quarter. Values will be changed to 1.00 for quarters where CWCCIS has a historical basis.
Note on HY31: Due to comments received from the field on compounded rates exponential growth in the PY+50 timeframe several methods were researched:, extending all of the EC11-2-XXX table 1 formulas out to 2099, Using the formula found in EC11-2-XXX notes to extend the future projections and using the last (2034) rate for all future projections. Because all of the methods with the exception of the last resulted in runaway exponential growth due to the magic of compounding the last table 1 factor is used for projected forcasting.