PDT Risk Checklist

Provided here is a checklist of risk items for consideration when performing a risk analysis.  Consideration of all feature accounts is critically important as presented within the civil works breakdown structure.

| FEATURE CODE | DESCRIPTION |
| --- | --- |
| 01 | Lands and Damages |
| 02 | Relocations |
| 03 | Reservoirs |
| 04 | Dams |
| 05 | Locks |
| 06 | Fish and Wildlife Facilities |
| 07 | Power Plant |
| 08 | Roads, Railroads, and Bridges |
| 09 | Channels and Canals |
| 10 | Breakwaters and Seawalls |
| 11 | Levees and Floodwalls |
| 12 | Navigation Ports & Harbors |
| 13 | Pumping Plants |
| 14 | Recreation Facilities |
| 15 | Floodway Control-Diversion Structure |
| 16 | Bank Stabilization |
| 17 | Beach Replenishment |
| 18 | Cultural Resource Preservation |
| 19 | Buildings, Grounds, & Utilities |
| 20 | Permanent Operation Equipment |
| 30 | Planning, Engineering and Design |
| 31 | Construction Management |

1.	Engineering and Construction Management Risk Document Checklist.

Risk management reports vary depending on the size, nature, and phase of the project. The following are examples of risk management documents and reports that may be useful:

- Risk management plan

- Risk information form

- Risk assessment report

- Risk handling priority list

- Risk handling plan of action

- Aggregated risk list

- Risk monitoring documentation:

- Project metrics

- Technical reports

- Earned value reports

- Watch list

- Schedule performance report

- Critical risk processes reports

2.  The following items are a composite of several checklists from various agencies.  They have been tailored to better address the more common USACE civil works project risks.  The list, though not all encompassing provides a valuable tool, meant to serve as an aid in PDT discussions of potential risk items for a specific project.

Organizational and Project Management Risks

- Project purpose and objectives are poorly defined

- Project scope definition is poor or incomplete

- Project schedule in question

- No control over staff priorities

- Project competing with other projects, funding and resources

- Functional and Technical labor units not available or overloaded

- Losing critical staff at crucial point of the project

- Inexperienced or inadequate staff assigned

- Product development by several sources or entities (virtual or remote efforts)

- Coordination/communication difficulties

- Communication breakdown with project team

- Insufficient time to plan

- Timely response to critical decisions by PM and/or management

- A/E/C Consultant or contractor delays

- Pressure to deliver project on an accelerated schedule

- Unanticipated project manager workload

- Internal red tape causes delay getting approvals, decisions

- Unplanned work that must be accommodated

- Local agency/regulator issues

- Priorities change on existing program

Contract Acquisition Risks

- Undefined acquisition strategy

- Lack of acquisition planning support/involvement

- Preference to SDB and 8(a) contracts

- Acquisition planning to accommodate funding stream or anticipated strategy

- Numerous separate contracts

- Acquisition strategy decreasing competition

- Acquisition strategy results in higher scope risk (Design Build)

Technical Risks

- Design development stage, incomplete or preliminary

- Confidence in scope, investigations, design, critical quantities

Geotechnical

Civil

Structural

Mechanical

Electrical

Architectural

Environmental

Controls

Other Specialized Disciplines

- Design confidence in products by others

- Consultant design not up to department standards

- Inaccurate or risky design assumptions on technical issues

- Innovative designs, highly complex, first of a kind, or prototypes

- Incomplete studies (geotech, hydrology and hydraulic, structural, HTRW, etc)

- Surveys late and/or surveys in question

- Sufficiency / availability of as-built data / base map data

- Borrow/fill sources identified / secured

- Sufficiency/condition of borrow / fill sites

- Right-of-way analysis in question

- Lacking critical subsurface information for under-water / in-water work

- Hazardous waste concerns

- Need for design exceptions or waivers

- Adaptive Management features (<3% of construction cost, excluding monitoring)

- Dredge Estimate scope, quantities, equipment

Correct dredge equipment decisions (type, size, number)

Reasonable productivity (seasonal, environmental, weather)

Consideration for adequate pumping for long pipeline runs

Adequate disposal facilities in size and number

Lands and Damages

- Real Estate plan defined

- Status of real estate / easement acquisition

- Objections to right-of-way appraisal take more time and/or money

- Ancillary owner rights, ownerships in question

- Freeway agreements

- Railroad involvement

- Relocations identified

- Records / as-built availability / inaccuracies

- Known and unknown utility impacts

- Relocations may not happen in time

- Environmental mitigation needs identified

- Vagrancy, loitering issues

- Quality of L&D estimates as “most likely” case

- Hidden estimate/schedule contingencies

Regulatory and Environmental Risks

- Established requirements for initial project studies and potential impacts

- Environmental and Water quality issues

- Adaptive Management features (<3% of construction cost, excluding monitoring)

- Conforming to the State implementation plan for air quality

- Historic/Cultural site, endangered species, or wetlands present

- Project in an area of high sensitivity for paleontology

- Project in an area of high sensitivity for cultural artifacts

- Numerous exclusion zones in project area / vicinity

- Hazardous waste preliminary site investigation required

- Status of critical environmental and regulatory studies

- Status of permits

- Lack of specialized staff (biology, anthropology, archeology, etc.)

- Reviewing agency requires higher-level review than assumed

- Permits or agency actions delayed or take longer than expected

- Reviewing agency requires higher-level review than assumed

- Potential for critical regulation changes

- New permits or new information required

- Project in the Coastal Zone

- Project on a Scenic Highway, state or national park

- Hazardous wildlife attractants on or near airports (FAA involvement)

- Negative community impacts expected

- Pressure to compress the study and permitting activities

Construction Risks

- Accelerated contract schedule

- Inefficient contractor

- Subcontractor capabilities

- Conflicts with other contracts

- Innovative project construction

- Timely delivery of critical GFE

- Permits, licenses, submittal approvals

- Permit and environmental work windows

- Environmental restrictions (equipment use, exhaust, paint fumes)

- Site access / restrictions (highways, bridges, dams, water, overhead / underground utilities)

- Adequate staging areas

- Rural / remote locale

- Inadequate skilled trades available for labor force

- Inadequate housing/utilities to support labor force

- Special equipment and equipment availability

- Material availability and delivery

- Productivity of critical work items

- Critical fabrication and delivery

- Unknown utilities

- Survey information

- Limited transportation / haul routes available

- Transportation / haul routes constricted or unusable during periods of time

- Unusual transportation haul distances

- Regulatory / operational work windows or outage periods

- Restricted schedule, accelerated schedule impacts

- In-water work

- Control and diversion of water

- Differing site conditions

- Unidentified hazardous waste

- Historic change order or modification growth

- Consideration for standard weather impact

- Adequacy of construction schedule depicting durations, sequencing, phasing, production rates

Estimate and Schedule Risks

- Estimate captures scope for all project features

- Estimate developed for current scope and design level

- Estimates developed in MCACES MII and/or CEDEP

- Estimate quality related to lesser designed features

- Estimate excludes contingency and escalation

- Estimate(s) quality when developed by others

- Estimate confidence in large and critical quantities

- Estimate include waste / drop off quantities

- Estimate reflects local market for labor and subsistence

- Estimate reasonableness of crews and productivities

- Estimate reflects local material costs and delivery

- Parametric estimates for unit prices adequate for critical items

- Consideration and local quotes for special equipment (cranes, barges, tugs, diving)

- Prime and subcontractor structure matches likely acquisition strategy

- Adequate schedule depicting all project features

- Schedule matches PED plan

- Schedule portrays critical construction features, matching estimate productivity

- Schedule depicts logical construction sequencing, phasing and parallel activities

- Estimate and schedule reflecting “most likely” occurrence

- Overall confidence in estimate and schedule

External Risks

- Adequacy of project funding (incremental or full funding)

- Priorities change on existing program

- Local communities pose objections

- Loss of public trust / goodwill

- Political factors change at local, state or federal

- Stakeholders request late changes

- New stakeholders emerge and demand new work

- Influential stakeholders request additional needs to serve other purposes

- Political opposition / threat of lawsuits

- Stakeholders choose time and / or cost over quality

- Market conditions and bidding competition

- Unexpected escalation on key materials

- Labor disruptions

- Acts of God (seismic events: volcanic activity, earthquakes, tsunamis; or severe weather: freezing, flooding or hurricane)