## Input
***COMPLETE THE BLUE FONT***
|  |  |  | DISTRICT | XXXXXX
|  |  |  | PROJECT NAME | XXXXXX
|  |  |  | PROJECT NO. | XXXXXX
|  |  |  | PROJECT LOCATION | XXXXXX
|  |  |  | PROGRAM YEAR | 2024 | 2024Q1
|  |  |  | DATE TPCS PREPARED | 2021-10-01 |  | Updated
|  |  |  | ENGINEERING REPORT AS BASIS | Report Name and date
|  |  |  | ENGINEERING & DESIGN PHASE -> 30 ACCOUNT |  |  |  |  | % of Construct | Districts % Vary | 30/31 Accounts
|  |  |  | PROJECT MANAGER, XXX |  |  |  | Program Management: | 2.5% | 2.5% | 30 | 29.5% | Sum per % of 30 Account
|  |  |  | CHIEF, DPM, XXX | [6 empty] | 30
|  |  |  | CHIEF, PLANNING, XXX |  |  |  | Planning & Environmental Compliance: | 1% | 1% | 30
|  |  |  | CHIEF, ENGINEERING, XXX |  |  |  | Engineering & Design: | 15% | 15% | 30
|  |  |  | CHIEF, COST ENGINEERING, XXX |  |  |  | Reviews, ATRs, IEPRs, VE: | 1% | 1% | 30
|  |  |  | CHIEF, ENGINEERING, XXX |  |  |  | Life Cycle Updates (cost, schedule, risks): | 1% | 1% | 30
|  |  |  | CHIEF, CONTRACTING, XXX |  |  |  | Contracting & Reprographics: | 1% | 1% | 30
|  |  |  | CHIEF, ENGINEERING, XXX |  |  |  | Engineering During Construction: | 3% | 3% | 30 |  |  | Escalate to Mid Point Construction
|  |  |  | CHIEF, PLANNING, XXX |  |  |  | Planning During Construction | 2% | 2% | 30
|  |  |  | CHIEF, OPERATIONS, XXX |  |  |  | Adaptive Mgmt & Monitoring: | 1% | 3% | 30
[8 empty] | Project Operations | 1% | 1% | 31
CONSTRUCTION PHASE -> 31 ACCOUNT
|  |  |  | CHIEF, CONSTRUCTION, XXX |  |  |  | Supervision & Assurance: | 10% | 10% | 31 | 14.5% | Sum per % of 31 Account
|  |  |  | CHIEF, OPERATIONS, XXX |  |  |  | Project Operation: | 2% | 2% | 30
|  |  |  | CHIEF, DPM, XXX |  |  |  | Program Management: | 2.5% | 2.5% | 31
[12 empty] | 44% | Sum per % of 30 & 31 Accounts
REAL ESTATE -> 01 ACCOUNT
CHIEF, REAL ESTATE, XXX
CULTURAL RESOURCES -> 18 ACCOUNT
CHIEF, PLANNING, XXX
SPENT THRU FYXX COSTS
CHIEF, PM-PB, xxxx
1980-10-01 | 1981 | 1981Q1 | 29495
1981-10-01 | 1982 | 1982Q1 | 29860
1982-10-01 | 1983 | 1983Q1 | 30225
1983-10-01 | 1984 | 1984Q1 | 30590
1984-10-01 | 1985 | 1985Q1 | 30956
1985-10-01 | 1986 | 1986Q1 | 31321
1986-10-01 | 1987 | 1987Q1 | 31686
1987-10-01 | 1988 | 1988Q1 | 32051
1988-10-01 | 1989 | 1989Q1 | 32417
1989-10-01 | 1990 | 1990Q1 | 32782
1990-10-01 | 1991 | 1991Q1 | 33147
1991-10-01 | 1992 | 1992Q1 | 33512
1992-10-01 | 1993 | 1993Q1 | 33878
1993-10-01 | 1994 | 1994Q1 | 34243
1994-10-01 | 1995 | 1995Q1 | 34608
1995-10-01 | 1996 | 1996Q1 | 34973
1996-10-01 | 1997 | 1997Q1 | 35339
1997-10-01 | 1998 | 1998Q1 | 35704
1998-10-01 | 1999 | 1999Q1 | 36069
1999-10-01 | 2000 | 2000Q1 | 36434
2000-10-01 | 2001 | 2001Q1 | 36800
2001-10-01 | 2002 | 2002Q1 | 37165
2002-10-01 | 2003 | 2003Q1 | 37530
2003-10-01 | 2004 | 2004Q1 | 37895
2004-10-01 | 2005 | 2005Q1 | 38261
2005-10-01 | 2006 | 2006Q1 | 38626
2006-10-01 | 2007 | 2007Q1 | 38991
2007-10-01 | 2008 | 2008Q1 | 39356
2008-10-01 | 2009 | 2009Q1 | 39722
2009-10-01 | 2010 | 2010Q1 | 40087
2010-10-01 | 2011 | 2011Q1 | 40452
2011-10-01 | 2012 | 2012Q1 | 40817
2012-10-01 | 2013 | 2013Q1 | 41183
2013-10-01 | 2014 | 2014Q1 | 41548
2014-10-01 | 2015 | 2015Q1 | 41913
2015-10-01 | 2016 | 2016Q1 | 42278
2016-10-01 | 2017 | 2017Q1 | 42644
2017-10-01 | 2018 | 2018Q1 | 43009
2018-10-01 | 2019 | 2019Q1 | 43374
2019-10-01 | 2020 | 2020Q1 | 43739
2020-10-01 | 2021 | 2021Q1 | 44105
2021-10-01 | 2022 | 2022Q1 | 44470
2022-10-01 | 2023 | 2023Q1 | 44835
2023-10-01 | 2024 | 2024Q1 | 45200
2024-10-01 | 2025 | 2025Q1 | 45566
2025-10-01 | 2026 | 2026Q1 | 45931
2026-10-01 | 2027 | 2027Q1 | 46296
2027-10-01 | 2028 | 2028Q1 | 46661
2028-10-01 | 2029 | 2029Q1 | 47027
2029-10-01 | 2030 | 2030Q1 | 47392
2030-10-01 | 2031 | 2031Q1 | 47757
2031-10-01 | 2032 | 2032Q1 | 48122
2032-10-01 | 2033 | 2033Q1 | 48488
2033-10-01 | 2034 | 2034Q1 | 48853
2034-10-01 | 2035 | 2035Q1 | 49218
2035-10-01 | 2036 | 2036Q1 | 49583
2036-10-01 | 2037 | 2037Q1 | 49949
2037-10-01 | 2038 | 2038Q1 | 50314
2038-10-01 | 2039 | 2039Q1 | 50679
2039-10-01 | 2040 | 2040Q1 | 51044
2040-10-01 | 2041 | 2041Q1 | 51410
2041-10-01 | 2042 | 2042Q1 | 51775
2042-10-01 | 2043 | 2043Q1 | 52140
2043-10-01 | 2044 | 2044Q1 | 52505
2044-10-01 | 2045 | 2045Q1 | 52871
2045-10-01 | 2046 | 2046Q1 | 53236
2046-10-01 | 2047 | 2047Q1 | 53601
2047-10-01 | 2048 | 2048Q1 | 53966
2048-10-01 | 2049 | 2049Q1 | 54332
2049-10-01 | 2050 | 2050Q1 | 54697
2050-10-01 | 2051 | 2051Q1 | 55062
2051-10-01 | 2052 | 2052Q1 | 55427
2052-10-01 | 2053 | 2053Q1 | 55793
2053-10-01 | 2054 | 2054Q1 | 56158
2054-10-01 | 2055 | 2055Q1 | 56523
2055-10-01 | 2056 | 2056Q1 | 56888
2056-10-01 | 2057 | 2057Q1 | 57254
2057-10-01 | 2058 | 2058Q1 | 57619
2058-10-01 | 2059 | 2059Q1 | 57984
2059-10-01 | 2060 | 2060Q1 | 58349
2060-10-01 | 2061 | 2061Q1 | 58715
2061-10-01 | 2062 | 2062Q1 | 59080
2062-10-01 | 2063 | 2063Q1 | 59445
2063-10-01 | 2064 | 2064Q1 | 59810
2064-10-01 | 2065 | 2065Q1 | 60176
2065-10-01 | 2066 | 2066Q1 | 60541
2066-10-01 | 2067 | 2067Q1 | 60906
2067-10-01 | 2068 | 2068Q1 | 61271
2068-10-01 | 2069 | 2069Q1 | 61637
2069-10-01 | 2070 | 2070Q1 | 62002
2070-10-01 | 2071 | 2071Q1 | 62367
2071-10-01 | 2072 | 2072Q1 | 62732
2072-10-01 | 2073 | 2073Q1 | 63098
2073-10-01 | 2074 | 2074Q1 | 63463
2074-10-01 | 2075 | 2075Q1 | 63828
2075-10-01 | 2076 | 2076Q1 | 64193
2076-10-01 | 2077 | 2077Q1 | 64559
2077-10-01 | 2078 | 2078Q1 | 64924
2078-10-01 | 2079 | 2079Q1 | 65289
2079-10-01 | 2080 | 2080Q1 | 65654
2080-10-01 | 2081 | 2081Q1 | 66020
2081-10-01 | 2082 | 2082Q1 | 66385
2082-10-01 | 2083 | 2083Q1 | 66750
2083-10-01 | 2084 | 2084Q1 | 67115
2084-10-01 | 2085 | 2085Q1 | 67481
2085-10-01 | 2086 | 2086Q1 | 67846
2086-10-01 | 2087 | 2087Q1 | 68211
2087-10-01 | 2088 | 2088Q1 | 68576
2088-10-01 | 2089 | 2089Q1 | 68942
2089-10-01 | 2090 | 2090Q1 | 69307
2090-10-01 | 2091 | 2091Q1 | 69672
2091-10-01 | 2092 | 2092Q1 | 70037
2092-10-01 | 2093 | 2093Q1 | 70403
2093-10-01 | 2094 | 2094Q1 | 70768
2094-10-01 | 2095 | 2095Q1 | 71133
2095-10-01 | 2096 | 2096Q1 | 71498
2096-10-01 | 2097 | 2097Q1 | 71864
2097-10-01 | 2098 | 2098Q1 | 72229
2098-10-01 | 2099 | 2099Q1 | 72594
2099-10-01 | 2100 | 2100Q1 | 72959
2100-10-01 | 2101 | 2101Q1 | 73324
Total Project Cost (TPCS) BASICS:
A completed TPCS will show the overall project cost by feature account of a project and an estimate of the total cost to complete the project(fully funded estimate). It is essentially a summary of a programs cost by summing each construction contract by WBS feature and its estimated lands damages and associated administrative costs. These costs are escalated to the midpoint of construction and summed to give a fully funded cost.
Things you need to complete a TPCS:
Projected budget year planned to obtain funding to support the project development and construction.
Effective price level date of estimate.
Estimate of construction costs for the appropriate work breakdown structure.
Estimates for other accounts (lands, damages, real estate, relocations, etc)
Midpoint of construction schedule.
Midpoint of design schedule.
Midpoint of Lands and Damages, Relocations...
30/31 accounts estimates or they may be calculated based on rule of thumb percentages (default on the spreadsheet).
Risk Based contingencies.
Current CWCCIS table (updated 2x per year, Mar and Sep) Downloadable from NWW’s web site.
Other data that may be nice to know: ( you will need this for the 902 limit)
Authorization legislation and date.
Baseline estimate (estimate presented to Congress for authorization) Most likely in a report by the Chief of Engineers. You need this for the Work Breakdown Structure (WBS) to track changes in the project.
Amount actually authorized by Congress.
Contracts awarded, contracts ongoing and the respective WBS code and amount (contingencies on completed work and ongoing construction are less than future construction work)
Total of expenditures by WBS feature and year.
Total project cost spreadsheet sums the account costs for a project/program based on the estimate data entered and will calculate the 30/31 accounts based on the percentages input into the data sheet.( For the 30/31 accounts the spreadsheet default is to use the rule of thumb percentages from the data sheet. These may be changed accordingly either thru changing the percentages in the data sheet or may be adjusted for each item individually. (The Excel goal seeking function may be useful))
Things to remember:
- Estimates should be less than two years old (ER 1110-2-1302).
- Make sure you are using the latest CWCCIS table/numbers for your TPCS!
- Check that the costs are reasonable for where you are at in the stage of the project! I.e.- If you have already completed the bid package for a contract and have it on the shelf you most likely have expended most of the design cost. Therefore the rule of thumb 30/31 account percentages and amounts may be too high.
How it works:
Each estimate for the project/program is entered on a separate page of the TPCS The estimate value (from MCACES)is entered in the left column of the page. Contingency is entered and the sum of the estimate and the total is calculated. Based on the date of the price level of the estimate, inflation is applied to bring the cost to the desired program year (middle column). From here the construction estimate is inflated to the midpoint of construction.
All of the estimates sum up to the top sheet (summary-its the one with the signature blocks on it). It is important to remember to check that the sheets sum correctly by WBS structure. Don’t mix accounts!
Fully Funded Contracts that have had funds obligated but not expended usually are entered at fully funded award price with 10% contingency. In general they are assumed to be at program year price level.
For a non fully funded contract that have been awarded escalation to the midpoint may be required. For this situation, make sure that you have an accurate total of estimated costs.
TPCS Sheet. Generally Obligations should be entered as an estimate and expenditures should be totaled and put in the spent thru column on the summary page. The key is to exclude contingency and escalation on spent funds.
GENERAL INSTRUCTIONS:
This worksheet is setup to include a summary sheet and four (4) separate contracts with one Construction WBS code. If more "Contract" sheets are added, or you need to have multiple Construction WBS codes then:
1- Fill out project data- this will populate the signatory blocks, program year, preparation date, etc.
2 - Change the "Sum" in reference column 3 to sum correctly to the sheets below,
3- Copy the revised formulas in column 3 to columns 4, 9 & 10, 15 & 16
4 - Use row "X" to check the summation of the spreadsheet.
5 - Select the appropriate Quarter for each item. Indexes & Time Period dates will come automatically. Check Time Periods.
6 Select Feature WBS. Feature description will come in automatically.
7- Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13 on the summary page
%'s are based on construction dollars amounts.
Accept default distribution of 30 and 31 accounts
or
Enter your preferred percentages
or
Use Goal Seek on each individual line within the TPCS spreadsheet to make the estimate match a 564
Enter responsible parties and percentages desired for 30/31 Accounts, this will populate the TPCS sheet dates and signatory block. Program Year sets the date for escalation calculations.

## TPCS
Column to check for math errors ( Adds up three ways.)
[6 empty] | Reference Columns: |  | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | Numbers show up three times
[8 empty] | 1: PROJECT:; 2: XXXXXX; 13: DISTRICT:; 14: XXXXXX |  |  | PREPARED: | 2021-10-01
[9 empty] | PROJECT NO: | XXXXXX
[9 empty] | LOCATION: | XXXXXX | [10 empty] | POC: | CHIEF, COST ENGINEERING, XXX
[9 empty] | This Estimate reflects the scope and schedule in report; |  | Report Name and date
[8 empty] | 1: Civil Works Work Breakdown Structure; 3: ESTIMATED COST; 8: PROJECT FIRST COST (Constant Dollar Basis) |  | TOTAL PROJECT COST (FULLY FUNDED)
[19 empty] | Program Year (Budget EC): |  | 2024
[19 empty] | Effective Price Level Date: |  | 1-Oct- 23
[19 empty] | REMAINING COST |  | Spent Thru: | TOTAL FIRST COST
[9 empty] | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG |  |  | 2015-10-01 |  | ESC | COST | CNTG | FULL
[9 empty] | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | ($K) | ($K) | (%) | ($K) | ($K) | ($K)
[7 empty] | Pull Down Menus for your Feature Accounts => |  | 02 | RELOCATIONS | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[7 empty] | Pull Down Menus for your Feature Accounts => |  | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[7 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[7 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
Pull Down Menus for your Feature Accounts =>
[24 empty] | _ | _ | _ | bar: 3 to 4; 6; 9 to 11; 13 to 14
[10 empty] | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 |  | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0 |  | 0 |  | Estimate Check
Program yr check
[9 empty] | 01 | LANDS AND DAMAGES | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  |  | 0 | - | 0 | 0 | 0 |  |  |  | FF Check | 0
[6 empty] | PED % of Construction Contract | #DIV/0! |  | 30 | PLANNING, ENGINEERING & DESIGN | 0 | 0 | 0% | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
COLUMN TO CHECK SPREAD SHEET
[6 empty] | % CM of Construction Contract | #DIV/0! |  | 31 | CONSTRUCTION MANAGEMENT | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  |  | 0 | - | 0 | 0 | 0
[24 empty] | _ | _ | _ | bar: 3 to 4; 6; 9 to 11; 13 to 14
[10 empty] | PROJECT COST TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0 |  | 0 | 0
[8 empty] | 3: CHIEF, COST ENGINEERING, XXX | [5 empty] | 0 | DIFFERENCE
[24 empty] | ESTIMATED TOTAL PROJECT COST: |  | 0 |  | 0 | CHECK COST
[8 empty] | 3: PROJECT MANAGER, XXX |  | ESTIMATED FEDERAL COST: | 65% | 0 |  | ======
[24 empty] | ESTIMATED NON-FEDERAL COST: | 35% | 0 |  | 0 | COMPLETED COST
[8 empty] | 3: CHIEF, REAL ESTATE, XXX | [6 empty] | COST NOT IN BELOW SHEET
[24 empty] | 22 - FEASIBILITY STUDY (CAP studies): |  | 2
[8 empty] | 3: CHIEF, PLANNING, XXX |  | ESTIMATED FEDERAL COST: | 50% | 1
[24 empty] | ESTIMATED NON-FEDERAL COST: | 50% | 1 |  |  | SUMMED COST IN BELOW SHEETS
[8 empty] | 3: CHIEF, ENGINEERING, XXX | [5 empty] | 0 | FUTURE COST |  | 0
[24 empty] | ESTIMATED FEDERAL COST OF PROJECT |  | 1
CHIEF, OPERATIONS, XXX
CHIEF, CONSTRUCTION, XXX
CHIEF, CONTRACTING, XXX
CHIEF, PM-PB, xxxx
CHIEF, DPM, XXX
| Pg Brk |  | 1 |  |  |  |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: XXXXXX; 11: DISTRICT:; 13: XXXXXX |  |  | PREPARED: | 2021-10-01
[8 empty] | 4 | LOCATION: | XXXXXX | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, XXX
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Report Name and date
| CWCCIS |  | Schedule | Time Period |  |  |  | 1: 6
[8 empty] | 7 | WBS Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
Estimate PL INDEX | Prog Year Index | MidPoint Index | Quarter | Check | CWCCIS CAT USED |  |  | 1: 8; 3: Estimate Prepared:; 6: 2016-05-06; 8: Program Year (Budget EC):; 11: 2024
[8 empty] | 9 |  |  | Estimate Price Level: |  |  | 2023-10-01 |  | Effective Price Level Date: |  |  | 1 -Oct-23
[8 empty] | 10 |  |  |  |  | RISK BASED
|  |  | 2024Q1 | 2023(Oct - Dec) |  | Price level date of M2 Estimate |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | ESC |  | COST | CNTG | FULL
|  |  | 2024Q1 |  |  | Program Year Price Level from INPUT |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 1 or CONTRACT 1
1166.71 | 1166.71 | 1166.71 | 2024Q1 | 2023(Oct - Dec) | 02 | Midpoint 02 |  | 15 | 02 | RELOCATIONS | 0 | 0 | 25% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 1144.9 | 1144.9 | 2024Q1 | 2023(Oct - Dec) | 06 | Midpoint 06 |  | 16 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 25% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
#N/A | #N/A | #N/A | 2024Q1 | 2023(Oct - Dec) | 0 | Midpoint |  | 17 |  |  | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
#N/A | #N/A | #N/A | 2024Q1 | 2023(Oct - Dec) | 0 | Midpoint |  | 18 |  |  | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
#N/A | #N/A | #N/A | 2024Q1 | 2023(Oct - Dec) | 0 | Midpoint |  | 19 |  |  | 0 | 0 |  | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 20 | [8 empty] | 0
[8 empty] | 21 |  |  | _ | _ | _ | _ |  |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 1149.32 | 1149.32 | 2024Q1 | 2023(Oct - Dec) | All | Lands And Damages Midpoint |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 25% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[6 empty] | (This uses the CWCCIS Composite Index escalation factor.) |  | 1: 25; 8: 0%
26
[8 empty] | 27 | 30 | PLANNING, ENGINEERING & DESIGN | [5 empty] | 0% | [5 empty] | 0%
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | Design mid point period |  | 28 | 2.5% | Project Management | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Design mid point period |  | 29 | 1% | Planning & Environmental Compliance | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Design mid point period |  | 30 | 15% | Engineering & Design | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Design mid point period |  | 31 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Design mid point period |  | 32 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Aggregate Construction Midpoint |  | 33 | 1% | Contracting & Reprographics | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Aggregate Construction Midpoint |  | 34 | 3% | Engineering During Construction | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Design mid point period |  | 35 | 2% | Planning During Construction | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Adaptive Management & Monitoring Midpoint |  |  | 3% | Adaptive Management & Monitoring | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From Post-Monitoring Midpoint |  |  | 1% | Project Operations | 0 | 0 | 7.95% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 30 | From WBS Account 01 Midpoint |  |  |  | Real Estate (All Federal Labor) |  | 0 | 25% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[7 empty] | 0 | 1: 36; 3: 0; 8: 0%; 9: 0; 10: 0; 14: 0% |  | 0 | 0
[8 empty] | 1: 37; 1: 31; 2: CONSTRUCTION MANAGEMENT; 8: 0%; 9: 0; 10: 0; 14: 0% |  | 0 | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 31 | AGGREGATE CONSTRUCTION MIDPOINT |  | 38 | 10% | Construction Management | 0 | 0 | 14% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 31 | From Aggregate Construction Midpoint |  | 39 | 2% | Project Operation: | 0 | 0 | 14% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0949 | 1.0949 | 1.0949 | 2024Q1 | 2023(Oct - Dec) | 31 | From Aggregate Construction Midpoint |  | 40 | 2.5% | Project Management | 0 | 0 | 14% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
41
[8 empty] | 1: 42; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 43 | [5 empty] | 0
Note on D67: MPJ- The price level of the M2 is usually the FY when ithe estimate was completed. Enter here. Program price year should be common across all contracts so it feeds from the input sheet.
Note on N37: USACE: Top 3 signatures: Cost, PM, Real Estate required by Regulations.
Note on V20: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V21: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V22: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V23: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V24: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on Y42: Include Study costs here (Generally these are NOT included table above) Check current CAP guidance. In most cases the study cost is not part of the "total project cost" but IS included in the federal spending limit/ceiling. Cost share percentage may vary- often the first 100K is fully federally funded.
SUMMARY SHEET
CONTRACT #1 OR PHASE 1
CONTRACT #2
CONTRACT #3
CONTRACT #4
CONTRACT #4
CONTRACT #3
CONTRACT #3 1d +w1
CONTRACT #2
CONTRACT #3
CONTRACT #4
CONTRACT #4
CONTRACT #3
Contract 4
CONTRACT #1 Reach 1b
CONTRACT #2
CONTRACT #3
CONTRACT #4
CONTRACT #4
CONTRACT #3
CONTRACT #2Reach 1c
CONTRACT #1 Reach 1b
CONTRACT #2
CONTRACT #3
CONTRACT #4
CONTRACT #4
CONTRACT #3
CONTRACT #2Reach 1c
CONTRACT #1 Reach 1b
CONTRACT #2
CONTRACT #3
CONTRACT #4
CONTRACT #4
CONTRACT #3
CONTRACT #2Reach 1c
CONTRACT #1 Reach 1b
CONTRACT #2
CONTRACT #3
CONTRACT #4
CONTRACT #4
CONTRACT #3
CONTRACT #2Reach 1c
Contract 3
Contract 4
Contract 5
Contract 6
Contract 7
Contract 8
Contract 9
Contract 10
Contract 11

## TPCS Rules
Estimated Cost (Price Level) is the initially developed cost estimate which includes contingencies. The effective price level date for Estimated Cost (shown in MONTH YYYY format) is usually the date of preparation of the cost estimate.
Project First Cost (Constant Dollar Cost) (Price Level) is the Estimated Cost BROUGHT TO THE EFFECTIVE PRICE LEVEL. The effective price level for Constant Dollar Cost (shown in MONTH YYYY format) is the date of the common point in time of the pricing used in the cost estimate. Constant Dollar Cost does not include inflation. Constant Dollar Cost at current price levels is the cost estimate used in feasibility reports and Chief's Reports (see paragraphs 5(a) and 5(b) below).
Total Project Cost is the Constant Dollar Cost FULLY FUNDED WITH ESCALATION to the estimated midpoint of construction. Total Project Cost (or Total Cost of Construction of GNFs when discussing navigation projects) is the cost estimate used in Project Partnership Agreements and Integral Determination Reports. Total Project Cost is the cost estimate provided non-Federal sponsors for their use in financial planning as it provides information regarding the overall non-Federal cost sharing obligation. See the enclosed tables for more detail of what is or is not included in the Total Project Cost.
Type of Program | CWBS* | Project Cost Component** | Brief Definition | For Chief's Report |  | For PPA's
|  |  |  | Project First Cost | Economic Cost for BCR | Total Project Cost
|  |  |  | Constant Cost Estimate "Oct (YYYY) Price Level" |  | Fully Funded Cost Estimate
Flood Risk Management | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Flood Risk Management | 02 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Flood Risk Management | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Flood Risk Management | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Flood Risk Management |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Flood Risk Management | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Flood Risk Management | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Flood Risk Management | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Flood Risk Management | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Flood Risk Management | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Flood Risk Management | By project element | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within cost shared project cost. | N | Y | Y
Ecosystem Restoration | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Ecosystem Restoration | 03 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Ecosystem Restoration | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Ecosystem Restoration | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Ecosystem Restoration |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Ecosystem Restoration | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Ecosystem Restoration | By project element | Monitoring and Adaptive Management | This represents the estimated costs of monitoring and or adaptive management to be cost shared for the project. | Y | Y | Y
Ecosystem Restoration | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Ecosystem Restoration | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Ecosystem Restoration | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Ecosystem Restoration | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Ecosystem Restoration |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Navigation and Harbors | 01,02 | Lands, Easements, Rights of Way, Relocations (LERR). This includes related Federal costs. | Estimated value/costs of LERR (to include breakout of related Federal administrative costs). | Y | Y | Y
Navigation and Harbors | 03 - 20 | Construction Elements (General Navigation Features) | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Navigation and Harbors | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Navigation and Harbors | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Navigation and Harbors |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Navigation and Harbors | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Navigation and Harbors | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Navigation and Harbors | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Navigation and Harbors | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Navigation and Harbors | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Navigation and Harbors | By project element | Local Service Facilities (LSF) | For Navigation Only: This represents the estimated cost of Local Service Facilities as defined in the Planning Guidance Notebook Appendix E. These are the responsibility of the non-Federal entity and are required as part of the PCA if they are necessary for project benefits to accrue. | N | Y | Y
Navigation and Harbors |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Inland Navigation | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Inland Navigation | 03 - 20 | Construction Elements (General Navigation Features) | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Inland Navigation | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Inland Navigation | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Inland Navigation |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Inland Navigation | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Inland Navigation | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Inland Navigation | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Inland Navigation | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Inland Navigation | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Inland Navigation | By project element | Local Service Facilities (LSF) | For Navigation Only: This represents the estimated cost of Local Service Facilities as defined in the Planning Guidance Notebook Appendix E. These are the responsibility of the non-Federal entity and are required as part of the PCA if they are necessary for project benefits to accrue. | N | Y | Y
Inland Navigation |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
COASTAL STORM | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
COASTAL STORM | 03 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
COASTAL STORM | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
COASTAL STORM | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
COASTAL STORM |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
COASTAL STORM | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
COASTAL STORM | By project element | Monitoring and Adaptive Management | This represents the estimated costs of monitoring and or adaptive management to be cost shared for the project. | Y | Y | Y
COASTAL STORM | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
COASTAL STORM | By project element | Continued Construction (periodic nourishment) | For Hurricane and Storm Damage Reduction Only: Estimate of Allowable Periodic Average future construction cost submitted for authorization. | Y | Y | Y
COASTAL STORM | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
COASTAL STORM | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
COASTAL STORM |  | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
COASTAL STORM |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Feature Code Definitions
CWBS | Definitions
01 Lands and Damages | This feature includes all costs of acquiring for the project (by purchase or condemnation) real property or permanent interests therein, including Government costs, damages, and costs of disposal of real estate. Government costs include planning expenses for the real estate portion of the General Design Memo and for the detailed Real Estate Memo; and project real estate office administration, surveys, and marking for land acquisition purposes and appraisals. For projects which require that costs be incurred on real estate activities, i.e., for records search, appraisals, and field inspection to assure compliance by local interests in the provision of local requirements on projects where no Federal land acquisition is involved, a memorandum statement will be provided with the PB-3 indicating the estimated costs of such real estate activities. These costs will be charged to feature 30, Engineering and Design and that feature will be properly footnoted to show the amount of such costs. A similar footnote will be shown on the PB-1's and PB-2a's for all such projects. This feature is credited with disposal receipts from sale of such items as standing crops, standing timber, structures, and improvements in place and acquired with the land. Disposal receipts from sale of excess land not turned in to the U.S. Treasury as miscellaneous receipts are credited to this feature. Lands or interests purchased for relocations and conveyed to others are included in the feature "Relocations.” Temporary interests such as leases are included in the feature or distributive item benefited thereby.
02 Relocations | This feature includes removing and relocating, or reconstructing property of others, such as roads, railroads, cemeteries, utilities, buildings, and other structures; and lands or interests purchased for such relocations and conveyed to others, including real estate planning and acquisition expenses. The cost of removal of improvements from the reservoir area for disposal is included in the feature “Reservoirs.” All alterations of railroad bridges in accordance with Section 3 of the 1946 Flood Control Act (22 USC 701p) are also included in this feature.
03 Reservoirs | This feature includes clearing lands in reservoirs and pools of debris, brush, trees, improvements, and structures. Any salvage, obtained by sale or disposal by the Government, of material removed in clearing operations is credited to this feature. This feature also includes bank stabilization, shoreline improvement, firebreaks, fencing, boundary line survey and marking of land which has been acquired or is to be acquired, rehabilitation of natural resources, erosion control, drainage, and rim grouting and mine sealing, etc., to prevent leakage. Site clearing, grouting, etc., incidental to and required for specific construction features is included as part of the construction features.
04 Dams | This feature includes dams and all other water collecting and storage facilities, whether man-made or natural, together with appurtenant diversion, regulation, and delivery facilities and spillways, outlet works, and power intake works, whether separate from the dam or not. In the case where the powerhouse is an integral part of the intake dam, the cost of the power intake dam is included in the feature "Power Plant." Any auxiliary dams or spillways detached from the main structures and floating trash and drift booms and barriers are included in this feature. The power intake works include such power items as forebay, penstocks, tunnels, surge tank, gates, operating equipment, and appurtenances. Service roads and service railroads on the dam are included in this feature. The additional cost of relocating highways and railroads across the dam is included in the feature "Relocations."
05 Locks | This feature includes facilities to provide for passage of waterborne traffic, including gates, valves, operating mechanisms, cribs, fills, lock walls, guide and guard walls, operating buildings, and excavation therefore. The lock structure is considered that part of the work within the limit lines extending from the upper end of the upper guide or guard walls to the lower end of the lower guide or guard walls, including dolphins within the lock approaches for tie up, guard, or guide purposes. Excavation or dredging• required in approaches outside of the limits defined above for the lock structure is included in the feature "Channels and Canals." The cost of a cofferdam or the properly allocable amount thereof, if required, is charged to this feature. Locks provided in connection with facilities for the prevention of encroachment of salt water are included in this feature. Locks in connection with fish facilities are included in the feature "Fish and Wildlife Facilities."
06 Fish and Wildlife Facilities | This feature includes items such as ladders, elevators, locks and related facilities for passage of fish at dams and navigation locks and maintenance of fish runs; and provision for wildlife preservation.
07 Power Plant | This feature includes those facilities specifically required for the production of power other than those included in the feature “Dams,” and consists of the following: powerhouse, turbines and governors, generators, accessory electrical equipment, miscellaneous power plant equipment, switchyard, and tailrace improvement for power. In the case where the powerhouse is an integral part of the power intake dam, the cost of the power intake dam is included in this feature. Where the structure of a dam also forms the foundation of the powerhouse, such foundation is considered a part of the dam. Units for production of power for the operation only of power for the operation only of navigation, flood control, or other purpose projects (excluding those projects with power as a feature) are included in other than this feature. The cost of a cofferdam or appropriate part is charged to this feature.
08 Roads, Railroads and Bridges | This feature includes permanent roads, railroads, and bridges required for access and other purposes in connection with the construction and operation of the project. This feature does not include roads, railroads, and bridges chargeable to the feature "Relocations," access roads to recreation facilities and areas, which will be charged to the feature "14. Recreation Facilities," and service roads and service railroads on structures.
09 Channels and Canals | This feature includes all forms of excavation (including dredging, preparation of spoil disposal area, and attendant facilities) necessary for the development and construction of channels, harbors, and canals for navigation purposes; and deepening, providing new, or improving existing watercourses for flood control and major drainage. Excavation of natural watercourse to provide adequate depths for navigation is included. Excavation for specific structures, such as dams and locks used in the development of waterways and conservation of water resources, is included with such structures. The removal of trees, brush, accumulated snags, drift, debris, water hyacinths and other aquatic growths from canals, harbors, and channels in navigable streams and tributaries thereof for navigational included in this feature. Excavation, clearing, and removal of accumulated snags, drifts, debris, and vegetable growth from streams for flood control and major drainage purposes also is included. Included in this feature are revetments, linings, dikes, and bulkheads constructed as channel improvement works for flood control or navigation, as against such items constructed for bank stabilization only. Also included are jetties constructed in connection with flood control channel improvements.
10 Breakwaters and Seawalls | This feature includes breakwaters, seawalls, piers, and like improvements constructed in connection with the protection of beaches, harbors, shores•, and port facilities against the force of waves and encroachment of seas or lakes by direct wave action. Jetties, groins, and like structures provided in seas, lakes, tidewater reaches of rivers and canals, and harbors to control water flow and current, to maintain depth of channels, and to provide protection, are included in this feature.
11 Levees and Floodwalls | This feature includes embankments and walls constructed to protect areas from inundation by overflow from creeks, rivers, lakes, canals, and other bodies of water. This feature consists of such items as: service roads on levee crown or landside berms, road ramps, closure structures, seepage control measures, erosion protection measures on levee slopes and on berms and bank slops when an integral part of the levees or floodwalls; and drainage facilities, constructed to provide means for the passage of accumulated drainage and seepage water and sewage from the protected area over or through levees and floodwalls, comprising such items as interceptor and collection sewers and ditches, and pressurized sewers and drainage structures, including outfalls through levees or floodwalls. Pumping plants are included in the feature "Pumping Plants." Levees locally called dikes are included in this feature.
13 Pumping Plants | This feature includes pumping plants construction to pass accumulated drainage and seepage water and sewage from the protected area over or through levees and floodwalls.
14 Recreation Facilities | This feature includes access roads; parking areas; public camping and picnicking areas, including tables and fireplaces; water supply; sanitary facilities; boat launching ramps; directional signs; and other facilities constructed primarily for public recreational use, including essential safety measures in connection therewith. The latter includes, as appropriate, sheltered anchorage areas for small craft, bathing areas readily accessible and reasonably safe, and safety provisions for visitors and fishermen in the project area. (Boat launching ramps, anchorage areas and beaches should be provided during construction to the extent they will definitely be needed and can be accomplished more economically than at a later date.)
15 Floodway Control and Diversion Structures | This feature includes floodway control and diversion structures to provide for the release of flood waters from streams where discharges exceed flood capacity of the stream, including items such as diversion dams, gated or ungated discharge structures, training walls, stilling basin, and those adjacent embankment sections forming part of the control structure. Construction of channels and levees not forming part of the main control structure, but necessary for operation of such structures is included in the appropriate feature "Channels and Canals" or "Levees and Floodwalls."
16 Bank Stabilization | This feature includes revetments, linings, training dikes, and bulkheads for stabilization of banks of watercourses to prevent erosion, sloughing, or meandering. Bank stabilization constructed in navigation channels or in connection with flood control channel improvement is included in• the feature "Channels and Canals."
17 Beach Replenishment | This feature includes replacement of eroded beaches, for purposes of recreation and shore protection, by direct deposit of materials obtained by dredging or land excavation.
19 Buildings, Grounds and Utilities | This feature includes permanent facilities such as operators' quarters, administration and shop buildings, storage buildings and areas, garage buildings and areas, community buildings, local streets and sidewalks, landscaping, and electric, gas, water, and sewage facilities. Where space in a dam, powerhouse, or other basic structure is used in lieu of construction of any of the above-mentioned buildings, such allocated space is not separated from the basic structure. Communication systems are• included in the feature "Permanent Operating Equipment."
20 Permanent Operating Equipment | This feature includes all project-owned operation and maintenance tools and equipment, such as laboratory, shop, warehousing, communications, and transportation equipment, and office furniture and equipment. The cost of installing sedimentation and degradation measuring facilities, including the surveys requisite to locating and monumenting range layouts, is charged to this feature. •The cost of planning the installation of sedimentation and degradation ranges is charged to the feature "Engineering and Design."
30 Engineering and Design | This feature includes all engineering, design, surveys, preparation of detailed plans and specifications, and related work required for the construction of the project, including relocations. Surveys and planning required in connection with land acquisition are charged to the features "Lands and Damages" or "Relocations," as applicable. Engineering and design performed by hired labor or as a pay item under a contract is included in this feature.
31 Supervision and Administration | This feature includes such functions as inspection, supervision, project office administration, and distributive costs of area office and general overhead charged to the project. Costs for OCE and Division Office Executive Direction and Management are not charged to Construction, General but to the General Expenses appropriation title.
Note on B6: *Civil Works Breakdown Structure
Note on F15: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F26: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F38: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F50: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F62: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).

## CWCCIS
| Date of Index Factors: | 2024-09-30 |  |  |  |  | Table A-1 Quarterly Indexes |  |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS
| CWCCIS ESCALATION CALCULATION |  |  |  |  | 1 |  | 1 |  |  | 1980Q1 | 1980Q2 | 1980Q3 | 1980Q4 | 1981Q1 | 1981Q2 | 1981Q3 | 1981Q4 | 1982Q1 | 1982Q2 | 1982Q3 | 1982Q4 | 1983Q1 | 1983Q2 | 1983Q3 | 1983Q4 | 1984Q1 | 1984Q2 | 1984Q3 | 1984Q4 | 1985Q1 | 1985Q2 | 1985Q3 | 1985Q4 | 1986Q1 | 1986Q2 | 1986Q3 | 1986Q4 | 1987Q1 | 1987Q2 | 1987Q3 | 1987Q4 | 1988Q1 | 1988Q2 | 1988Q3 | 1988Q4 | 1989Q1 | 1989Q2 | 1989Q3 | 1989Q4 | 1990Q1 | 1990Q2 | 1990Q3 | 1990Q4 | 1991Q1 | 1991Q2 | 1991Q3 | 1991Q4 | 1992Q1 | 1992Q2 | 1992Q3 | 1992Q4 | 1993Q1 | 1993Q2 | 1993Q3 | 1993Q4 | 1994Q1 | 1994Q2 | 1994Q3 | 1994Q4 | 1995Q1 | 1995Q2 | 1995Q3 | 1995Q4 | 1996Q1 | 1996Q2 | 1996Q3 | 1996Q4 | 1997Q1 | 1997Q2 | 1997Q3 | 1997Q4 | 1998Q1 | 1998Q2 | 1998Q3 | 1998Q4 | 1999Q1 | 1999Q2 | 1999Q3 | 1999Q4 | 2000Q1 | 2000Q2 | 2000Q3 | 2000Q4 | 2001Q1 | 2001Q2 | 2001Q3 | 2001Q4 | 2002Q1 | 2002Q2 | 2002Q3 | 2002Q4 | 2003Q1 | 2003Q2 | 2003Q3 | 2003Q4 | 2004Q1 | 2004Q2 | 2004Q3 | 2004Q4 | 2005Q1 | 2005Q2 | 2005Q3 | 2005Q4 | 2006Q1 | 2006Q2 | 2006Q3 | 2006Q4 | 2007Q1 | 2007Q2 | 2007Q3 | 2007Q4 | 2008Q1 | 2008Q2 | 2008Q3 | 2008Q4 | 2009Q1 | 2009Q2 | 2009Q3 | 2009Q4 | 2010Q1 | 2010Q2 | 2010Q3 | 2010Q4 | 2011Q1 | 2011Q2 | 2011Q3 | 2011Q4 | 2012Q1 | 2012Q2 | 2012Q3 | 2012Q4 | 2013Q1 | 2013Q2 | 2013Q3 | 2013Q4 | 2014Q1 | 2014Q2 | 2014Q3 | 2014Q4 | 2015Q1 | 2015Q2 | 2015Q3 | 2015Q4 | 2016Q1 | 2016Q2 | 2016Q3 | 2016Q4 | 2017Q1 | 2017Q2 | 2017Q3 | 2017Q4 | 2018Q1 | 2018Q2 | 2018Q3 | 2018Q4 | 2019Q1 | 2019Q2 | 2019Q3 | 2019Q4 | 2020Q1 | 2020Q2 | 2020Q3 | 2020Q4 | 2021Q1 | 2021Q2 | 2021Q3 | 2021Q4 | 2022Q1 | 2022Q2 | 2022Q3 | 2022Q4 | 2023Q1 | 2023Q2 | 2023Q3 | 2023Q4 | 2024Q1 | 2024Q2 | 2024Q3 | 2024Q4 | 2025Q1 | 2025Q2 | 2025Q3 | 2025Q4 | 2026Q1 | 2026Q2 | 2026Q3 | 2026Q4 | 2027Q1 | 2027Q2 | 2027Q3 | 2027Q4 | 2028Q1 | 2028Q2 | 2028Q3 | 2028Q4 | 2029Q1 | 2029Q2 | 2029Q3 | 2029Q4 | 2030Q1 | 2030Q2 | 2030Q3 | 2030Q4 | 2031Q1 | 2031Q2 | 2031Q3 | 2031Q4 | 2032Q1 | 2032Q2 | 2032Q3 | 2032Q4 | 2033Q1 | 2033Q2 | 2033Q3 | 2033Q4 | 2034Q1 | 2034Q2 | 2034Q3 | 2034Q4 | 2035Q1 | 2035Q2 | 2035Q3 | 2035Q4 | 2036Q1 | 2036Q2 | 2036Q3 | 2036Q4 | 2037Q1 | 2037Q2 | 2037Q3 | 2037Q4 | 2038Q1 | 2038Q2 | 2038Q3 | 2038Q4 | 2039Q1 | 2039Q2 | 2039Q3 | 2039Q4 | 2040Q1 | 2040Q2 | 2040Q3 | 2040Q4 | 2041Q1 | 2041Q2 | 2041Q3 | 2041Q4 | 2042Q1 | 2042Q2 | 2042Q3 | 2042Q4 | 2043Q1 | 2043Q2 | 2043Q3 | 2043Q4 | 2044Q1 | 2044Q2 | 2044Q3 | 2044Q4 | 2045Q1 | 2045Q2 | 2045Q3 | 2045Q4 | 2046Q1 | 2046Q2 | 2046Q3 | 2046Q4 | 2047Q1 | 2047Q2 | 2047Q3 | 2047Q4 | 2048Q1 | 2048Q2 | 2048Q3 | 2048Q4 | 2049Q1 | 2049Q2 | 2049Q3 | 2049Q4 | 2050Q1 | 2050Q2 | 2050Q3 | 2050Q4 | 2051Q1 | 2051Q2 | 2051Q3 | 2051Q4 | 2052Q1 | 2052Q2 | 2052Q3 | 2052Q4 | 2053Q1 | 2053Q2 | 2053Q3 | 2053Q4 | 2054Q1 | 2054Q2 | 2054Q3 | 2054Q4 | 2055Q1 | 2055Q2 | 2055Q3 | 2055Q4 | 2056Q1 | 2056Q2 | 2056Q3 | 2056Q4 | 2057Q1 | 2057Q2 | 2057Q3 | 2057Q4 | 2058Q1 | 2058Q2 | 2058Q3 | 2058Q4 | 2059Q1 | 2059Q2 | 2059Q3 | 2059Q4 | 2060Q1 | 2060Q2 | 2060Q3 | 2060Q4 | 2061Q1 | 2061Q2 | 2061Q3 | 2061Q4 | 2062Q1 | 2062Q2 | 2062Q3 | 2062Q4 | 2063Q1 | 2063Q2 | 2063Q3 | 2063Q4 | 2064Q1 | 2064Q2 | 2064Q3 | 2064Q4 | 2065Q1 | 2065Q2 | 2065Q3 | 2065Q4 | 2066Q1 | 2066Q2 | 2066Q3 | 2066Q4 | 2067Q1 | 2067Q2 | 2067Q3 | 2067Q4 | 2068Q1 | 2068Q2 | 2068Q3 | 2068Q4 | 2069Q1 | 2069Q2 | 2069Q3 | 2069Q4 | 2070Q1 | 2070Q2 | 2070Q3 | 2070Q4 | 2071Q1 | 2071Q2 | 2071Q3 | 2071Q4 | 2072Q1 | 2072Q2 | 2072Q3 | 2072Q4 | 2073Q1 | 2073Q2 | 2073Q3 | 2073Q4 | 2074Q1 | 2074Q2 | 2074Q3 | 2074Q4 | 2075Q1 | 2075Q2 | 2075Q3 | 2075Q4 | 2076Q1 | 2076Q2 | 2076Q3 | 2076Q4 | 2077Q1 | 2077Q2 | 2077Q3 | 2077Q4 | 2078Q1 | 2078Q2 | 2078Q3 | 2078Q4 | 2079Q1 | 2079Q2 | 2079Q3 | 2079Q4 | 2080Q1 | 2080Q2 | 2080Q3 | 2080Q4 | 2081Q1 | 2081Q2 | 2081Q3 | 2081Q4 | 2082Q1 | 2082Q2 | 2082Q3 | 2082Q4 | 2083Q1 | 2083Q2 | 2083Q3 | 2083Q4 | 2084Q1 | 2084Q2 | 2084Q3 | 2084Q4 | 2085Q1 | 2085Q2 | 2085Q3 | 2085Q4 | 2086Q1 | 2086Q2 | 2086Q3 | 2086Q4 | 2087Q1 | 2087Q2 | 2087Q3 | 2087Q4 | 2088Q1 | 2088Q2 | 2088Q3 | 2088Q4 | 2089Q1 | 2089Q2 | 2089Q3 | 2089Q4 | 2090Q1 | 2090Q2 | 2090Q3 | 2090Q4 | 2091Q1 | 2091Q2 | 2091Q3 | 2091Q4 | 2092Q1 | 2092Q2 | 2092Q3 | 2092Q4 | 2093Q1 | 2093Q2 | 2093Q3 | 2093Q4 | 2094Q1 | 2094Q2 | 2094Q3 | 2094Q4 | 2095Q1 | 2095Q2 | 2095Q3 | 2095Q4 | 2096Q1 | 2096Q2 | 2096Q3 | 2096Q4 | 2097Q1 | 2097Q2 | 2097Q3 | 2097Q4 | 2098Q1 | 2098Q2 | 2098Q3 | 2098Q4 | 2099Q1 | 2099Q2 | 2099Q3 | 2099Q4 | 2100Q1 | 2100Q2 | 2100Q3 | 2100Q4
Enter Code below | [5 empty] | 2 |  | 2 |  |  | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00 | 1Q01 | 2Q01 | 3Q01 | 4Q01 | 1Q02 | 2Q02 | 3Q02 | 4Q02 | 1Q03 | 2Q03 | 3Q03 | 4Q03 | 1Q04 | 2Q04 | 3Q04 | 4Q04 | 1Q05 | 2Q05 | 3Q05 | 4Q05 | 1Q06 | 2Q06 | 3Q06 | 4Q06 | 1Q07 | 2Q07 | 3Q07 | 4Q07 | 1Q08 | 2Q08 | 3Q08 | 4Q08 | 1Q09 | 2Q09 | 3Q09 | 4Q09 | 1Q10 | 2Q10 | 3Q10 | 4Q10 | 1Q11 | 2Q11 | 3Q11 | 4Q11 | 1Q12 | 2Q12 | 3Q12 | 4Q12 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | 1Q20 | 2Q20 | 3Q20 | 4Q20 | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22 | 2Q22 | 3Q22 | 4Q22 | 1Q23 | 2Q23 | 3Q23 | 4Q23 | 1Q24 | 2Q24 | 3Q24 | 4Q24 | 1Q25 | 2Q25 | 3Q25 | 4Q25 | 1Q26 | 2Q26 | 3Q26 | 4Q26 | 1Q27 | 2Q27 | 3Q27 | 4Q27 | 1Q28 | 2Q28 | 3Q28 | 4Q28 | 1Q29 | 2Q29 | 3Q29 | 4Q29 | 1Q30 | 2Q30 | 3Q30 | 4Q30 | 1Q31 | 2Q31 | 3Q31 | 4Q31 | 1Q32 | 2Q32 | 3Q32 | 4Q32 | 1Q33 | 2Q33 | 3Q33 | 4Q33 | 1Q34 | 2Q34 | 3Q34 | 4Q34 | 1Q35 | 2Q35 | 3Q35 | 4Q35 | 1Q36 | 2Q36 | 3Q36 | 4Q36 | 1Q37 | 2Q37 | 3Q37 | 4Q37 | 1Q38 | 2Q38 | 3Q38 | 4Q38 | 1Q39 | 2Q39 | 3Q39 | 4Q39 | 1Q40 | 2Q40 | 3Q40 | 4Q40 | 1Q41 | 2Q41 | 3Q41 | 4Q41 | 1Q42 | 2Q42 | 3Q42 | 4Q42 | 1Q43 | 2Q43 | 3Q43 | 4Q43 | 1Q44 | 2Q44 | 3Q44 | 4Q44 | 1Q45 | 2Q45 | 3Q45 | 4Q45 | 1Q46 | 2Q46 | 3Q46 | 4Q46 | 1Q47 | 2Q47 | 3Q47 | 4Q47 | 1Q48 | 2Q48 | 3Q48 | 4Q48 | 1Q49 | 2Q49 | 3Q49 | 4Q49 | 1Q50 | 2Q50 | 3Q50 | 4Q50 | 1Q51 | 2Q51 | 3Q51 | 4Q51 | 1Q52 | 2Q52 | 3Q52 | 4Q52 | 1Q53 | 2Q53 | 3Q53 | 4Q53 | 1Q54 | 2Q54 | 3Q54 | 4Q54 | 1Q55 | 2Q55 | 3Q55 | 4Q55 | 1Q56 | 2Q56 | 3Q56 | 4Q56 | 1Q57 | 2Q57 | 3Q57 | 4Q57 | 1Q58 | 2Q58 | 3Q58 | 4Q58 | 1Q59 | 2Q59 | 3Q59 | 4Q59 | 1Q60 | 2Q60 | 3Q60 | 4Q60 | 1Q61 | 2Q61 | 3Q61 | 4Q61 | 1Q62 | 2Q62 | 3Q62 | 4Q62 | 1Q63 | 2Q63 | 3Q63 | 4Q63 | 1Q64 | 2Q64 | 3Q64 | 4Q64 | 1Q65 | 2Q65 | 3Q65 | 4Q65 | 1Q66 | 2Q66 | 3Q66 | 4Q66 | 1Q67 | 2Q67 | 3Q67 | 4Q67 | 1Q68 | 2Q68 | 3Q68 | 4Q68 | 1Q69 | 2Q69 | 3Q69 | 4Q69 | 1Q70 | 2Q70 | 3Q70 | 4Q70 | 1Q71 | 2Q71 | 3Q71 | 4Q71 | 1Q72 | 2Q72 | 3Q72 | 4Q72 | 1Q73 | 2Q73 | 3Q73 | 4Q73 | 1Q74 | 2Q74 | 3Q74 | 4Q74 | 1Q75 | 2Q75 | 3Q75 | 4Q75 | 1Q76 | 2Q76 | 3Q76 | 4Q76 | 1Q77 | 2Q77 | 3Q77 | 4Q77 | 1Q78 | 2Q78 | 3Q78 | 4Q78 | 1Q79 | 2Q79 | 3Q79 | 4Q79 | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00
ALL | 0 |  | 25 | th row |  | 3 |  | 3 |  |  | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00 | 1Q01 | 2Q01 | 3Q01 | 4Q01 | 1Q02 | 2Q02 | 3Q02 | 4Q02 | 1Q03 | 2Q03 | 3Q03 | 4Q03 | 1Q04 | 2Q04 | 3Q04 | 4Q04 | 1Q05 | 2Q05 | 3Q05 | 4Q05 | 1Q06 | 2Q06 | 3Q06 | 4Q06 | 1Q07 | 2Q07 | 3Q07 | 4Q07 | 1Q08 | 2Q08 | 3Q08 | 4Q08 | 1Q09 | 2Q09 | 3Q09 | 4Q09 | 1Q10 | 2Q10 | 3Q10 | 4Q10 | 1Q11 | 2Q11 | 3Q11 | 4Q11 | 1Q12 | 2Q12 | 3Q12 | 4Q12 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | 1Q20 | 2Q20 | 3Q20 | 4Q20 | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22 | 2Q22 | 3Q22 | 4Q22 | 1Q23* | 2Q23* | 3Q23* | 4Q23* | 1Q24* | 2Q24* | 3Q24* | 4Q24* | 1Q25* | 2Q25* | 3Q25* | 4Q25* | 1Q26* | 2Q26* | 3Q26* | 4Q26* | 1Q27* | 2Q27* | 3Q27* | 4Q27* | 1Q28* | 2Q28* | 3Q28* | 4Q28* | 1Q29* | 2Q29* | 3Q29* | 4Q29* | 1Q30* | 2Q30* | 3Q30* | 4Q30* | 1Q31* | 2Q31* | 3Q31* | 4Q31* | 1Q32* | 2Q32* | 3Q32* | 4Q32* | 1Q33* | 2Q33* | 3Q33* | 4Q33* | 1Q34* | 2Q34* | 3Q34* | 4Q34* | 1Q35* | 2Q35* | 3Q35* | 4Q35* | 1Q36* | 2Q36* | 3Q36* | 4Q36* | 1Q37* | 2Q37* | 3Q37* | 4Q37* | 1Q38* | 2Q38* | 3Q38* | 4Q38* | 1Q39* | 2Q39* | 3Q39* | 4Q39* | 1Q40* | 2Q40* | 3Q40* | 4Q40* | 1Q41* | 2Q41* | 3Q41* | 4Q41* | 1Q42* | 2Q42* | 3Q42* | 4Q42* | 1Q43* | 2Q43* | 3Q43* | 4Q43* | 1Q44* | 2Q44* | 3Q44* | 4Q44* | 1Q45* | 2Q45* | 3Q45* | 4Q45* | 1Q46* | 2Q46* | 3Q46* | 4Q46* | 1Q47* | 2Q47* | 3Q47* | 4Q47* | 1Q48* | 2Q48* | 3Q48* | 4Q48* | 1Q49* | 2Q49* | 3Q49* | 4Q49* | 1Q50* | 2Q50* | 3Q50* | 4Q50* | 1Q51* | 2Q51* | 3Q51* | 4Q51* | 1Q52* | 2Q52* | 3Q52* | 4Q52* | 1Q53* | 2Q53* | 3Q53* | 4Q53* | 1Q54* | 2Q54* | 3Q54* | 4Q54* | 1Q55* | 2Q55* | 3Q55* | 4Q55* | 1Q56* | 2Q56* | 3Q56* | 4Q56* | 1Q57* | 2Q57* | 3Q57* | 4Q57* | 1Q58* | 2Q58* | 3Q58* | 4Q58* | 1Q59* | 2Q59* | 3Q59* | 4Q59* | 1Q60* | 2Q60* | 3Q60* | 4Q60* | 1Q61* | 2Q61* | 3Q61* | 4Q61* | 1Q62* | 2Q62* | 3Q62* | 4Q62* | 1Q63* | 2Q63* | 3Q63* | 4Q63* | 1Q64* | 2Q64* | 3Q64* | 4Q64* | 1Q65* | 2Q65* | 3Q65* | 4Q65* | 1Q66* | 2Q66* | 3Q66* | 4Q66* | 1Q67* | 2Q67* | 3Q67* | 4Q67* | 1Q68* | 2Q68* | 3Q68* | 4Q68* | 1Q69* | 2Q69* | 3Q69* | 4Q69* | 1Q70* | 2Q70* | 3Q70* | 4Q70* | 1Q71* | 2Q71* | 3Q71* | 4Q71* | 1Q72* | 2Q72* | 3Q72* | 4Q72* | 1Q73* | 2Q73* | 3Q73* | 4Q73* | 1Q74* | 2Q74* | 3Q74* | 4Q74* | 1Q75* | 2Q75* | 3Q75* | 4Q75* | 1Q76* | 2Q76* | 3Q76* | 4Q76* | 1Q77* | 2Q77* | 3Q77* | 4Q77* | 1Q78* | 2Q78* | 3Q78* | 4Q78* | 1Q79* | 2Q79* | 3Q79* | 4Q79* | 1Q80* | 2Q80* | 3Q80* | 4Q80* | 1Q81* | 2Q81* | 3Q81* | 4Q81* | 1Q82* | 2Q82* | 3Q82* | 4Q82* | 1Q83* | 2Q83* | 3Q83* | 4Q83* | 1Q84* | 2Q84* | 3Q84* | 4Q84* | 1Q85* | 2Q85* | 3Q85* | 4Q85* | 1Q86* | 2Q86* | 3Q86* | 4Q86* | 1Q87* | 2Q87* | 3Q87* | 4Q87* | 1Q88* | 2Q88* | 3Q88* | 4Q88* | 1Q89* | 2Q89* | 3Q89* | 4Q89* | 1Q90* | 2Q90* | 3Q90* | 4Q90* | 1Q91* | 2Q91* | 3Q91* | 4Q91* | 1Q92* | 2Q92* | 3Q92* | 4Q92* | 1Q93* | 2Q93* | 3Q93* | 4Q93* | 1Q94* | 2Q94* | 3Q94* | 4Q94* | 1Q95* | 2Q95* | 3Q95* | 4Q95* | 1Q96* | 2Q96* | 3Q96* | 4Q96* | 1Q97* | 2Q97* | 3Q97* | 4Q97* | 1Q98* | 2Q98* | 3Q98* | 4Q98* | 1Q99* | 2Q99* | 3Q99* | 4Q99* | 1Q100* | 2Q00* | 3Q00* | 4Q00*
[6 empty] | 4 |  | 4 |  |  | 1979 | 1980 | 1980 | 1980 | 1980 | 1981 | 1981 | 1981 | 1981 | 1982 | 1982 | 1982 | 1982 | 1983 | 1983 | 1983 | 1983 | 1984 | 1984 | 1984 | 1984 | 1985 | 1985 | 1985 | 1985 | 1986 | 1986 | 1986 | 1986 | 1987 | 1987 | 1987 | 1987 | 1988 | 1988 | 1988 | 1988 | 1989 | 1989 | 1989 | 1989 | 1990 | 1990 | 1990 | 1990 | 1991 | 1991 | 1991 | 1991 | 1992 | 1992 | 1992 | 1992 | 1993 | 1993 | 1993 | 1993 | 1994 | 1994 | 1994 | 1994 | 1995 | 1995 | 1995 | 1995 | 1996 | 1996 | 1996 | 1996 | 1997 | 1997 | 1997 | 1997 | 1998 | 1998 | 1998 | 1998 | 1999 | 1999 | 1999 | 1999 | 2000 | 2000 | 2000 | 2000 | 2001 | 2001 | 2001 | 2001 | 2002 | 2002 | 2002 | 2002 | 2003 | 2003 | 2003 | 2003 | 2004 | 2004 | 2004 | 2004 | 2005 | 2005 | 2005 | 2005 | 2006 | 2006 | 2006 | 2006 | 2007 | 2007 | 2007 | 2007 | 2008 | 2008 | 2008 | 2008 | 2009 | 2009 | 2009 | 2009 | 2010 | 2010 | 2010 | 2010 | 2011 | 2011 | 2011 | 2011 | 2012 | 2012 | 2012 | 2012 | 2013 | 2013 | 2013 | 2013 | 2014 | 2014 | 2014 | 2014 | 2015 | 2015 | 2015 | 2015 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031 | 2031 | 2031 | 2032 | 2032 | 2032 | 2032 | 2033 | 2033 | 2033 | 2033 | 2034 | 2034 | 2034 | 2034 | 2035 | 2035 | 2035 | 2035 | 2036 | 2036 | 2036 | 2036 | 2037 | 2037 | 2037 | 2037 | 2038 | 2038 | 2038 | 2038 | 2039 | 2039 | 2039 | 2039 | 2040 | 2040 | 2040 | 2040 | 2041 | 2041 | 2041 | 2041 | 2042 | 2042 | 2042 | 2042 | 2043 | 2043 | 2043 | 2043 | 2044 | 2044 | 2044 | 2044 | 2045 | 2045 | 2045 | 2045 | 2046 | 2046 | 2046 | 2046 | 2047 | 2047 | 2047 | 2047 | 2048 | 2048 | 2048 | 2048 | 2049 | 2049 | 2049 | 2049 | 2050 | 2050 | 2050 | 2050 | 2051 | 2051 | 2051 | 2051 | 2052 | 2052 | 2052 | 2052 | 2053 | 2053 | 2053 | 2053 | 2054 | 2054 | 2054 | 2054 | 2055 | 2055 | 2055 | 2055 | 2056 | 2056 | 2056 | 2056 | 2057 | 2057 | 2057 | 2057 | 2058 | 2058 | 2058 | 2058 | 2059 | 2059 | 2059 | 2059 | 2060 | 2060 | 2060 | 2060 | 2061 | 2061 | 2061 | 2061 | 2062 | 2062 | 2062 | 2062 | 2063 | 2063 | 2063 | 2063 | 2064 | 2064 | 2064 | 2064 | 2065 | 2065 | 2065 | 2065 | 2066 | 2066 | 2066 | 2066 | 2067 | 2067 | 2067 | 2067 | 2068 | 2068 | 2068 | 2068 | 2069 | 2069 | 2069 | 2069 | 2070 | 2070 | 2070 | 2070 | 2071 | 2071 | 2071 | 2071 | 2072 | 2072 | 2072 | 2072 | 2073 | 2073 | 2073 | 2073 | 2074 | 2074 | 2074 | 2074 | 2075 | 2075 | 2075 | 2075 | 2076 | 2076 | 2076 | 2076 | 2077 | 2077 | 2077 | 2077 | 2078 | 2078 | 2078 | 2078 | 2079 | 2079 | 2079 | 2079 | 2080 | 2080 | 2080 | 2080 | 2081 | 2081 | 2081 | 2081 | 2082 | 2082 | 2082 | 2082 | 2083 | 2083 | 2083 | 2083 | 2084 | 2084 | 2084 | 2084 | 2085 | 2085 | 2085 | 2085 | 2086 | 2086 | 2086 | 2086 | 2087 | 2087 | 2087 | 2087 | 2088 | 2088 | 2088 | 2088 | 2089 | 2089 | 2089 | 2089 | 2090 | 2090 | 2090 | 2090 | 2091 | 2091 | 2091 | 2091 | 2092 | 2092 | 2092 | 2092 | 2093 | 2093 | 2093 | 2093 | 2094 | 2094 | 2094 | 2094 | 2095 | 2095 | 2095 | 2095 | 2096 | 2096 | 2096 | 2096 | 2097 | 2097 | 2097 | 2097 | 2098 | 2098 | 2098 | 2098 | 2099 | 2099 | 2099 | 2099 | 2100 | 2100 | 2100
| Pick FY Quarter - Check Dates | FY Quarter | Dates | Index |  | 5 | CWBS | 5 |  | Wt % | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep)
| Estimate Pricing Level Date: | 2024Q1 |  | 1149.32 | / | 6 | 02 | 6 | RELOCATIONS | 5% | 271.87 | 274.31 | 285.26 | 289.3 | 295.1 | 301.18 | 312.75 | 315.63 | 320.53 | 322.08 | 333.33 | 333.67 | 335.14 | 338.18 | 345.35 | 344.78 | 345.52 | 348.83 | 352.68 | 351.02 | 353.13 | 354.92 | 357.91 | 355.77 | 355.59 | 359.01 | 359.28 | 359.55 | 361.04 | 363.87 | 368.87 | 371.5 | 374.44 | 379.38 | 383.85 | 384.02 | 388.26 | 393.87 | 398.1 | 398.06 | 397.7 | 402.35 | 406.27 | 405.48 | 407.61 | 409.79 | 415.17 | 412.51 | 416.6 | 423.9 | 424.33 | 424.64 | 432.27 | 444.84 | 440.26 | 444.4 | 453.13 | 453.19 | 455.09 | 455.63 | 459.16 | 463.37 | 466.65 | 466.2 | 466.08 | 471.21 | 477.34 | 478.46 | 481.69 | 487.33 | 488.95 | 487 | 488.93 | 492.32 | 491.1 | 488.69 | 492.81 | 499.56 | 509.16 | 503.04 | 506.82 | 508.77 | 508.18 | 508.11 | 508.75 | 510.79 | 516.87 | 516.78 | 519.56 | 530.58 | 535.25 | 534.41 | 535.7 | 538.79 | 543.21 | 549.21 | 559.04 | 583.39 | 595.63 | 608.05 | 612.78 | 617.37 | 619.16 | 625.19 | 639.51 | 643.94 | 647.71 | 655.73 | 660.22 | 678.49 | 685.41 | 681.9 | 685.16 | 701.29 | 728.77 | 727.11 | 708.97 | 699.5 | 706.43 | 707.53 | 715.45 | 727.79 | 733.68 | 732.86 | 741.6 | 754.5 | 762.57 | 763.99 | 768.33 | 774.53 | 776.41 | 776.53 | 787.84 | 795.56 | 794.68 | 797.33 | 805.1 | 809.41 | 817.5 | 818.24 | 822.62 | 817.79 | 825.5 | 820.72 | 823.25 | 827.92 | 841.23 | 838.77 | 845.05 | 856.5 | 866.08 | 869.55 | 866.37 | 879.92 | 894.71 | 898.57 | 904.17 | 909.16 | 916.44 | 914.4 | 918.54 | 920.64 | 933.71 | 956.45 | 980.2 | 1032.05 | 1047.49 | 1059.94 | 1126.43 | 1143.58 | 1134.19 | 1127.52 | 1133.08 | 1146.67 | 1159.84 | 1155.72 | 1166.71 | 1170.71 | 1181 | 1188.97 | 1196.94 | 1204.92 | 1212.89 | 1225.09 | 1229.31 | 1237.38 | 1245.45 | 1253.52 | 1261.28 | 1269.55 | 1277.83 | 1286.11 | 1294.07 | 1302.56 | 1311.06 | 1319.55 | 1327.71 | 1336.43 | 1345.14 | 1353.86 | 1362.23 | 1371.18 | 1380.12 | 1389.06 | 1397.65 | 1406.83 | 1416 | 1425.18 | 1433.99 | 1443.4 | 1452.82 | 1462.23 | 1471.28 | 1480.93 | 1490.59 | 1500.25 | 1509.53 | 1519.44 | 1529.35 | 1539.25 | 1548.78 | 1558.94 | 1569.11 | 1579.28 | 1589.04 | 1599.48 | 1609.91 | 1620.34 | 1630.36 | 1641.06 | 1651.76 | 1662.47 | 1672.75 | 1683.73 | 1694.71 | 1705.69 | 1716.24 | 1727.51 | 1738.77 | 1750.04 | 1760.86 | 1772.42 | 1783.98 | 1795.54 | 1806.65 | 1818.5 | 1830.36 | 1842.22 | 1853.62 | 1865.79 | 1877.95 | 1890.12 | 1901.81 | 1914.3 | 1926.78 | 1939.26 | 1951.26 | 1964.07 | 1976.88 | 1989.68 | 2001.99 | 2015.13 | 2028.27 | 2041.42 | 2054.04 | 2067.53 | 2081.01 | 2094.49 | 2107.45 | 2121.28 | 2135.12 | 2148.95 | 2162.24 | 2176.44 | 2190.63 | 2204.82 | 2218.46 | 2233.02 | 2247.59 | 2262.15 | 2276.14 | 2291.08 | 2306.02 | 2320.96 | 2335.32 | 2350.65 | 2365.98 | 2381.31 | 2396.04 | 2411.77 | 2427.49 | 2443.22 | 2458.34 | 2474.47 | 2490.61 | 2506.75 | 2522.25 | 2538.81 | 2555.37 | 2571.92 | 2587.83 | 2604.82 | 2621.8 | 2638.79 | 2655.12 | 2672.54 | 2689.97 | 2707.4 | 2724.15 | 2742.03 | 2759.91 | 2777.79 | 2794.98 | 2813.32 | 2831.67 | 2850.01 | 2867.65 | 2886.47 | 2905.29 | 2924.12 | 2942.2 | 2961.52 | 2980.83 | 3000.14 | 3018.7 | 3038.52 | 3058.33 | 3078.15 | 3097.19 | 3117.52 | 3137.85 | 3158.18 | 3177.71 | 3198.57 | 3219.43 | 3240.29 | 3260.34 | 3281.74 | 3303.14 | 3324.54 | 3345.1 | 3367.06 | 3389.02 | 3410.98 | 3432.08 | 3454.6 | 3477.13 | 3499.66 | 3521.31 | 3544.42 | 3567.54 | 3590.65 | 3612.86 | 3636.58 | 3660.29 | 3684.01 | 3706.8 | 3731.13 | 3755.46 | 3779.79 | 3803.18 | 3828.14 | 3853.1 | 3878.07 | 3902.06 | 3927.67 | 3953.28 | 3978.9 | 4003.51 | 4029.79 | 4056.07 | 4082.35 | 4107.6 | 4134.57 | 4161.53 | 4188.49 | 4214.4 | 4242.06 | 4269.73 | 4297.39 | 4323.98 | 4352.36 | 4380.74 | 4409.12 | 4436.4 | 4465.52 | 4494.64 | 4523.76 | 4551.75 | 4581.62 | 4611.5 | 4641.38 | 4670.09 | 4700.75 | 4731.4 | 4762.05 | 4791.51 | 4822.96 | 4854.42 | 4885.87 | 4916.09 | 4948.36 | 4980.63 | 5012.9 | 5043.91 | 5077.02 | 5110.13 | 5143.24 | 5175.05 | 5209.02 | 5242.99 | 5276.96 | 5309.6 | 5344.46 | 5379.31 | 5414.16 | 5447.65 | 5483.41 | 5519.17 | 5554.93 | 5589.29 | 5625.98 | 5662.67 | 5699.36 | 5734.61 | 5772.26 | 5809.9 | 5847.54 | 5883.71 | 5922.33 | 5960.96 | 5999.58 | 6036.69 | 6076.32 | 6115.94 | 6155.57 | 6193.64 | 6234.3 | 6274.95 | 6315.61 | 6354.68 | 6396.39 | 6438.1 | 6479.82 | 6519.9 | 6562.7 | 6605.49 | 6648.29 | 6689.42 | 6733.33 | 6777.24 | 6821.15 | 6863.34 | 6908.39 | 6953.45 | 6998.5 | 7041.79 | 7088.01 | 7134.23 | 7180.46 | 7224.88 | 7272.3 | 7319.72 | 7367.15 | 7412.72 | 7461.38 | 7510.04 | 7558.69 | 7605.45 | 7655.38 | 7705.3 | 7755.22 | 7803.2 | 7854.42 | 7905.64 | 7956.86 | 8006.08 | 8058.63 | 8111.18 | 8163.74 | 8214.24 | 8268.16 | 8322.07 | 8375.99
| Middle Point of Construction Date: | 2025Q1 |  | 1175.33 | = | 7 | 03 | 7 | RESERVOIRS | 5% | 274.7 | 276.51 | 293.22 | 297.8 | 300.01 | 305.39 | 325.04 | 330.69 | 335.73 | 336.83 | 356.25 | 357.68 | 359.13 | 360.28 | 370.01 | 370.86 | 371.61 | 372.33 | 379.08 | 378.13 | 379.31 | 381.22 | 383.57 | 383.71 | 384.37 | 386.05 | 387.94 | 388.09 | 389.18 | 390.97 | 398.32 | 399.74 | 402.12 | 405.81 | 410.03 | 411.79 | 414.93 | 418.28 | 423.45 | 424.66 | 426.62 | 432.72 | 440.03 | 441.87 | 443.75 | 445.96 | 448.72 | 449.9 | 452.29 | 455.74 | 459.63 | 460.86 | 463.31 | 466.47 | 468.97 | 469.52 | 471.63 | 476.39 | 481 | 481.85 | 483.22 | 489.04 | 494.52 | 495.36 | 497.21 | 501.71 | 505.9 | 506.27 | 507.4 | 510.01 | 512.1 | 514.82 | 517.4 | 520.17 | 522.7 | 525.43 | 532.68 | 539.36 | 544.82 | 545.17 | 546.17 | 549.66 | 554.69 | 558.99 | 563.32 | 563.43 | 570.76 | 574.83 | 578.45 | 588.04 | 596.92 | 597.44 | 599.3 | 601.96 | 608.05 | 612.58 | 618.26 | 622.07 | 631.33 | 636.79 | 643.64 | 648.68 | 655.31 | 659.06 | 666.12 | 668.01 | 669.42 | 686.51 | 694.1 | 706.17 | 718.54 | 718.99 | 720.94 | 725.82 | 737.53 | 744.72 | 754.07 | 755.1 | 766.33 | 770.44 | 778.06 | 780.49 | 798.39 | 799.72 | 802.29 | 811.14 | 821.33 | 824.47 | 828.38 | 833.59 | 844.93 | 845.07 | 849.84 | 853.83 | 869.35 | 869.57 | 871.75 | 874.82 | 893.52 | 895.08 | 898.38 | 900.9 | 920.24 | 922.38 | 926.33 | 929.06 | 946.27 | 946.67 | 948.17 | 952.07 | 968.29 | 970.05 | 967.86 | 972.35 | 981.61 | 992.51 | 997.24 | 1004.15 | 1030.73 | 1034.15 | 1038.12 | 1041.2 | 1043.92 | 1048.97 | 1056.25 | 1079.72 | 1106.5 | 1121.89 | 1133.29 | 1146.88 | 1151.93 | 1167.41 | 1186.3 | 1197.43 | 1211.96 | 1221.21 | 1233.52 | 1241.42 | 1249.34 | 1257.77 | 1266.21 | 1274.64 | 1283.07 | 1295.98 | 1300.45 | 1308.99 | 1317.52 | 1326.06 | 1334.26 | 1343.02 | 1351.78 | 1360.53 | 1368.95 | 1377.94 | 1386.92 | 1395.91 | 1404.54 | 1413.76 | 1422.98 | 1432.2 | 1441.06 | 1450.52 | 1459.98 | 1469.44 | 1478.53 | 1488.23 | 1497.94 | 1507.65 | 1516.97 | 1526.93 | 1536.89 | 1546.84 | 1556.41 | 1566.63 | 1576.85 | 1587.06 | 1596.88 | 1607.36 | 1617.84 | 1628.33 | 1638.4 | 1649.15 | 1659.91 | 1670.66 | 1681 | 1692.03 | 1703.07 | 1714.1 | 1724.7 | 1736.02 | 1747.34 | 1758.67 | 1769.55 | 1781.16 | 1792.78 | 1804.39 | 1815.55 | 1827.47 | 1839.39 | 1851.31 | 1862.76 | 1874.98 | 1887.21 | 1899.44 | 1911.19 | 1923.73 | 1936.28 | 1948.82 | 1960.88 | 1973.75 | 1986.62 | 1999.49 | 2011.86 | 2025.07 | 2038.27 | 2051.48 | 2064.17 | 2077.72 | 2091.27 | 2104.82 | 2117.84 | 2131.74 | 2145.64 | 2159.54 | 2172.9 | 2187.17 | 2201.43 | 2215.69 | 2229.4 | 2244.03 | 2258.67 | 2273.3 | 2287.36 | 2302.38 | 2317.39 | 2332.41 | 2346.84 | 2362.24 | 2377.64 | 2393.05 | 2407.85 | 2423.66 | 2439.46 | 2455.27 | 2470.46 | 2486.67 | 2502.89 | 2519.11 | 2534.69 | 2551.33 | 2567.96 | 2584.6 | 2600.59 | 2617.66 | 2634.73 | 2651.8 | 2668.21 | 2685.72 | 2703.23 | 2720.75 | 2737.58 | 2755.55 | 2773.52 | 2791.49 | 2808.76 | 2827.19 | 2845.63 | 2864.07 | 2881.78 | 2900.7 | 2919.62 | 2938.53 | 2956.71 | 2976.12 | 2995.53 | 3014.93 | 3033.59 | 3053.5 | 3073.41 | 3093.32 | 3112.46 | 3132.89 | 3153.32 | 3173.75 | 3193.38 | 3214.34 | 3235.31 | 3256.27 | 3276.41 | 3297.92 | 3319.42 | 3340.93 | 3361.6 | 3383.66 | 3405.73 | 3427.79 | 3449 | 3471.64 | 3494.28 | 3516.92 | 3538.67 | 3561.9 | 3585.13 | 3608.36 | 3630.68 | 3654.51 | 3678.34 | 3702.17 | 3725.08 | 3749.53 | 3773.98 | 3798.43 | 3821.93 | 3847.01 | 3872.1 | 3897.19 | 3921.3 | 3947.04 | 3972.78 | 3998.52 | 4023.25 | 4049.66 | 4076.07 | 4102.48 | 4127.86 | 4154.95 | 4182.05 | 4209.14 | 4235.18 | 4262.98 | 4290.78 | 4318.58 | 4345.29 | 4373.82 | 4402.34 | 4430.86 | 4458.27 | 4487.54 | 4516.8 | 4546.06 | 4574.19 | 4604.21 | 4634.24 | 4664.26 | 4693.12 | 4723.92 | 4754.73 | 4785.53 | 4815.14 | 4846.74 | 4878.35 | 4909.96 | 4940.33 | 4972.76 | 5005.19 | 5037.62 | 5068.78 | 5102.05 | 5135.32 | 5168.59 | 5200.57 | 5234.7 | 5268.84 | 5302.98 | 5335.78 | 5370.81 | 5405.83 | 5440.86 | 5474.51 | 5510.45 | 5546.38 | 5582.32 | 5616.85 | 5653.72 | 5690.59 | 5727.46 | 5762.89 | 5800.72 | 5838.54 | 5876.37 | 5912.72 | 5951.53 | 5990.35 | 6029.16 | 6066.45 | 6106.27 | 6146.09 | 6185.92 | 6224.18 | 6265.04 | 6305.89 | 6346.75 | 6386.01 | 6427.93 | 6469.85 | 6511.76 | 6552.05 | 6595.06 | 6638.06 | 6681.07 | 6722.4 | 6766.53 | 6810.65 | 6854.78 | 6897.18 | 6942.46 | 6987.73 | 7033 | 7076.51 | 7122.96 | 7169.41 | 7215.86 | 7260.5 | 7308.16 | 7355.81 | 7403.47 | 7449.27 | 7498.17 | 7547.07 | 7595.96 | 7642.95 | 7693.12 | 7743.29 | 7793.46 | 7841.67 | 7893.14 | 7944.62 | 7996.09 | 8045.55 | 8098.36 | 8151.18 | 8203.99 | 8254.74 | 8308.92 | 8363.11 | 8417.29 | 8469.36 | 8524.95 | 8580.55 | 8636.14 | 8689.56 | 8746.6 | 8803.64 | 8860.68
[6 empty] | 8 | 04 | 8 | DAMS | 15% | 268.61 | 272.52 | 281.67 | 285.68 | 291.27 | 297.99 | 308.49 | 311.94 | 317.12 | 318.98 | 328.96 | 329.62 | 329.81 | 331.82 | 337.99 | 339.43 | 339.85 | 343.07 | 347.13 | 346.95 | 348.18 | 350.26 | 351.95 | 351.5 | 351.32 | 353.16 | 353.43 | 353.83 | 355.05 | 356.86 | 360.95 | 363.11 | 366.73 | 370.67 | 374.28 | 375.6 | 380.19 | 383.99 | 387.52 | 388.29 | 389.13 | 392.24 | 396.69 | 397.57 | 400.37 | 402.16 | 404.98 | 404.39 | 406.6 | 409.86 | 412.2 | 412.6 | 416.86 | 423.16 | 424.3 | 426.5 | 430.77 | 434.22 | 437.46 | 439.04 | 443.1 | 449.75 | 453.64 | 453.85 | 455.02 | 458.98 | 462.87 | 463.99 | 465.98 | 470.03 | 472.01 | 473.15 | 475.97 | 479.55 | 480.64 | 480.07 | 482.4 | 487.32 | 492.58 | 491.25 | 494.04 | 496.25 | 498.01 | 498.82 | 500.65 | 501.87 | 505.85 | 507.48 | 509.54 | 517.86 | 523.54 | 523.71 | 524.83 | 527.44 | 530.53 | 535 | 543.14 | 561.95 | 574.06 | 587.47 | 594.9 | 598.72 | 603.91 | 611.03 | 625.48 | 631.2 | 637.92 | 647.39 | 651.74 | 668.81 | 674.55 | 673.9 | 678.85 | 694.86 | 719.14 | 720.13 | 705.76 | 697.72 | 701.88 | 701.98 | 708.05 | 715.18 | 723.36 | 723.26 | 729.81 | 742.73 | 751.52 | 752.53 | 758.31 | 763.62 | 764.46 | 765.52 | 772.81 | 776.78 | 781.78 | 782.77 | 789.65 | 794.6 | 799.78 | 800.7 | 807.1 | 804.97 | 809.36 | 806.3 | 809.87 | 812.8 | 824.03 | 821.98 | 828.34 | 836.42 | 845.12 | 846.76 | 844.46 | 855.23 | 867.57 | 879.62 | 886.33 | 890.72 | 896.58 | 893.69 | 897.27 | 901 | 904.37 | 911.27 | 928.87 | 967.68 | 1000.71 | 1027.87 | 1064.57 | 1091.01 | 1102.4 | 1104.72 | 1119.09 | 1131.93 | 1145.32 | 1145.95 | 1160.26 | 1162.18 | 1163.24 | 1171.09 | 1178.94 | 1186.8 | 1194.65 | 1206.66 | 1210.83 | 1218.77 | 1226.72 | 1234.67 | 1242.31 | 1250.46 | 1258.62 | 1266.77 | 1274.61 | 1282.97 | 1291.34 | 1299.71 | 1307.75 | 1316.33 | 1324.92 | 1333.5 | 1341.75 | 1350.56 | 1359.36 | 1368.17 | 1376.63 | 1385.67 | 1394.71 | 1403.74 | 1412.43 | 1421.7 | 1430.97 | 1440.24 | 1449.15 | 1458.66 | 1468.18 | 1477.69 | 1486.83 | 1496.59 | 1506.35 | 1516.11 | 1525.49 | 1535.5 | 1545.51 | 1555.53 | 1565.15 | 1575.42 | 1585.7 | 1595.97 | 1605.84 | 1616.38 | 1626.92 | 1637.46 | 1647.59 | 1658.41 | 1669.22 | 1680.04 | 1690.43 | 1701.53 | 1712.62 | 1723.72 | 1734.38 | 1745.77 | 1757.15 | 1768.54 | 1779.48 | 1791.16 | 1802.84 | 1814.52 | 1825.74 | 1837.73 | 1849.71 | 1861.7 | 1873.21 | 1885.51 | 1897.8 | 1910.1 | 1921.92 | 1934.53 | 1947.15 | 1959.76 | 1971.89 | 1984.83 | 1997.77 | 2010.72 | 2023.16 | 2036.44 | 2049.72 | 2063 | 2075.76 | 2089.38 | 2103.01 | 2116.63 | 2129.73 | 2143.71 | 2157.69 | 2171.67 | 2185.1 | 2199.44 | 2213.79 | 2228.13 | 2241.91 | 2256.63 | 2271.34 | 2286.06 | 2300.2 | 2315.3 | 2330.4 | 2345.5 | 2360.01 | 2375.5 | 2390.99 | 2406.48 | 2421.37 | 2437.26 | 2453.16 | 2469.05 | 2484.32 | 2500.63 | 2516.94 | 2533.24 | 2548.92 | 2565.65 | 2582.38 | 2599.11 | 2615.19 | 2632.35 | 2649.52 | 2666.69 | 2683.18 | 2700.79 | 2718.41 | 2736.02 | 2752.94 | 2771.02 | 2789.09 | 2807.16 | 2824.52 | 2843.06 | 2861.6 | 2880.14 | 2897.96 | 2916.98 | 2936 | 2955.03 | 2973.31 | 2992.82 | 3012.34 | 3031.86 | 3050.61 | 3070.64 | 3090.66 | 3110.68 | 3129.93 | 3150.47 | 3171.02 | 3191.56 | 3211.31 | 3232.39 | 3253.46 | 3274.54 | 3294.8 | 3316.43 | 3338.05 | 3359.68 | 3380.46 | 3402.65 | 3424.84 | 3447.03 | 3468.36 | 3491.12 | 3513.89 | 3536.66 | 3558.53 | 3581.89 | 3605.25 | 3628.61 | 3651.06 | 3675.02 | 3698.99 | 3722.95 | 3745.98 | 3770.57 | 3795.16 | 3819.75 | 3843.38 | 3868.61 | 3893.83 | 3919.06 | 3943.31 | 3969.19 | 3995.07 | 4020.96 | 4045.83 | 4072.39 | 4098.95 | 4125.5 | 4151.02 | 4178.27 | 4205.52 | 4232.77 | 4258.95 | 4286.91 | 4314.86 | 4342.82 | 4369.68 | 4398.37 | 4427.05 | 4455.73 | 4483.3 | 4512.72 | 4542.15 | 4571.58 | 4599.86 | 4630.05 | 4660.25 | 4690.44 | 4719.46 | 4750.44 | 4781.41 | 4812.39 | 4842.16 | 4873.95 | 4905.73 | 4937.52 | 4968.06 | 5000.67 | 5033.28 | 5065.89 | 5097.23 | 5130.69 | 5164.15 | 5197.6 | 5229.76 | 5264.09 | 5298.41 | 5332.74 | 5365.73 | 5400.95 | 5436.17 | 5471.39 | 5505.24 | 5541.38 | 5577.51 | 5613.65 | 5648.38 | 5685.45 | 5722.53 | 5759.6 | 5795.23 | 5833.27 | 5871.31 | 5909.35 | 5945.91 | 5984.94 | 6023.97 | 6063 | 6100.5 | 6140.55 | 6180.59 | 6220.64 | 6259.12 | 6300.2 | 6341.29 | 6382.37 | 6421.85 | 6464.01 | 6506.16 | 6548.31 | 6588.82 | 6632.07 | 6675.32 | 6718.57 | 6760.13 | 6804.51 | 6848.88 | 6893.25 | 6935.9 | 6981.42 | 7026.95 | 7072.48 | 7116.23 | 7162.94 | 7209.65 | 7256.36 | 7301.25 | 7349.18 | 7397.1 | 7445.03 | 7491.08 | 7540.25 | 7589.43 | 7638.6 | 7685.85 | 7736.3 | 7786.75 | 7837.2 | 7885.68 | 7937.44 | 7989.21 | 8040.97 | 8090.71 | 8143.82 | 8196.93 | 8250.03
|  |  | Escalation Percentage: -> | 102.3% |  | 9 | 05 | 9 | LOCKS | 2% | 267.29 | 271.45 | 280.61 | 285.09 | 290.51 | 297.43 | 307.88 | 311.66 | 316.52 | 318.59 | 328.44 | 329.3 | 329.66 | 332.24 | 338.19 | 339.29 | 339.75 | 342.69 | 346.67 | 346.19 | 345.85 | 348 | 349.9 | 349.39 | 348.48 | 350.45 | 351.03 | 351.44 | 352.56 | 354.8 | 358.68 | 361.3 | 365.49 | 370.09 | 373.68 | 374.96 | 378.98 | 383.12 | 385.9 | 386.53 | 386.61 | 389.75 | 393.42 | 393.88 | 396.33 | 398.06 | 400.61 | 399.93 | 402.01 | 405.84 | 407.64 | 407.9 | 411.78 | 418.65 | 419.5 | 422.06 | 426.64 | 429.83 | 432.86 | 434.57 | 438.73 | 445.29 | 449.25 | 449.32 | 449.94 | 453.54 | 457.63 | 458.66 | 460.32 | 464.19 | 466.28 | 467.21 | 469.68 | 473.13 | 474.11 | 472.96 | 474.43 | 478.77 | 484.44 | 482.76 | 485.77 | 488.74 | 490.22 | 490.8 | 492.11 | 493.23 | 497.55 | 498.84 | 500.92 | 510.32 | 516.3 | 516.21 | 517.34 | 520.67 | 523.36 | 528.58 | 537.81 | 560.55 | 572.89 | 588.45 | 595.76 | 599.22 | 602.17 | 610.26 | 624.39 | 630.3 | 638.4 | 648.48 | 652.21 | 671.85 | 677.88 | 676.32 | 682.18 | 701.14 | 730.54 | 728.97 | 708.16 | 696.16 | 699.79 | 701.92 | 708.17 | 718.31 | 725.64 | 725.88 | 733.84 | 748.48 | 756.76 | 756.73 | 760.93 | 765.02 | 765.35 | 764.34 | 771.04 | 775.23 | 778.58 | 780.15 | 787.1 | 792.29 | 799.14 | 799.98 | 804.23 | 800.49 | 805.36 | 801.48 | 802.59 | 805.92 | 818.83 | 815.96 | 823.42 | 832.66 | 842.09 | 844.22 | 843.17 | 856.82 | 870.64 | 881.41 | 888.34 | 892.45 | 897.14 | 892.82 | 896.16 | 899.9 | 903.62 | 911.01 | 931.5 | 976.85 | 1013.65 | 1042.24 | 1084.76 | 1110.29 | 1121.99 | 1117.99 | 1127.79 | 1141.8 | 1153.81 | 1153.09 | 1167.05 | 1168.54 | 1175 | 1182.93 | 1190.86 | 1198.79 | 1206.73 | 1218.86 | 1223.07 | 1231.1 | 1239.12 | 1247.15 | 1254.87 | 1263.1 | 1271.34 | 1279.58 | 1287.49 | 1295.95 | 1304.4 | 1312.85 | 1320.97 | 1329.64 | 1338.31 | 1346.98 | 1355.31 | 1364.21 | 1373.11 | 1382 | 1390.55 | 1399.68 | 1408.81 | 1417.94 | 1426.71 | 1436.07 | 1445.44 | 1454.8 | 1463.8 | 1473.41 | 1483.02 | 1492.63 | 1501.86 | 1511.72 | 1521.58 | 1531.43 | 1540.91 | 1551.02 | 1561.14 | 1571.25 | 1580.97 | 1591.35 | 1601.73 | 1612.1 | 1622.08 | 1632.72 | 1643.37 | 1654.02 | 1664.25 | 1675.18 | 1686.1 | 1697.02 | 1707.52 | 1718.73 | 1729.94 | 1741.15 | 1751.92 | 1763.42 | 1774.92 | 1786.42 | 1797.47 | 1809.27 | 1821.06 | 1832.86 | 1844.2 | 1856.31 | 1868.41 | 1880.52 | 1892.15 | 1904.57 | 1916.99 | 1929.41 | 1941.35 | 1954.09 | 1966.83 | 1979.58 | 1991.82 | 2004.9 | 2017.97 | 2031.04 | 2043.61 | 2057.02 | 2070.44 | 2083.85 | 2096.74 | 2110.51 | 2124.27 | 2138.03 | 2151.26 | 2165.38 | 2179.5 | 2193.62 | 2207.19 | 2221.68 | 2236.17 | 2250.65 | 2264.58 | 2279.44 | 2294.31 | 2309.17 | 2323.46 | 2338.71 | 2353.96 | 2369.21 | 2383.87 | 2399.51 | 2415.16 | 2430.81 | 2445.85 | 2461.9 | 2477.96 | 2494.01 | 2509.44 | 2525.91 | 2542.38 | 2558.85 | 2574.68 | 2591.58 | 2608.48 | 2625.38 | 2641.63 | 2658.97 | 2676.31 | 2693.64 | 2710.31 | 2728.1 | 2745.89 | 2763.68 | 2780.78 | 2799.03 | 2817.28 | 2835.54 | 2853.08 | 2871.8 | 2890.53 | 2909.26 | 2927.26 | 2946.47 | 2965.69 | 2984.9 | 3003.37 | 3023.08 | 3042.79 | 3062.51 | 3081.45 | 3101.68 | 3121.91 | 3142.13 | 3161.57 | 3182.32 | 3203.08 | 3223.83 | 3243.77 | 3265.06 | 3286.36 | 3307.65 | 3328.11 | 3349.96 | 3371.8 | 3393.65 | 3414.64 | 3437.05 | 3459.47 | 3481.88 | 3503.42 | 3526.42 | 3549.41 | 3572.41 | 3594.51 | 3618.1 | 3641.7 | 3665.29 | 3687.97 | 3712.17 | 3736.38 | 3760.59 | 3783.85 | 3808.69 | 3833.53 | 3858.37 | 3882.23 | 3907.72 | 3933.2 | 3958.68 | 3983.17 | 4009.32 | 4035.46 | 4061.61 | 4086.74 | 4113.56 | 4140.39 | 4167.21 | 4192.99 | 4220.51 | 4248.04 | 4275.56 | 4302.01 | 4330.25 | 4358.48 | 4386.72 | 4413.86 | 4442.83 | 4471.81 | 4500.78 | 4528.62 | 4558.35 | 4588.07 | 4617.8 | 4646.36 | 4676.86 | 4707.36 | 4737.86 | 4767.17 | 4798.46 | 4829.75 | 4861.05 | 4891.12 | 4923.22 | 4955.33 | 4987.43 | 5018.29 | 5051.23 | 5084.17 | 5117.11 | 5148.76 | 5182.56 | 5216.35 | 5250.15 | 5282.63 | 5317.3 | 5351.98 | 5386.65 | 5419.98 | 5455.55 | 5491.13 | 5526.71 | 5560.9 | 5597.4 | 5633.9 | 5670.4 | 5705.48 | 5742.93 | 5780.38 | 5817.83 | 5853.82 | 5892.25 | 5930.67 | 5969.1 | 6006.02 | 6045.45 | 6084.87 | 6124.29 | 6162.18 | 6202.63 | 6243.08 | 6283.52 | 6322.39 | 6363.9 | 6405.4 | 6446.9 | 6486.78 | 6529.36 | 6571.94 | 6614.51 | 6655.43 | 6699.12 | 6742.81 | 6786.49 | 6828.47 | 6873.3 | 6918.12 | 6962.94 | 7006.01 | 7052 | 7097.99 | 7143.98 | 7188.17 | 7235.35 | 7282.54 | 7329.72 | 7375.06 | 7423.47 | 7471.88 | 7520.29 | 7566.82 | 7616.48 | 7666.15 | 7715.82 | 7763.55 | 7814.51 | 7865.47 | 7916.43 | 7965.4 | 8017.69 | 8069.97 | 8122.26 | 8172.51 | 8226.15 | 8279.79 | 8333.44
[6 empty] | 10 | 06 | 10 | FISH & WILDLIFE FACILITIES | 5% | 272.96 | 276.04 | 284.61 | 287.69 | 293.79 | 300 | 309.83 | 312.44 | 317.17 | 318.26 | 327.74 | 327.83 | 327.53 | 329.77 | 336.78 | 337.58 | 337.59 | 341.9 | 345.41 | 344.61 | 344.74 | 346.93 | 349.22 | 347.84 | 347.27 | 349.61 | 349.34 | 349.75 | 350.28 | 352.65 | 356.54 | 359.07 | 362.38 | 367.09 | 370.86 | 371.49 | 374.97 | 379.49 | 382.47 | 382.81 | 382.1 | 385.48 | 388.93 | 389.01 | 391.31 | 393.28 | 396.94 | 395.33 | 398.09 | 402.68 | 403.56 | 403.94 | 409.21 | 419.09 | 417.86 | 421.18 | 427.15 | 429.69 | 432.59 | 434.12 | 438.14 | 444.64 | 447.98 | 447.96 | 447.8 | 452.65 | 457.78 | 459.09 | 461.23 | 466.4 | 468.57 | 468.4 | 469.97 | 474.07 | 474.38 | 472.57 | 474.86 | 480.31 | 487.47 | 483.86 | 487.08 | 489.21 | 489.75 | 489.55 | 490.33 | 491.91 | 496.69 | 497.31 | 499.28 | 508.67 | 514.07 | 513.82 | 514.15 | 516.87 | 520.35 | 525.69 | 534.75 | 558.9 | 571.55 | 586.56 | 593.35 | 597.76 | 600.97 | 608.18 | 624.32 | 630.14 | 636.39 | 645.47 | 649.01 | 668.79 | 674.11 | 671.55 | 675.58 | 693.72 | 722.13 | 719.86 | 698.29 | 686.42 | 689.95 | 691.34 | 696.93 | 707.21 | 712.33 | 711.42 | 718.73 | 732.94 | 740.7 | 740.08 | 744.72 | 749.69 | 749.6 | 749.46 | 758.43 | 764.29 | 764.9 | 766.75 | 774.03 | 779.64 | 785.65 | 786.93 | 792.02 | 788.66 | 793.12 | 788.51 | 790.9 | 795.09 | 807.3 | 804.64 | 811.91 | 823.16 | 831.76 | 834.07 | 833.09 | 846.58 | 860.94 | 867.95 | 873.73 | 878.35 | 881.63 | 877.83 | 880.38 | 883.42 | 890.83 | 904.43 | 925.56 | 974.85 | 1002.62 | 1025.12 | 1078.05 | 1100.62 | 1105.63 | 1100.49 | 1108.19 | 1122.28 | 1134.8 | 1132.27 | 1144.9 | 1147.14 | 1152 | 1159.78 | 1167.55 | 1175.33 | 1183.1 | 1195 | 1199.13 | 1207 | 1214.87 | 1222.74 | 1230.3 | 1238.38 | 1246.46 | 1254.53 | 1262.29 | 1270.58 | 1278.86 | 1287.15 | 1295.11 | 1303.61 | 1312.11 | 1320.62 | 1328.78 | 1337.51 | 1346.23 | 1354.95 | 1363.33 | 1372.28 | 1381.23 | 1390.18 | 1398.78 | 1407.96 | 1417.14 | 1426.32 | 1435.15 | 1444.57 | 1453.99 | 1463.41 | 1472.46 | 1482.13 | 1491.79 | 1501.46 | 1510.75 | 1520.66 | 1530.58 | 1540.5 | 1550.03 | 1560.2 | 1570.37 | 1580.55 | 1590.33 | 1600.76 | 1611.2 | 1621.64 | 1631.67 | 1642.38 | 1653.09 | 1663.81 | 1674.1 | 1685.09 | 1696.08 | 1707.06 | 1717.62 | 1728.9 | 1740.17 | 1751.45 | 1762.28 | 1773.85 | 1785.42 | 1796.99 | 1808.1 | 1819.97 | 1831.84 | 1843.71 | 1855.11 | 1867.29 | 1879.47 | 1891.64 | 1903.35 | 1915.84 | 1928.33 | 1940.83 | 1952.83 | 1965.65 | 1978.47 | 1991.29 | 2003.61 | 2016.76 | 2029.91 | 2043.06 | 2055.7 | 2069.19 | 2082.69 | 2096.18 | 2109.15 | 2122.99 | 2136.84 | 2150.68 | 2163.99 | 2178.19 | 2192.39 | 2206.6 | 2220.25 | 2234.82 | 2249.4 | 2263.97 | 2277.98 | 2292.93 | 2307.88 | 2322.83 | 2337.2 | 2352.54 | 2367.89 | 2383.23 | 2397.97 | 2413.71 | 2429.45 | 2445.19 | 2460.32 | 2476.47 | 2492.62 | 2508.77 | 2524.29 | 2540.86 | 2557.43 | 2573.99 | 2589.92 | 2606.92 | 2623.92 | 2640.92 | 2657.26 | 2674.7 | 2692.14 | 2709.58 | 2726.34 | 2744.24 | 2762.14 | 2780.03 | 2797.23 | 2815.59 | 2833.95 | 2852.31 | 2869.96 | 2888.8 | 2907.63 | 2926.47 | 2944.58 | 2963.9 | 2983.23 | 3002.56 | 3021.13 | 3040.97 | 3060.8 | 3080.63 | 3099.68 | 3120.03 | 3140.38 | 3160.72 | 3180.28 | 3201.15 | 3222.03 | 3242.9 | 3262.96 | 3284.38 | 3305.8 | 3327.22 | 3347.8 | 3369.78 | 3391.75 | 3413.73 | 3434.84 | 3457.39 | 3479.94 | 3502.48 | 3524.15 | 3547.28 | 3570.41 | 3593.55 | 3615.78 | 3639.51 | 3663.25 | 3686.98 | 3709.79 | 3734.14 | 3758.49 | 3782.84 | 3806.24 | 3831.23 | 3856.21 | 3881.19 | 3905.2 | 3930.84 | 3956.47 | 3982.11 | 4006.74 | 4033.04 | 4059.34 | 4085.64 | 4110.91 | 4137.9 | 4164.88 | 4191.87 | 4217.8 | 4245.48 | 4273.17 | 4300.86 | 4327.46 | 4355.87 | 4384.27 | 4412.68 | 4439.98 | 4469.12 | 4498.26 | 4527.41 | 4555.41 | 4585.32 | 4615.22 | 4645.12 | 4673.86 | 4704.53 | 4735.21 | 4765.89 | 4795.38 | 4826.85 | 4858.33 | 4889.81 | 4920.06 | 4952.35 | 4984.65 | 5016.94 | 5047.98 | 5081.11 | 5114.25 | 5147.38 | 5179.22 | 5213.22 | 5247.22 | 5281.21 | 5313.88 | 5348.76 | 5383.64 | 5418.52 | 5452.04 | 5487.83 | 5523.62 | 5559.41 | 5593.8 | 5630.52 | 5667.23 | 5703.95 | 5739.24 | 5776.91 | 5814.58 | 5852.25 | 5888.46 | 5927.11 | 5965.76 | 6004.41 | 6041.56 | 6081.21 | 6120.87 | 6160.53 | 6198.64 | 6239.33 | 6280.01 | 6320.7 | 6359.8 | 6401.55 | 6443.29 | 6485.04 | 6525.16 | 6567.99 | 6610.82 | 6653.65 | 6694.81 | 6738.76 | 6782.7 | 6826.64 | 6868.88 | 6913.96 | 6959.05 | 7004.14 | 7047.47 | 7093.73 | 7139.99 | 7186.25 | 7230.7 | 7278.16 | 7325.63 | 7373.09 | 7418.7 | 7467.4 | 7516.09 | 7564.79 | 7611.59 | 7661.55 | 7711.51 | 7761.47 | 7809.49 | 7860.75 | 7912.01 | 7963.27 | 8012.53 | 8065.13 | 8117.72 | 8170.32
| Paste the Web Address into browser for downloadable (.pdf) source of factors: |  |  |  |  | 11 | 07 | 11 | POWER PLANT | 10% | 254.91 | 261.92 | 271.8 | 276.78 | 282.49 | 290.3 | 299.66 | 305.47 | 309.82 | 312.2 | 318.6 | 318.44 | 319.76 | 322.14 | 326.42 | 328.13 | 329.23 | 331.22 | 336.05 | 336.13 | 335.55 | 336.98 | 338.59 | 338.98 | 339.42 | 341.68 | 342.4 | 343.89 | 344.84 | 346.64 | 350.24 | 352.88 | 355.43 | 359.77 | 362.57 | 365.95 | 370.58 | 375.63 | 379.26 | 380.68 | 382.72 | 385.98 | 390.04 | 392.37 | 395.96 | 398.37 | 400.46 | 401.16 | 403.39 | 406.1 | 407.68 | 408.81 | 411.75 | 415.92 | 417.3 | 419.18 | 422.2 | 424.51 | 426.7 | 429.08 | 432.79 | 437.55 | 440.85 | 442.1 | 441.89 | 444.43 | 446.64 | 447.38 | 447.1 | 450.74 | 453.52 | 455.29 | 457.05 | 458.84 | 460.27 | 459.69 | 461.41 | 464.12 | 467.99 | 467.98 | 469.5 | 472.63 | 473.85 | 474.95 | 476.65 | 478.03 | 481.14 | 482.73 | 483.76 | 489.01 | 493.68 | 493.88 | 494.64 | 496.8 | 499.15 | 502.53 | 508.32 | 524.12 | 534.82 | 545 | 550.58 | 555.21 | 557.62 | 565.16 | 578.01 | 583.39 | 591.74 | 602.27 | 605.88 | 621.78 | 628.04 | 628.54 | 635.04 | 648.1 | 672.38 | 676.86 | 660.73 | 657.37 | 660.93 | 664.75 | 670.51 | 677.22 | 683.75 | 684.61 | 690.66 | 702.31 | 709.32 | 709.88 | 713.57 | 717.4 | 717.04 | 718.99 | 722.83 | 725.97 | 728.72 | 730.08 | 735.33 | 738.7 | 743.11 | 744.66 | 746.47 | 743.2 | 745.99 | 743.39 | 741.76 | 745.13 | 752.67 | 751.99 | 756.08 | 760.68 | 766.03 | 768.15 | 771.29 | 779.8 | 789.39 | 796.24 | 800.68 | 804.9 | 808.46 | 808.21 | 811.48 | 812.05 | 814.58 | 820.49 | 833.37 | 865.7 | 899.04 | 926.74 | 968.78 | 996.24 | 1013.4 | 1015.93 | 1033.18 | 1045.85 | 1051.1 | 1055.21 | 1063.71 | 1068.22 | 1071.04 | 1078.27 | 1085.5 | 1092.73 | 1099.96 | 1111.02 | 1114.85 | 1122.17 | 1129.49 | 1136.81 | 1143.84 | 1151.35 | 1158.85 | 1166.36 | 1173.58 | 1181.28 | 1188.99 | 1196.69 | 1204.09 | 1212 | 1219.9 | 1227.8 | 1235.4 | 1243.51 | 1251.62 | 1259.73 | 1267.52 | 1275.84 | 1284.16 | 1292.48 | 1300.47 | 1309.01 | 1317.55 | 1326.08 | 1334.29 | 1343.04 | 1351.8 | 1360.56 | 1368.98 | 1377.96 | 1386.95 | 1395.94 | 1404.57 | 1413.79 | 1423.01 | 1432.23 | 1441.09 | 1450.55 | 1460.01 | 1469.47 | 1478.56 | 1488.26 | 1497.97 | 1507.67 | 1517 | 1526.96 | 1536.92 | 1546.87 | 1556.44 | 1566.66 | 1576.88 | 1587.09 | 1596.91 | 1607.39 | 1617.87 | 1628.36 | 1638.43 | 1649.18 | 1659.94 | 1670.69 | 1681.03 | 1692.06 | 1703.1 | 1714.13 | 1724.74 | 1736.06 | 1747.38 | 1758.7 | 1769.58 | 1781.19 | 1792.81 | 1804.43 | 1815.59 | 1827.51 | 1839.42 | 1851.34 | 1862.79 | 1875.02 | 1887.25 | 1899.48 | 1911.23 | 1923.77 | 1936.32 | 1948.86 | 1960.92 | 1973.79 | 1986.66 | 1999.53 | 2011.9 | 2025.11 | 2038.31 | 2051.52 | 2064.21 | 2077.76 | 2091.31 | 2104.86 | 2117.88 | 2131.78 | 2145.68 | 2159.59 | 2172.95 | 2187.21 | 2201.47 | 2215.73 | 2229.44 | 2244.08 | 2258.71 | 2273.34 | 2287.41 | 2302.42 | 2317.44 | 2332.45 | 2346.88 | 2362.28 | 2377.69 | 2393.09 | 2407.9 | 2423.7 | 2439.51 | 2455.32 | 2470.5 | 2486.72 | 2502.94 | 2519.15 | 2534.74 | 2551.38 | 2568.01 | 2584.65 | 2600.64 | 2617.71 | 2634.78 | 2651.85 | 2668.26 | 2685.77 | 2703.29 | 2720.8 | 2737.63 | 2755.6 | 2773.57 | 2791.54 | 2808.81 | 2827.25 | 2845.68 | 2864.12 | 2881.84 | 2900.76 | 2919.67 | 2938.59 | 2956.77 | 2976.18 | 2995.58 | 3014.99 | 3033.64 | 3053.56 | 3073.47 | 3093.38 | 3112.52 | 3132.95 | 3153.38 | 3173.81 | 3193.44 | 3214.4 | 3235.37 | 3256.33 | 3276.47 | 3297.98 | 3319.49 | 3340.99 | 3361.66 | 3383.73 | 3405.79 | 3427.86 | 3449.06 | 3471.7 | 3494.34 | 3516.98 | 3538.74 | 3561.97 | 3585.2 | 3608.42 | 3630.75 | 3654.58 | 3678.41 | 3702.24 | 3725.15 | 3749.6 | 3774.05 | 3798.5 | 3822 | 3847.09 | 3872.18 | 3897.26 | 3921.37 | 3947.11 | 3972.85 | 3998.59 | 4023.33 | 4049.74 | 4076.15 | 4102.56 | 4127.93 | 4155.03 | 4182.13 | 4209.22 | 4235.26 | 4263.06 | 4290.86 | 4318.66 | 4345.38 | 4373.9 | 4402.42 | 4430.95 | 4458.36 | 4487.62 | 4516.89 | 4546.15 | 4574.27 | 4604.3 | 4634.33 | 4664.35 | 4693.21 | 4724.01 | 4754.82 | 4785.62 | 4815.23 | 4846.84 | 4878.44 | 4910.05 | 4940.43 | 4972.85 | 5005.28 | 5037.71 | 5068.88 | 5102.15 | 5135.42 | 5168.69 | 5200.67 | 5234.8 | 5268.94 | 5303.08 | 5335.88 | 5370.91 | 5405.93 | 5440.96 | 5474.62 | 5510.55 | 5546.49 | 5582.42 | 5616.96 | 5653.83 | 5690.7 | 5727.57 | 5763 | 5800.83 | 5838.66 | 5876.48 | 5912.84 | 5951.65 | 5990.46 | 6029.27 | 6066.57 | 6106.39 | 6146.21 | 6186.03 | 6224.3 | 6265.16 | 6306.01 | 6346.87 | 6386.13 | 6428.05 | 6469.97 | 6511.89 | 6552.17 | 6595.18 | 6638.19 | 6681.2 | 6722.53 | 6766.66 | 6810.78 | 6854.91 | 6897.31 | 6942.59 | 6987.86 | 7033.14 | 7076.64 | 7123.1 | 7169.55 | 7216 | 7260.64 | 7308.3 | 7355.95 | 7403.61 | 7449.41 | 7498.31 | 7547.21 | 7596.11
| No longer published under EM 1110-2-1304 CWCCIS | https://www.usace.army.mil/Cost-Engineering/cwccis/ |  |  |  | 12 | 08 | 12 | ROADS, RAILROADS & BRIDGES | 10% | 271.87 | 274.31 | 285.26 | 289.3 | 295.1 | 301.18 | 312.75 | 315.63 | 320.53 | 322.08 | 333.33 | 333.67 | 335.14 | 338.18 | 345.35 | 344.78 | 345.52 | 348.83 | 352.68 | 351.02 | 353.13 | 354.92 | 357.91 | 355.77 | 355.59 | 359.01 | 359.28 | 359.55 | 361.04 | 363.87 | 368.87 | 371.5 | 374.44 | 379.38 | 383.85 | 384.02 | 388.26 | 393.87 | 398.1 | 398.06 | 397.7 | 402.35 | 406.27 | 405.48 | 407.61 | 409.79 | 415.17 | 412.51 | 416.6 | 423.9 | 424.33 | 424.64 | 432.27 | 444.84 | 440.26 | 444.4 | 453.13 | 453.19 | 455.09 | 455.63 | 459.16 | 463.37 | 466.65 | 466.2 | 466.08 | 471.21 | 477.34 | 478.46 | 481.69 | 487.33 | 488.95 | 487 | 488.93 | 492.32 | 491.1 | 488.69 | 492.81 | 499.56 | 509.16 | 503.04 | 506.82 | 508.77 | 508.18 | 508.11 | 508.75 | 510.79 | 516.87 | 516.78 | 519.56 | 530.58 | 535.25 | 534.41 | 535.7 | 538.79 | 543.21 | 549.21 | 559.04 | 583.39 | 595.63 | 608.05 | 612.78 | 617.37 | 619.16 | 625.19 | 639.51 | 643.94 | 647.71 | 655.73 | 660.22 | 678.49 | 685.41 | 681.9 | 685.16 | 701.29 | 728.77 | 727.11 | 708.97 | 699.5 | 706.43 | 707.53 | 715.45 | 727.79 | 733.68 | 732.86 | 741.6 | 754.5 | 762.57 | 763.99 | 768.33 | 774.53 | 776.41 | 776.53 | 787.84 | 795.56 | 794.68 | 797.33 | 805.1 | 809.41 | 817.5 | 818.24 | 822.62 | 817.79 | 825.5 | 820.72 | 823.25 | 827.92 | 841.23 | 838.77 | 845.05 | 856.5 | 866.08 | 869.55 | 866.37 | 879.92 | 894.71 | 898.57 | 904.17 | 909.16 | 916.44 | 914.4 | 918.54 | 920.64 | 933.71 | 956.45 | 980.2 | 1032.05 | 1047.49 | 1059.94 | 1126.43 | 1143.58 | 1134.19 | 1127.52 | 1133.08 | 1146.67 | 1159.84 | 1155.72 | 1166.71 | 1170.71 | 1181 | 1188.97 | 1196.94 | 1204.92 | 1212.89 | 1225.09 | 1229.31 | 1237.38 | 1245.45 | 1253.52 | 1261.28 | 1269.55 | 1277.83 | 1286.11 | 1294.07 | 1302.56 | 1311.06 | 1319.55 | 1327.71 | 1336.43 | 1345.14 | 1353.86 | 1362.23 | 1371.18 | 1380.12 | 1389.06 | 1397.65 | 1406.83 | 1416 | 1425.18 | 1433.99 | 1443.4 | 1452.82 | 1462.23 | 1471.28 | 1480.93 | 1490.59 | 1500.25 | 1509.53 | 1519.44 | 1529.35 | 1539.25 | 1548.78 | 1558.94 | 1569.11 | 1579.28 | 1589.04 | 1599.48 | 1609.91 | 1620.34 | 1630.36 | 1641.06 | 1651.76 | 1662.47 | 1672.75 | 1683.73 | 1694.71 | 1705.69 | 1716.24 | 1727.51 | 1738.77 | 1750.04 | 1760.86 | 1772.42 | 1783.98 | 1795.54 | 1806.65 | 1818.5 | 1830.36 | 1842.22 | 1853.62 | 1865.79 | 1877.95 | 1890.12 | 1901.81 | 1914.3 | 1926.78 | 1939.26 | 1951.26 | 1964.07 | 1976.88 | 1989.68 | 2001.99 | 2015.13 | 2028.27 | 2041.42 | 2054.04 | 2067.53 | 2081.01 | 2094.49 | 2107.45 | 2121.28 | 2135.12 | 2148.95 | 2162.24 | 2176.44 | 2190.63 | 2204.82 | 2218.46 | 2233.02 | 2247.59 | 2262.15 | 2276.14 | 2291.08 | 2306.02 | 2320.96 | 2335.32 | 2350.65 | 2365.98 | 2381.31 | 2396.04 | 2411.77 | 2427.49 | 2443.22 | 2458.34 | 2474.47 | 2490.61 | 2506.75 | 2522.25 | 2538.81 | 2555.37 | 2571.92 | 2587.83 | 2604.82 | 2621.8 | 2638.79 | 2655.12 | 2672.54 | 2689.97 | 2707.4 | 2724.15 | 2742.03 | 2759.91 | 2777.79 | 2794.98 | 2813.32 | 2831.67 | 2850.01 | 2867.65 | 2886.47 | 2905.29 | 2924.12 | 2942.2 | 2961.52 | 2980.83 | 3000.14 | 3018.7 | 3038.52 | 3058.33 | 3078.15 | 3097.19 | 3117.52 | 3137.85 | 3158.18 | 3177.71 | 3198.57 | 3219.43 | 3240.29 | 3260.34 | 3281.74 | 3303.14 | 3324.54 | 3345.1 | 3367.06 | 3389.02 | 3410.98 | 3432.08 | 3454.6 | 3477.13 | 3499.66 | 3521.31 | 3544.42 | 3567.54 | 3590.65 | 3612.86 | 3636.58 | 3660.29 | 3684.01 | 3706.8 | 3731.13 | 3755.46 | 3779.79 | 3803.18 | 3828.14 | 3853.1 | 3878.07 | 3902.06 | 3927.67 | 3953.28 | 3978.9 | 4003.51 | 4029.79 | 4056.07 | 4082.35 | 4107.6 | 4134.57 | 4161.53 | 4188.49 | 4214.4 | 4242.06 | 4269.73 | 4297.39 | 4323.98 | 4352.36 | 4380.74 | 4409.12 | 4436.4 | 4465.52 | 4494.64 | 4523.76 | 4551.75 | 4581.62 | 4611.5 | 4641.38 | 4670.09 | 4700.75 | 4731.4 | 4762.05 | 4791.51 | 4822.96 | 4854.42 | 4885.87 | 4916.09 | 4948.36 | 4980.63 | 5012.9 | 5043.91 | 5077.02 | 5110.13 | 5143.24 | 5175.05 | 5209.02 | 5242.99 | 5276.96 | 5309.6 | 5344.46 | 5379.31 | 5414.16 | 5447.65 | 5483.41 | 5519.17 | 5554.93 | 5589.29 | 5625.98 | 5662.67 | 5699.36 | 5734.61 | 5772.26 | 5809.9 | 5847.54 | 5883.71 | 5922.33 | 5960.96 | 5999.58 | 6036.69 | 6076.32 | 6115.94 | 6155.57 | 6193.64 | 6234.3 | 6274.95 | 6315.61 | 6354.68 | 6396.39 | 6438.1 | 6479.82 | 6519.9 | 6562.7 | 6605.49 | 6648.29 | 6689.42 | 6733.33 | 6777.24 | 6821.15 | 6863.34 | 6908.39 | 6953.45 | 6998.5 | 7041.79 | 7088.01 | 7134.23 | 7180.46 | 7224.88 | 7272.3 | 7319.72 | 7367.15 | 7412.72 | 7461.38 | 7510.04 | 7558.69 | 7605.45 | 7655.38 | 7705.3 | 7755.22 | 7803.2 | 7854.42 | 7905.64 | 7956.86 | 8006.08 | 8058.63 | 8111.18 | 8163.74 | 8214.24 | 8268.16 | 8322.07 | 8375.99
| Table 1 FY2 | https://www.publications.usace.army.mil/USACE-Publications/Engineer-Circulars/ |  |  |  | 13 | 09 | 13 | CHANNELS & CANALS | 3% | 265.64 | 270.82 | 281.65 | 287.98 | 293.61 | 301.38 | 313.41 | 317.89 | 325.51 | 328.36 | 339.24 | 340.71 | 342.1 | 343.64 | 348.71 | 349.82 | 350.85 | 352.53 | 357.12 | 357.17 | 356.12 | 357.8 | 359.39 | 359.65 | 360.57 | 362.65 | 364.2 | 364.3 | 367.72 | 369.39 | 374.27 | 375.45 | 378.91 | 381.47 | 386.02 | 387.57 | 394.41 | 397.56 | 404.46 | 406 | 408.91 | 412.18 | 419.85 | 421.37 | 423.64 | 426.24 | 429.12 | 429.87 | 432.46 | 436.45 | 440.83 | 441.51 | 444.91 | 448.13 | 451.04 | 451.92 | 455.98 | 459.44 | 460.96 | 462.02 | 464.74 | 469.56 | 473.89 | 474.38 | 478.3 | 482.06 | 485.4 | 485.86 | 488.99 | 492.02 | 493.05 | 494.6 | 500.35 | 503.18 | 504.72 | 505.95 | 509.67 | 515.79 | 519.24 | 519.75 | 522.7 | 525.67 | 528.21 | 530.31 | 533.17 | 533.64 | 537.32 | 539.98 | 543.14 | 552.98 | 556.82 | 557.3 | 562.22 | 565.12 | 566.01 | 568.24 | 574.07 | 580.55 | 589.71 | 593.18 | 602.74 | 606.87 | 617.59 | 621.31 | 634.12 | 639.7 | 643.34 | 650.07 | 658.19 | 666.22 | 672.31 | 674.92 | 679 | 687.99 | 696.83 | 700.63 | 708.75 | 714.03 | 722.16 | 718.6 | 726.21 | 727.34 | 738.67 | 740.12 | 745.5 | 752.01 | 763.2 | 769.05 | 779.45 | 787.23 | 792.32 | 796.23 | 804.86 | 806.09 | 816.37 | 817.99 | 825.51 | 827.5 | 833.72 | 834.66 | 843.99 | 845.53 | 854.33 | 855.68 | 863.89 | 865.14 | 875.09 | 874.05 | 879.83 | 882.78 | 890.06 | 891.49 | 877.6 | 882.34 | 891.7 | 915.14 | 925.43 | 929.79 | 943.11 | 943.71 | 951.95 | 957.07 | 958.35 | 960.53 | 971.15 | 985.61 | 1007.96 | 1028.67 | 1044.05 | 1069.86 | 1082.35 | 1106.27 | 1139.18 | 1147.24 | 1170.38 | 1176.06 | 1196.36 | 1200.66 | 1210.04 | 1218.21 | 1226.38 | 1234.54 | 1242.71 | 1255.21 | 1259.54 | 1267.81 | 1276.08 | 1284.34 | 1292.29 | 1300.77 | 1309.25 | 1317.74 | 1325.89 | 1334.59 | 1343.3 | 1352 | 1360.36 | 1369.29 | 1378.22 | 1387.15 | 1395.73 | 1404.89 | 1414.05 | 1423.22 | 1432.02 | 1441.42 | 1450.82 | 1460.22 | 1469.25 | 1478.9 | 1488.54 | 1498.19 | 1507.45 | 1517.35 | 1527.24 | 1537.14 | 1546.65 | 1556.8 | 1566.95 | 1577.1 | 1586.86 | 1597.28 | 1607.69 | 1618.11 | 1628.12 | 1638.81 | 1649.49 | 1660.18 | 1670.45 | 1681.41 | 1692.38 | 1703.34 | 1713.88 | 1725.13 | 1736.38 | 1747.63 | 1758.44 | 1769.98 | 1781.53 | 1793.07 | 1804.16 | 1816 | 1827.85 | 1839.69 | 1851.07 | 1863.22 | 1875.37 | 1887.52 | 1899.2 | 1911.66 | 1924.13 | 1936.6 | 1948.58 | 1961.37 | 1974.16 | 1986.95 | 1999.24 | 2012.36 | 2025.49 | 2038.61 | 2051.22 | 2064.68 | 2078.15 | 2091.61 | 2104.55 | 2118.37 | 2132.18 | 2145.99 | 2159.27 | 2173.44 | 2187.62 | 2201.79 | 2215.41 | 2229.95 | 2244.49 | 2259.04 | 2273.01 | 2287.93 | 2302.85 | 2317.77 | 2332.11 | 2347.42 | 2362.73 | 2378.03 | 2392.74 | 2408.45 | 2424.16 | 2439.86 | 2454.96 | 2471.07 | 2487.18 | 2503.3 | 2518.79 | 2535.32 | 2551.85 | 2568.39 | 2584.27 | 2601.24 | 2618.2 | 2635.16 | 2651.46 | 2668.87 | 2686.27 | 2703.68 | 2720.4 | 2738.26 | 2756.12 | 2773.97 | 2791.13 | 2809.45 | 2827.78 | 2846.1 | 2863.7 | 2882.5 | 2901.3 | 2920.09 | 2938.16 | 2957.45 | 2976.73 | 2996.02 | 3014.55 | 3034.34 | 3054.13 | 3073.91 | 3092.93 | 3113.23 | 3133.53 | 3153.84 | 3173.35 | 3194.18 | 3215.01 | 3235.84 | 3255.85 | 3277.22 | 3298.6 | 3319.97 | 3340.5 | 3362.43 | 3384.36 | 3406.29 | 3427.36 | 3449.86 | 3472.35 | 3494.85 | 3516.47 | 3539.55 | 3562.63 | 3585.72 | 3607.9 | 3631.58 | 3655.26 | 3678.94 | 3701.7 | 3726 | 3750.3 | 3774.6 | 3797.95 | 3822.88 | 3847.81 | 3872.74 | 3896.69 | 3922.27 | 3947.85 | 3973.43 | 3998.01 | 4024.25 | 4050.49 | 4076.74 | 4101.96 | 4128.88 | 4155.81 | 4182.73 | 4208.61 | 4236.23 | 4263.86 | 4291.48 | 4318.03 | 4346.37 | 4374.72 | 4403.06 | 4430.3 | 4459.38 | 4488.46 | 4517.54 | 4545.49 | 4575.32 | 4605.16 | 4635 | 4663.67 | 4694.28 | 4724.89 | 4755.51 | 4784.93 | 4816.33 | 4847.74 | 4879.15 | 4909.33 | 4941.56 | 4973.78 | 5006.01 | 5036.98 | 5070.04 | 5103.1 | 5136.16 | 5167.94 | 5201.86 | 5235.78 | 5269.7 | 5302.3 | 5337.11 | 5371.91 | 5406.72 | 5440.16 | 5475.87 | 5511.58 | 5547.29 | 5581.61 | 5618.25 | 5654.88 | 5691.52 | 5726.73 | 5764.32 | 5801.91 | 5839.5 | 5875.62 | 5914.19 | 5952.76 | 5991.33 | 6028.39 | 6067.96 | 6107.53 | 6147.1 | 6185.13 | 6225.73 | 6266.33 | 6306.93 | 6345.94 | 6387.6 | 6429.25 | 6470.91 | 6510.94 | 6553.67 | 6596.41 | 6639.15 | 6680.22 | 6724.07 | 6767.92 | 6811.77 | 6853.91 | 6898.9 | 6943.88 | 6988.87 | 7032.11 | 7078.27 | 7124.43 | 7170.58 | 7214.94 | 7262.3 | 7309.66 | 7357.02 | 7402.53 | 7451.12 | 7499.71 | 7548.3 | 7595 | 7644.85 | 7694.7 | 7744.56 | 7792.47 | 7843.62 | 7894.77 | 7945.92 | 7995.07 | 8047.55 | 8100.03 | 8152.51 | 8202.94 | 8256.79 | 8310.63 | 8364.48 | 8416.22 | 8471.46 | 8526.71 | 8581.95
[6 empty] | 14 | 10 | 14 | BREAKWATER & SEAWALLS | 5% | 268.87 | 275.43 | 284.94 | 291.47 | 297.87 | 307 | 317.48 | 322.03 | 329.54 | 332.77 | 341.4 | 342.84 | 344.42 | 346.28 | 350.15 | 351.06 | 351.96 | 353.84 | 357.66 | 357.81 | 360.2 | 360.88 | 362.49 | 363.08 | 364.15 | 366.12 | 367.26 | 367.48 | 371.39 | 372.87 | 376.57 | 377.7 | 381.39 | 383.48 | 387.91 | 389.42 | 399.19 | 402.23 | 408.93 | 410.56 | 416.23 | 418.83 | 426.15 | 427.58 | 431.75 | 434.02 | 436.95 | 437.42 | 440.32 | 444.65 | 449.52 | 450.14 | 453.92 | 457.1 | 459.86 | 459.59 | 464.97 | 467.37 | 469.13 | 470.36 | 473.69 | 477.42 | 480.99 | 481.23 | 486.3 | 489.3 | 492.45 | 493.39 | 497.41 | 499.61 | 500.41 | 501.47 | 508.28 | 510.27 | 511.29 | 512.16 | 515.93 | 520.56 | 523.14 | 523.68 | 526.04 | 526.7 | 528.42 | 530.28 | 533 | 532.9 | 535.39 | 537.42 | 539.67 | 551.63 | 554.03 | 554.89 | 560.3 | 563.87 | 564.09 | 566.98 | 572.43 | 579.15 | 587.47 | 594.67 | 603.21 | 607.88 | 618.82 | 622.23 | 633.85 | 640.07 | 642.8 | 647.89 | 654.97 | 660.82 | 666.4 | 668.25 | 672.17 | 679.9 | 689.75 | 696.2 | 704.84 | 708.1 | 714.7 | 707.23 | 714.39 | 715.35 | 722.61 | 723.34 | 730.49 | 737.82 | 747.94 | 753.93 | 757.76 | 764.47 | 768.52 | 772.18 | 782 | 784.6 | 792.86 | 792.77 | 800.38 | 802.68 | 807.76 | 806.83 | 818.17 | 818.72 | 824.48 | 824.1 | 831.82 | 831.91 | 838.22 | 837.49 | 842.48 | 844.31 | 849.56 | 850.53 | 836.69 | 841.08 | 848.92 | 874.05 | 883.72 | 886.87 | 896.39 | 897.36 | 905 | 908.51 | 908.8 | 910.87 | 923.38 | 933.83 | 954.45 | 979.48 | 992.88 | 1022.1 | 1033.68 | 1059.88 | 1091.38 | 1099.18 | 1120.44 | 1123.69 | 1140.73 | 1144.23 | 1151.46 | 1159.23 | 1167 | 1174.78 | 1182.55 | 1194.44 | 1198.56 | 1206.43 | 1214.3 | 1222.17 | 1229.73 | 1237.8 | 1245.87 | 1253.94 | 1261.7 | 1269.98 | 1278.26 | 1286.55 | 1294.5 | 1303 | 1311.5 | 1320 | 1328.16 | 1336.88 | 1345.6 | 1354.32 | 1362.69 | 1371.64 | 1380.58 | 1389.53 | 1398.12 | 1407.3 | 1416.48 | 1425.66 | 1434.48 | 1443.89 | 1453.31 | 1462.72 | 1471.77 | 1481.43 | 1491.09 | 1500.75 | 1510.04 | 1519.95 | 1529.86 | 1539.77 | 1549.3 | 1559.47 | 1569.64 | 1579.81 | 1589.58 | 1600.01 | 1610.45 | 1620.88 | 1630.91 | 1641.61 | 1652.32 | 1663.03 | 1673.31 | 1684.3 | 1695.28 | 1706.26 | 1716.82 | 1728.09 | 1739.36 | 1750.63 | 1761.46 | 1773.02 | 1784.58 | 1796.14 | 1807.25 | 1819.12 | 1830.98 | 1842.84 | 1854.24 | 1866.41 | 1878.59 | 1890.76 | 1902.45 | 1914.94 | 1927.43 | 1939.92 | 1951.92 | 1964.73 | 1977.54 | 1990.35 | 2002.67 | 2015.81 | 2028.96 | 2042.1 | 2054.74 | 2068.22 | 2081.71 | 2095.2 | 2108.16 | 2122 | 2135.84 | 2149.67 | 2162.97 | 2177.17 | 2191.37 | 2205.56 | 2219.21 | 2233.78 | 2248.34 | 2262.91 | 2276.91 | 2291.85 | 2306.8 | 2321.75 | 2336.11 | 2351.44 | 2366.78 | 2382.11 | 2396.85 | 2412.58 | 2428.31 | 2444.05 | 2459.16 | 2475.31 | 2491.45 | 2507.59 | 2523.1 | 2539.66 | 2556.23 | 2572.79 | 2588.7 | 2605.7 | 2622.69 | 2639.68 | 2656.01 | 2673.44 | 2690.88 | 2708.31 | 2725.07 | 2742.95 | 2760.84 | 2778.73 | 2795.92 | 2814.27 | 2832.62 | 2850.98 | 2868.61 | 2887.44 | 2906.27 | 2925.1 | 2943.2 | 2962.51 | 2981.83 | 3001.15 | 3019.72 | 3039.54 | 3059.36 | 3079.18 | 3098.23 | 3118.57 | 3138.91 | 3159.24 | 3178.79 | 3199.65 | 3220.52 | 3241.38 | 3261.43 | 3282.84 | 3304.25 | 3325.66 | 3346.23 | 3368.2 | 3390.16 | 3412.13 | 3433.23 | 3455.77 | 3478.3 | 3500.84 | 3522.5 | 3545.62 | 3568.74 | 3591.86 | 3614.08 | 3637.81 | 3661.53 | 3685.25 | 3708.05 | 3732.39 | 3756.73 | 3781.07 | 3804.46 | 3829.43 | 3854.4 | 3879.37 | 3903.37 | 3929 | 3954.62 | 3980.24 | 4004.86 | 4031.15 | 4057.44 | 4083.72 | 4108.99 | 4135.96 | 4162.93 | 4189.9 | 4215.82 | 4243.49 | 4271.17 | 4298.84 | 4325.43 | 4353.82 | 4382.22 | 4410.61 | 4437.89 | 4467.02 | 4496.15 | 4525.28 | 4553.28 | 4583.17 | 4613.05 | 4642.94 | 4671.66 | 4702.33 | 4732.99 | 4763.66 | 4793.13 | 4824.59 | 4856.05 | 4887.51 | 4917.75 | 4950.03 | 4982.31 | 5014.59 | 5045.61 | 5078.73 | 5111.85 | 5144.97 | 5176.8 | 5210.78 | 5244.76 | 5278.74 | 5311.39 | 5346.26 | 5381.12 | 5415.98 | 5449.49 | 5485.26 | 5521.03 | 5556.8 | 5591.18 | 5627.88 | 5664.58 | 5701.28 | 5736.55 | 5774.2 | 5811.86 | 5849.51 | 5885.7 | 5924.33 | 5962.96 | 6001.6 | 6038.72 | 6078.36 | 6118 | 6157.64 | 6195.73 | 6236.4 | 6277.07 | 6317.74 | 6356.82 | 6398.55 | 6440.27 | 6482 | 6522.1 | 6564.91 | 6607.72 | 6650.53 | 6691.67 | 6735.6 | 6779.52 | 6823.44 | 6865.66 | 6910.72 | 6955.79 | 7000.85 | 7044.16 | 7090.4 | 7136.64 | 7182.88 | 7227.31 | 7274.75 | 7322.19 | 7369.63 | 7415.22 | 7463.89 | 7512.57 | 7561.24 | 7608.02 | 7657.96 | 7707.9 | 7757.83 | 7805.83 | 7857.06 | 7908.3 | 7959.54 | 8008.78 | 8061.35 | 8113.92 | 8166.49
[6 empty] | 15 | 11 | 15 | LEVEES & FLOODWALLS | 5% | 270.52 | 275.78 | 285.6 | 291.08 | 296.16 | 303.75 | 315.68 | 320.28 | 326.15 | 328.53 | 339.43 | 340.6 | 341.33 | 343.87 | 349.13 | 350.51 | 351.28 | 353.23 | 357.74 | 357.71 | 357.94 | 359.12 | 360.8 | 360.91 | 360.26 | 362.26 | 363.58 | 363.91 | 366.29 | 368.16 | 372.27 | 374.39 | 378.8 | 382.73 | 386.7 | 388.36 | 394.83 | 398.49 | 402.75 | 404 | 405.46 | 408.36 | 414.01 | 415.03 | 417.23 | 419.02 | 421.7 | 422.01 | 424.47 | 428.96 | 433.01 | 433.35 | 436.37 | 441.4 | 444.14 | 445.43 | 449.93 | 453.36 | 455.18 | 456.83 | 460.62 | 466.66 | 471.12 | 471.24 | 473.49 | 476.42 | 480.07 | 480.75 | 482.63 | 485.59 | 487.37 | 489.24 | 493.85 | 496.31 | 497.18 | 496.64 | 497.88 | 502.33 | 506.75 | 506.45 | 509.22 | 512.18 | 514.03 | 515.05 | 516.54 | 516.31 | 519.93 | 521.86 | 523.8 | 536.25 | 541.49 | 541.59 | 545.36 | 549.52 | 550.19 | 554.42 | 563.84 | 582.42 | 594.09 | 607.65 | 615.61 | 618 | 623.58 | 630.33 | 644.64 | 651.23 | 658.68 | 666.93 | 669.92 | 687.06 | 693.47 | 691.82 | 697.52 | 714.17 | 739.43 | 737.4 | 721.64 | 712.69 | 718.95 | 719.93 | 726.98 | 735.23 | 744.32 | 745.35 | 753.7 | 767.06 | 776.75 | 779.51 | 785.64 | 789.19 | 790.48 | 790.25 | 798.03 | 800.91 | 806.93 | 807.9 | 814.93 | 818.17 | 824.49 | 824.81 | 829.76 | 825.49 | 830.81 | 827.98 | 829 | 830.77 | 843.12 | 841.09 | 847.11 | 853.8 | 862.71 | 863.98 | 854.63 | 864.74 | 877.35 | 898.23 | 906.43 | 909.95 | 914.36 | 912.39 | 916.23 | 919.83 | 920.57 | 923.99 | 941.65 | 976.27 | 1011.76 | 1044.11 | 1071.77 | 1098.56 | 1110.59 | 1116.15 | 1132.2 | 1144.19 | 1163.12 | 1163.16 | 1174.39 | 1176.07 | 1176.49 | 1184.43 | 1192.37 | 1200.31 | 1208.26 | 1220.41 | 1224.62 | 1232.66 | 1240.7 | 1248.73 | 1256.46 | 1264.71 | 1272.95 | 1281.2 | 1289.13 | 1297.59 | 1306.05 | 1314.51 | 1322.64 | 1331.33 | 1340.01 | 1348.69 | 1357.03 | 1365.94 | 1374.85 | 1383.76 | 1392.32 | 1401.45 | 1410.59 | 1419.73 | 1428.52 | 1437.89 | 1447.27 | 1456.65 | 1465.66 | 1475.28 | 1484.9 | 1494.52 | 1503.76 | 1513.64 | 1523.51 | 1533.38 | 1542.86 | 1552.99 | 1563.12 | 1573.24 | 1582.98 | 1593.37 | 1603.76 | 1614.15 | 1624.13 | 1634.79 | 1645.46 | 1656.12 | 1666.36 | 1677.3 | 1688.24 | 1699.18 | 1709.69 | 1720.91 | 1732.13 | 1743.35 | 1754.14 | 1765.65 | 1777.17 | 1788.68 | 1799.75 | 1811.56 | 1823.37 | 1835.19 | 1846.54 | 1858.66 | 1870.78 | 1882.9 | 1894.55 | 1906.99 | 1919.42 | 1931.86 | 1943.81 | 1956.57 | 1969.33 | 1982.09 | 1994.35 | 2007.44 | 2020.53 | 2033.62 | 2046.2 | 2059.63 | 2073.06 | 2086.49 | 2099.4 | 2113.18 | 2126.96 | 2140.74 | 2153.99 | 2168.12 | 2182.26 | 2196.4 | 2209.99 | 2224.5 | 2239 | 2253.51 | 2267.45 | 2282.33 | 2297.22 | 2312.1 | 2326.4 | 2341.67 | 2356.94 | 2372.21 | 2386.89 | 2402.56 | 2418.22 | 2433.89 | 2448.95 | 2465.02 | 2481.1 | 2497.17 | 2512.62 | 2529.11 | 2545.61 | 2562.1 | 2577.95 | 2594.87 | 2611.79 | 2628.71 | 2644.98 | 2662.34 | 2679.7 | 2697.06 | 2713.75 | 2731.56 | 2749.37 | 2767.18 | 2784.3 | 2802.58 | 2820.85 | 2839.13 | 2856.69 | 2875.45 | 2894.2 | 2912.95 | 2930.97 | 2950.21 | 2969.45 | 2988.69 | 3007.17 | 3026.91 | 3046.65 | 3066.39 | 3085.36 | 3105.61 | 3125.86 | 3146.12 | 3165.58 | 3186.36 | 3207.14 | 3227.92 | 3247.88 | 3269.2 | 3290.52 | 3311.84 | 3332.33 | 3354.2 | 3376.08 | 3397.95 | 3418.97 | 3441.41 | 3463.85 | 3486.3 | 3507.86 | 3530.89 | 3553.91 | 3576.94 | 3599.07 | 3622.69 | 3646.32 | 3669.94 | 3692.64 | 3716.88 | 3741.12 | 3765.36 | 3788.65 | 3813.52 | 3838.39 | 3863.26 | 3887.16 | 3912.67 | 3938.19 | 3963.7 | 3988.22 | 4014.4 | 4040.58 | 4066.76 | 4091.92 | 4118.78 | 4145.64 | 4172.5 | 4198.31 | 4225.86 | 4253.42 | 4280.98 | 4307.46 | 4335.74 | 4364.01 | 4392.29 | 4419.46 | 4448.47 | 4477.48 | 4506.49 | 4534.36 | 4564.13 | 4593.89 | 4623.65 | 4652.26 | 4682.79 | 4713.33 | 4743.87 | 4773.22 | 4804.55 | 4835.88 | 4867.21 | 4897.32 | 4929.46 | 4961.61 | 4993.76 | 5024.65 | 5057.63 | 5090.61 | 5123.59 | 5155.29 | 5189.13 | 5222.97 | 5256.81 | 5289.33 | 5324.05 | 5358.77 | 5393.48 | 5426.85 | 5462.47 | 5498.09 | 5533.72 | 5567.95 | 5604.5 | 5641.04 | 5677.59 | 5712.71 | 5750.21 | 5787.71 | 5825.21 | 5861.25 | 5899.72 | 5938.19 | 5976.67 | 6013.64 | 6053.11 | 6092.58 | 6132.06 | 6169.99 | 6210.49 | 6250.99 | 6291.49 | 6330.41 | 6371.96 | 6413.52 | 6455.07 | 6495 | 6537.64 | 6580.27 | 6622.9 | 6663.87 | 6707.61 | 6751.36 | 6795.1 | 6837.13 | 6882.01 | 6926.89 | 6971.77 | 7014.9 | 7060.94 | 7106.99 | 7153.04 | 7197.29 | 7244.53 | 7291.77 | 7339.02 | 7384.42 | 7432.89 | 7481.36 | 7529.83 | 7576.41 | 7626.14 | 7675.87 | 7725.61 | 7773.4 | 7824.42 | 7875.45 | 7926.47 | 7975.51 | 8027.86 | 8080.21 | 8132.56 | 8182.87 | 8236.58 | 8290.29 | 8344.01
[6 empty] | 16 | 12 | 16 | NAVIGATION PORTS & HARBORS | 10% | 296.3 | 313.31 | 320.93 | 319.65 | 330.51 | 349.87 | 353.82 | 359.31 | 366.59 | 368.34 | 376.27 | 376.98 | 380.06 | 363.25 | 364.66 | 368.73 | 373.05 | 379.74 | 381.11 | 385.87 | 385.63 | 374.08 | 376.9 | 371.31 | 372.96 | 368.74 | 374.47 | 365.23 | 360.11 | 354.3 | 355.95 | 366.15 | 366.8 | 368.08 | 366.12 | 371.23 | 374.55 | 379.56 | 381.82 | 389.13 | 390.24 | 388.71 | 385.42 | 423.17 | 409.44 | 394.25 | 398.68 | 406.79 | 402.75 | 404.05 | 409.82 | 414.28 | 415.43 | 419.76 | 419.6 | 421.51 | 416.32 | 421.58 | 422.01 | 431 | 429.5 | 437.84 | 436.89 | 434.34 | 439.35 | 449.73 | 446.82 | 469.89 | 465.98 | 463.12 | 458.42 | 465.36 | 459.69 | 457.07 | 454.85 | 458.59 | 455.42 | 459.42 | 466.91 | 480.03 | 485.6 | 495.16 | 501.01 | 519.15 | 512.19 | 502.64 | 505.06 | 499.47 | 491.92 | 502.81 | 509.07 | 521.2 | 525.66 | 527.04 | 524.41 | 529.19 | 537.22 | 562.46 | 569.88 | 608.44 | 592.73 | 617.25 | 632.02 | 688.11 | 649.53 | 675.74 | 683.98 | 688.3 | 692.6 | 696.34 | 706.31 | 713.66 | 738.66 | 791.33 | 844.82 | 767.18 | 693.15 | 698.1 | 700.97 | 721.64 | 735.18 | 744.79 | 739.8 | 759.65 | 775.94 | 824.07 | 820.39 | 813.49 | 818.43 | 834.42 | 811.06 | 847.13 | 827.74 | 829.45 | 829.74 | 843.32 | 838.49 | 848.4 | 845.17 | 832.72 | 774.14 | 775.5 | 786.88 | 778.77 | 744.87 | 753.77 | 777.12 | 781.16 | 789.3 | 796.59 | 812.6 | 836.56 | 850.24 | 855.82 | 882.24 | 894.76 | 852.58 | 877.57 | 870.61 | 872.39 | 870.01 | 813.87 | 846.89 | 857.47 | 888.81 | 929.81 | 978.19 | 1023.54 | 1030.78 | 1149.59 | 1199.98 | 1225.37 | 1131.28 | 1095.47 | 1067.62 | 1126.29 | 1076.96 | 1121.83 | 1132 | 1132 | 1147.28 | 1154.92 | 1162.56 | 1166.38 | 1176.31 | 1184.03 | 1191.75 | 1199.47 | 1206.89 | 1214.82 | 1222.74 | 1230.66 | 1238.27 | 1246.4 | 1254.53 | 1262.66 | 1270.47 | 1278.81 | 1287.15 | 1295.49 | 1303.5 | 1312.06 | 1320.61 | 1329.17 | 1337.39 | 1346.17 | 1354.95 | 1363.73 | 1372.16 | 1381.17 | 1390.18 | 1399.18 | 1407.84 | 1417.08 | 1426.32 | 1435.56 | 1444.44 | 1453.92 | 1463.41 | 1472.89 | 1482 | 1491.73 | 1501.45 | 1511.18 | 1520.53 | 1530.51 | 1540.49 | 1550.47 | 1560.06 | 1570.3 | 1580.54 | 1590.78 | 1600.63 | 1611.13 | 1621.64 | 1632.14 | 1642.24 | 1653.02 | 1663.8 | 1674.58 | 1684.94 | 1696 | 1707.06 | 1718.12 | 1728.75 | 1740.1 | 1751.44 | 1762.79 | 1773.7 | 1785.34 | 1796.98 | 1808.62 | 1819.81 | 1831.76 | 1843.7 | 1855.65 | 1867.13 | 1879.38 | 1891.64 | 1903.89 | 1915.67 | 1928.25 | 1940.82 | 1953.4 | 1965.48 | 1978.38 | 1991.28 | 2004.18 | 2016.58 | 2029.82 | 2043.06 | 2056.29 | 2069.01 | 2082.59 | 2096.18 | 2109.76 | 2122.81 | 2136.74 | 2150.68 | 2164.61 | 2178 | 2192.3 | 2206.59 | 2220.89 | 2234.63 | 2249.3 | 2263.97 | 2278.63 | 2292.73 | 2307.78 | 2322.83 | 2337.88 | 2352.34 | 2367.78 | 2383.22 | 2398.66 | 2413.5 | 2429.34 | 2445.19 | 2461.03 | 2476.25 | 2492.51 | 2508.76 | 2525.01 | 2540.63 | 2557.31 | 2573.99 | 2590.66 | 2606.69 | 2623.8 | 2640.91 | 2658.02 | 2674.47 | 2692.02 | 2709.58 | 2727.13 | 2744 | 2762.01 | 2780.02 | 2798.04 | 2815.35 | 2833.83 | 2852.31 | 2870.79 | 2888.54 | 2907.5 | 2926.47 | 2945.43 | 2963.65 | 2983.1 | 3002.55 | 3022.01 | 3040.7 | 3060.66 | 3080.62 | 3100.58 | 3119.76 | 3140.24 | 3160.72 | 3181.19 | 3200.87 | 3221.88 | 3242.89 | 3263.9 | 3284.1 | 3305.65 | 3327.21 | 3348.77 | 3369.48 | 3391.6 | 3413.72 | 3435.83 | 3457.09 | 3479.78 | 3502.47 | 3525.17 | 3546.97 | 3570.26 | 3593.54 | 3616.82 | 3639.19 | 3663.08 | 3686.97 | 3710.86 | 3733.81 | 3758.32 | 3782.83 | 3807.34 | 3830.89 | 3856.04 | 3881.18 | 3906.33 | 3930.5 | 3956.3 | 3982.1 | 4007.9 | 4032.69 | 4059.16 | 4085.63 | 4112.1 | 4137.54 | 4164.7 | 4191.86 | 4219.02 | 4245.11 | 4272.98 | 4300.84 | 4328.71 | 4355.49 | 4384.08 | 4412.67 | 4441.26 | 4468.73 | 4498.06 | 4527.4 | 4556.73 | 4584.92 | 4615.01 | 4645.11 | 4675.2 | 4704.13 | 4735 | 4765.88 | 4796.76 | 4826.43 | 4858.11 | 4889.79 | 4921.47 | 4951.92 | 4984.42 | 5016.93 | 5049.43 | 5080.67 | 5114.02 | 5147.37 | 5180.72 | 5212.77 | 5246.98 | 5281.2 | 5315.42 | 5348.3 | 5383.41 | 5418.51 | 5453.62 | 5487.35 | 5523.37 | 5559.39 | 5595.41 | 5630.03 | 5666.98 | 5703.94 | 5740.89 | 5776.41 | 5814.32 | 5852.24 | 5890.16 | 5926.59 | 5965.5 | 6004.4 | 6043.3 | 6080.68 | 6120.6 | 6160.51 | 6200.43 | 6238.78 | 6279.73 | 6320.69 | 6361.64 | 6400.99 | 6443.01 | 6485.02 | 6527.04 | 6567.42 | 6610.53 | 6653.63 | 6696.74 | 6738.17 | 6782.4 | 6826.63 | 6870.86 | 6913.36 | 6958.74 | 7004.12 | 7049.5 | 7093.11 | 7139.67 | 7186.23 | 7232.79 | 7277.53 | 7325.3 | 7373.07 | 7420.84 | 7466.75 | 7515.76 | 7564.77 | 7613.78 | 7660.88 | 7711.17 | 7761.45 | 7811.74 | 7860.06 | 7911.66 | 7963.25 | 8014.84
[6 empty] | 17 | 13 | 17 | PUMPING PLANT | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1155 | 1162.8 | 1170.59 | 1178.39 | 1186.19 | 1198.12 | 1202.25 | 1210.14 | 1218.03 | 1225.92 | 1233.51 | 1241.6 | 1249.7 | 1257.8 | 1265.58 | 1273.89 | 1282.19 | 1290.5 | 1298.48 | 1307.01 | 1315.53 | 1324.05 | 1332.24 | 1340.99 | 1349.73 | 1358.48 | 1366.88 | 1375.86 | 1384.83 | 1393.8 | 1402.42 | 1411.63 | 1420.83 | 1430.04 | 1438.89 | 1448.33 | 1457.77 | 1467.22 | 1476.3 | 1485.99 | 1495.68 | 1505.37 | 1514.68 | 1524.62 | 1534.56 | 1544.51 | 1554.06 | 1564.26 | 1574.46 | 1584.66 | 1594.47 | 1604.93 | 1615.4 | 1625.87 | 1635.92 | 1646.66 | 1657.4 | 1668.14 | 1678.46 | 1689.47 | 1700.49 | 1711.51 | 1722.1 | 1733.4 | 1744.71 | 1756.01 | 1766.87 | 1778.47 | 1790.07 | 1801.67 | 1812.81 | 1824.71 | 1836.61 | 1848.51 | 1859.94 | 1872.15 | 1884.36 | 1896.57 | 1908.3 | 1920.83 | 1933.35 | 1945.88 | 1957.92 | 1970.77 | 1983.62 | 1996.47 | 2008.82 | 2022.01 | 2035.2 | 2048.38 | 2061.05 | 2074.58 | 2088.11 | 2101.64 | 2114.64 | 2128.52 | 2142.4 | 2156.28 | 2169.62 | 2183.86 | 2198.1 | 2212.35 | 2226.03 | 2240.64 | 2255.25 | 2269.87 | 2283.91 | 2298.9 | 2313.89 | 2328.88 | 2343.29 | 2358.67 | 2374.05 | 2389.43 | 2404.22 | 2420 | 2435.78 | 2451.56 | 2466.73 | 2482.92 | 2499.11 | 2515.3 | 2530.86 | 2547.47 | 2564.09 | 2580.7 | 2596.66 | 2613.71 | 2630.75 | 2647.8 | 2664.18 | 2681.66 | 2699.15 | 2716.64 | 2733.44 | 2751.39 | 2769.33 | 2787.27 | 2804.51 | 2822.92 | 2841.33 | 2859.74 | 2877.43 | 2896.32 | 2915.21 | 2934.09 | 2952.24 | 2971.62 | 2991 | 3010.38 | 3029 | 3048.88 | 3068.77 | 3088.65 | 3107.76 | 3128.16 | 3148.56 | 3168.95 | 3188.56 | 3209.49 | 3230.42 | 3251.35 | 3271.46 | 3292.93 | 3314.41 | 3335.88 | 3356.52 | 3378.55 | 3400.58 | 3422.62 | 3443.79 | 3466.39 | 3489 | 3511.6 | 3533.33 | 3556.52 | 3579.71 | 3602.9 | 3625.19 | 3648.99 | 3672.78 | 3696.58 | 3719.45 | 3743.86 | 3768.28 | 3792.69 | 3816.15 | 3841.2 | 3866.25 | 3891.3 | 3915.37 | 3941.07 | 3966.77 | 3992.48 | 4017.17 | 4043.54 | 4069.91 | 4096.28 | 4121.62 | 4148.67 | 4175.73 | 4202.78 | 4228.78 | 4256.54 | 4284.3 | 4312.06 | 4338.73 | 4367.21 | 4395.69 | 4424.17 | 4451.54 | 4480.76 | 4509.98 | 4539.2 | 4567.28 | 4597.26 | 4627.24 | 4657.22 | 4686.03 | 4716.79 | 4747.54 | 4778.3 | 4807.86 | 4839.42 | 4870.98 | 4902.54 | 4932.87 | 4965.25 | 4997.63 | 5030.01 | 5061.12 | 5094.34 | 5127.56 | 5160.79 | 5192.71 | 5226.8 | 5260.88 | 5294.97 | 5327.72 | 5362.69 | 5397.66 | 5432.64 | 5466.24 | 5502.12 | 5538 | 5573.88 | 5608.37 | 5645.18 | 5681.99 | 5718.81 | 5754.18 | 5791.95 | 5829.72 | 5867.49 | 5903.79 | 5942.54 | 5981.3 | 6020.05 | 6057.29 | 6097.05 | 6136.81 | 6176.57 | 6214.78 | 6255.57 | 6296.37 | 6337.16 | 6376.36 | 6418.22 | 6460.07 | 6501.93 | 6542.15 | 6585.09 | 6628.03 | 6670.98 | 6712.25 | 6756.3 | 6800.36 | 6844.42 | 6886.76 | 6931.97 | 6977.17 | 7022.38 | 7065.82 | 7112.2 | 7158.58 | 7204.96 | 7249.53 | 7297.12 | 7344.7 | 7392.29 | 7438.02 | 7486.84 | 7535.66 | 7584.49 | 7631.41 | 7681.5 | 7731.59 | 7781.68 | 7829.82 | 7881.22 | 7932.61 | 7984.01 | 8033.4 | 8086.13 | 8138.86 | 8191.59
| CWCCIS EM1110-2-1304 updates occur twice yearly on 31 March and 30 September. |  |  |  |  | 18 | 14 | 18 | RECREATION FACILITIES | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1155 | 1162.8 | 1170.59 | 1178.39 | 1186.19 | 1198.12 | 1202.25 | 1210.14 | 1218.03 | 1225.92 | 1233.51 | 1241.6 | 1249.7 | 1257.8 | 1265.58 | 1273.89 | 1282.19 | 1290.5 | 1298.48 | 1307.01 | 1315.53 | 1324.05 | 1332.24 | 1340.99 | 1349.73 | 1358.48 | 1366.88 | 1375.86 | 1384.83 | 1393.8 | 1402.42 | 1411.63 | 1420.83 | 1430.04 | 1438.89 | 1448.33 | 1457.77 | 1467.22 | 1476.3 | 1485.99 | 1495.68 | 1505.37 | 1514.68 | 1524.62 | 1534.56 | 1544.51 | 1554.06 | 1564.26 | 1574.46 | 1584.66 | 1594.47 | 1604.93 | 1615.4 | 1625.87 | 1635.92 | 1646.66 | 1657.4 | 1668.14 | 1678.46 | 1689.47 | 1700.49 | 1711.51 | 1722.1 | 1733.4 | 1744.71 | 1756.01 | 1766.87 | 1778.47 | 1790.07 | 1801.67 | 1812.81 | 1824.71 | 1836.61 | 1848.51 | 1859.94 | 1872.15 | 1884.36 | 1896.57 | 1908.3 | 1920.83 | 1933.35 | 1945.88 | 1957.92 | 1970.77 | 1983.62 | 1996.47 | 2008.82 | 2022.01 | 2035.2 | 2048.38 | 2061.05 | 2074.58 | 2088.11 | 2101.64 | 2114.64 | 2128.52 | 2142.4 | 2156.28 | 2169.62 | 2183.86 | 2198.1 | 2212.35 | 2226.03 | 2240.64 | 2255.25 | 2269.87 | 2283.91 | 2298.9 | 2313.89 | 2328.88 | 2343.29 | 2358.67 | 2374.05 | 2389.43 | 2404.22 | 2420 | 2435.78 | 2451.56 | 2466.73 | 2482.92 | 2499.11 | 2515.3 | 2530.86 | 2547.47 | 2564.09 | 2580.7 | 2596.66 | 2613.71 | 2630.75 | 2647.8 | 2664.18 | 2681.66 | 2699.15 | 2716.64 | 2733.44 | 2751.39 | 2769.33 | 2787.27 | 2804.51 | 2822.92 | 2841.33 | 2859.74 | 2877.43 | 2896.32 | 2915.21 | 2934.09 | 2952.24 | 2971.62 | 2991 | 3010.38 | 3029 | 3048.88 | 3068.77 | 3088.65 | 3107.76 | 3128.16 | 3148.56 | 3168.95 | 3188.56 | 3209.49 | 3230.42 | 3251.35 | 3271.46 | 3292.93 | 3314.41 | 3335.88 | 3356.52 | 3378.55 | 3400.58 | 3422.62 | 3443.79 | 3466.39 | 3489 | 3511.6 | 3533.33 | 3556.52 | 3579.71 | 3602.9 | 3625.19 | 3648.99 | 3672.78 | 3696.58 | 3719.45 | 3743.86 | 3768.28 | 3792.69 | 3816.15 | 3841.2 | 3866.25 | 3891.3 | 3915.37 | 3941.07 | 3966.77 | 3992.48 | 4017.17 | 4043.54 | 4069.91 | 4096.28 | 4121.62 | 4148.67 | 4175.73 | 4202.78 | 4228.78 | 4256.54 | 4284.3 | 4312.06 | 4338.73 | 4367.21 | 4395.69 | 4424.17 | 4451.54 | 4480.76 | 4509.98 | 4539.2 | 4567.28 | 4597.26 | 4627.24 | 4657.22 | 4686.03 | 4716.79 | 4747.54 | 4778.3 | 4807.86 | 4839.42 | 4870.98 | 4902.54 | 4932.87 | 4965.25 | 4997.63 | 5030.01 | 5061.12 | 5094.34 | 5127.56 | 5160.79 | 5192.71 | 5226.8 | 5260.88 | 5294.97 | 5327.72 | 5362.69 | 5397.66 | 5432.64 | 5466.24 | 5502.12 | 5538 | 5573.88 | 5608.37 | 5645.18 | 5681.99 | 5718.81 | 5754.18 | 5791.95 | 5829.72 | 5867.49 | 5903.79 | 5942.54 | 5981.3 | 6020.05 | 6057.29 | 6097.05 | 6136.81 | 6176.57 | 6214.78 | 6255.57 | 6296.37 | 6337.16 | 6376.36 | 6418.22 | 6460.07 | 6501.93 | 6542.15 | 6585.09 | 6628.03 | 6670.98 | 6712.25 | 6756.3 | 6800.36 | 6844.42 | 6886.76 | 6931.97 | 6977.17 | 7022.38 | 7065.82 | 7112.2 | 7158.58 | 7204.96 | 7249.53 | 7297.12 | 7344.7 | 7392.29 | 7438.02 | 7486.84 | 7535.66 | 7584.49 | 7631.41 | 7681.5 | 7731.59 | 7781.68 | 7829.82 | 7881.22 | 7932.61 | 7984.01 | 8033.4 | 8086.13 | 8138.86 | 8191.59
| Feature codes 02 to 20 and Composite index reflect the indices in the 30 September 2024 EM1110-2-1304 CWCCIS |  |  |  |  | 19 | 15 | 19 | FLOODWAY CONTROL & DIVERSION STRUCTURE | 2% | 272.96 | 276.04 | 284.61 | 287.69 | 293.79 | 300 | 309.83 | 312.44 | 317.17 | 318.26 | 327.74 | 327.83 | 327.53 | 329.77 | 336.78 | 337.58 | 337.59 | 341.9 | 345.41 | 344.61 | 344.74 | 346.93 | 349.22 | 347.84 | 347.27 | 349.61 | 349.34 | 349.75 | 350.28 | 352.65 | 356.54 | 359.07 | 362.38 | 367.09 | 370.86 | 371.49 | 374.97 | 379.49 | 382.47 | 382.81 | 382.1 | 385.48 | 388.93 | 389.01 | 391.31 | 393.28 | 396.94 | 395.33 | 398.09 | 402.68 | 403.56 | 403.94 | 409.21 | 419.09 | 417.86 | 421.18 | 427.15 | 429.69 | 432.59 | 434.12 | 438.14 | 444.64 | 447.98 | 447.96 | 447.8 | 452.65 | 457.78 | 459.09 | 461.23 | 466.4 | 468.57 | 468.4 | 469.97 | 474.07 | 474.38 | 472.57 | 474.86 | 480.31 | 487.47 | 483.86 | 487.08 | 489.21 | 489.75 | 489.55 | 490.33 | 491.91 | 496.69 | 497.31 | 499.28 | 508.67 | 514.07 | 513.82 | 514.15 | 516.87 | 520.35 | 525.69 | 534.75 | 558.9 | 571.55 | 586.56 | 593.35 | 597.76 | 600.97 | 608.18 | 624.32 | 630.14 | 636.39 | 645.47 | 649.01 | 668.79 | 674.11 | 671.55 | 675.58 | 693.72 | 722.13 | 719.86 | 698.29 | 686.42 | 689.95 | 691.34 | 696.93 | 707.21 | 712.33 | 711.42 | 718.73 | 732.94 | 740.7 | 740.08 | 744.72 | 749.69 | 749.6 | 749.46 | 758.43 | 764.29 | 764.9 | 766.75 | 774.03 | 779.64 | 785.65 | 786.93 | 792.02 | 788.66 | 793.12 | 788.51 | 790.9 | 795.09 | 807.3 | 804.64 | 811.91 | 823.16 | 831.76 | 834.07 | 833.09 | 846.58 | 860.94 | 867.95 | 873.73 | 878.35 | 881.63 | 877.83 | 880.38 | 883.42 | 890.83 | 904.43 | 925.56 | 974.85 | 1002.62 | 1025.12 | 1078.05 | 1100.62 | 1105.63 | 1100.49 | 1108.19 | 1122.28 | 1134.8 | 1132.27 | 1144.9 | 1147.14 | 1152 | 1159.78 | 1167.55 | 1175.33 | 1183.1 | 1195 | 1199.13 | 1207 | 1214.87 | 1222.74 | 1230.3 | 1238.38 | 1246.46 | 1254.53 | 1262.29 | 1270.58 | 1278.86 | 1287.15 | 1295.11 | 1303.61 | 1312.11 | 1320.62 | 1328.78 | 1337.51 | 1346.23 | 1354.95 | 1363.33 | 1372.28 | 1381.23 | 1390.18 | 1398.78 | 1407.96 | 1417.14 | 1426.32 | 1435.15 | 1444.57 | 1453.99 | 1463.41 | 1472.46 | 1482.13 | 1491.79 | 1501.46 | 1510.75 | 1520.66 | 1530.58 | 1540.5 | 1550.03 | 1560.2 | 1570.37 | 1580.55 | 1590.33 | 1600.76 | 1611.2 | 1621.64 | 1631.67 | 1642.38 | 1653.09 | 1663.81 | 1674.1 | 1685.09 | 1696.08 | 1707.06 | 1717.62 | 1728.9 | 1740.17 | 1751.45 | 1762.28 | 1773.85 | 1785.42 | 1796.99 | 1808.1 | 1819.97 | 1831.84 | 1843.71 | 1855.11 | 1867.29 | 1879.47 | 1891.64 | 1903.35 | 1915.84 | 1928.33 | 1940.83 | 1952.83 | 1965.65 | 1978.47 | 1991.29 | 2003.61 | 2016.76 | 2029.91 | 2043.06 | 2055.7 | 2069.19 | 2082.69 | 2096.18 | 2109.15 | 2122.99 | 2136.84 | 2150.68 | 2163.99 | 2178.19 | 2192.39 | 2206.6 | 2220.25 | 2234.82 | 2249.4 | 2263.97 | 2277.98 | 2292.93 | 2307.88 | 2322.83 | 2337.2 | 2352.54 | 2367.89 | 2383.23 | 2397.97 | 2413.71 | 2429.45 | 2445.19 | 2460.32 | 2476.47 | 2492.62 | 2508.77 | 2524.29 | 2540.86 | 2557.43 | 2573.99 | 2589.92 | 2606.92 | 2623.92 | 2640.92 | 2657.26 | 2674.7 | 2692.14 | 2709.58 | 2726.34 | 2744.24 | 2762.14 | 2780.03 | 2797.23 | 2815.59 | 2833.95 | 2852.31 | 2869.96 | 2888.8 | 2907.63 | 2926.47 | 2944.58 | 2963.9 | 2983.23 | 3002.56 | 3021.13 | 3040.97 | 3060.8 | 3080.63 | 3099.68 | 3120.03 | 3140.38 | 3160.72 | 3180.28 | 3201.15 | 3222.03 | 3242.9 | 3262.96 | 3284.38 | 3305.8 | 3327.22 | 3347.8 | 3369.78 | 3391.75 | 3413.73 | 3434.84 | 3457.39 | 3479.94 | 3502.48 | 3524.15 | 3547.28 | 3570.41 | 3593.55 | 3615.78 | 3639.51 | 3663.25 | 3686.98 | 3709.79 | 3734.14 | 3758.49 | 3782.84 | 3806.24 | 3831.23 | 3856.21 | 3881.19 | 3905.2 | 3930.84 | 3956.47 | 3982.11 | 4006.74 | 4033.04 | 4059.34 | 4085.64 | 4110.91 | 4137.9 | 4164.88 | 4191.87 | 4217.8 | 4245.48 | 4273.17 | 4300.86 | 4327.46 | 4355.87 | 4384.27 | 4412.68 | 4439.98 | 4469.12 | 4498.26 | 4527.41 | 4555.41 | 4585.32 | 4615.22 | 4645.12 | 4673.86 | 4704.53 | 4735.21 | 4765.89 | 4795.38 | 4826.85 | 4858.33 | 4889.81 | 4920.06 | 4952.35 | 4984.65 | 5016.94 | 5047.98 | 5081.11 | 5114.25 | 5147.38 | 5179.22 | 5213.22 | 5247.22 | 5281.21 | 5313.88 | 5348.76 | 5383.64 | 5418.52 | 5452.04 | 5487.83 | 5523.62 | 5559.41 | 5593.8 | 5630.52 | 5667.23 | 5703.95 | 5739.24 | 5776.91 | 5814.58 | 5852.25 | 5888.46 | 5927.11 | 5965.76 | 6004.41 | 6041.56 | 6081.21 | 6120.87 | 6160.53 | 6198.64 | 6239.33 | 6280.01 | 6320.7 | 6359.8 | 6401.55 | 6443.29 | 6485.04 | 6525.16 | 6567.99 | 6610.82 | 6653.65 | 6694.81 | 6738.76 | 6782.7 | 6826.64 | 6868.88 | 6913.96 | 6959.05 | 7004.14 | 7047.47 | 7093.73 | 7139.99 | 7186.25 | 7230.7 | 7278.16 | 7325.63 | 7373.09 | 7418.7 | 7467.4 | 7516.09 | 7564.79 | 7611.59 | 7661.55 | 7711.51 | 7761.47 | 7809.49 | 7860.75 | 7912.01 | 7963.27 | 8012.53 | 8065.13 | 8117.72 | 8170.32
[6 empty] | 20 | 16 | 20 | BANK STABILIZATION | 2% | 252.82 | 257.63 | 266.45 | 273.32 | 279.15 | 286.12 | 295.88 | 299.36 | 305.34 | 308.27 | 318.02 | 320.08 | 321.52 | 322.52 | 327.18 | 327.81 | 329.24 | 331.83 | 336.53 | 336.61 | 339.5 | 342.69 | 344.67 | 344.96 | 346.37 | 349.19 | 351.15 | 351.23 | 354.5 | 357.36 | 360.96 | 362.01 | 365.31 | 368.11 | 370.12 | 371.45 | 376.09 | 379.56 | 383.04 | 384.58 | 386.68 | 391.12 | 394.94 | 396.05 | 398.72 | 402.16 | 404.24 | 405.03 | 406.86 | 411.41 | 414.73 | 415.36 | 419.18 | 423.02 | 424.66 | 427.08 | 430.35 | 433.67 | 435.18 | 436.35 | 439.89 | 444.59 | 449.63 | 450.08 | 453.16 | 456.47 | 459.29 | 459.9 | 462.5 | 464.94 | 466.65 | 467.64 | 472.31 | 476.13 | 478.33 | 479.14 | 483.67 | 488.48 | 492.81 | 493.47 | 496.2 | 500.74 | 503.53 | 505.51 | 508.86 | 511.15 | 515.13 | 516.86 | 519.9 | 530.24 | 534.49 | 534.58 | 538.56 | 542.73 | 544.59 | 547.71 | 553.65 | 561.04 | 568.83 | 574.2 | 584.95 | 591.3 | 599.32 | 603.93 | 619.29 | 627.39 | 632.75 | 642.25 | 654.93 | 666.89 | 672.89 | 678.39 | 685.5 | 693.62 | 705.31 | 710.77 | 718.39 | 722.75 | 726.93 | 725.05 | 731.87 | 734.65 | 743.86 | 745.72 | 751.63 | 757.16 | 765.44 | 765.87 | 771.7 | 779.14 | 784.52 | 784.53 | 790.84 | 793.64 | 801.54 | 805.25 | 812.74 | 817.68 | 824.94 | 825.65 | 833.88 | 837.55 | 844.72 | 846.91 | 856.95 | 861.3 | 871.24 | 868.28 | 878.14 | 883.04 | 892.9 | 894.64 | 893.48 | 901.37 | 910.43 | 923.01 | 934.16 | 939 | 954.24 | 953.88 | 965.11 | 971.43 | 975.81 | 977.64 | 991.62 | 1008.67 | 1030.08 | 1043.86 | 1071.74 | 1095.93 | 1117.78 | 1131.29 | 1167.74 | 1179.48 | 1195.89 | 1204.26 | 1233.62 | 1241.69 | 1250.17 | 1258.61 | 1267.05 | 1275.49 | 1283.92 | 1296.84 | 1301.31 | 1309.85 | 1318.4 | 1326.94 | 1335.15 | 1343.91 | 1352.67 | 1361.44 | 1369.86 | 1378.85 | 1387.84 | 1396.84 | 1405.48 | 1414.7 | 1423.93 | 1433.15 | 1442.02 | 1451.49 | 1460.95 | 1470.42 | 1479.51 | 1489.22 | 1498.94 | 1508.65 | 1517.98 | 1527.94 | 1537.91 | 1547.87 | 1557.45 | 1567.67 | 1577.89 | 1588.12 | 1597.94 | 1608.43 | 1618.92 | 1629.41 | 1639.49 | 1650.25 | 1661.01 | 1671.77 | 1682.11 | 1693.16 | 1704.2 | 1715.24 | 1725.85 | 1737.18 | 1748.51 | 1759.83 | 1770.72 | 1782.34 | 1793.97 | 1805.59 | 1816.76 | 1828.68 | 1840.61 | 1852.54 | 1864 | 1876.23 | 1888.47 | 1900.7 | 1912.46 | 1925.01 | 1937.57 | 1950.12 | 1962.18 | 1975.06 | 1987.94 | 2000.82 | 2013.2 | 2026.41 | 2039.63 | 2052.84 | 2065.54 | 2079.1 | 2092.66 | 2106.22 | 2119.25 | 2133.16 | 2147.07 | 2160.98 | 2174.35 | 2188.62 | 2202.89 | 2217.16 | 2230.88 | 2245.52 | 2260.17 | 2274.81 | 2288.88 | 2303.91 | 2318.93 | 2333.96 | 2348.39 | 2363.81 | 2379.22 | 2394.64 | 2409.45 | 2425.27 | 2441.08 | 2456.9 | 2472.1 | 2488.33 | 2504.55 | 2520.78 | 2536.37 | 2553.02 | 2569.67 | 2586.32 | 2602.32 | 2619.4 | 2636.48 | 2653.56 | 2669.98 | 2687.5 | 2705.03 | 2722.56 | 2739.4 | 2757.38 | 2775.36 | 2793.34 | 2810.62 | 2829.07 | 2847.52 | 2865.97 | 2883.7 | 2902.63 | 2921.56 | 2940.48 | 2958.68 | 2978.1 | 2997.52 | 3016.94 | 3035.6 | 3055.53 | 3075.45 | 3095.38 | 3114.53 | 3134.97 | 3155.41 | 3175.86 | 3195.5 | 3216.48 | 3237.45 | 3258.43 | 3278.59 | 3300.11 | 3321.63 | 3343.15 | 3363.83 | 3385.91 | 3407.99 | 3430.07 | 3451.29 | 3473.94 | 3496.6 | 3519.25 | 3541.02 | 3564.27 | 3587.51 | 3610.75 | 3633.09 | 3656.94 | 3680.79 | 3704.63 | 3727.55 | 3752.02 | 3776.49 | 3800.95 | 3824.47 | 3849.57 | 3874.67 | 3899.78 | 3923.9 | 3949.66 | 3975.42 | 4001.17 | 4025.92 | 4052.35 | 4078.78 | 4105.2 | 4130.6 | 4157.71 | 4184.82 | 4211.94 | 4237.99 | 4265.81 | 4293.63 | 4321.45 | 4348.18 | 4376.72 | 4405.26 | 4433.81 | 4461.23 | 4490.52 | 4519.8 | 4549.09 | 4577.23 | 4607.27 | 4637.32 | 4667.36 | 4696.23 | 4727.06 | 4757.89 | 4788.71 | 4818.34 | 4849.96 | 4881.59 | 4913.22 | 4943.61 | 4976.06 | 5008.51 | 5040.96 | 5072.15 | 5105.44 | 5138.73 | 5172.03 | 5204.02 | 5238.18 | 5272.34 | 5306.5 | 5339.33 | 5374.37 | 5409.42 | 5444.47 | 5478.15 | 5514.11 | 5550.07 | 5586.03 | 5620.58 | 5657.48 | 5694.37 | 5731.26 | 5766.72 | 5804.57 | 5842.42 | 5880.28 | 5916.65 | 5955.49 | 5994.33 | 6033.16 | 6070.48 | 6110.33 | 6150.18 | 6190.02 | 6228.32 | 6269.2 | 6310.08 | 6350.97 | 6390.25 | 6432.2 | 6474.14 | 6516.09 | 6556.4 | 6599.44 | 6642.47 | 6685.51 | 6726.87 | 6771.02 | 6815.18 | 6859.33 | 6901.77 | 6947.07 | 6992.37 | 7037.67 | 7081.21 | 7127.69 | 7174.17 | 7220.65 | 7265.32 | 7313.01 | 7360.7 | 7408.39 | 7454.22 | 7503.15 | 7552.08 | 7601.01 | 7648.03 | 7698.23 | 7748.43 | 7798.64 | 7846.88 | 7898.39 | 7949.89 | 8001.4 | 8050.9 | 8103.74 | 8156.59 | 8209.44 | 8260.22 | 8314.44 | 8368.66 | 8422.88 | 8474.99 | 8530.62 | 8586.25 | 8641.88 | 8695.34 | 8752.41 | 8809.49 | 8866.57
[6 empty] | 21 | 17 | 21 | BEACH REPLENISHMENT | 2% | 262.51 | 266.77 | 278.85 | 284.04 | 287.68 | 293.48 | 307.19 | 311.48 | 317.47 | 319.47 | 334.99 | 336.48 | 338.31 | 339.12 | 345.4 | 346.48 | 347.61 | 348.8 | 354.71 | 354.44 | 356.26 | 357.84 | 360.19 | 360.68 | 361.64 | 364.59 | 366.87 | 366.99 | 370.06 | 371.75 | 376.2 | 377.19 | 380.01 | 382.4 | 385.05 | 386.6 | 394.09 | 397.39 | 402.05 | 404.39 | 408.11 | 411.77 | 417.43 | 418.79 | 421.46 | 424.52 | 427.62 | 429.07 | 431.08 | 437.09 | 443.07 | 443.82 | 446.08 | 450.52 | 454.06 | 454.39 | 457.05 | 460.68 | 462.35 | 463.56 | 465.83 | 471.98 | 479.09 | 479.43 | 482.58 | 486.02 | 489.99 | 490.51 | 492.64 | 494.85 | 496.49 | 498.23 | 503.53 | 506.24 | 508.4 | 510.21 | 514.77 | 520.48 | 525.81 | 526.51 | 527.91 | 531.22 | 534.34 | 537.36 | 540.77 | 539.82 | 544.75 | 547.51 | 550.76 | 568.85 | 574.22 | 574.58 | 580.2 | 585.05 | 585.18 | 588.23 | 593.35 | 597.42 | 605.82 | 610.94 | 619.98 | 626.28 | 635.25 | 639.56 | 650.69 | 658.21 | 661.81 | 669.01 | 676.88 | 686.56 | 696 | 698.14 | 700.69 | 705.47 | 713.5 | 717.74 | 727.05 | 730.99 | 740.35 | 741.15 | 747.83 | 748.86 | 765.59 | 766.53 | 771.39 | 778.88 | 787.89 | 789.66 | 795.15 | 798.73 | 806.02 | 807.05 | 812.95 | 815.76 | 828.49 | 829.61 | 834.45 | 837.27 | 845.68 | 846.05 | 852.65 | 855.4 | 864.56 | 866.46 | 871.59 | 874.2 | 886.42 | 885.91 | 890.36 | 893.94 | 906.3 | 907.51 | 897.47 | 901.83 | 911.64 | 928.49 | 936.64 | 941.4 | 958.55 | 959.67 | 965.66 | 969.51 | 972.29 | 974.95 | 983.87 | 1000.49 | 1022.6 | 1039.2 | 1050.41 | 1070.45 | 1082.54 | 1103.2 | 1129.38 | 1137.36 | 1163.63 | 1170.63 | 1185.37 | 1191.31 | 1198.72 | 1206.81 | 1214.9 | 1222.99 | 1231.09 | 1243.47 | 1247.76 | 1255.95 | 1264.14 | 1272.33 | 1280.2 | 1288.6 | 1297.01 | 1305.41 | 1313.49 | 1322.11 | 1330.73 | 1339.35 | 1347.64 | 1356.48 | 1365.33 | 1374.17 | 1382.67 | 1391.75 | 1400.83 | 1409.9 | 1418.62 | 1427.94 | 1437.25 | 1446.56 | 1455.51 | 1465.06 | 1474.62 | 1484.17 | 1493.35 | 1503.15 | 1512.96 | 1522.76 | 1532.18 | 1542.24 | 1552.29 | 1562.35 | 1572.01 | 1582.33 | 1592.65 | 1602.97 | 1612.89 | 1623.47 | 1634.06 | 1644.65 | 1654.82 | 1665.68 | 1676.55 | 1687.41 | 1697.85 | 1708.99 | 1720.14 | 1731.28 | 1741.99 | 1753.43 | 1764.86 | 1776.3 | 1787.28 | 1799.02 | 1810.75 | 1822.48 | 1833.75 | 1845.79 | 1857.83 | 1869.86 | 1881.43 | 1893.78 | 1906.13 | 1918.48 | 1930.35 | 1943.02 | 1955.69 | 1968.36 | 1980.54 | 1993.54 | 2006.54 | 2019.54 | 2032.03 | 2045.37 | 2058.71 | 2072.05 | 2084.86 | 2098.55 | 2112.23 | 2125.92 | 2139.07 | 2153.11 | 2167.15 | 2181.19 | 2194.69 | 2209.09 | 2223.5 | 2237.9 | 2251.75 | 2266.53 | 2281.31 | 2296.09 | 2310.29 | 2325.46 | 2340.62 | 2355.79 | 2370.36 | 2385.92 | 2401.48 | 2417.04 | 2431.99 | 2447.95 | 2463.92 | 2479.88 | 2495.22 | 2511.6 | 2527.98 | 2544.36 | 2560.1 | 2576.9 | 2593.71 | 2610.51 | 2626.66 | 2643.9 | 2661.14 | 2678.38 | 2694.95 | 2712.64 | 2730.33 | 2748.02 | 2765.02 | 2783.17 | 2801.32 | 2819.47 | 2836.91 | 2855.53 | 2874.16 | 2892.78 | 2910.67 | 2929.78 | 2948.88 | 2967.99 | 2986.35 | 3005.95 | 3025.55 | 3045.16 | 3063.99 | 3084.11 | 3104.22 | 3124.33 | 3143.66 | 3164.29 | 3184.93 | 3205.56 | 3225.39 | 3246.57 | 3267.74 | 3288.91 | 3309.25 | 3330.98 | 3352.7 | 3374.42 | 3395.29 | 3417.58 | 3439.87 | 3462.15 | 3483.57 | 3506.44 | 3529.3 | 3552.17 | 3574.15 | 3597.61 | 3621.07 | 3644.53 | 3667.07 | 3691.14 | 3715.21 | 3739.29 | 3762.42 | 3787.11 | 3811.81 | 3836.51 | 3860.24 | 3885.58 | 3910.92 | 3936.26 | 3960.61 | 3986.6 | 4012.6 | 4038.6 | 4063.58 | 4090.26 | 4116.93 | 4143.6 | 4169.23 | 4196.6 | 4223.97 | 4251.34 | 4277.64 | 4305.71 | 4333.79 | 4361.87 | 4388.85 | 4417.66 | 4446.47 | 4475.28 | 4502.96 | 4532.52 | 4562.08 | 4591.64 | 4620.04 | 4650.37 | 4680.69 | 4711.02 | 4740.16 | 4771.28 | 4802.39 | 4833.51 | 4863.41 | 4895.33 | 4927.25 | 4959.18 | 4989.85 | 5022.61 | 5055.36 | 5088.11 | 5119.59 | 5153.2 | 5186.8 | 5220.41 | 5252.7 | 5287.18 | 5321.66 | 5356.14 | 5389.27 | 5424.65 | 5460.02 | 5495.4 | 5529.39 | 5565.69 | 5601.98 | 5638.28 | 5673.16 | 5710.39 | 5747.63 | 5784.87 | 5820.66 | 5858.86 | 5897.07 | 5935.28 | 5971.99 | 6011.19 | 6050.4 | 6089.6 | 6127.27 | 6167.49 | 6207.71 | 6247.92 | 6286.58 | 6327.84 | 6369.11 | 6410.37 | 6450.03 | 6492.36 | 6534.7 | 6577.04 | 6617.73 | 6661.17 | 6704.6 | 6748.04 | 6789.79 | 6834.36 | 6878.92 | 6923.49 | 6966.32 | 7012.05 | 7057.78 | 7103.5 | 7147.45 | 7194.36 | 7241.28 | 7288.19 | 7333.28 | 7381.42 | 7429.55 | 7477.69 | 7523.95 | 7573.33 | 7622.72 | 7672.11 | 7719.57 | 7770.24 | 7820.91 | 7871.58 | 7920.28 | 7972.27 | 8024.25 | 8076.24 | 8126.2 | 8179.54 | 8232.89 | 8286.23 | 8337.49 | 8392.21 | 8446.94 | 8501.67
| The 30 and 31 feature codes can be based on the updating factors from Table 1 in |  |  |  |  | 22 | 18 | 22 | CULTURAL RESOURCE PRESERVATION | 2% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1155 | 1162.8 | 1170.59 | 1178.39 | 1186.19 | 1198.12 | 1202.25 | 1210.14 | 1218.03 | 1225.92 | 1233.51 | 1241.6 | 1249.7 | 1257.8 | 1265.58 | 1273.89 | 1282.19 | 1290.5 | 1298.48 | 1307.01 | 1315.53 | 1324.05 | 1332.24 | 1340.99 | 1349.73 | 1358.48 | 1366.88 | 1375.86 | 1384.83 | 1393.8 | 1402.42 | 1411.63 | 1420.83 | 1430.04 | 1438.89 | 1448.33 | 1457.77 | 1467.22 | 1476.3 | 1485.99 | 1495.68 | 1505.37 | 1514.68 | 1524.62 | 1534.56 | 1544.51 | 1554.06 | 1564.26 | 1574.46 | 1584.66 | 1594.47 | 1604.93 | 1615.4 | 1625.87 | 1635.92 | 1646.66 | 1657.4 | 1668.14 | 1678.46 | 1689.47 | 1700.49 | 1711.51 | 1722.1 | 1733.4 | 1744.71 | 1756.01 | 1766.87 | 1778.47 | 1790.07 | 1801.67 | 1812.81 | 1824.71 | 1836.61 | 1848.51 | 1859.94 | 1872.15 | 1884.36 | 1896.57 | 1908.3 | 1920.83 | 1933.35 | 1945.88 | 1957.92 | 1970.77 | 1983.62 | 1996.47 | 2008.82 | 2022.01 | 2035.2 | 2048.38 | 2061.05 | 2074.58 | 2088.11 | 2101.64 | 2114.64 | 2128.52 | 2142.4 | 2156.28 | 2169.62 | 2183.86 | 2198.1 | 2212.35 | 2226.03 | 2240.64 | 2255.25 | 2269.87 | 2283.91 | 2298.9 | 2313.89 | 2328.88 | 2343.29 | 2358.67 | 2374.05 | 2389.43 | 2404.22 | 2420 | 2435.78 | 2451.56 | 2466.73 | 2482.92 | 2499.11 | 2515.3 | 2530.86 | 2547.47 | 2564.09 | 2580.7 | 2596.66 | 2613.71 | 2630.75 | 2647.8 | 2664.18 | 2681.66 | 2699.15 | 2716.64 | 2733.44 | 2751.39 | 2769.33 | 2787.27 | 2804.51 | 2822.92 | 2841.33 | 2859.74 | 2877.43 | 2896.32 | 2915.21 | 2934.09 | 2952.24 | 2971.62 | 2991 | 3010.38 | 3029 | 3048.88 | 3068.77 | 3088.65 | 3107.76 | 3128.16 | 3148.56 | 3168.95 | 3188.56 | 3209.49 | 3230.42 | 3251.35 | 3271.46 | 3292.93 | 3314.41 | 3335.88 | 3356.52 | 3378.55 | 3400.58 | 3422.62 | 3443.79 | 3466.39 | 3489 | 3511.6 | 3533.33 | 3556.52 | 3579.71 | 3602.9 | 3625.19 | 3648.99 | 3672.78 | 3696.58 | 3719.45 | 3743.86 | 3768.28 | 3792.69 | 3816.15 | 3841.2 | 3866.25 | 3891.3 | 3915.37 | 3941.07 | 3966.77 | 3992.48 | 4017.17 | 4043.54 | 4069.91 | 4096.28 | 4121.62 | 4148.67 | 4175.73 | 4202.78 | 4228.78 | 4256.54 | 4284.3 | 4312.06 | 4338.73 | 4367.21 | 4395.69 | 4424.17 | 4451.54 | 4480.76 | 4509.98 | 4539.2 | 4567.28 | 4597.26 | 4627.24 | 4657.22 | 4686.03 | 4716.79 | 4747.54 | 4778.3 | 4807.86 | 4839.42 | 4870.98 | 4902.54 | 4932.87 | 4965.25 | 4997.63 | 5030.01 | 5061.12 | 5094.34 | 5127.56 | 5160.79 | 5192.71 | 5226.8 | 5260.88 | 5294.97 | 5327.72 | 5362.69 | 5397.66 | 5432.64 | 5466.24 | 5502.12 | 5538 | 5573.88 | 5608.37 | 5645.18 | 5681.99 | 5718.81 | 5754.18 | 5791.95 | 5829.72 | 5867.49 | 5903.79 | 5942.54 | 5981.3 | 6020.05 | 6057.29 | 6097.05 | 6136.81 | 6176.57 | 6214.78 | 6255.57 | 6296.37 | 6337.16 | 6376.36 | 6418.22 | 6460.07 | 6501.93 | 6542.15 | 6585.09 | 6628.03 | 6670.98 | 6712.25 | 6756.3 | 6800.36 | 6844.42 | 6886.76 | 6931.97 | 6977.17 | 7022.38 | 7065.82 | 7112.2 | 7158.58 | 7204.96 | 7249.53 | 7297.12 | 7344.7 | 7392.29 | 7438.02 | 7486.84 | 7535.66 | 7584.49 | 7631.41 | 7681.5 | 7731.59 | 7781.68 | 7829.82 | 7881.22 | 7932.61 | 7984.01 | 8033.4 | 8086.13 | 8138.86 | 8191.59
| Table 1 FY26 Program Cost Estimate Updating Rates 31 March 2024 |  |  |  |  | 23 | 19 | 23 | BUILDINGS, GROUNDS & UTILITIES | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1155 | 1162.8 | 1170.59 | 1178.39 | 1186.19 | 1198.12 | 1202.25 | 1210.14 | 1218.03 | 1225.92 | 1233.51 | 1241.6 | 1249.7 | 1257.8 | 1265.58 | 1273.89 | 1282.19 | 1290.5 | 1298.48 | 1307.01 | 1315.53 | 1324.05 | 1332.24 | 1340.99 | 1349.73 | 1358.48 | 1366.88 | 1375.86 | 1384.83 | 1393.8 | 1402.42 | 1411.63 | 1420.83 | 1430.04 | 1438.89 | 1448.33 | 1457.77 | 1467.22 | 1476.3 | 1485.99 | 1495.68 | 1505.37 | 1514.68 | 1524.62 | 1534.56 | 1544.51 | 1554.06 | 1564.26 | 1574.46 | 1584.66 | 1594.47 | 1604.93 | 1615.4 | 1625.87 | 1635.92 | 1646.66 | 1657.4 | 1668.14 | 1678.46 | 1689.47 | 1700.49 | 1711.51 | 1722.1 | 1733.4 | 1744.71 | 1756.01 | 1766.87 | 1778.47 | 1790.07 | 1801.67 | 1812.81 | 1824.71 | 1836.61 | 1848.51 | 1859.94 | 1872.15 | 1884.36 | 1896.57 | 1908.3 | 1920.83 | 1933.35 | 1945.88 | 1957.92 | 1970.77 | 1983.62 | 1996.47 | 2008.82 | 2022.01 | 2035.2 | 2048.38 | 2061.05 | 2074.58 | 2088.11 | 2101.64 | 2114.64 | 2128.52 | 2142.4 | 2156.28 | 2169.62 | 2183.86 | 2198.1 | 2212.35 | 2226.03 | 2240.64 | 2255.25 | 2269.87 | 2283.91 | 2298.9 | 2313.89 | 2328.88 | 2343.29 | 2358.67 | 2374.05 | 2389.43 | 2404.22 | 2420 | 2435.78 | 2451.56 | 2466.73 | 2482.92 | 2499.11 | 2515.3 | 2530.86 | 2547.47 | 2564.09 | 2580.7 | 2596.66 | 2613.71 | 2630.75 | 2647.8 | 2664.18 | 2681.66 | 2699.15 | 2716.64 | 2733.44 | 2751.39 | 2769.33 | 2787.27 | 2804.51 | 2822.92 | 2841.33 | 2859.74 | 2877.43 | 2896.32 | 2915.21 | 2934.09 | 2952.24 | 2971.62 | 2991 | 3010.38 | 3029 | 3048.88 | 3068.77 | 3088.65 | 3107.76 | 3128.16 | 3148.56 | 3168.95 | 3188.56 | 3209.49 | 3230.42 | 3251.35 | 3271.46 | 3292.93 | 3314.41 | 3335.88 | 3356.52 | 3378.55 | 3400.58 | 3422.62 | 3443.79 | 3466.39 | 3489 | 3511.6 | 3533.33 | 3556.52 | 3579.71 | 3602.9 | 3625.19 | 3648.99 | 3672.78 | 3696.58 | 3719.45 | 3743.86 | 3768.28 | 3792.69 | 3816.15 | 3841.2 | 3866.25 | 3891.3 | 3915.37 | 3941.07 | 3966.77 | 3992.48 | 4017.17 | 4043.54 | 4069.91 | 4096.28 | 4121.62 | 4148.67 | 4175.73 | 4202.78 | 4228.78 | 4256.54 | 4284.3 | 4312.06 | 4338.73 | 4367.21 | 4395.69 | 4424.17 | 4451.54 | 4480.76 | 4509.98 | 4539.2 | 4567.28 | 4597.26 | 4627.24 | 4657.22 | 4686.03 | 4716.79 | 4747.54 | 4778.3 | 4807.86 | 4839.42 | 4870.98 | 4902.54 | 4932.87 | 4965.25 | 4997.63 | 5030.01 | 5061.12 | 5094.34 | 5127.56 | 5160.79 | 5192.71 | 5226.8 | 5260.88 | 5294.97 | 5327.72 | 5362.69 | 5397.66 | 5432.64 | 5466.24 | 5502.12 | 5538 | 5573.88 | 5608.37 | 5645.18 | 5681.99 | 5718.81 | 5754.18 | 5791.95 | 5829.72 | 5867.49 | 5903.79 | 5942.54 | 5981.3 | 6020.05 | 6057.29 | 6097.05 | 6136.81 | 6176.57 | 6214.78 | 6255.57 | 6296.37 | 6337.16 | 6376.36 | 6418.22 | 6460.07 | 6501.93 | 6542.15 | 6585.09 | 6628.03 | 6670.98 | 6712.25 | 6756.3 | 6800.36 | 6844.42 | 6886.76 | 6931.97 | 6977.17 | 7022.38 | 7065.82 | 7112.2 | 7158.58 | 7204.96 | 7249.53 | 7297.12 | 7344.7 | 7392.29 | 7438.02 | 7486.84 | 7535.66 | 7584.49 | 7631.41 | 7681.5 | 7731.59 | 7781.68 | 7829.82 | 7881.22 | 7932.61 | 7984.01 | 8033.4 | 8086.13 | 8138.86 | 8191.59
[5 empty] | Select | 24 | 20 | 24 | PERMANENT OPERATING EQUIPMENT | 2% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 469.97 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1155 | 1162.8 | 1170.59 | 1178.39 | 1186.19 | 1198.12 | 1202.25 | 1210.14 | 1218.03 | 1225.92 | 1233.51 | 1241.6 | 1249.7 | 1257.8 | 1265.58 | 1273.89 | 1282.19 | 1290.5 | 1298.48 | 1307.01 | 1315.53 | 1324.05 | 1332.24 | 1340.99 | 1349.73 | 1358.48 | 1366.88 | 1375.86 | 1384.83 | 1393.8 | 1402.42 | 1411.63 | 1420.83 | 1430.04 | 1438.89 | 1448.33 | 1457.77 | 1467.22 | 1476.3 | 1485.99 | 1495.68 | 1505.37 | 1514.68 | 1524.62 | 1534.56 | 1544.51 | 1554.06 | 1564.26 | 1574.46 | 1584.66 | 1594.47 | 1604.93 | 1615.4 | 1625.87 | 1635.92 | 1646.66 | 1657.4 | 1668.14 | 1678.46 | 1689.47 | 1700.49 | 1711.51 | 1722.1 | 1733.4 | 1744.71 | 1756.01 | 1766.87 | 1778.47 | 1790.07 | 1801.67 | 1812.81 | 1824.71 | 1836.61 | 1848.51 | 1859.94 | 1872.15 | 1884.36 | 1896.57 | 1908.3 | 1920.83 | 1933.35 | 1945.88 | 1957.92 | 1970.77 | 1983.62 | 1996.47 | 2008.82 | 2022.01 | 2035.2 | 2048.38 | 2061.05 | 2074.58 | 2088.11 | 2101.64 | 2114.64 | 2128.52 | 2142.4 | 2156.28 | 2169.62 | 2183.86 | 2198.1 | 2212.35 | 2226.03 | 2240.64 | 2255.25 | 2269.87 | 2283.91 | 2298.9 | 2313.89 | 2328.88 | 2343.29 | 2358.67 | 2374.05 | 2389.43 | 2404.22 | 2420 | 2435.78 | 2451.56 | 2466.73 | 2482.92 | 2499.11 | 2515.3 | 2530.86 | 2547.47 | 2564.09 | 2580.7 | 2596.66 | 2613.71 | 2630.75 | 2647.8 | 2664.18 | 2681.66 | 2699.15 | 2716.64 | 2733.44 | 2751.39 | 2769.33 | 2787.27 | 2804.51 | 2822.92 | 2841.33 | 2859.74 | 2877.43 | 2896.32 | 2915.21 | 2934.09 | 2952.24 | 2971.62 | 2991 | 3010.38 | 3029 | 3048.88 | 3068.77 | 3088.65 | 3107.76 | 3128.16 | 3148.56 | 3168.95 | 3188.56 | 3209.49 | 3230.42 | 3251.35 | 3271.46 | 3292.93 | 3314.41 | 3335.88 | 3356.52 | 3378.55 | 3400.58 | 3422.62 | 3443.79 | 3466.39 | 3489 | 3511.6 | 3533.33 | 3556.52 | 3579.71 | 3602.9 | 3625.19 | 3648.99 | 3672.78 | 3696.58 | 3719.45 | 3743.86 | 3768.28 | 3792.69 | 3816.15 | 3841.2 | 3866.25 | 3891.3 | 3915.37 | 3941.07 | 3966.77 | 3992.48 | 4017.17 | 4043.54 | 4069.91 | 4096.28 | 4121.62 | 4148.67 | 4175.73 | 4202.78 | 4228.78 | 4256.54 | 4284.3 | 4312.06 | 4338.73 | 4367.21 | 4395.69 | 4424.17 | 4451.54 | 4480.76 | 4509.98 | 4539.2 | 4567.28 | 4597.26 | 4627.24 | 4657.22 | 4686.03 | 4716.79 | 4747.54 | 4778.3 | 4807.86 | 4839.42 | 4870.98 | 4902.54 | 4932.87 | 4965.25 | 4997.63 | 5030.01 | 5061.12 | 5094.34 | 5127.56 | 5160.79 | 5192.71 | 5226.8 | 5260.88 | 5294.97 | 5327.72 | 5362.69 | 5397.66 | 5432.64 | 5466.24 | 5502.12 | 5538 | 5573.88 | 5608.37 | 5645.18 | 5681.99 | 5718.81 | 5754.18 | 5791.95 | 5829.72 | 5867.49 | 5903.79 | 5942.54 | 5981.3 | 6020.05 | 6057.29 | 6097.05 | 6136.81 | 6176.57 | 6214.78 | 6255.57 | 6296.37 | 6337.16 | 6376.36 | 6418.22 | 6460.07 | 6501.93 | 6542.15 | 6585.09 | 6628.03 | 6670.98 | 6712.25 | 6756.3 | 6800.36 | 6844.42 | 6886.76 | 6931.97 | 6977.17 | 7022.38 | 7065.82 | 7112.2 | 7158.58 | 7204.96 | 7249.53 | 7297.12 | 7344.7 | 7392.29 | 7438.02 | 7486.84 | 7535.66 | 7584.49 | 7631.41 | 7681.5 | 7731.59 | 7781.68 | 7829.82 | 7881.22 | 7932.61 | 7984.01 | 8033.4 | 8086.13 | 8138.86 | 8191.59
[5 empty] | Class | 25 | ALL | 25 |  | 100% | 270.89 | 276.33 | 285.85 | 289.76 | 295.87 | 303.91 | 314.31 | 318.24 | 323.45 | 325.24 | 335.09 | 335.72 | 336.75 | 337.22 | 342.77 | 344.12 | 345.25 | 348.43 | 352.39 | 352.45 | 353.23 | 353.64 | 355.73 | 354.66 | 354.6 | 356.25 | 357.4 | 356.91 | 357.75 | 359.01 | 362.94 | 366.08 | 369.3 | 373.44 | 376.76 | 378.56 | 383.22 | 387.78 | 391.19 | 392.55 | 393.28 | 396.19 | 399.75 | 404.15 | 405.07 | 405.25 | 408.48 | 408.68 | 410.77 | 414.89 | 417.22 | 418.01 | 422.05 | 428.85 | 429.04 | 431.4 | 435.65 | 438.47 | 440.77 | 442.92 | 446.34 | 452.21 | 455.44 | 455.24 | 456.46 | 460.75 | 464.13 | 467.28 | 468.6 | 471.96 | 473.39 | 474.74 | 476.72 | 478.83 | 478.86 | 478.01 | 479.74 | 484.42 | 490.61 | 490.05 | 493.28 | 496.38 | 498.13 | 500.48 | 501.17 | 501.33 | 505.47 | 506.11 | 507.18 | 516.82 | 522.4 | 523.44 | 525.26 | 528.3 | 530.64 | 535.59 | 544.89 | 566.51 | 578.67 | 595.09 | 599.22 | 604.49 | 608.79 | 620.94 | 630.43 | 638.08 | 644.95 | 654.19 | 657.49 | 674.89 | 681.29 | 680.42 | 687.9 | 708.36 | 738.89 | 731.03 | 705.87 | 697.73 | 702.67 | 705.72 | 713.39 | 722.89 | 729.23 | 731.19 | 739.86 | 756.92 | 764.34 | 764.82 | 769.23 | 775.01 | 773.35 | 777.41 | 782.27 | 786.67 | 789.56 | 792.07 | 797.85 | 802.53 | 808.31 | 807.52 | 805.97 | 801.94 | 808.19 | 803.77 | 801.82 | 805.71 | 818.83 | 817.3 | 823.47 | 831.91 | 841.4 | 845.51 | 844.49 | 855.27 | 869.33 | 881.15 | 882.69 | 888.93 | 892.31 | 890.36 | 893.31 | 890.14 | 897.67 | 907.64 | 928.78 | 971.54 | 1005.06 | 1033.84 | 1073.97 | 1108.73 | 1120.16 | 1120.76 | 1121.67 | 1130.44 | 1138.98 | 1144.03 | 1149.32 | 1155.42 | 1159.67 | 1166.74 | 1175.33 | 1183.16 | 1190.98 | 1202.18 | 1206.91 | 1214.84 | 1222.76 | 1230.68 | 1238.29 | 1246.42 | 1254.55 | 1262.68 | 1270.49 | 1278.83 | 1287.17 | 1295.51 | 1303.52 | 1312.08 | 1320.63 | 1329.19 | 1337.41 | 1346.19 | 1354.97 | 1363.75 | 1372.19 | 1381.19 | 1390.2 | 1399.21 | 1407.86 | 1417.1 | 1426.35 | 1435.59 | 1444.47 | 1453.95 | 1463.43 | 1472.91 | 1482.02 | 1491.75 | 1501.48 | 1511.21 | 1520.56 | 1530.54 | 1540.52 | 1550.5 | 1560.09 | 1570.33 | 1580.57 | 1590.81 | 1600.65 | 1611.16 | 1621.67 | 1632.17 | 1642.27 | 1653.05 | 1663.83 | 1674.61 | 1684.97 | 1696.03 | 1707.09 | 1718.15 | 1728.78 | 1740.13 | 1751.47 | 1762.82 | 1773.73 | 1785.37 | 1797.01 | 1808.66 | 1819.84 | 1831.79 | 1843.73 | 1855.68 | 1867.16 | 1879.42 | 1891.67 | 1903.93 | 1915.71 | 1928.28 | 1940.86 | 1953.43 | 1965.51 | 1978.42 | 1991.32 | 2004.22 | 2016.62 | 2029.85 | 2043.09 | 2056.33 | 2069.05 | 2082.63 | 2096.21 | 2109.79 | 2122.85 | 2136.78 | 2150.71 | 2164.65 | 2178.04 | 2192.34 | 2206.63 | 2220.93 | 2234.67 | 2249.34 | 2264 | 2278.67 | 2292.77 | 2307.82 | 2322.87 | 2337.92 | 2352.38 | 2367.82 | 2383.26 | 2398.7 | 2413.54 | 2429.39 | 2445.23 | 2461.07 | 2476.3 | 2492.55 | 2508.8 | 2525.06 | 2540.68 | 2557.36 | 2574.03 | 2590.71 | 2606.74 | 2623.85 | 2640.96 | 2658.07 | 2674.51 | 2692.07 | 2709.62 | 2727.18 | 2744.05 | 2762.06 | 2780.07 | 2798.09 | 2815.39 | 2833.87 | 2852.35 | 2870.84 | 2888.59 | 2907.56 | 2926.52 | 2945.48 | 2963.7 | 2983.15 | 3002.61 | 3022.06 | 3040.75 | 3060.71 | 3080.67 | 3100.63 | 3119.81 | 3140.29 | 3160.77 | 3181.25 | 3200.93 | 3221.94 | 3242.95 | 3263.96 | 3284.15 | 3305.71 | 3327.27 | 3348.82 | 3369.54 | 3391.66 | 3413.78 | 3435.89 | 3457.15 | 3479.84 | 3502.53 | 3525.23 | 3547.04 | 3570.32 | 3593.6 | 3616.88 | 3639.26 | 3663.15 | 3687.03 | 3710.92 | 3733.88 | 3758.39 | 3782.9 | 3807.41 | 3830.96 | 3856.11 | 3881.25 | 3906.4 | 3930.56 | 3956.36 | 3982.17 | 4007.97 | 4032.76 | 4059.23 | 4085.7 | 4112.17 | 4137.61 | 4164.77 | 4191.93 | 4219.09 | 4245.19 | 4273.05 | 4300.92 | 4328.79 | 4355.56 | 4384.15 | 4412.74 | 4441.33 | 4468.81 | 4498.14 | 4527.48 | 4556.81 | 4585 | 4615.09 | 4645.19 | 4675.29 | 4704.21 | 4735.09 | 4765.96 | 4796.84 | 4826.52 | 4858.2 | 4889.88 | 4921.56 | 4952.01 | 4984.51 | 5017.02 | 5049.52 | 5080.76 | 5114.11 | 5147.46 | 5180.81 | 5212.86 | 5247.08 | 5281.29 | 5315.51 | 5348.39 | 5383.5 | 5418.61 | 5453.71 | 5487.45 | 5523.47 | 5559.49 | 5595.51 | 5630.12 | 5667.08 | 5704.04 | 5740.99 | 5776.51 | 5814.42 | 5852.34 | 5890.26 | 5926.7 | 5965.6 | 6004.5 | 6043.41 | 6080.79 | 6120.71 | 6160.62 | 6200.53 | 6238.89 | 6279.84 | 6320.8 | 6361.75 | 6401.1 | 6443.12 | 6485.14 | 6527.15 | 6567.53 | 6610.64 | 6653.75 | 6696.86 | 6738.29 | 6782.52 | 6826.75 | 6870.98 | 6913.48 | 6958.86 | 7004.24 | 7049.62 | 7093.23 | 7139.79 | 7186.35 | 7232.91 | 7277.66 | 7325.43 | 7373.2 | 7420.97 | 7466.88 | 7515.89 | 7564.9 | 7613.91 | 7661.02 | 7711.3 | 7761.59 | 7811.88 | 7860.2 | 7911.8 | 7963.39 | 8014.98 | 8064.57 | 8117.5 | 8170.44 | 8223.37 | 24412914.82
|  |  |  | Government Personnel | 1 | 26 | 30 | 26 | Planning Engineering and Design |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.0025 | 1.005 | 1.0075 | 1.01 | 1.0125 | 1.0151 | 1.0176 | 1.0201 | 1.03 | 1.04 | 1.0499 | 1.0599 | 1.0715 | 1.0832 | 1.0949 | 1.1065 | 1.1151 | 1.1237 | 1.1322 | 1.1408 | 1.1497 | 1.1585 | 1.1673 | 1.1762 | 1.1853 | 1.1944 | 1.2035 | 1.2126 | 1.222 | 1.2314 | 1.2408 | 1.2502 | 1.2599 | 1.2696 | 1.2793 | 1.289 | 1.299 | 1.309 | 1.319 | 1.329 | 1.3389 | 1.3489 | 1.3589 | 1.3688 | 1.3794 | 1.39 | 1.4007 | 1.4113 | 1.4222 | 1.4331 | 1.4441 | 1.455 | 1.4663 | 1.4776 | 1.4888 | 1.5001 | 1.5114 | 1.5226 | 1.5339 | 1.5451 | 1.5571 | 1.5691 | 1.581 | 1.593 | 1.6054 | 1.6177 | 1.6301 | 1.6424 | 1.6551 | 1.6679 | 1.6806 | 1.6933 | 1.7064 | 1.7196 | 1.7327 | 1.7458 | 1.7593 | 1.7729 | 1.7864 | 1.7999 | 1.8139 | 1.8278 | 1.8418 | 1.8557 | 1.8701 | 1.8845 | 1.8989 | 1.9133 | 1.9281 | 1.9429 | 1.9577 | 1.9726 | 1.9878 | 2.0031 | 2.0184 | 2.0337 | 2.0495 | 2.0652 | 2.081 | 2.0968 | 2.113 | 2.1293 | 2.1455 | 2.1618 | 2.1785 | 2.1953 | 2.212 | 2.2288 | 2.246 | 2.2633 | 2.2806 | 2.2979 | 2.3157 | 2.3335 | 2.3513 | 2.3691 | 2.3875 | 2.4058 | 2.4242 | 2.4425 | 2.4615 | 2.4804 | 2.4993 | 2.5183 | 2.5378 | 2.5573 | 2.5768 | 2.5963 | 2.6164 | 2.6366 | 2.6567 | 2.6768 | 2.6976 | 2.7183 | 2.739 | 2.7598 | 2.7812 | 2.8026 | 2.824 | 2.8453 | 2.8674 | 2.8894 | 2.9115 | 2.9335 | 2.9563 | 2.979 | 3.0018 | 3.0245 | 3.0479 | 3.0714 | 3.0948 | 3.1182 | 3.1424 | 3.1666 | 3.1907 | 3.2149 | 3.2398 | 3.2647 | 3.2897 | 3.3146 | 3.3403 | 3.366 | 3.3916 | 3.4173 | 3.4438 | 3.4703 | 3.4968 | 3.5233 | 3.5506 | 3.5779 | 3.6052 | 3.6325 | 3.6606 | 3.6888 | 3.7169 | 3.7451 | 3.7741 | 3.8031 | 3.8322 | 3.8612 | 3.8911 | 3.921 | 3.951 | 3.9809 | 4.0117 | 4.0426 | 4.0734 | 4.1043 | 4.1361 | 4.1679 | 4.1997 | 4.2315 | 4.2643 | 4.2971 | 4.3299 | 4.3627 | 4.3965 | 4.4303 | 4.4641 | 4.4979 | 4.5328 | 4.5677 | 4.6025 | 4.6374 | 4.6733 | 4.7093 | 4.7452 | 4.7811 | 4.8182 | 4.8553 | 4.8923 | 4.9294 | 4.9676 | 5.0058 | 5.044 | 5.0822 | 5.1216 | 5.1609 | 5.2003 | 5.2397 | 5.2803 | 5.3209 | 5.3615 | 5.4021 | 5.444 | 5.4859 | 5.5277 | 5.5696 | 5.6128 | 5.6559 | 5.6991 | 5.7423 | 5.7868 | 5.8313 | 5.8758 | 5.9203 | 5.9662 | 6.012 | 6.0579 | 6.1038 | 6.1511 | 6.1984 | 6.2457 | 6.293 | 6.3418 | 6.3906 | 6.4393 | 6.4881 | 6.5384 | 6.5887 | 6.639 | 6.6892 | 6.7411 | 6.7929 | 6.8448 | 6.8966 | 6.9501 | 7.0035 | 7.057 | 7.1104 | 7.1655 | 7.2206 | 7.2757 | 7.3308 | 7.3876 | 7.4445 | 7.5013 | 7.5581 | 7.6167 | 7.6752 | 7.7338 | 7.7924 | 7.8528 | 7.9132 | 7.9736 | 8.034 | 8.0962 | 8.1585 | 8.2207 | 8.283 | 8.3472 | 8.4114 | 8.4756 | 8.5398 | 8.606 | 8.6721 | 8.7383 | 8.8045 | 8.8727 | 8.941 | 9.0092 | 9.0774 | 9.1478 | 9.2181 | 9.2885 | 9.3588 | 9.4314 | 9.5039 | 9.5764 | 9.649 | 9.7238 | 9.7985 | 9.8733 | 9.9481 | 10.0252 | 10.1023 | 10.1794 | 10.2565 | 10.336 | 10.4155 | 10.4949 | 10.5744 | 10.6564 | 10.7383 | 10.8203 | 10.9022 | 10.9867 | 11.0712 | 11.1557 | 11.2402 | 8.4302 | 5.6201
| Instructions for Feature Codes 30 and 31: In Cells F27 and F28 Enter the Table 1 class that is going to be used for the 30 and 31 accounts either class 1 or class 2. Inflation factors differ if work is to be performed by Government personnel or AE contractor. Class 1 is for government personnel and Class 2 is for everything else. Class 1 includes salary increases, step increases, health insurance, attrition rates, retirement, etc. Note: the Class 1 factor can be higher than the Class 2 factor, when the FEPCA formula is used by OMB to predict future raises, and this will affect the TPCS. In addition, EC11-2-XXX does not provide a historical index as it is only concerned with future projections. |  |  | Government Personnel | 1 | 27 | 31 | 27 | Construction Management |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.0025 | 1.005 | 1.0075 | 1.01 | 1.0125 | 1.0151 | 1.0176 | 1.0201 | 1.03 | 1.04 | 1.0499 | 1.0599 | 1.0715 | 1.0832 | 1.0949 | 1.1065 | 1.1151 | 1.1237 | 1.1322 | 1.1408 | 1.1497 | 1.1585 | 1.1673 | 1.1762 | 1.1853 | 1.1944 | 1.2035 | 1.2126 | 1.222 | 1.2314 | 1.2408 | 1.2502 | 1.2599 | 1.2696 | 1.2793 | 1.289 | 1.299 | 1.309 | 1.319 | 1.329 | 1.3389 | 1.3489 | 1.3589 | 1.3688 | 1.3794 | 1.39 | 1.4007 | 1.4113 | 1.4222 | 1.4331 | 1.4441 | 1.455 | 1.4663 | 1.4776 | 1.4888 | 1.5001 | 1.5114 | 1.5226 | 1.5339 | 1.5451 | 1.5571 | 1.5691 | 1.581 | 1.593 | 1.6054 | 1.6177 | 1.6301 | 1.6424 | 1.6551 | 1.6679 | 1.6806 | 1.6933 | 1.7064 | 1.7196 | 1.7327 | 1.7458 | 1.7593 | 1.7729 | 1.7864 | 1.7999 | 1.8139 | 1.8278 | 1.8418 | 1.8557 | 1.8701 | 1.8845 | 1.8989 | 1.9133 | 1.9281 | 1.9429 | 1.9577 | 1.9726 | 1.9878 | 2.0031 | 2.0184 | 2.0337 | 2.0495 | 2.0652 | 2.081 | 2.0968 | 2.113 | 2.1293 | 2.1455 | 2.1618 | 2.1785 | 2.1953 | 2.212 | 2.2288 | 2.246 | 2.2633 | 2.2806 | 2.2979 | 2.3157 | 2.3335 | 2.3513 | 2.3691 | 2.3875 | 2.4058 | 2.4242 | 2.4425 | 2.4615 | 2.4804 | 2.4993 | 2.5183 | 2.5378 | 2.5573 | 2.5768 | 2.5963 | 2.6164 | 2.6366 | 2.6567 | 2.6768 | 2.6976 | 2.7183 | 2.739 | 2.7598 | 2.7812 | 2.8026 | 2.824 | 2.8453 | 2.8674 | 2.8894 | 2.9115 | 2.9335 | 2.9563 | 2.979 | 3.0018 | 3.0245 | 3.0479 | 3.0714 | 3.0948 | 3.1182 | 3.1424 | 3.1666 | 3.1907 | 3.2149 | 3.2398 | 3.2647 | 3.2897 | 3.3146 | 3.3403 | 3.366 | 3.3916 | 3.4173 | 3.4438 | 3.4703 | 3.4968 | 3.5233 | 3.5506 | 3.5779 | 3.6052 | 3.6325 | 3.6606 | 3.6888 | 3.7169 | 3.7451 | 3.7741 | 3.8031 | 3.8322 | 3.8612 | 3.8911 | 3.921 | 3.951 | 3.9809 | 4.0117 | 4.0426 | 4.0734 | 4.1043 | 4.1361 | 4.1679 | 4.1997 | 4.2315 | 4.2643 | 4.2971 | 4.3299 | 4.3627 | 4.3965 | 4.4303 | 4.4641 | 4.4979 | 4.5328 | 4.5677 | 4.6025 | 4.6374 | 4.6733 | 4.7093 | 4.7452 | 4.7811 | 4.8182 | 4.8553 | 4.8923 | 4.9294 | 4.9676 | 5.0058 | 5.044 | 5.0822 | 5.1216 | 5.1609 | 5.2003 | 5.2397 | 5.2803 | 5.3209 | 5.3615 | 5.4021 | 5.444 | 5.4859 | 5.5277 | 5.5696 | 5.6128 | 5.6559 | 5.6991 | 5.7423 | 5.7868 | 5.8313 | 5.8758 | 5.9203 | 5.9662 | 6.012 | 6.0579 | 6.1038 | 6.1511 | 6.1984 | 6.2457 | 6.293 | 6.3418 | 6.3906 | 6.4393 | 6.4881 | 6.5384 | 6.5887 | 6.639 | 6.6892 | 6.7411 | 6.7929 | 6.8448 | 6.8966 | 6.9501 | 7.0035 | 7.057 | 7.1104 | 7.1655 | 7.2206 | 7.2757 | 7.3308 | 7.3876 | 7.4445 | 7.5013 | 7.5581 | 7.6167 | 7.6752 | 7.7338 | 7.7924 | 7.8528 | 7.9132 | 7.9736 | 8.034 | 8.0962 | 8.1585 | 8.2207 | 8.283 | 8.3472 | 8.4114 | 8.4756 | 8.5398 | 8.606 | 8.6721 | 8.7383 | 8.8045 | 8.8727 | 8.941 | 9.0092 | 9.0774 | 9.1478 | 9.2181 | 9.2885 | 9.3588 | 9.4314 | 9.5039 | 9.5764 | 9.649 | 9.7238 | 9.7985 | 9.8733 | 9.9481 | 10.0252 | 10.1023 | 10.1794 | 10.2565 | 10.336 | 10.4155 | 10.4949 | 10.5744 | 10.6564 | 10.7383 | 10.8203 | 10.9022 | 10.9867 | 11.0712 | 11.1557 | 11.2402 | 8.4302 | 5.6201
|  |  |  | 1 | Government Personnel |  |  |  | Table 1 FY26 Table 1 Class 1 Factors | 31 March 2024 |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1% |  |  |  | 1% |  |  |  | 3.9% |  |  |  | 4.4% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1% |  |  |  | 3.1%
|  |  |  | 2 | AE Contractor |  |  |  | Table 1 FY26 Table 1 Class 2 Factors | 31 March 2024 |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1 |  |  |  | 1% |  |  |  | 1% |  |  |  | 4.5% |  |  |  | 3% |  |  |  | 2.7% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6% |  |  |  | 2.6%
Enter "updating factor" 1 and 2 for previous year, current year, and projected years. Historical years, change to 1.0%.
Note on J30: Table 1 Factors are yearly factors for inflating costs to future values and do not include historical rates. Rates will be shown in the first calendar year quarter. Values will be changed to 1.00 for quarters where CWCCIS has a historical basis.
Note on J31: Table 1 Factors are yearly factors for inflating costs to future values and do not include historical rates. Rates will be shown in the first calendar year quarter. Values will be changed to 1.00 for quarters where CWCCIS has a historical basis.

## Midpoint Calculator
Feature | 07 POWER PLANT |  |  |  |  | NOT USED |  | Days
| Month | Day | Year | CWCCIS | 1 | 02 RELOCATIONS | January | 31
Construction Start | 10 | 12 | 2024 | 2025Q1 | 2 | 03 RESERVOIRS | February | 28.25 | Use this sheet to determine the midpoint of construction.
Construction End | 3 | 12 | 2030 | 2030Q2 | 3 | 04 DAMS | March | 31
Midpoint | 6 | 27 | 2027 | 2027Q3 | 4 | 05 LOCKS | April | 30 | Cells with gray fill and blue text are input cells.
Feature | NOT USED |  |  |  | 5 | 06 FISH & WILDLIFE FACILITIES | May | 31
| Month | Day | Year | CWCCIS | 6 | 07 POWER PLANT | June | 30 | Cells with yellow fill are output cells.
Construction Start | 1 | 1 | 2000 | 2000Q2 | 7 | 08 ROADS, RAILROADS & BRIDGES | July | 31
Construction End | 1 | 1 | 2001 | 2001Q2 | 8 | 09 CHANNELS & CANALS | August | 31
Midpoint | 7 | 2 | 2000 | 2000Q4 | 9 | 10 BREAKWATER & SEAWALLS | September | 30
Feature | NOT USED |  |  |  | 10 | 11 LEVEES & FLOODWALLS | October | 31
| Month | Day | Year | CWCCIS | 11 | 12 NAVIGATION PORTS & HARBORS | Novermber | 30
Construction Start | 1 | 1 | 2000 | 2000Q2 | 12 | 13 PUMPING PLANT | December | 31
Construction End | 1 | 1 | 2001 | 2001Q2 |  | 14 RECREATION FACILITIES
Midpoint | 7 | 2 | 2000 | 2000Q4 |  | 15 FLOODWAY CONTROL & DIVERSION STRUCTURE
Feature | NOT USED |  |  |  |  | 16 BANK STABILIZATION
| Month | Day | Year | CWCCIS |  | 17 BEACH REPLENISHMENT
Construction Start | 1 | 1 | 2000 | 2000Q2 |  | 18 CULTURAL RESOURCE PRESERVATION
Construction End | 1 | 1 | 2001 | 2001Q2 |  | 19 BUILDINGS, GROUNDS & UTILITIES
Midpoint | 7 | 2 | 2000 | 2000Q4 |  | 20 PERMANENT OPERATING EQUIPMENT
Feature | NOT USED |  |  |  |  | 30 Planning Engineering and Design
| Month | Day | Year | CWCCIS |  | 31 Construction Management
Construction Start | 1 | 1 | 2000 | 2000Q2
Construction End | 1 | 1 | 2001 | 2001Q2
Midpoint | 7 | 2 | 2000 | 2000Q4
Feature | NOT USED
| Month | Day | Year | CWCCIS
Construction Start | 1 | 1 | 2000 | 2000Q2
Construction End | 1 | 1 | 2001 | 2001Q2
Midpoint | 7 | 2 | 2000 | 2000Q4
Feature | NOT USED
| Month | Day | Year | CWCCIS
Construction Start | 1 | 1 | 2000 | 2000Q2
Construction End | 1 | 1 | 2001 | 2001Q2
Midpoint | 7 | 2 | 2000 | 2000Q4