## Instructions
Total Project Cost Summary
B-1. General.
A Total Project Cost Summary (TPCS) is required for all civil works cost estimates submitted for approval at all levels within the U.S. Army Corps of Engineers (Corps). The summary and supporting contract cost sheets are the basis for the official Project Cost Estimate (PB-3) ER 11-2-240. It is a living document, developed from feasibility to project completion to present current working estimate (cost, schedule (escalation), risks (contingencies). The TPCS must consider current escalation tables, which are updated twice annually: March and September.
The TPC reflects all applicable project feature costs, contingencies, escalation to Project First Cost and inflation to Fully Funded Project Costs and is presented in Federal and non-Federal dollars. The TPC emerges when the TPCS form is completed (shown in Figures B-2). The TPCS is a PDT product. While the cost engineer prepares the basic elements of the form, the PM, Real Estate and Construction offices play a major role in establishing Program Year, Federal and non-Federal shares, spent costs, 01 Lands and Damages, 30 PED and 31 Construction Management values.
For the cost engineer, the Total Project Cost form is developed and presented with three different estimates over time: Estimated Cost (Price Level), Project First Cost - Constant Dollar, and Total Project Cost – Fully Funded (reference Figure B-2).
i. Estimated Cost (Effective Price Level) (TPCS columns C through F) is the current developed cost estimate which includes contingencies. The effective price level date for Estimated Cost (shown in DAY MONTH YYYY format) is commonly reported as the previous 1 Oct 20XX to support economic study and escalation to Project First Cost.
ii. Project First Cost - Constant Dollar Cost (TPCS columns G through K) is the Estimated Cost then escalated to the PROGRAM YEAR effective price level by applying the appropriate escalation from the CWCCIS tables. The Project First Cost - Constant Dollar (shown in 1 OCT 20XX) is the cost estimate used in feasibility reports and Chief of Engineer’s Report (Chief’s Report) for Congressional funding requests.
iii. Total Project Cost (TPCS columns L through O) is the FULLY FUNDED WITH INFLATION to represent the total cost of the project. The inflation to midpoint of each activity is added from the Project First Cost column set. Total Project Cost (or Total Cost of Construction of GNFs when discussing navigation projects) is the cost estimate used in Project Partnership Agreements and Integral Determination Reports. Total Project Cost is the cost estimate provided to non-Federal sponsors for their use in financial planning as it provides information regarding the overall non-Federal cost sharing obligation.
The Project First Cost – Constant Dollar Cost estimate is to be used in the Chief's Reports and other decision documents to support the funding request. The Project First Cost should include, among other things, an estimate of: (i) construction and management costs, including both Federal costs and non-Federal sponsor in-kind contributions, as applicable; (ii) planning engineering and design costs; (iii) lands, easements, rights-of-way, relocations and dredged materials (LERRD) values; and (iv) contingencies. Where several years elapse between the signing of the Chief's Report and the consideration of legislation to authorize a project, the Project First Cost must be updated to reflect the current Project First Cost date for Congressional funding consideration, in accordance with ER 1110-2-1302.
Figure B-1 illustrates the TPC process. Figures B-2 (summary sheet) and B-3 (sample supporting sheet) are examples based upon feasibility estimate reporting requirements in Engineer Regulation (ER) 1105-2-100, Planning Guidance Notebook. “Two project cost estimates shall be displayed in the feasibility report; one based on constant dollars and one based on projected inflation rates.” The guidance notebook is referring to the Project First Cost and the Total Project Cost columns J and O. The TPCS (summary sheet) is a signature document for the appropriate district managerial approvals. ER 1105-2-100 states that project cost estimates will be prepared by or reviewed by the cost engineering office in the district and the chief of that office will sign the estimate. Real estate estimates included in the project cost are reviewed, approved, and signed by the chief or designee of the real estate office. Project Management is the third required signature that assumes responsibility for the TPCS value. Figure B-2 also lists other review/approval signatures that may be a district requirement.
Preparing a TPC during the feasibility phase is required, because it is the first document that will show the estimated total project cost at the anticipated authorizing budget year and forecast the total project cost inflated through construction based on the known scope and schedule.
B-2. Sample TPCS (Figure B-2) is in a spreadsheet format beginning with the total project cost summary followed by contract cost summary supporting sheets appearing like Figure B-3. The TPCS template can be downloaded from the Cost MCX website.
B-3. TPCS Form Procedures
a. Estimated Cost (Price Level)
TPCS Headers: Ensure the form presents the formal project name, project number, location, author and date.
Column A: WBS Number – Enter the Civil Works Breakdown code for each feature (refer to the Civil Works Work Breakdown Structure Appendix).
Column B: Civil Works Feature and Sub-Feature Description - For the summary sheet Figure B-2, enter the feature code title. For the supporting sheets like Figure B-3, enter and identify the project phase, contract, etc. as well as the CWWBS description of the Item. For Figure B-3, separate lines for the same WBS element may be prudent, pending certain programs or presentations desired. The various phases or contracts on the Figure B-3 sheets is to make distinction between varying schedules of occurrence, associated escalation and risks (contingencies).
The first primary column set, sub columns C through F, is the estimated cost plus contingencies, typically in current or most recent estimated dollars (must be less than 2 years old) that includes all feature accounts: the MCACES construction estimate(s), estimates for lands and damages, preconstruction, engineering and design, and construction management. The following paragraphs are instructions for completing data entry for each scheduled contract (figure B-2 and B-3). Figure B-2 serves as the summary roll-up from the supporting sheets such as Figure B-3.
Column C: COST- Entered in this column are the estimates of those costs that require funding or are remaining costs yet to incur. The costs should reflect the actual estimated costs in $1000s based on the previous October price level that the estimate was prepared. Note: For the Real Estate estimate, ensure the estimate is recent and the contingencies (incremental costs) are separated from the appraisal quote for presentation in the contingency column.
Column D: CNTG (contingency) - This is the dollar amount of contingency determined from a risk-based analysis. It is the result of Column C times the entered contingency percent in Column E or an actual amount determined by a cost risk analysis.
Column E: CNTG % (contingency percentage) - Enter the percentage of contingency (from risk analysis). For 30 and 31 accounts you may want to use the average of the construction element contingencies in lieu of developing a separate contingency. For 01 Lands and Damages, the Chief of Real Estate is responsible to provide a signed estimate of costs and should be able to provide contingency data, also referred to as incremental costs. Ensure that the real estate contingency is separated from the real estate estimate and presented separately as contingency. Contingency is the full dollar value of the various features, converted to a contingency. Reliance solely on a per cent value can induce errors when differing contingency sources such as real estate are also used.
Column F: TOTAL - This is the sum of columns C and D.
b. Project First Cost – Constant Dollar.
The second primary column set is the Project First Cost, also known as the Constant Dollar total. This totaled cost is the one reflected in all Chief’s reports for requested funding: effective price level for the year of the Chief’s Report submissions. Typically the year of the report submission is the year prior to the anticipated funding. This total can become more complicated for ongoing projects with spent costs that require additional funding.
Column G; - ESC (escalation) This column is the percentage of escalation from the first column set to the PROGRAM YEAR DATE. This moves the estimate cost from the price level when it was prepared to the Program Year price on a constant dollar basis. This escalation is calculated utilizing the Civil Works Construction Cost Index System (CWCCIS) found in EM 1110-2-1304. The CWCCIS is a reflection of the OMB projected rates for future costs, experienced inflation for past costs for each of the Feature categories. The escalation tables are updated twice annually: March and September. To determine the escalation percent, locate the CWCCIS index factors of the Feature account or element for the 1st quarter date of the program year and divide by the index factor of the established or initial estimate date (no less than 2 years old). Subtract value of 1 and multiply by 100 to obtain the percent escalation.
Column H; COST - This is the cost from Column C with the added percent of escalation computed in Column G.
Estimated Cost to Project First Cost
|  |  |  | Cost Index |  | Project First Cost
EPL Estimate + Contingency | + | Contingency | x | (Budget Year) | = | Budget Year
(1 Oct 20XX) Risk Based
(Current Dollars) |  | (risk based) |  | Cost Index |  | Constant Dollars
(EPL - Current Estimate)
Column I: CNTG (contingency) - This is the Contingency value from Column D with the added escalation determined in Column G.
Column J: TOTAL- This is the sum of Columns H and I. This is the constant dollar estimate at PROGRAM YEAR price level, 1 October, also referred to as Project First Cost, excluding any project spent costs, within the Chief’s Report. For ongoing projects, the Project First Cost would include Spent Costs to reflect total first costs for the project.
SPENT THRU - Enter the amount of EXPENDED Federal funds for each Feature (this information is commonly obtained from project or program managers. Caution here is advised. If these funds have been expended by a sponsor, but the Government has not yet spent reflective Federal funds, those costs must remain in the Project First Costs, excluding escalation and contingencies. The spent costs of FEDERAL project dollars, already received and expended, is entered as actual amount spent in the year it was spent. The year of the expenditure must exclude inflation and contingencies because no further inflation or risks on these costs can occur. This is entered on the TPCS (figure B- 2) (PAGE 1) only.
c. Total Project Cost (Fully Funded with Inflation).
The third primary column of the TPCS is the total project cost estimate inflated through project completion, which is the second cost estimate referred to from the Planning Guidance Notebook. For financial analysis, an inflated dollar basis is to be used for the sponsor’s information. Reasonably accurate and complete cost estimates and schedules are necessary for the Federal Government and the non-Federal sponsors to make prudent financial and budgetary decisions in obtaining and expending funds.
The project schedule is used to forecast when project elements will begin and the duration of each element. Knowing how each activity/element is funded and its respective duration will illustrate when the costs are expected to occur. In cases where multiple construction contracts or phases are planned, each should be addressed separately to present a more realistic escalation to design and construction midpoints for each contract. It is recommended that separate contracts be presented as a subset spreadsheet with values that roll up to the summary level total (Figure B-3).
Column L: INFLATED – This is the inflation percentage from PROGRAM YEAR price level to the MIDPOINT of the performance period of each Feature item. Midpoint dates are determined from the Project Schedule. The amount shown in the column is the percentage of increase.
For construction contracts and other project elements having a relatively short duration, choosing an index coinciding with the midpoint of the duration may be adequate to escalate the costs for inflation. Also, activities/elements that are primarily level of effort, where costs are relatively consistent throughout the duration, a date at the midpoint of the duration is usually adequate to select the CWCCIS index to inflate the activity/element cost.
Project First Cost |  | Cost Index
Budget Year | x | (Midpt of Activity) | = | Fully Funded
Constant Dollars |  | Cost Index
(Budget Year)
m. Column M: COST- Is the cost from Column H with midpoint inflation added from the CWCCIS calculations (column L).
n. Column N: CNTG (contingency) - This is the Contingency dollar value from Column I with the added inflation factor (column L).
o. Column O: FULL (fully funded amount) Is the fully funded estimate amount for the Item (Column M + Column N + Spent Costs). The overall summation of column O on the TPCS (Figure B-2) is the TOTAL PROJECT COST ESTIMATE inflated through the Project Schedule midpoint for each separate activity.
p. Column P: Found on the supporting sheets, such as Figure B-3, for the TPC summary, the column presents the midpoint date for the inflated value for each Feature.
The costs of water resources studies and projects developed by the Corps are shared between Federal and non-Federal entities as defined in laws and administrative provisions. The Water Resources Development Act of 1986, established new cost sharing rules for all studies and projects conducted by the Corps. The cost sharing provisions of the Water Resources Development Act of 1986 place greater financial responsibilities on non-Federal sponsors of Corps projects. The amount of non-Federal share varies depending upon the project purpose and the general and specific laws that apply to each project. Coordination with Project and Program Management is required to clarify this share percentage. Cost sharing can and does change over time.
The total project cost inflated through construction is divided into Federal cost and non-Federal cost. The non-Federal cost is for the sponsor’s information and financial analysis. The cost engineer must coordinate with the project manager to determine the appropriate cost sharing percentages applicable to the project. To illustrate, the cost of feasibility studies is shared equally (50/50) and the remaining project cost may be shared 25 percent non-Federal cost and 75 percent Federal cost. Guidance on cost sharing for each civil works mission and authority is presented in ER 1105-2-100 and coordination with the project manager is necessary.
B-4. Section 902 Project Cost Limit.
When appropriate for authorized projects spanning several years, the TPCS is updated annually for comparison to the Section 902 project cost limit. It can be computed and presented on the updated TPCS to serve as a current working estimate.
The maximum project cost limit imposed by Section 902 is a numerical value specified by law, which must be computed in a legally supportable manner. It is not an estimate of the current cost of the project. The construction component of the authorized cost will be updated to account for current scope, quantities, costs, schedules and risks and applying escalation using the current CWCCIS escalation tables. The real estate component of the authorized cost will be updated to account for historical inflation based on changes to the Consumer Price Index. ER 1105-2-100, appendix G, paragraph G-15a provides detailed guidance on the calculations necessary to determine the numerical value.

## Input
DISTRICT | XXX District
PROJECT NAME | Project X Major Rehabilitation
PROJECT NUMBER | P2 xxxxxx
PROJECT LOCATION | Somewhere
PROGRAM YEAR | 2020
ESTIMATE PREPARED DATE | 2019-10-01
DATE TPCS PREPARED | 2019-10-01
ENGINEERING REPORT AS BASIS | Project X Major Rehabilitation Report June 2019
ENGINEERING & DESIGN PHASE -> 30 ACCOUNT |  | % of Construct | Districts % Vary | 30/31 Accounts
PROJECT MANAGER, xxx | Program Management: | 2.5% | 2.5% | 30 | 29.5% | Sum per % of 30 Account | Project Management
CHIEF, DPM, xxx |  |  |  | 30 |  |  | Planning & Environmental Compliance
CHIEF, PLANNING, xxx | Planning & Environmental Compliance: | 1% | 1% | 30 |  |  | Engineering & Design
CHIEF, ENGINEERING, xxx | Engineering & Design: | 15% | 15% | 30 |  |  | Reviews, ATRs, IEPRs, VE
CHIEF, COST ENGINEERING, xxx | Reviews, ATRs, IEPRs, VE: | 1% | 1% | 30 |  |  | Life Cycle Updates (cost, schedule, risks)
CHIEF, ENGINEERING, xxx | Life Cycle Updates (cost, schedule, risks): | 1% | 1% | 30 |  |  | Contracting & Reprographics
| Contracting & Reprographics: | 1% | 1% | 30 |  |  | Engineering During Construction
CHIEF, CONTRACTING,xxx | Engineering During Construction: | 3% | 3% | 30 |  |  | Planning During Construction
CHIEF, ENGINEERING, xxx | Planning During Construction | 2% | 2% | 30 |  | Escalate to Mid Point Construction | Adaptive Management & Monitoring
CHIEF, PLANNING, xxx | Adaptive Mgmt & Monitoring: | 1% | 3% | 30
CHIEF, OPERATIONS, xxx | Project Operations | 1% | 1% | 31
CONSTRUCTION PHASE -> 31 ACCOUNT
CHIEF, CONSTRUCTION, xxx | Supervision & Assurance: | 10% | 10% | 31 | 14.5% | Sum per % of 31 Account
CHIEF, OPERATIONS, xxx | Project Operation: | 2% | 2% | 30
CHIEF, DPM, xxx | Program Management: | 2.5% | 2.5% | 31
[5 empty] | 44% | Sum per % of 30 & 31 Accounts
REAL ESTATE -> 01 ACCOUNT
CHIEF, REAL ESTATE, xxx
CULTURAL RESOURCES -> 18 ACCOUNT
CHIEF, PLANNING, xxx
SPENT THRU FYXX COSTS
CHIEF, PM-PB, xxxx
1980-10-01 | 1981 | 1981Q1 | 29495
1981-10-01 | 1982 | 1982Q1 | 29860
1982-10-01 | 1983 | 1983Q1 | 30225
1983-10-01 | 1984 | 1984Q1 | 30590
1984-10-01 | 1985 | 1985Q1 | 30956
1985-10-01 | 1986 | 1986Q1 | 31321
1986-10-01 | 1987 | 1987Q1 | 31686
1987-10-01 | 1988 | 1988Q1 | 32051
1988-10-01 | 1989 | 1989Q1 | 32417
1989-10-01 | 1990 | 1990Q1 | 32782
1990-10-01 | 1991 | 1991Q1 | 33147
1991-10-01 | 1992 | 1992Q1 | 33512
1992-10-01 | 1993 | 1993Q1 | 33878
1993-10-01 | 1994 | 1994Q1 | 34243
1994-10-01 | 1995 | 1995Q1 | 34608
1995-10-01 | 1996 | 1996Q1 | 34973
1996-10-01 | 1997 | 1997Q1 | 35339
1997-10-01 | 1998 | 1998Q1 | 35704
1998-10-01 | 1999 | 1999Q1 | 36069
1999-10-01 | 2000 | 2000Q1 | 36434
2000-10-01 | 2001 | 2001Q1 | 36800
2001-10-01 | 2002 | 2002Q1 | 37165
2002-10-01 | 2003 | 2003Q1 | 37530
2003-10-01 | 2004 | 2004Q1 | 37895
2004-10-01 | 2005 | 2005Q1 | 38261
2005-10-01 | 2006 | 2006Q1 | 38626
2006-10-01 | 2007 | 2007Q1 | 38991
2007-10-01 | 2008 | 2008Q1 | 39356
2008-10-01 | 2009 | 2009Q1 | 39722
2009-10-01 | 2010 | 2010Q1 | 40087
2010-10-01 | 2011 | 2011Q1 | 40452
2011-10-01 | 2012 | 2012Q1 | 40817
2012-10-01 | 2013 | 2013Q1 | 41183
2013-10-01 | 2014 | 2014Q1 | 41548
2014-10-01 | 2015 | 2015Q1 | 41913
2015-10-01 | 2016 | 2016Q1 | 42278
2016-10-01 | 2017 | 2017Q1 | 42644
2017-10-01 | 2018 | 2018Q1 | 43009
2018-10-01 | 2019 | 2019Q1 | 43374
2019-10-01 | 2020 | 2020Q1 | 43739
2020-10-01 | 2021 | 2021Q1 | 44105
2021-10-01 | 2022 | 2022Q1 | 44470
2022-10-01 | 2023 | 2023Q1 | 44835
2023-10-01 | 2024 | 2024Q1 | 45200
2024-10-01 | 2025 | 2025Q1 | 45566
2025-10-01 | 2026 | 2026Q1 | 45931
2026-10-01 | 2027 | 2027Q1 | 46296
2027-10-01 | 2028 | 2028Q1 | 46661
2028-10-01 | 2029 | 2029Q1 | 47027
2029-10-01 | 2030 | 2030Q1 | 47392
2030-10-01 | 2031 | 2031Q1 | 47757
2031-10-01 | 2032 | 2032Q1 | 48122
2032-10-01 | 2033 | 2033Q1 | 48488
2033-10-01 | 2034 | 2034Q1 | 48853
2034-10-01 | 2035 | 2035Q1 | 49218
2035-10-01 | 2036 | 2036Q1 | 49583
2036-10-01 | 2037 | 2037Q1 | 49949
2037-10-01 | 2038 | 2038Q1 | 50314
2038-10-01 | 2039 | 2039Q1 | 50679
2039-10-01 | 2040 | 2040Q1 | 51044
2040-10-01 | 2041 | 2041Q1 | 51410
2041-10-01 | 2042 | 2042Q1 | 51775
2042-10-01 | 2043 | 2043Q1 | 52140
2043-10-01 | 2044 | 2044Q1 | 52505
2044-10-01 | 2045 | 2045Q1 | 52871
2045-10-01 | 2046 | 2046Q1 | 53236
2046-10-01 | 2047 | 2047Q1 | 53601
2047-10-01 | 2048 | 2048Q1 | 53966
2048-10-01 | 2049 | 2049Q1 | 54332
2049-10-01 | 2050 | 2050Q1 | 54697
2050-10-01 | 2051 | 2051Q1 | 55062
2051-10-01 | 2052 | 2052Q1 | 55427
2052-10-01 | 2053 | 2053Q1 | 55793
2053-10-01 | 2054 | 2054Q1 | 56158
2054-10-01 | 2055 | 2055Q1 | 56523
2055-10-01 | 2056 | 2056Q1 | 56888
2056-10-01 | 2057 | 2057Q1 | 57254
2057-10-01 | 2058 | 2058Q1 | 57619
2058-10-01 | 2059 | 2059Q1 | 57984
2059-10-01 | 2060 | 2060Q1 | 58349
2060-10-01 | 2061 | 2061Q1 | 58715
2061-10-01 | 2062 | 2062Q1 | 59080
2062-10-01 | 2063 | 2063Q1 | 59445
2063-10-01 | 2064 | 2064Q1 | 59810
2064-10-01 | 2065 | 2065Q1 | 60176
2065-10-01 | 2066 | 2066Q1 | 60541
2066-10-01 | 2067 | 2067Q1 | 60906
2067-10-01 | 2068 | 2068Q1 | 61271
2068-10-01 | 2069 | 2069Q1 | 61637
2069-10-01 | 2070 | 2070Q1 | 62002
2070-10-01 | 2071 | 2071Q1 | 62367
2071-10-01 | 2072 | 2072Q1 | 62732
2072-10-01 | 2073 | 2073Q1 | 63098
2073-10-01 | 2074 | 2074Q1 | 63463
2074-10-01 | 2075 | 2075Q1 | 63828
2075-10-01 | 2076 | 2076Q1 | 64193
2076-10-01 | 2077 | 2077Q1 | 64559
2077-10-01 | 2078 | 2078Q1 | 64924
2078-10-01 | 2079 | 2079Q1 | 65289
2079-10-01 | 2080 | 2080Q1 | 65654
2080-10-01 | 2081 | 2081Q1 | 66020
2081-10-01 | 2082 | 2082Q1 | 66385
2082-10-01 | 2083 | 2083Q1 | 66750
2083-10-01 | 2084 | 2084Q1 | 67115
2084-10-01 | 2085 | 2085Q1 | 67481
2085-10-01 | 2086 | 2086Q1 | 67846
2086-10-01 | 2087 | 2087Q1 | 68211
2087-10-01 | 2088 | 2088Q1 | 68576
2088-10-01 | 2089 | 2089Q1 | 68942
2089-10-01 | 2090 | 2090Q1 | 69307
2090-10-01 | 2091 | 2091Q1 | 69672
2091-10-01 | 2092 | 2092Q1 | 70037
2092-10-01 | 2093 | 2093Q1 | 70403
2093-10-01 | 2094 | 2094Q1 | 70768
2094-10-01 | 2095 | 2095Q1 | 71133
2095-10-01 | 2096 | 2096Q1 | 71498
2096-10-01 | 2097 | 2097Q1 | 71864
2097-10-01 | 2098 | 2098Q1 | 72229
2098-10-01 | 2099 | 2099Q1 | 72594
2099-10-01 | 2100 | 2100Q1 | 72959
2100-10-01 | 2101 | 2101Q1 | 73324

## TPCS
|  | Legend |  | Represents Formula's | 0 | Cell Entry | [19 empty] | 0 |  | 0 | 0 | Check
Schedule
Estimate PL INDEX | Prog Year Index | MidPoint Index | Time Period | CWCCIS CAT USED |  | Quarter
Column to check for math errors ( Adds up three ways.)
[8 empty] | 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 |  | 15 | 16 | 17 | 18 | 19 | Numbers show up three times
[8 empty] | 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 12: XXX District |  |  | PREPARED: | 2019-10-01
[9 empty] | PROJECT NO: | P2 xxxxxx | [8 empty] | POC: | CHIEF, COST ENGINEERING, xxx
[9 empty] | LOCATION: | Somewhere
[9 empty] | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
[8 empty] | 1: Civil Works Work Breakdown Structure; 3: ESTIMATED COST; 8: PROJECT FIRST COST (Constant Dollar Basis) | TOTAL PROJECT COST (FULLY FUNDED)
[19 empty] | Program Year (Budget EC): |  | 2020
[19 empty] | Effective Price Level Date: |  | 1 OCT 19
[21 empty] | Spent Thru: | TOTAL FIRST COST
[9 empty] | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | 2023-10-01 |  | INFLATED | COST | CNTG | FULL
[9 empty] | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | ($K) | ($K) | (%) | ($K) | ($K) | ($K)
[9 empty] | A | B | C | D | E | F |  | G | H | I | J |  |  | K | L | M | N | O
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 03 | RESERVOIRS | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 04 | DAMS | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 05 | LOCKS | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 07 | POWER PLANT | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 09 | CHANNELS & CANALS | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[5 empty] | Pull Down Menus for your Feature Accounts => |  |  |  | 10 | BREAKWATER & SEAWALLS | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[24 empty] | _ | _ | _ | bar: 3 to 4; 6; 9 to 11; 13
[10 empty] | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 |  | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0 |  | 0 | 0 | Estimate Check
Program yr check
[9 empty] | 01 | LANDS AND DAMAGES | 0 | 0 | - | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0 |  |  |  | FF Check | 0
[5 empty] | PED % of Construction Contract (w/o Cont) | #DIV/0! |  |  | 30 | PLANNING, ENGINEERING & DESIGN | 0 | 0 | 0% | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
COLUMN TO CHECK SPREAD SHEET
[5 empty] | % CM of Construction Contract (w/o Cont) | #DIV/0! |  |  | 31 | CONSTRUCTION MANAGEMENT | 0 | 0 | 0% | 0 |  | - | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0
[10 empty] | PROJECT COST TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  | 0 | 0 | - | 0 | 0 | 0 |  | 0 | 0
[8 empty] | 3: CHIEF, COST ENGINEERING, xxx | [5 empty] | 0 | DIFFERENCE
[24 empty] | ESTIMATED TOTAL PROJECT COST: |  | 0 |  | 0 | CHECK COST | bar: 2 to 5
[8 empty] | 3: PROJECT MANAGER, xxx | [5 empty] | ======
[28 empty] | 0 | COMPLETED COST | bar: 2 to 5
[8 empty] | 3: CHIEF, REAL ESTATE, xxx | [6 empty] | COST NOT IN BELOW SHEET
CHIEF, PLANNING, xxx
SUMMED COST IN BELOW SHEETS
[8 empty] | 3: CHIEF, ENGINEERING, xxx | [5 empty] | 0 | FUTURE COST |  | 0
CHIEF, OPERATIONS, xxx
CHIEF, CONSTRUCTION, xxx
CHIEF, CONTRACTING,xxx
CHIEF, PM-PB, xxxx
CHIEF, DPM, xxx
| Pg Brk |  |  |  |  | 1 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  | Program Year (Budget EC): |  |  | 2020
[8 empty] | 9 |  |  | Effective Price Level: |  |  | 2023-10-01 |  | Effective Price Level Date: |  |  | 1 OCT 19
[8 empty] | 10 |  |  |  |  | RISK BASED
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 1 or CONTRACT 1
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
[8 empty] | 1: 23; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 24 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
25
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 26 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 27
[8 empty] | 28 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 29 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 31 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 33 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 34 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 35 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 36 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 37 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 38 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 39 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 39 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 31 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 40 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 31 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 41 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 31 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 42 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 43
[8 empty] | 1: 44; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 45 | [5 empty] | 0
| Pg Brk |  |  |  |  | 2 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  | Program Year (Budget EC): |  |  | 2020
[8 empty] | 9 |  |  | Effective Price Level: |  |  | 2023-10-01 |  | Effective Price Level Date: |  |  | 1 OCT 19
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 2 or CONTRACT 2
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 | No del | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
| Pg Brk |  |  |  |  | 3 |  | 1: 6 | [5 empty] | 0
[8 empty] | 1 | [5 empty] | **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  | Program Year (Budget EC): |  |  | 2020
[8 empty] | 9 |  |  | Effective Price Level: |  |  | 2023-10-01 |  | Effective Price Level Date: |  |  | 1 OCT 19
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 3 or CONTRACT 3
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
| Pg Brk |  |  |  |  | 4 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  |  |  | Program Year (Budget EC): | 2020
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2023-10-01; 10: Effective Price Level Date:; 11: 1 OCT 19 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 4 or CONTRACT 4
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
| Pg Brk |  |  |  |  | 5 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  |  |  | Program Year (Budget EC): | 2020
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2023-10-01; 10: Effective Price Level Date:; 11: 1 OCT 19 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 5 or CONTRACT 5
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
| Pg Brk |  |  |  |  | 6 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  |  |  | Program Year (Budget EC): | 2020
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2023-10-01; 10: Effective Price Level Date:; 11: 1 OCT 19 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 6 or CONTRACT 6
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
| Pg Brk |  |  |  |  | 7 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  |  |  | Program Year (Budget EC): | 2020
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2023-10-01; 10: Effective Price Level Date:; 11: 1 OCT 19 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 7 or CONTRACT 7
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
| Pg Brk |  |  |  |  | 8 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  |  |  | Program Year (Budget EC): | 2020
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2023-10-01; 10: Effective Price Level Date:; 11: 1 OCT 19 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 8 or CONTRACT 8
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
| Pg Brk |  |  |  |  | 9 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
| CWCCIS |  | Time Period |  |  | Schedule |  | 1: 6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  |  |  | Program Year (Budget EC): | 2020
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2023-10-01; 10: Effective Price Level Date:; 11: 1 OCT 19 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 9 or CONTRACT 9
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
| Pg Brk |  |  |  |  | 9 |  | 1: 1; 6: **** CONTRACT COST SUMMARY ****
2
[8 empty] | 1: 3; 1: PROJECT:; 2: Project X Major Rehabilitation; 11: DISTRICT:; 13: XXX District |  |  | PREPARED: | 2019-10-01
[8 empty] | 4 | LOCATION: | Somewhere | [8 empty] | POC: |  | CHIEF, COST ENGINEERING, xxx
[8 empty] | 5 | This Estimate reflects the scope and schedule in report; |  | Project X Major Rehabilitation Report June 2019
| CWCCIS |  | Time Period |  |  | Schedule |  | 1: 6
[8 empty] | 7 | Civil Works Work Breakdown Structure |  | ESTIMATED COST |  |  |  |  | PROJECT FIRST COST (Constant Dollar Basis) |  |  |  |  | TOTAL PROJECT COST (FULLY FUNDED)
[8 empty] | 8 |  |  | Estimate Prepared: |  |  | 2019-10-01 |  |  |  | Program Year (Budget EC): | 2020
[8 empty] | 1: 9; 3: Effective Price Level:; 6: 2023-10-01; 10: Effective Price Level Date:; 11: 1 OCT 19 |  | FULLY FUNDED PROJECT ESTIMATE
10
| Price Level of Estimate |  | 2023(Oct - Dec) |  | Price level date of M2 ==> | 2024Q1 |  | 11 | WBS | Civil Works | COST | CNTG | CNTG | TOTAL |  | ESC | COST | CNTG | TOTAL |  | Mid-Point | INFLATED |  | COST | CNTG | FULL
| Program Year Price Level |  | 2019(Oct - Dec) |  | Program Year Price Level ==> | 2020Q1 |  | 12 | NUMBER | Feature & Sub-Feature Description | ($K) | ($K) | (%) | ($K) |  | (%) | ($K) | ($K) | ($K) |  | Date | (%) |  | ($K) | ($K) | ($K)
[8 empty] | 13 | A | B | C | D | E | F |  | G | H | I | J |  | P | L |  | M | N | O
[8 empty] | 14 |  | PHASE 10 or CONTRACT 10
1233.52 | 1038.12 | 1041.2 | 2020(Jan - Mar) | 03 | Midpoint 03 | 2020Q2 |  | 15 | 03 | RESERVOIRS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1160.26 | 897.27 | 901 | 2020(Jan - Mar) | 04 | Midpoint 04 | 2020Q2 |  | 16 | 04 | DAMS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1167.05 | 896.16 | 899.9 | 2020(Jan - Mar) | 05 | Midpoint 05 | 2020Q2 |  | 17 | 05 | LOCKS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1144.9 | 880.38 | 883.42 | 2020(Jan - Mar) | 06 | Midpoint 06 | 2020Q2 |  | 18 | 06 | FISH & WILDLIFE FACILITIES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1063.71 | 811.48 | 812.05 | 2020(Jan - Mar) | 07 | Midpoint 07 | 2020Q2 |  | 19 | 07 | POWER PLANT | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1166.71 | 918.54 | 920.64 | 2020(Jan - Mar) | 08 | Midpoint 08 | 2020Q2 |  | 20 | 08 | ROADS, RAILROADS & BRIDGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1196.36 | 951.95 | 957.07 | 2020(Jan - Mar) | 09 | Midpoint 09 | 2020Q2 |  | 21 | 09 | CHANNELS & CANALS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
1140.73 | 905 | 908.51 | 2020(Jan - Mar) | 10 | Midpoint 10 | 2020Q2 |  | 22 | 10 | BREAKWATER & SEAWALLS | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0
20
[8 empty] | 1: 21; 3: _; 4: _; 5: _; 6: _; 9: _; 10: _; 11: _ |  | _ | _ | _
[8 empty] | 22 |  | CONSTRUCTION ESTIMATE TOTALS: | 0 | 0 | 0% | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 |  | 0
23
1149.32 | 893.31 | 844.49 | 2017(Oct - Dec) | All | Lands And Damages Midpoint | 2018Q1 |  | 24 | 01 | LANDS AND DAMAGES | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | (This uses the CWCCIS Composite Index escalation factor). |  |  | 1: 25
[8 empty] | 26 | 30 | PLANNING, ENGINEERING & DESIGN
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | ENTER Design mid point period | 2018Q2 |  | 27 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 28 | 1% | Planning & Environmental Compliance | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 29 | 15% | Engineering & Design | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 30 | 1% | Reviews, ATRs, IEPRs, VE | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From From ENTER Design mid point period | 2018Q2 |  | 31 | 1% | Life Cycle Updates (cost, schedule, risks) | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 30 | From ENTER Design mid point period | 2018Q2 |  | 32 | 1% | Contracting & Reprographics | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | AGGREGATE CONSTRUCTION MIDPOINT | 2020Q2 |  | 33 | 3% | Engineering During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 30 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 34 | 2% | Planning During Construction | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2021(Oct - Dec) | 30 | Enter Midpoint period | 2022Q1 |  | 35 | 3% | Adaptive Management & Monitoring | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.025 | Enter Midpoint period | 2018Q2 |  | 36 | 1% | Project Operations | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2018(Jan - Mar) | 0.01 | From WBS Account 01 Midpoint | 2022Q1 |  | 37 |  | Real Estate (All Federal Labor) | 0 | 0 | 0% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL PED: | 0
[8 empty] | 37 | 31 | CONSTRUCTION MANAGEMENT
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | ENTER CONSTRUCTION MIDPOINT | 2020Q2 |  | 1 | 10% | Construction Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 2 | 2% | Project Operation: | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
1.0382 | 1 | 1 | 2020(Jan - Mar) | 0 | From Aggreagate Constrction Midpoint | 2020Q2 |  | 3 | 2.5% | Project Management | 0 | 0 | 10% | 0 |  | 0% | 0 | 0 | 0 |  | 0 | 0% |  | 0 | 0 | 0 |  | 0
[5 empty] | TOTAL Constr Mgmt: | 0 |  | 1: 4
[8 empty] | 1: 5; 2: CONTRACT COST TOTALS:; 3: 0; 4: 0; 6: 0; 9: 0; 10: 0; 11: 0 |  | 0 | 0 | 0 |  | 0 | checks if the same
[8 empty] | 1: 6 | [5 empty] | 0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
Note on F1: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V19: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V20: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V21: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V22: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V23: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V24: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V25: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V26: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V30: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V32: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on V34: Enter the amounts spent thru the past Fiscal year in the appropriate cells in reference column 13
Note on N39: USACE: Top 3 signatures: Cost, PM, Real Estate required by Regulations.
Note on G69: MPJ- The price level of the M2 is usually the FY when the estimate was completed. Enter here. Program price year should be common across all contracts so it feeds from the input sheet.
Note on Q87: Neubauer, James G CIV USARMY CENWW (US): Check the escalation tables

## TPCS Rules
Estimated Cost (Price Level) is the initially developed cost estimate which includes contingencies. The effective price level date for Estimated Cost (shown in MONTH YYYY format) is usually the date of preparation of the cost estimate.
Project First Cost (Constant Dollar Cost) (Price Level) is the Estimated Cost BROUGHT TO THE EFFECTIVE PRICE LEVEL. The effective price level for Constant Dollar Cost (shown in MONTH YYYY format) is the date of the common point in time of the pricing used in the cost estimate. Constant Dollar Cost does not include inflation. Constant Dollar Cost at current price levels is the cost estimate used in feasibility reports and Chief's Reports (see paragraphs 5(a) and 5(b) below). THE CONSTANT DOLLAR COST SHOULD BE EXPRESSED AS THE FY OF THE CHIEF'S REPORT TO ENSURE THAT THE CW PROGRAM TOTALS IN ONE FY DOLLAR TO ASA AND CONGRESS.
Total Project Cost is the Constant Dollar Cost FULLY FUNDED WITH ESCALATION to the estimated midpoint of construction. Total Project Cost (or Total Cost of Construction of GNFs when discussing navigation projects) is the cost estimate used in Project Partnership Agreements and Integral Determination Reports. Total Project Cost is the cost estimate provided non-Federal sponsors for their use in financial planning as it provides information regarding the overall non-Federal cost sharing obligation. See the enclosed tables for more detail of what is or is not included in the Total Project Cost.
Type of Program | CWBS* | Project Cost Component** | Brief Definition | For Chief's Report |  | For PPA's
|  |  |  | Project First Cost | Economic Cost for BCR | Total Project Cost
|  |  |  | Constant Cost Estimate "Oct (YYYY) Price Level" |  | Fully Funded Cost Estimate
Flood Risk Management | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Flood Risk Management | 02 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Flood Risk Management | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Flood Risk Management | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Flood Risk Management |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Flood Risk Management | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Flood Risk Management | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Flood Risk Management | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Flood Risk Management | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Flood Risk Management | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Flood Risk Management | By project element | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within cost shared project cost. | N | Y | Y
Ecosystem Restoration | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Ecosystem Restoration | 03 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Ecosystem Restoration | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Ecosystem Restoration | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Ecosystem Restoration |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Ecosystem Restoration | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Ecosystem Restoration | By project element | Monitoring and Adaptive Management | This represents the estimated costs of monitoring and or adaptive management to be cost shared for the project. | Y | Y | Y
Ecosystem Restoration | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Ecosystem Restoration | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Ecosystem Restoration | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Ecosystem Restoration | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Ecosystem Restoration |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Navigation and Harbors | 01,02 | Lands, Easements, Rights of Way, Relocations (LERR). This includes related Federal costs. | Estimated value/costs of LERR (to include breakout of related Federal administrative costs). | Y | Y | Y
Navigation and Harbors | 03 - 20 | Construction Elements (General Navigation Features) | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Navigation and Harbors | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Navigation and Harbors | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Navigation and Harbors |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Navigation and Harbors | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Navigation and Harbors | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Navigation and Harbors | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Navigation and Harbors | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Navigation and Harbors | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Navigation and Harbors | By project element | Local Service Facilities (LSF) | For Navigation Only: This represents the estimated cost of Local Service Facilities as defined in the Planning Guidance Notebook Appendix E. These are the responsibility of the non-Federal entity and are required as part of the PCA if they are necessary for project benefits to accrue. | N | Y | Y
Navigation and Harbors |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Inland Navigation | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
Inland Navigation | 03 - 20 | Construction Elements (General Navigation Features) | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
Inland Navigation | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
Inland Navigation | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
Inland Navigation |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
Inland Navigation | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
Inland Navigation | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
Inland Navigation | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
Inland Navigation | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
Inland Navigation | By project element | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
Inland Navigation | By project element | Local Service Facilities (LSF) | For Navigation Only: This represents the estimated cost of Local Service Facilities as defined in the Planning Guidance Notebook Appendix E. These are the responsibility of the non-Federal entity and are required as part of the PCA if they are necessary for project benefits to accrue. | N | Y | Y
Inland Navigation |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
COASTAL STORM | 01,02 | Lands, Easements, Rights of Way, Relocations, and Dredged Material Disposal Areas (LERRD). This includes related Federal administrative costs. | Estimated value/costs of LERRD for the project (to include breakout of related Federal administrative costs). | Y | Y | Y
COASTAL STORM | 03 - 20 | Construction Elements | Physical Construction cost estimate broken out by Civil Works Breakdown Structure(CWBS). | Y | Y | Y
COASTAL STORM | 30 | Planning, Engineering, and Design (post feasibility work) | Estimated costs for post feasibility planning, engineering, and design for the project. This cost should include the estimate of Preconstruction Engineering and Design (PED) phase costs as well as the planning, engineering, and design costs during the construction phase to complete the project. | Y | Y | Y
COASTAL STORM | 31 | Construction Management | Estimated costs for construction management of project | Y | Y | Y
COASTAL STORM |  | Fish and Wildlife Mitigation | Estimated costs of Mitigation | Y | Y | Y
COASTAL STORM | 18 | Cultural Mitigation | Estimated costs of Mitigation | Y | Y*** | Y
COASTAL STORM | By project element | Monitoring and Adaptive Management | This represents the estimated costs of monitoring and or adaptive management to be cost shared for the project. | Y | Y | Y
COASTAL STORM | By project element | Contingency | This is the Risk Based contingency established for the project. | Y | Y | Y
COASTAL STORM | By project element | Continued Construction (periodic nourishment) | For Hurricane and Storm Damage Reduction Only: Estimate of Allowable Periodic Average future construction cost submitted for authorization. | Y | Y | Y
COASTAL STORM | By project element | Interest During Construction (IDC) | Estimate of interest accumulated during construction(Economic cost) | N | Y | Y
COASTAL STORM | By project element | Operation, Maintenance, Repair, Replacement, and Rehabilitation (OMRR&R) | Annualized estimate of Operation, Maintenance, Replacement and Rehabilitation cost. | N | Y | N
COASTAL STORM |  | Inflation through midpoint construction | Estimate of inflation using appropriate Civil Works Construction Cost Index System (CWCCIS) factors applied to the Constant Dollar Cost | N | N | Y
COASTAL STORM |  | Associated and Other Costs | Associated financial costs that are not part of the recommended Federal project but are a necessary non-Federal responsibility. These cost are required to be shown within the Chief's report, as a separate total but are not to be included within the cost shared project cost. | N | Y | Y
Feature Code Definitions
CWBS | Definitions
01 Lands and Damages | This feature includes all costs of acquiring for the project (by purchase or condemnation) real property or permanent interests therein, including Government costs, damages, and costs of disposal of real estate. Government costs include planning expenses for the real estate portion of the General Design Memo and for the detailed Real Estate Memo; and project real estate office administration, surveys, and marking for land acquisition purposes and appraisals. For projects which require that costs be incurred on real estate activities, i.e., for records search, appraisals, and field inspection to assure compliance by local interests in the provision of local requirements on projects where no Federal land acquisition is involved, a memorandum statement will be provided with the PB-3 indicating the estimated costs of such real estate activities. These costs will be charged to feature 30, Engineering and Design and that feature will be properly footnoted to show the amount of such costs. A similar footnote will be shown on the PB-1's and PB-2a's for all such projects. This feature is credited with disposal receipts from sale of such items as standing crops, standing timber, structures, and improvements in place and acquired with the land. Disposal receipts from sale of excess land not turned in to the U.S. Treasury as miscellaneous receipts are credited to this feature. Lands or interests purchased for relocations and conveyed to others are included in the feature "Relocations.” Temporary interests such as leases are included in the feature or distributive item benefited thereby.
02 Relocations | This feature includes removing and relocating, or reconstructing property of others, such as roads, railroads, cemeteries, utilities, buildings, and other structures; and lands or interests purchased for such relocations and conveyed to others, including real estate planning and acquisition expenses. The cost of removal of improvements from the reservoir area for disposal is included in the feature “Reservoirs.” All alterations of railroad bridges in accordance with Section 3 of the 1946 Flood Control Act (22 USC 701p) are also included in this feature.
03 Reservoirs | This feature includes clearing lands in reservoirs and pools of debris, brush, trees, improvements, and structures. Any salvage, obtained by sale or disposal by the Government, of material removed in clearing operations is credited to this feature. This feature also includes bank stabilization, shoreline improvement, firebreaks, fencing, boundary line survey and marking of land which has been acquired or is to be acquired, rehabilitation of natural resources, erosion control, drainage, and rim grouting and mine sealing, etc., to prevent leakage. Site clearing, grouting, etc., incidental to and required for specific construction features is included as part of the construction features.
04 Dams | This feature includes dams and all other water collecting and storage facilities, whether man-made or natural, together with appurtenant diversion, regulation, and delivery facilities and spillways, outlet works, and power intake works, whether separate from the dam or not. In the case where the powerhouse is an integral part of the intake dam, the cost of the power intake dam is included in the feature "Power Plant." Any auxiliary dams or spillways detached from the main structures and floating trash and drift booms and barriers are included in this feature. The power intake works include such power items as forebay, penstocks, tunnels, surge tank, gates, operating equipment, and appurtenances. Service roads and service railroads on the dam are included in this feature. The additional cost of relocating highways and railroads across the dam is included in the feature "Relocations."
05 Locks | This feature includes facilities to provide for passage of waterborne traffic, including gates, valves, operating mechanisms, cribs, fills, lock walls, guide and guard walls, operating buildings, and excavation therefore. The lock structure is considered that part of the work within the limit lines extending from the upper end of the upper guide or guard walls to the lower end of the lower guide or guard walls, including dolphins within the lock approaches for tie up, guard, or guide purposes. Excavation or dredging• required in approaches outside of the limits defined above for the lock structure is included in the feature "Channels and Canals." The cost of a cofferdam or the properly allocable amount thereof, if required, is charged to this feature. Locks provided in connection with facilities for the prevention of encroachment of salt water are included in this feature. Locks in connection with fish facilities are included in the feature "Fish and Wildlife Facilities."
06 Fish and Wildlife Facilities | This feature includes items such as ladders, elevators, locks and related facilities for passage of fish at dams and navigation locks and maintenance of fish runs; and provision for wildlife preservation.
07 Power Plant | This feature includes those facilities specifically required for the production of power other than those included in the feature “Dams,” and consists of the following: powerhouse, turbines and governors, generators, accessory electrical equipment, miscellaneous power plant equipment, switchyard, and tailrace improvement for power. In the case where the powerhouse is an integral part of the power intake dam, the cost of the power intake dam is included in this feature. Where the structure of a dam also forms the foundation of the powerhouse, such foundation is considered a part of the dam. Units for production of power for the operation only of power for the operation only of navigation, flood control, or other purpose projects (excluding those projects with power as a feature) are included in other than this feature. The cost of a cofferdam or appropriate part is charged to this feature.
08 Roads, Railroads and Bridges | This feature includes permanent roads, railroads, and bridges required for access and other purposes in connection with the construction and operation of the project. This feature does not include roads, railroads, and bridges chargeable to the feature "Relocations," access roads to recreation facilities and areas, which will be charged to the feature "14. Recreation Facilities," and service roads and service railroads on structures.
09 Channels and Canals | This feature includes all forms of excavation (including dredging, preparation of spoil disposal area, and attendant facilities) necessary for the development and construction of channels, harbors, and canals for navigation purposes; and deepening, providing new, or improving existing watercourses for flood control and major drainage. Excavation of natural watercourse to provide adequate depths for navigation is included. Excavation for specific structures, such as dams and locks used in the development of waterways and conservation of water resources, is included with such structures. The removal of trees, brush, accumulated snags, drift, debris, water hyacinths and other aquatic growths from canals, harbors, and channels in navigable streams and tributaries thereof for navigational included in this feature. Excavation, clearing, and removal of accumulated snags, drifts, debris, and vegetable growth from streams for flood control and major drainage purposes also is included. Included in this feature are revetments, linings, dikes, and bulkheads constructed as channel improvement works for flood control or navigation, as against such items constructed for bank stabilization only. Also included are jetties constructed in connection with flood control channel improvements.
10 Breakwaters and Seawalls | This feature includes breakwaters, seawalls, piers, and like improvements constructed in connection with the protection of beaches, harbors, shores•, and port facilities against the force of waves and encroachment of seas or lakes by direct wave action. Jetties, groins, and like structures provided in seas, lakes, tidewater reaches of rivers and canals, and harbors to control water flow and current, to maintain depth of channels, and to provide protection, are included in this feature.
11 Levees and Floodwalls | This feature includes embankments and walls constructed to protect areas from inundation by overflow from creeks, rivers, lakes, canals, and other bodies of water. This feature consists of such items as: service roads on levee crown or landside berms, road ramps, closure structures, seepage control measures, erosion protection measures on levee slopes and on berms and bank slops when an integral part of the levees or floodwalls; and drainage facilities, constructed to provide means for the passage of accumulated drainage and seepage water and sewage from the protected area over or through levees and floodwalls, comprising such items as interceptor and collection sewers and ditches, and pressurized sewers and drainage structures, including outfalls through levees or floodwalls. Pumping plants are included in the feature "Pumping Plants." Levees locally called dikes are included in this feature.
13 Pumping Plants | This feature includes pumping plants construction to pass accumulated drainage and seepage water and sewage from the protected area over or through levees and floodwalls.
14 Recreation Facilities | This feature includes access roads; parking areas; public camping and picnicking areas, including tables and fireplaces; water supply; sanitary facilities; boat launching ramps; directional signs; and other facilities constructed primarily for public recreational use, including essential safety measures in connection therewith. The latter includes, as appropriate, sheltered anchorage areas for small craft, bathing areas readily accessible and reasonably safe, and safety provisions for visitors and fishermen in the project area. (Boat launching ramps, anchorage areas and beaches should be provided during construction to the extent they will definitely be needed and can be accomplished more economically than at a later date.)
15 Floodway Control and Diversion Structures | This feature includes floodway control and diversion structures to provide for the release of flood waters from streams where discharges exceed flood capacity of the stream, including items such as diversion dams, gated or ungated discharge structures, training walls, stilling basin, and those adjacent embankment sections forming part of the control structure. Construction of channels and levees not forming part of the main control structure, but necessary for operation of such structures is included in the appropriate feature "Channels and Canals" or "Levees and Floodwalls."
16 Bank Stabilization | This feature includes revetments, linings, training dikes, and bulkheads for stabilization of banks of watercourses to prevent erosion, sloughing, or meandering. Bank stabilization constructed in navigation channels or in connection with flood control channel improvement is included in• the feature "Channels and Canals."
17 Beach Replenishment | This feature includes replacement of eroded beaches, for purposes of recreation and shore protection, by direct deposit of materials obtained by dredging or land excavation.
19 Buildings, Grounds and Utilities | This feature includes permanent facilities such as operators' quarters, administration and shop buildings, storage buildings and areas, garage buildings and areas, community buildings, local streets and sidewalks, landscaping, and electric, gas, water, and sewage facilities. Where space in a dam, powerhouse, or other basic structure is used in lieu of construction of any of the above-mentioned buildings, such allocated space is not separated from the basic structure. Communication systems are• included in the feature "Permanent Operating Equipment."
20 Permanent Operating Equipment | This feature includes all project-owned operation and maintenance tools and equipment, such as laboratory, shop, warehousing, communications, and transportation equipment, and office furniture and equipment. The cost of installing sedimentation and degradation measuring facilities, including the surveys requisite to locating and monumenting range layouts, is charged to this feature. •The cost of planning the installation of sedimentation and degradation ranges is charged to the feature "Engineering and Design."
30 Engineering and Design | This feature includes all engineering, design, surveys, preparation of detailed plans and specifications, and related work required for the construction of the project, including relocations. Surveys and planning required in connection with land acquisition are charged to the features "Lands and Damages" or "Relocations," as applicable. Engineering and design performed by hired labor or as a pay item under a contract is included in this feature.
31 Supervision and Administration | This feature includes such functions as inspection, supervision, project office administration, and distributive costs of area office and general overhead charged to the project. Costs for OCE and Division Office Executive Direction and Management are not charged to Construction, General but to the General Expenses appropriation title.
Note on B6: *Civil Works Breakdown Structure
Note on F15: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F26: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F38: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F50: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on F62: ***Note that some cultural mitigation costs are not included in the Benefit-to-Cost Ratio (BCR).
Note on A73: *Civil Works Breakdown Structure

## CWCCIS
| Date of Index Factors: | 2025-10-28 |  |  |  |  | Table A-1 Quarterly Indexes |  |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS |  |  |  | FY QTRS
| CWCCIS ESCALATION CALCULATION |  |  |  |  | 1 |  | 1 |  |  | 1980Q1 | 1980Q2 | 1980Q3 | 1980Q4 | 1981Q1 | 1981Q2 | 1981Q3 | 1981Q4 | 1982Q1 | 1982Q2 | 1982Q3 | 1982Q4 | 1983Q1 | 1983Q2 | 1983Q3 | 1983Q4 | 1984Q1 | 1984Q2 | 1984Q3 | 1984Q4 | 1985Q1 | 1985Q2 | 1985Q3 | 1985Q4 | 1986Q1 | 1986Q2 | 1986Q3 | 1986Q4 | 1987Q1 | 1987Q2 | 1987Q3 | 1987Q4 | 1988Q1 | 1988Q2 | 1988Q3 | 1988Q4 | 1989Q1 | 1989Q2 | 1989Q3 | 1989Q4 | 1990Q1 | 1990Q2 | 1990Q3 | 1990Q4 | 1991Q1 | 1991Q2 | 1991Q3 | 1991Q4 | 1992Q1 | 1992Q2 | 1992Q3 | 1992Q4 | 1993Q1 | 1993Q2 | 1993Q3 | 1993Q4 | 1994Q1 | 1994Q2 | 1994Q3 | 1994Q4 | 1995Q1 | 1995Q2 | 1995Q3 | 1995Q4 | 1996Q1 | 1996Q2 | 1996Q3 | 1996Q4 | 1997Q1 | 1997Q2 | 1997Q3 | 1997Q4 | 1998Q1 | 1998Q2 | 1998Q3 | 1998Q4 | 1999Q1 | 1999Q2 | 1999Q3 | 1999Q4 | 2000Q1 | 2000Q2 | 2000Q3 | 2000Q4 | 2001Q1 | 2001Q2 | 2001Q3 | 2001Q4 | 2002Q1 | 2002Q2 | 2002Q3 | 2002Q4 | 2003Q1 | 2003Q2 | 2003Q3 | 2003Q4 | 2004Q1 | 2004Q2 | 2004Q3 | 2004Q4 | 2005Q1 | 2005Q2 | 2005Q3 | 2005Q4 | 2006Q1 | 2006Q2 | 2006Q3 | 2006Q4 | 2007Q1 | 2007Q2 | 2007Q3 | 2007Q4 | 2008Q1 | 2008Q2 | 2008Q3 | 2008Q4 | 2009Q1 | 2009Q2 | 2009Q3 | 2009Q4 | 2010Q1 | 2010Q2 | 2010Q3 | 2010Q4 | 2011Q1 | 2011Q2 | 2011Q3 | 2011Q4 | 2012Q1 | 2012Q2 | 2012Q3 | 2012Q4 | 2013Q1 | 2013Q2 | 2013Q3 | 2013Q4 | 2014Q1 | 2014Q2 | 2014Q3 | 2014Q4 | 2015Q1 | 2015Q2 | 2015Q3 | 2015Q4 | 2016Q1 | 2016Q2 | 2016Q3 | 2016Q4 | 2017Q1 | 2017Q2 | 2017Q3 | 2017Q4 | 2018Q1 | 2018Q2 | 2018Q3 | 2018Q4 | 2019Q1 | 2019Q2 | 2019Q3 | 2019Q4 | 2020Q1 | 2020Q2 | 2020Q3 | 2020Q4 | 2021Q1 | 2021Q2 | 2021Q3 | 2021Q4 | 2022Q1 | 2022Q2 | 2022Q3 | 2022Q4 | 2023Q1 | 2023Q2 | 2023Q3 | 2023Q4 | 2024Q1 | 2024Q2 | 2024Q3 | 2024Q4 | 2025Q1 | 2025Q2 | 2025Q3 | 2025Q4 | 2026Q1 | 2026Q2 | 2026Q3 | 2026Q4 | 2027Q1 | 2027Q2 | 2027Q3 | 2027Q4 | 2028Q1 | 2028Q2 | 2028Q3 | 2028Q4 | 2029Q1 | 2029Q2 | 2029Q3 | 2029Q4 | 2030Q1 | 2030Q2 | 2030Q3 | 2030Q4 | 2031Q1 | 2031Q2 | 2031Q3 | 2031Q4 | 2032Q1 | 2032Q2 | 2032Q3 | 2032Q4 | 2033Q1 | 2033Q2 | 2033Q3 | 2033Q4 | 2034Q1 | 2034Q2 | 2034Q3 | 2034Q4 | 2035Q1 | 2035Q2 | 2035Q3 | 2035Q4 | 2036Q1 | 2036Q2 | 2036Q3 | 2036Q4 | 2037Q1 | 2037Q2 | 2037Q3 | 2037Q4 | 2038Q1 | 2038Q2 | 2038Q3 | 2038Q4 | 2039Q1 | 2039Q2 | 2039Q3 | 2039Q4 | 2040Q1 | 2040Q2 | 2040Q3 | 2040Q4 | 2041Q1 | 2041Q2 | 2041Q3 | 2041Q4 | 2042Q1 | 2042Q2 | 2042Q3 | 2042Q4 | 2043Q1 | 2043Q2 | 2043Q3 | 2043Q4 | 2044Q1 | 2044Q2 | 2044Q3 | 2044Q4 | 2045Q1 | 2045Q2 | 2045Q3 | 2045Q4 | 2046Q1 | 2046Q2 | 2046Q3 | 2046Q4 | 2047Q1 | 2047Q2 | 2047Q3 | 2047Q4 | 2048Q1 | 2048Q2 | 2048Q3 | 2048Q4 | 2049Q1 | 2049Q2 | 2049Q3 | 2049Q4 | 2050Q1 | 2050Q2 | 2050Q3 | 2050Q4 | 2051Q1 | 2051Q2 | 2051Q3 | 2051Q4 | 2052Q1 | 2052Q2 | 2052Q3 | 2052Q4 | 2053Q1 | 2053Q2 | 2053Q3 | 2053Q4 | 2054Q1 | 2054Q2 | 2054Q3 | 2054Q4 | 2055Q1 | 2055Q2 | 2055Q3 | 2055Q4 | 2056Q1 | 2056Q2 | 2056Q3 | 2056Q4 | 2057Q1 | 2057Q2 | 2057Q3 | 2057Q4 | 2058Q1 | 2058Q2 | 2058Q3 | 2058Q4 | 2059Q1 | 2059Q2 | 2059Q3 | 2059Q4 | 2060Q1 | 2060Q2 | 2060Q3 | 2060Q4 | 2061Q1 | 2061Q2 | 2061Q3 | 2061Q4 | 2062Q1 | 2062Q2 | 2062Q3 | 2062Q4 | 2063Q1 | 2063Q2 | 2063Q3 | 2063Q4 | 2064Q1 | 2064Q2 | 2064Q3 | 2064Q4 | 2065Q1 | 2065Q2 | 2065Q3 | 2065Q4 | 2066Q1 | 2066Q2 | 2066Q3 | 2066Q4 | 2067Q1 | 2067Q2 | 2067Q3 | 2067Q4 | 2068Q1 | 2068Q2 | 2068Q3 | 2068Q4 | 2069Q1 | 2069Q2 | 2069Q3 | 2069Q4 | 2070Q1 | 2070Q2 | 2070Q3 | 2070Q4 | 2071Q1 | 2071Q2 | 2071Q3 | 2071Q4 | 2072Q1 | 2072Q2 | 2072Q3 | 2072Q4 | 2073Q1 | 2073Q2 | 2073Q3 | 2073Q4 | 2074Q1 | 2074Q2 | 2074Q3 | 2074Q4 | 2075Q1 | 2075Q2 | 2075Q3 | 2075Q4 | 2076Q1 | 2076Q2 | 2076Q3 | 2076Q4 | 2077Q1 | 2077Q2 | 2077Q3 | 2077Q4 | 2078Q1 | 2078Q2 | 2078Q3 | 2078Q4 | 2079Q1 | 2079Q2 | 2079Q3 | 2079Q4 | 2080Q1 | 2080Q2 | 2080Q3 | 2080Q4 | 2081Q1 | 2081Q2 | 2081Q3 | 2081Q4 | 2082Q1 | 2082Q2 | 2082Q3 | 2082Q4 | 2083Q1 | 2083Q2 | 2083Q3 | 2083Q4 | 2084Q1 | 2084Q2 | 2084Q3 | 2084Q4 | 2085Q1 | 2085Q2 | 2085Q3 | 2085Q4 | 2086Q1 | 2086Q2 | 2086Q3 | 2086Q4 | 2087Q1 | 2087Q2 | 2087Q3 | 2087Q4 | 2088Q1 | 2088Q2 | 2088Q3 | 2088Q4 | 2089Q1 | 2089Q2 | 2089Q3 | 2089Q4 | 2090Q1 | 2090Q2 | 2090Q3 | 2090Q4 | 2091Q1 | 2091Q2 | 2091Q3 | 2091Q4 | 2092Q1 | 2092Q2 | 2092Q3 | 2092Q4 | 2093Q1 | 2093Q2 | 2093Q3 | 2093Q4 | 2094Q1 | 2094Q2 | 2094Q3 | 2094Q4 | 2095Q1 | 2095Q2 | 2095Q3 | 2095Q4 | 2096Q1 | 2096Q2 | 2096Q3 | 2096Q4 | 2097Q1 | 2097Q2 | 2097Q3 | 2097Q4 | 2098Q1 | 2098Q2 | 2098Q3 | 2098Q4 | 2099Q1 | 2099Q2 | 2099Q3 | 2099Q4 | 2100Q1 | 2100Q2 | 2100Q3 | 2100Q4
Enter Code below | [5 empty] | 2 |  | 2 |  |  | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00 | 1Q01 | 2Q01 | 3Q01 | 4Q01 | 1Q02 | 2Q02 | 3Q02 | 4Q02 | 1Q03 | 2Q03 | 3Q03 | 4Q03 | 1Q04 | 2Q04 | 3Q04 | 4Q04 | 1Q05 | 2Q05 | 3Q05 | 4Q05 | 1Q06 | 2Q06 | 3Q06 | 4Q06 | 1Q07 | 2Q07 | 3Q07 | 4Q07 | 1Q08 | 2Q08 | 3Q08 | 4Q08 | 1Q09 | 2Q09 | 3Q09 | 4Q09 | 1Q10 | 2Q10 | 3Q10 | 4Q10 | 1Q11 | 2Q11 | 3Q11 | 4Q11 | 1Q12 | 2Q12 | 3Q12 | 4Q12 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | 1Q20 | 2Q20 | 3Q20 | 4Q20 | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22 | 2Q22 | 3Q22 | 4Q22 | 1Q23 | 2Q23 | 3Q23 | 4Q23 | 1Q24 | 2Q24 | 3Q24 | 4Q24 | 1Q25 | 2Q25 | 3Q25 | 4Q25 | 1Q26 | 2Q26 | 3Q26 | 4Q26 | 1Q27 | 2Q27 | 3Q27 | 4Q27 | 1Q28 | 2Q28 | 3Q28 | 4Q28 | 1Q29 | 2Q29 | 3Q29 | 4Q29 | 1Q30 | 2Q30 | 3Q30 | 4Q30 | 1Q31 | 2Q31 | 3Q31 | 4Q31 | 1Q32 | 2Q32 | 3Q32 | 4Q32 | 1Q33 | 2Q33 | 3Q33 | 4Q33 | 1Q34 | 2Q34 | 3Q34 | 4Q34 | 1Q35 | 2Q35 | 3Q35 | 4Q35 | 1Q36 | 2Q36 | 3Q36 | 4Q36 | 1Q37 | 2Q37 | 3Q37 | 4Q37 | 1Q38 | 2Q38 | 3Q38 | 4Q38 | 1Q39 | 2Q39 | 3Q39 | 4Q39 | 1Q40 | 2Q40 | 3Q40 | 4Q40 | 1Q41 | 2Q41 | 3Q41 | 4Q41 | 1Q42 | 2Q42 | 3Q42 | 4Q42 | 1Q43 | 2Q43 | 3Q43 | 4Q43 | 1Q44 | 2Q44 | 3Q44 | 4Q44 | 1Q45 | 2Q45 | 3Q45 | 4Q45 | 1Q46 | 2Q46 | 3Q46 | 4Q46 | 1Q47 | 2Q47 | 3Q47 | 4Q47 | 1Q48 | 2Q48 | 3Q48 | 4Q48 | 1Q49 | 2Q49 | 3Q49 | 4Q49 | 1Q50 | 2Q50 | 3Q50 | 4Q50 | 1Q51 | 2Q51 | 3Q51 | 4Q51 | 1Q52 | 2Q52 | 3Q52 | 4Q52 | 1Q53 | 2Q53 | 3Q53 | 4Q53 | 1Q54 | 2Q54 | 3Q54 | 4Q54 | 1Q55 | 2Q55 | 3Q55 | 4Q55 | 1Q56 | 2Q56 | 3Q56 | 4Q56 | 1Q57 | 2Q57 | 3Q57 | 4Q57 | 1Q58 | 2Q58 | 3Q58 | 4Q58 | 1Q59 | 2Q59 | 3Q59 | 4Q59 | 1Q60 | 2Q60 | 3Q60 | 4Q60 | 1Q61 | 2Q61 | 3Q61 | 4Q61 | 1Q62 | 2Q62 | 3Q62 | 4Q62 | 1Q63 | 2Q63 | 3Q63 | 4Q63 | 1Q64 | 2Q64 | 3Q64 | 4Q64 | 1Q65 | 2Q65 | 3Q65 | 4Q65 | 1Q66 | 2Q66 | 3Q66 | 4Q66 | 1Q67 | 2Q67 | 3Q67 | 4Q67 | 1Q68 | 2Q68 | 3Q68 | 4Q68 | 1Q69 | 2Q69 | 3Q69 | 4Q69 | 1Q70 | 2Q70 | 3Q70 | 4Q70 | 1Q71 | 2Q71 | 3Q71 | 4Q71 | 1Q72 | 2Q72 | 3Q72 | 4Q72 | 1Q73 | 2Q73 | 3Q73 | 4Q73 | 1Q74 | 2Q74 | 3Q74 | 4Q74 | 1Q75 | 2Q75 | 3Q75 | 4Q75 | 1Q76 | 2Q76 | 3Q76 | 4Q76 | 1Q77 | 2Q77 | 3Q77 | 4Q77 | 1Q78 | 2Q78 | 3Q78 | 4Q78 | 1Q79 | 2Q79 | 3Q79 | 4Q79 | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00
ALL | COMPOSITE INDEX (WEIGHTED AVERAGE) |  | 25 | th row |  | 3 |  | 3 |  |  | 1Q80 | 2Q80 | 3Q80 | 4Q80 | 1Q81 | 2Q81 | 3Q81 | 4Q81 | 1Q82 | 2Q82 | 3Q82 | 4Q82 | 1Q83 | 2Q83 | 3Q83 | 4Q83 | 1Q84 | 2Q84 | 3Q84 | 4Q84 | 1Q85 | 2Q85 | 3Q85 | 4Q85 | 1Q86 | 2Q86 | 3Q86 | 4Q86 | 1Q87 | 2Q87 | 3Q87 | 4Q87 | 1Q88 | 2Q88 | 3Q88 | 4Q88 | 1Q89 | 2Q89 | 3Q89 | 4Q89 | 1Q90 | 2Q90 | 3Q90 | 4Q90 | 1Q91 | 2Q91 | 3Q91 | 4Q91 | 1Q92 | 2Q92 | 3Q92 | 4Q92 | 1Q93 | 2Q93 | 3Q93 | 4Q93 | 1Q94 | 2Q94 | 3Q94 | 4Q94 | 1Q95 | 2Q95 | 3Q95 | 4Q95 | 1Q96 | 2Q96 | 3Q96 | 4Q96 | 1Q97 | 2Q97 | 3Q97 | 4Q97 | 1Q98 | 2Q98 | 3Q98 | 4Q98 | 1Q99 | 2Q99 | 3Q99 | 4Q99 | 1Q00 | 2Q00 | 3Q00 | 4Q00 | 1Q01 | 2Q01 | 3Q01 | 4Q01 | 1Q02 | 2Q02 | 3Q02 | 4Q02 | 1Q03 | 2Q03 | 3Q03 | 4Q03 | 1Q04 | 2Q04 | 3Q04 | 4Q04 | 1Q05 | 2Q05 | 3Q05 | 4Q05 | 1Q06 | 2Q06 | 3Q06 | 4Q06 | 1Q07 | 2Q07 | 3Q07 | 4Q07 | 1Q08 | 2Q08 | 3Q08 | 4Q08 | 1Q09 | 2Q09 | 3Q09 | 4Q09 | 1Q10 | 2Q10 | 3Q10 | 4Q10 | 1Q11 | 2Q11 | 3Q11 | 4Q11 | 1Q12 | 2Q12 | 3Q12 | 4Q12 | 1Q13 | 2Q13 | 3Q13 | 4Q13 | 1Q14 | 2Q14 | 3Q14 | 4Q14 | 1Q15 | 2Q15 | 3Q15 | 4Q15 | 1Q16 | 2Q16 | 3Q16 | 4Q16 | 1Q17 | 2Q17 | 3Q17 | 4Q17 | 1Q18 | 2Q18 | 3Q18 | 4Q18 | 1Q19 | 2Q19 | 3Q19 | 4Q19 | 1Q20 | 2Q20 | 3Q20 | 4Q20 | 1Q21 | 2Q21 | 3Q21 | 4Q21 | 1Q22 | 2Q22 | 3Q22 | 4Q22 | 1Q23 | 2Q23 | 3Q23 | 4Q23 | 1Q24 | 2Q24 | 3Q24 | 4Q24 | 1Q25 | 2Q25 | 3Q25* | 4Q25* | 1Q26* | 2Q26* | 3Q26* | 4Q26* | 1Q27* | 2Q27* | 3Q27* | 4Q27* | 1Q28* | 2Q28* | 3Q28* | 4Q28* | 1Q29* | 2Q29* | 3Q29* | 4Q29* | 1Q30* | 2Q30* | 3Q30* | 4Q30* | 1Q31* | 2Q31* | 3Q31* | 4Q31* | 1Q32* | 2Q32* | 3Q32* | 4Q32* | 1Q33* | 2Q33* | 3Q33* | 4Q33* | 1Q34* | 2Q34* | 3Q34* | 4Q34* | 1Q35* | 2Q35* | 3Q35* | 4Q35* | 1Q36* | 2Q36* | 3Q36* | 4Q36* | 1Q37* | 2Q37* | 3Q37* | 4Q37* | 1Q38* | 2Q38* | 3Q38* | 4Q38* | 1Q39* | 2Q39* | 3Q39* | 4Q39* | 1Q40* | 2Q40* | 3Q40* | 4Q40* | 1Q41* | 2Q41* | 3Q41* | 4Q41* | 1Q42* | 2Q42* | 3Q42* | 4Q42* | 1Q43* | 2Q43* | 3Q43* | 4Q43* | 1Q44* | 2Q44* | 3Q44* | 4Q44* | 1Q45* | 2Q45* | 3Q45* | 4Q45* | 1Q46* | 2Q46* | 3Q46* | 4Q46* | 1Q47* | 2Q47* | 3Q47* | 4Q47* | 1Q48* | 2Q48* | 3Q48* | 4Q48* | 1Q49* | 2Q49* | 3Q49* | 4Q49* | 1Q50* | 2Q50* | 3Q50* | 4Q50* | 1Q51* | 2Q51* | 3Q51* | 4Q51* | 1Q52* | 2Q52* | 3Q52* | 4Q52* | 1Q53* | 2Q53* | 3Q53* | 4Q53* | 1Q54* | 2Q54* | 3Q54* | 4Q54* | 1Q55* | 2Q55* | 3Q55* | 4Q55* | 1Q56* | 2Q56* | 3Q56* | 4Q56* | 1Q57* | 2Q57* | 3Q57* | 4Q57* | 1Q58* | 2Q58* | 3Q58* | 4Q58* | 1Q59* | 2Q59* | 3Q59* | 4Q59* | 1Q60* | 2Q60* | 3Q60* | 4Q60* | 1Q61* | 2Q61* | 3Q61* | 4Q61* | 1Q62* | 2Q62* | 3Q62* | 4Q62* | 1Q63* | 2Q63* | 3Q63* | 4Q63* | 1Q64* | 2Q64* | 3Q64* | 4Q64* | 1Q65* | 2Q65* | 3Q65* | 4Q65* | 1Q66* | 2Q66* | 3Q66* | 4Q66* | 1Q67* | 2Q67* | 3Q67* | 4Q67* | 1Q68* | 2Q68* | 3Q68* | 4Q68* | 1Q69* | 2Q69* | 3Q69* | 4Q69* | 1Q70* | 2Q70* | 3Q70* | 4Q70* | 1Q71* | 2Q71* | 3Q71* | 4Q71* | 1Q72* | 2Q72* | 3Q72* | 4Q72* | 1Q73* | 2Q73* | 3Q73* | 4Q73* | 1Q74* | 2Q74* | 3Q74* | 4Q74* | 1Q75* | 2Q75* | 3Q75* | 4Q75* | 1Q76* | 2Q76* | 3Q76* | 4Q76* | 1Q77* | 2Q77* | 3Q77* | 4Q77* | 1Q78* | 2Q78* | 3Q78* | 4Q78* | 1Q79* | 2Q79* | 3Q79* | 4Q79* | 1Q80* | 2Q80* | 3Q80* | 4Q80* | 1Q81* | 2Q81* | 3Q81* | 4Q81* | 1Q82* | 2Q82* | 3Q82* | 4Q82* | 1Q83* | 2Q83* | 3Q83* | 4Q83* | 1Q84* | 2Q84* | 3Q84* | 4Q84* | 1Q85* | 2Q85* | 3Q85* | 4Q85* | 1Q86* | 2Q86* | 3Q86* | 4Q86* | 1Q87* | 2Q87* | 3Q87* | 4Q87* | 1Q88* | 2Q88* | 3Q88* | 4Q88* | 1Q89* | 2Q89* | 3Q89* | 4Q89* | 1Q90* | 2Q90* | 3Q90* | 4Q90* | 1Q91* | 2Q91* | 3Q91* | 4Q91* | 1Q92* | 2Q92* | 3Q92* | 4Q92* | 1Q93* | 2Q93* | 3Q93* | 4Q93* | 1Q94* | 2Q94* | 3Q94* | 4Q94* | 1Q95* | 2Q95* | 3Q95* | 4Q95* | 1Q96* | 2Q96* | 3Q96* | 4Q96* | 1Q97* | 2Q97* | 3Q97* | 4Q97* | 1Q98* | 2Q98* | 3Q98* | 4Q98* | 1Q99* | 2Q99* | 3Q99* | 4Q99* | 1Q100* | 2Q00* | 3Q00* | 4Q00*
[6 empty] | 4 |  | 4 |  |  | 1979 | 1980 | 1980 | 1980 | 1980 | 1981 | 1981 | 1981 | 1981 | 1982 | 1982 | 1982 | 1982 | 1983 | 1983 | 1983 | 1983 | 1984 | 1984 | 1984 | 1984 | 1985 | 1985 | 1985 | 1985 | 1986 | 1986 | 1986 | 1986 | 1987 | 1987 | 1987 | 1987 | 1988 | 1988 | 1988 | 1988 | 1989 | 1989 | 1989 | 1989 | 1990 | 1990 | 1990 | 1990 | 1991 | 1991 | 1991 | 1991 | 1992 | 1992 | 1992 | 1992 | 1993 | 1993 | 1993 | 1993 | 1994 | 1994 | 1994 | 1994 | 1995 | 1995 | 1995 | 1995 | 1996 | 1996 | 1996 | 1996 | 1997 | 1997 | 1997 | 1997 | 1998 | 1998 | 1998 | 1998 | 1999 | 1999 | 1999 | 1999 | 2000 | 2000 | 2000 | 2000 | 2001 | 2001 | 2001 | 2001 | 2002 | 2002 | 2002 | 2002 | 2003 | 2003 | 2003 | 2003 | 2004 | 2004 | 2004 | 2004 | 2005 | 2005 | 2005 | 2005 | 2006 | 2006 | 2006 | 2006 | 2007 | 2007 | 2007 | 2007 | 2008 | 2008 | 2008 | 2008 | 2009 | 2009 | 2009 | 2009 | 2010 | 2010 | 2010 | 2010 | 2011 | 2011 | 2011 | 2011 | 2012 | 2012 | 2012 | 2012 | 2013 | 2013 | 2013 | 2013 | 2014 | 2014 | 2014 | 2014 | 2015 | 2015 | 2015 | 2015 | 2016 | 2016 | 2016 | 2016 | 2017 | 2017 | 2017 | 2017 | 2018 | 2018 | 2018 | 2018 | 2019 | 2019 | 2019 | 2019 | 2020 | 2020 | 2020 | 2020 | 2021 | 2021 | 2021 | 2021 | 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029 | 2030 | 2030 | 2030 | 2030 | 2031 | 2031 | 2031 | 2031 | 2032 | 2032 | 2032 | 2032 | 2033 | 2033 | 2033 | 2033 | 2034 | 2034 | 2034 | 2034 | 2035 | 2035 | 2035 | 2035 | 2036 | 2036 | 2036 | 2036 | 2037 | 2037 | 2037 | 2037 | 2038 | 2038 | 2038 | 2038 | 2039 | 2039 | 2039 | 2039 | 2040 | 2040 | 2040 | 2040 | 2041 | 2041 | 2041 | 2041 | 2042 | 2042 | 2042 | 2042 | 2043 | 2043 | 2043 | 2043 | 2044 | 2044 | 2044 | 2044 | 2045 | 2045 | 2045 | 2045 | 2046 | 2046 | 2046 | 2046 | 2047 | 2047 | 2047 | 2047 | 2048 | 2048 | 2048 | 2048 | 2049 | 2049 | 2049 | 2049 | 2050 | 2050 | 2050 | 2050 | 2051 | 2051 | 2051 | 2051 | 2052 | 2052 | 2052 | 2052 | 2053 | 2053 | 2053 | 2053 | 2054 | 2054 | 2054 | 2054 | 2055 | 2055 | 2055 | 2055 | 2056 | 2056 | 2056 | 2056 | 2057 | 2057 | 2057 | 2057 | 2058 | 2058 | 2058 | 2058 | 2059 | 2059 | 2059 | 2059 | 2060 | 2060 | 2060 | 2060 | 2061 | 2061 | 2061 | 2061 | 2062 | 2062 | 2062 | 2062 | 2063 | 2063 | 2063 | 2063 | 2064 | 2064 | 2064 | 2064 | 2065 | 2065 | 2065 | 2065 | 2066 | 2066 | 2066 | 2066 | 2067 | 2067 | 2067 | 2067 | 2068 | 2068 | 2068 | 2068 | 2069 | 2069 | 2069 | 2069 | 2070 | 2070 | 2070 | 2070 | 2071 | 2071 | 2071 | 2071 | 2072 | 2072 | 2072 | 2072 | 2073 | 2073 | 2073 | 2073 | 2074 | 2074 | 2074 | 2074 | 2075 | 2075 | 2075 | 2075 | 2076 | 2076 | 2076 | 2076 | 2077 | 2077 | 2077 | 2077 | 2078 | 2078 | 2078 | 2078 | 2079 | 2079 | 2079 | 2079 | 2080 | 2080 | 2080 | 2080 | 2081 | 2081 | 2081 | 2081 | 2082 | 2082 | 2082 | 2082 | 2083 | 2083 | 2083 | 2083 | 2084 | 2084 | 2084 | 2084 | 2085 | 2085 | 2085 | 2085 | 2086 | 2086 | 2086 | 2086 | 2087 | 2087 | 2087 | 2087 | 2088 | 2088 | 2088 | 2088 | 2089 | 2089 | 2089 | 2089 | 2090 | 2090 | 2090 | 2090 | 2091 | 2091 | 2091 | 2091 | 2092 | 2092 | 2092 | 2092 | 2093 | 2093 | 2093 | 2093 | 2094 | 2094 | 2094 | 2094 | 2095 | 2095 | 2095 | 2095 | 2096 | 2096 | 2096 | 2096 | 2097 | 2097 | 2097 | 2097 | 2098 | 2098 | 2098 | 2098 | 2099 | 2099 | 2099 | 2099 | 2100 | 2100 | 2100
| Pick FY Quarter - Check Dates | FY Quarter | Dates | Index |  | 5 | CWBS | 5 | - FEATURE CODES | Wt % | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep) | (Oct - Dec) | (Jan - Mar) | (Apr - Jun) | (Jul - Sep)
| Estimate Pricing Level Date: | 2024Q1 |  | 1149.32 | / | 6 | 02 | 6 | RELOCATIONS | 5% | 271.87 | 274.31 | 285.26 | 289.3 | 295.1 | 301.18 | 312.75 | 315.63 | 320.53 | 322.08 | 333.33 | 333.67 | 335.14 | 338.18 | 345.35 | 344.78 | 345.52 | 348.83 | 352.68 | 351.02 | 353.13 | 354.92 | 357.91 | 355.77 | 355.59 | 359.01 | 359.28 | 359.55 | 361.04 | 363.87 | 368.87 | 371.5 | 374.44 | 379.38 | 383.85 | 384.02 | 388.26 | 393.87 | 398.1 | 398.06 | 397.7 | 402.35 | 406.27 | 405.48 | 407.61 | 409.79 | 415.17 | 412.51 | 416.6 | 423.9 | 424.33 | 424.64 | 432.27 | 444.84 | 440.26 | 444.4 | 453.13 | 453.19 | 455.09 | 455.63 | 459.16 | 463.37 | 466.65 | 466.2 | 466.08 | 471.21 | 477.34 | 478.46 | 481.69 | 487.33 | 488.95 | 487 | 488.93 | 492.32 | 491.1 | 488.69 | 492.81 | 499.56 | 509.16 | 503.04 | 506.82 | 508.77 | 508.18 | 508.11 | 508.75 | 510.79 | 516.87 | 516.78 | 519.56 | 530.58 | 535.25 | 534.41 | 535.7 | 538.79 | 543.21 | 549.21 | 559.04 | 583.39 | 595.63 | 608.05 | 612.78 | 617.37 | 619.16 | 625.19 | 639.51 | 643.94 | 647.71 | 655.73 | 660.22 | 678.49 | 685.41 | 681.9 | 685.16 | 701.29 | 728.77 | 727.11 | 708.97 | 699.5 | 706.43 | 707.53 | 715.45 | 727.79 | 733.68 | 732.86 | 741.6 | 754.5 | 762.57 | 763.99 | 768.33 | 774.53 | 776.41 | 776.53 | 787.84 | 795.56 | 794.68 | 797.33 | 805.1 | 809.41 | 817.5 | 818.24 | 822.62 | 817.79 | 825.5 | 820.72 | 823.25 | 827.92 | 841.23 | 838.77 | 845.05 | 856.5 | 866.08 | 869.55 | 866.37 | 879.92 | 894.71 | 898.57 | 904.17 | 909.16 | 916.44 | 914.4 | 918.54 | 920.64 | 933.71 | 956.45 | 980.2 | 1032.05 | 1047.49 | 1059.94 | 1126.43 | 1143.58 | 1134.19 | 1127.52 | 1133.08 | 1146.67 | 1159.84 | 1155.72 | 1166.71 | 1170.71 | 1180.82 | 1185.09 | 1192.85 | 1210.71 | 1218.28 | 1226.2 | 1234.12 | 1242.04 | 1249.96 | 1262.07 | 1266.99 | 1275.31 | 1283.63 | 1291.94 | 1299.93 | 1308.47 | 1317 | 1325.53 | 1333.73 | 1342.49 | 1351.24 | 1360 | 1368.41 | 1377.39 | 1386.37 | 1395.36 | 1403.99 | 1413.2 | 1422.42 | 1431.64 | 1440.49 | 1449.95 | 1459.4 | 1468.86 | 1477.94 | 1487.65 | 1497.35 | 1507.05 | 1516.37 | 1526.32 | 1536.28 | 1546.23 | 1555.8 | 1566.01 | 1576.22 | 1586.43 | 1596.25 | 1606.72 | 1617.2 | 1627.68 | 1637.75 | 1648.5 | 1659.25 | 1670 | 1680.33 | 1691.36 | 1702.39 | 1713.42 | 1724.02 | 1735.34 | 1746.65 | 1757.97 | 1768.84 | 1780.45 | 1792.07 | 1803.68 | 1814.83 | 1826.75 | 1838.66 | 1850.57 | 1862.02 | 1874.24 | 1886.46 | 1898.69 | 1910.43 | 1922.97 | 1935.51 | 1948.05 | 1960.1 | 1972.97 | 1985.84 | 1998.7 | 2011.07 | 2024.27 | 2037.47 | 2050.67 | 2063.35 | 2076.9 | 2090.44 | 2103.99 | 2117 | 2130.9 | 2144.79 | 2158.69 | 2172.04 | 2186.3 | 2200.56 | 2214.81 | 2228.52 | 2243.14 | 2257.77 | 2272.4 | 2286.46 | 2301.47 | 2316.47 | 2331.48 | 2345.91 | 2361.3 | 2376.7 | 2392.1 | 2406.9 | 2422.7 | 2438.5 | 2454.3 | 2469.48 | 2485.69 | 2501.9 | 2518.11 | 2533.68 | 2550.32 | 2566.95 | 2583.58 | 2599.56 | 2616.62 | 2633.69 | 2650.75 | 2667.15 | 2684.66 | 2702.16 | 2719.67 | 2736.5 | 2754.46 | 2772.42 | 2790.38 | 2807.64 | 2826.07 | 2844.5 | 2862.93 | 2880.64 | 2899.55 | 2918.46 | 2937.37 | 2955.54 | 2974.94 | 2994.34 | 3013.74 | 3032.38 | 3052.29 | 3072.19 | 3092.1 | 3111.23 | 3131.65 | 3152.07 | 3172.49 | 3192.12 | 3213.07 | 3234.02 | 3254.98 | 3275.11 | 3296.61 | 3318.11 | 3339.61 | 3360.27 | 3382.32 | 3404.38 | 3426.44 | 3447.63 | 3470.26 | 3492.89 | 3515.52 | 3537.27 | 3560.49 | 3583.71 | 3606.93 | 3629.24 | 3653.06 | 3676.88 | 3700.71 | 3723.6 | 3748.04 | 3772.48 | 3796.93 | 3820.41 | 3845.49 | 3870.57 | 3895.65 | 3919.74 | 3945.47 | 3971.2 | 3996.93 | 4021.66 | 4048.06 | 4074.45 | 4100.85 | 4126.22 | 4153.31 | 4180.39 | 4207.47 | 4233.5 | 4261.29 | 4289.08 | 4316.87 | 4343.57 | 4372.08 | 4400.6 | 4429.11 | 4456.51 | 4485.76 | 4515.01 | 4544.26 | 4572.38 | 4602.39 | 4632.4 | 4662.41 | 4691.26 | 4722.05 | 4752.84 | 4783.64 | 4813.23 | 4844.82 | 4876.42 | 4908.01 | 4938.37 | 4970.79 | 5003.21 | 5035.62 | 5066.77 | 5100.03 | 5133.29 | 5166.55 | 5198.51 | 5232.63 | 5266.75 | 5300.88 | 5333.67 | 5368.68 | 5403.69 | 5438.7 | 5472.34 | 5508.26 | 5544.19 | 5580.11 | 5614.63 | 5651.48 | 5688.33 | 5725.19 | 5760.61 | 5798.42 | 5836.23 | 5874.04 | 5910.38 | 5949.18 | 5987.97 | 6026.77 | 6064.05 | 6103.86 | 6143.66 | 6183.46 | 6221.72 | 6262.56 | 6303.4 | 6344.23 | 6383.48 | 6425.38 | 6467.28 | 6509.18 | 6549.45 | 6592.44 | 6635.43 | 6678.42 | 6719.74 | 6763.85 | 6807.95 | 6852.06 | 6894.45 | 6939.71 | 6984.96 | 7030.22 | 7073.71 | 7120.14 | 7166.57 | 7213 | 7257.62 | 7305.26 | 7352.9 | 7400.54 | 7446.32 | 7495.2 | 7544.08 | 7592.95 | 7639.93 | 7690.07 | 7740.22 | 7790.37 | 7838.56 | 7890.02 | 7941.47 | 7992.92 | 8042.37 | 8095.16 | 8147.95 | 8200.74 | 8251.47 | 8305.63 | 8359.79 | 8413.96
| Middle Point of Construction Date: | 2025Q1 |  | 1162.49 | = | 7 | 03 | 7 | RESERVOIRS | 5% | 274.7 | 276.51 | 293.22 | 297.8 | 300.01 | 305.39 | 325.04 | 330.69 | 335.73 | 336.83 | 356.25 | 357.68 | 359.13 | 360.28 | 370.01 | 370.86 | 371.61 | 372.33 | 379.08 | 378.13 | 379.31 | 381.22 | 383.57 | 383.71 | 384.37 | 386.05 | 387.94 | 388.09 | 389.18 | 390.97 | 398.32 | 399.74 | 402.12 | 405.81 | 410.03 | 411.79 | 414.93 | 418.28 | 423.45 | 424.66 | 426.62 | 432.72 | 440.03 | 441.87 | 443.75 | 445.96 | 448.72 | 449.9 | 452.29 | 455.74 | 459.63 | 460.86 | 463.31 | 466.47 | 468.97 | 469.52 | 471.63 | 476.39 | 481 | 481.85 | 483.22 | 489.04 | 494.52 | 495.36 | 497.21 | 501.71 | 505.9 | 506.27 | 507.4 | 510.01 | 512.1 | 514.82 | 517.4 | 520.17 | 522.7 | 525.43 | 532.68 | 539.36 | 544.82 | 545.17 | 546.17 | 549.66 | 554.69 | 558.99 | 563.32 | 563.43 | 570.76 | 574.83 | 578.45 | 588.04 | 596.92 | 597.44 | 599.3 | 601.96 | 608.05 | 612.58 | 618.26 | 622.07 | 631.33 | 636.79 | 643.64 | 648.68 | 655.31 | 659.06 | 666.12 | 668.01 | 669.42 | 686.51 | 694.1 | 706.17 | 718.54 | 718.99 | 720.94 | 725.82 | 737.53 | 744.72 | 754.07 | 755.1 | 766.33 | 770.44 | 778.06 | 780.49 | 798.39 | 799.72 | 802.29 | 811.14 | 821.33 | 824.47 | 828.38 | 833.59 | 844.93 | 845.07 | 849.84 | 853.83 | 869.35 | 869.57 | 871.75 | 874.82 | 893.52 | 895.08 | 898.38 | 900.9 | 920.24 | 922.38 | 926.33 | 929.06 | 946.27 | 946.67 | 948.17 | 952.07 | 968.29 | 970.05 | 967.86 | 972.35 | 981.61 | 992.51 | 997.24 | 1004.15 | 1030.73 | 1034.15 | 1038.12 | 1041.2 | 1043.92 | 1048.97 | 1056.25 | 1079.72 | 1106.5 | 1121.89 | 1133.29 | 1146.88 | 1151.93 | 1167.41 | 1186.3 | 1197.43 | 1211.96 | 1221.21 | 1233.52 | 1241.42 | 1288.19 | 1297.53 | 1305.73 | 1313.68 | 1322.4 | 1331 | 1339.59 | 1348.19 | 1356.78 | 1369.93 | 1375.28 | 1384.3 | 1393.33 | 1402.36 | 1411.03 | 1420.29 | 1429.56 | 1438.82 | 1447.72 | 1457.22 | 1466.72 | 1476.23 | 1485.36 | 1495.11 | 1504.86 | 1514.61 | 1523.98 | 1533.98 | 1543.99 | 1553.99 | 1563.6 | 1573.87 | 1584.13 | 1594.39 | 1604.26 | 1614.79 | 1625.32 | 1635.85 | 1645.97 | 1656.77 | 1667.58 | 1678.38 | 1688.76 | 1699.85 | 1710.93 | 1722.02 | 1732.67 | 1744.04 | 1755.42 | 1766.79 | 1777.72 | 1789.39 | 1801.06 | 1812.73 | 1823.94 | 1835.91 | 1847.88 | 1859.86 | 1871.36 | 1883.65 | 1895.93 | 1908.21 | 1920.02 | 1932.62 | 1945.22 | 1957.83 | 1969.94 | 1982.87 | 1995.8 | 2008.73 | 2021.16 | 2034.42 | 2047.69 | 2060.96 | 2073.71 | 2087.32 | 2100.93 | 2114.54 | 2127.62 | 2141.59 | 2155.55 | 2169.52 | 2182.94 | 2197.27 | 2211.6 | 2225.93 | 2239.7 | 2254.4 | 2269.1 | 2283.8 | 2297.93 | 2313.01 | 2328.1 | 2343.18 | 2357.68 | 2373.15 | 2388.63 | 2404.1 | 2418.98 | 2434.85 | 2450.73 | 2466.61 | 2481.87 | 2498.16 | 2514.45 | 2530.74 | 2546.4 | 2563.11 | 2579.83 | 2596.54 | 2612.6 | 2629.75 | 2646.9 | 2664.05 | 2680.53 | 2698.13 | 2715.72 | 2733.32 | 2750.23 | 2768.28 | 2786.33 | 2804.38 | 2821.73 | 2840.25 | 2858.78 | 2877.3 | 2895.1 | 2914.1 | 2933.1 | 2952.11 | 2970.37 | 2989.87 | 3009.36 | 3028.86 | 3047.6 | 3067.6 | 3087.61 | 3107.61 | 3126.84 | 3147.36 | 3167.89 | 3188.41 | 3208.13 | 3229.19 | 3250.25 | 3271.31 | 3291.55 | 3313.15 | 3334.76 | 3356.36 | 3377.13 | 3399.29 | 3421.46 | 3443.63 | 3464.93 | 3487.67 | 3510.42 | 3533.16 | 3555.02 | 3578.35 | 3601.69 | 3625.02 | 3647.45 | 3671.39 | 3695.33 | 3719.28 | 3742.28 | 3766.85 | 3791.41 | 3815.98 | 3839.58 | 3864.79 | 3889.99 | 3915.19 | 3939.41 | 3965.27 | 3991.13 | 4016.99 | 4041.84 | 4068.37 | 4094.9 | 4121.43 | 4146.92 | 4174.14 | 4201.37 | 4228.59 | 4254.74 | 4282.67 | 4310.6 | 4338.53 | 4365.37 | 4394.02 | 4422.68 | 4451.33 | 4478.87 | 4508.27 | 4537.67 | 4567.06 | 4595.32 | 4625.48 | 4655.65 | 4685.81 | 4714.8 | 4745.74 | 4776.69 | 4807.64 | 4837.38 | 4869.13 | 4900.89 | 4932.64 | 4963.15 | 4995.73 | 5028.31 | 5060.89 | 5092.19 | 5125.62 | 5159.04 | 5192.47 | 5224.59 | 5258.89 | 5293.18 | 5327.47 | 5360.43 | 5395.62 | 5430.8 | 5465.99 | 5499.8 | 5535.9 | 5572 | 5608.1 | 5642.8 | 5679.84 | 5716.88 | 5753.91 | 5789.51 | 5827.51 | 5865.51 | 5903.52 | 5940.04 | 5979.03 | 6018.02 | 6057.01 | 6094.48 | 6134.48 | 6174.49 | 6214.49 | 6252.93 | 6293.98 | 6335.02 | 6376.07 | 6415.51 | 6457.62 | 6499.73 | 6541.84 | 6582.31 | 6625.52 | 6668.73 | 6711.93 | 6753.45 | 6797.78 | 6842.11 | 6886.44 | 6929.04 | 6974.53 | 7020.01 | 7065.49 | 7109.2 | 7155.86 | 7202.53 | 7249.19 | 7294.04 | 7341.92 | 7389.79 | 7437.67 | 7483.68 | 7532.81 | 7581.93 | 7631.05 | 7678.26 | 7728.66 | 7779.06 | 7829.46 | 7877.89 | 7929.6 | 7981.31 | 8033.03 | 8082.72 | 8135.77 | 8188.83 | 8241.88 | 8292.87 | 8347.3 | 8401.74 | 8456.17 | 8508.48 | 8564.33 | 8620.18 | 8676.03 | 8729.7 | 8787.01 | 8844.31 | 8901.61 | 8956.68 | 9015.47 | 9074.26 | 9133.05
[6 empty] | 8 | 04 | 8 | DAMS | 15% | 268.61 | 272.52 | 281.67 | 285.68 | 291.27 | 297.99 | 308.49 | 311.94 | 317.12 | 318.98 | 328.96 | 329.62 | 329.81 | 331.82 | 337.99 | 339.43 | 339.85 | 343.07 | 347.13 | 346.95 | 348.18 | 350.26 | 351.95 | 351.5 | 351.32 | 353.16 | 353.43 | 353.83 | 355.05 | 356.86 | 360.95 | 363.11 | 366.73 | 370.67 | 374.28 | 375.6 | 380.19 | 383.99 | 387.52 | 388.29 | 389.13 | 392.24 | 396.69 | 397.57 | 400.37 | 402.16 | 404.98 | 404.39 | 406.6 | 409.86 | 412.2 | 412.6 | 416.86 | 423.16 | 424.3 | 426.5 | 430.77 | 434.22 | 437.46 | 439.04 | 443.1 | 449.75 | 453.64 | 453.85 | 455.02 | 458.98 | 462.87 | 463.99 | 465.98 | 470.03 | 472.01 | 473.15 | 475.97 | 479.55 | 480.64 | 480.07 | 482.4 | 487.32 | 492.58 | 491.25 | 494.04 | 496.25 | 498.01 | 498.82 | 500.65 | 501.87 | 505.85 | 507.48 | 509.54 | 517.86 | 523.54 | 523.71 | 524.83 | 527.44 | 530.53 | 535 | 543.14 | 561.95 | 574.06 | 587.47 | 594.9 | 598.72 | 603.91 | 611.03 | 625.48 | 631.2 | 637.92 | 647.39 | 651.74 | 668.81 | 674.55 | 673.9 | 678.85 | 694.86 | 719.14 | 720.13 | 705.76 | 697.72 | 701.88 | 701.98 | 708.05 | 715.18 | 723.36 | 723.26 | 729.81 | 742.73 | 751.52 | 752.53 | 758.31 | 763.62 | 764.46 | 765.52 | 772.81 | 776.78 | 781.78 | 782.77 | 789.65 | 794.6 | 799.78 | 800.7 | 807.1 | 804.97 | 809.36 | 806.3 | 809.87 | 812.8 | 824.03 | 821.98 | 828.34 | 836.42 | 845.12 | 846.76 | 844.46 | 855.23 | 867.57 | 879.62 | 886.33 | 890.72 | 896.58 | 893.69 | 897.27 | 901 | 904.37 | 911.27 | 928.87 | 967.68 | 1000.71 | 1027.87 | 1064.57 | 1091.01 | 1102.4 | 1104.72 | 1119.09 | 1131.93 | 1145.32 | 1145.95 | 1160.26 | 1162.18 | 1168.01 | 1169.2 | 1176.6 | 1192.78 | 1204.2 | 1212.03 | 1219.85 | 1227.68 | 1235.51 | 1247.48 | 1252.35 | 1260.57 | 1268.79 | 1277.01 | 1284.91 | 1293.34 | 1301.78 | 1310.21 | 1318.32 | 1326.97 | 1335.62 | 1344.28 | 1352.59 | 1361.47 | 1370.35 | 1379.23 | 1387.76 | 1396.87 | 1405.98 | 1415.09 | 1423.84 | 1433.19 | 1442.54 | 1451.88 | 1460.86 | 1470.45 | 1480.04 | 1489.63 | 1498.85 | 1508.68 | 1518.52 | 1528.36 | 1537.82 | 1547.91 | 1558 | 1568.1 | 1577.8 | 1588.16 | 1598.51 | 1608.87 | 1618.82 | 1629.45 | 1640.07 | 1650.7 | 1660.91 | 1671.81 | 1682.72 | 1693.62 | 1704.09 | 1715.28 | 1726.47 | 1737.65 | 1748.4 | 1759.88 | 1771.35 | 1782.83 | 1793.86 | 1805.63 | 1817.41 | 1829.18 | 1840.5 | 1852.58 | 1864.66 | 1876.74 | 1888.35 | 1900.75 | 1913.14 | 1925.54 | 1937.45 | 1950.17 | 1962.88 | 1975.6 | 1987.82 | 2000.87 | 2013.92 | 2026.97 | 2039.51 | 2052.89 | 2066.28 | 2079.67 | 2092.53 | 2106.27 | 2120.01 | 2133.74 | 2146.94 | 2161.03 | 2175.13 | 2189.22 | 2202.76 | 2217.22 | 2231.68 | 2246.14 | 2260.03 | 2274.87 | 2289.7 | 2304.54 | 2318.79 | 2334.01 | 2349.23 | 2364.45 | 2379.08 | 2394.7 | 2410.31 | 2425.93 | 2440.94 | 2456.96 | 2472.98 | 2489 | 2504.4 | 2520.84 | 2537.28 | 2553.72 | 2569.52 | 2586.38 | 2603.25 | 2620.12 | 2636.32 | 2653.63 | 2670.93 | 2688.24 | 2704.87 | 2722.62 | 2740.38 | 2758.13 | 2775.2 | 2793.41 | 2811.63 | 2829.84 | 2847.35 | 2866.04 | 2884.73 | 2903.42 | 2921.38 | 2940.56 | 2959.73 | 2978.91 | 2997.34 | 3017.01 | 3036.69 | 3056.36 | 3075.27 | 3095.45 | 3115.64 | 3135.83 | 3155.23 | 3175.94 | 3196.65 | 3217.36 | 3237.26 | 3258.51 | 3279.76 | 3301.01 | 3321.43 | 3343.23 | 3365.03 | 3386.84 | 3407.79 | 3430.16 | 3452.52 | 3474.89 | 3496.39 | 3519.34 | 3542.29 | 3565.24 | 3587.3 | 3610.84 | 3634.39 | 3657.94 | 3680.57 | 3704.72 | 3728.88 | 3753.04 | 3776.26 | 3801.05 | 3825.83 | 3850.62 | 3874.44 | 3899.87 | 3925.31 | 3950.74 | 3975.18 | 4001.27 | 4027.36 | 4053.46 | 4078.53 | 4105.3 | 4132.08 | 4158.85 | 4184.57 | 4212.04 | 4239.51 | 4266.98 | 4293.37 | 4321.56 | 4349.74 | 4377.92 | 4405 | 4433.92 | 4462.83 | 4491.74 | 4519.53 | 4549.2 | 4578.86 | 4608.53 | 4637.04 | 4667.48 | 4697.91 | 4728.35 | 4757.6 | 4788.83 | 4820.06 | 4851.29 | 4881.3 | 4913.34 | 4945.38 | 4977.42 | 5008.21 | 5041.09 | 5073.96 | 5106.84 | 5138.43 | 5172.16 | 5205.88 | 5239.61 | 5272.03 | 5306.63 | 5341.24 | 5375.84 | 5409.1 | 5444.6 | 5480.11 | 5515.61 | 5549.74 | 5586.16 | 5622.59 | 5659.02 | 5694.03 | 5731.4 | 5768.78 | 5806.16 | 5842.07 | 5880.42 | 5918.77 | 5957.12 | 5993.97 | 6033.31 | 6072.66 | 6112 | 6149.81 | 6190.18 | 6230.55 | 6270.91 | 6309.71 | 6351.12 | 6392.54 | 6433.96 | 6473.76 | 6516.25 | 6558.75 | 6601.24 | 6642.08 | 6685.67 | 6729.27 | 6772.87 | 6814.77 | 6859.5 | 6904.23 | 6948.97 | 6991.95 | 7037.85 | 7083.74 | 7129.64 | 7173.74 | 7220.83 | 7267.92 | 7315.01 | 7360.26 | 7408.57 | 7456.89 | 7505.2 | 7551.63 | 7601.2 | 7650.77 | 7700.34 | 7747.97 | 7798.83 | 7849.69 | 7900.54 | 7949.42 | 8001.6 | 8053.78 | 8105.96 | 8156.1 | 8209.64 | 8263.18 | 8316.71
|  |  | Escalation Percentage: -> | 101.1% |  | 9 | 05 | 9 | LOCKS | 2% | 267.29 | 271.45 | 280.61 | 285.09 | 290.51 | 297.43 | 307.88 | 311.66 | 316.52 | 318.59 | 328.44 | 329.3 | 329.66 | 332.24 | 338.19 | 339.29 | 339.75 | 342.69 | 346.67 | 346.19 | 345.85 | 348 | 349.9 | 349.39 | 348.48 | 350.45 | 351.03 | 351.44 | 352.56 | 354.8 | 358.68 | 361.3 | 365.49 | 370.09 | 373.68 | 374.96 | 378.98 | 383.12 | 385.9 | 386.53 | 386.61 | 389.75 | 393.42 | 393.88 | 396.33 | 398.06 | 400.61 | 399.93 | 402.01 | 405.84 | 407.64 | 407.9 | 411.78 | 418.65 | 419.5 | 422.06 | 426.64 | 429.83 | 432.86 | 434.57 | 438.73 | 445.29 | 449.25 | 449.32 | 449.94 | 453.54 | 457.63 | 458.66 | 460.32 | 464.19 | 466.28 | 467.21 | 469.68 | 473.13 | 474.11 | 472.96 | 474.43 | 478.77 | 484.44 | 482.76 | 485.77 | 488.74 | 490.22 | 490.8 | 492.11 | 493.23 | 497.55 | 498.84 | 500.92 | 510.32 | 516.3 | 516.21 | 517.34 | 520.67 | 523.36 | 528.58 | 537.81 | 560.55 | 572.89 | 588.45 | 595.76 | 599.22 | 602.17 | 610.26 | 624.39 | 630.3 | 638.4 | 648.48 | 652.21 | 671.85 | 677.88 | 676.32 | 682.18 | 701.14 | 730.54 | 728.97 | 708.16 | 696.16 | 699.79 | 701.92 | 708.17 | 718.31 | 725.64 | 725.88 | 733.84 | 748.48 | 756.76 | 756.73 | 760.93 | 765.02 | 765.35 | 764.34 | 771.04 | 775.23 | 778.58 | 780.15 | 787.1 | 792.29 | 799.14 | 799.98 | 804.23 | 800.49 | 805.36 | 801.48 | 802.59 | 805.92 | 818.83 | 815.96 | 823.42 | 832.66 | 842.09 | 844.22 | 843.17 | 856.82 | 870.64 | 881.41 | 888.34 | 892.45 | 897.14 | 892.82 | 896.16 | 899.9 | 903.62 | 911.01 | 931.5 | 976.85 | 1013.65 | 1042.24 | 1084.76 | 1110.29 | 1121.99 | 1117.99 | 1127.79 | 1141.8 | 1153.81 | 1153.09 | 1167.05 | 1168.54 | 1173.19 | 1174.2 | 1181.42 | 1197.99 | 1211.66 | 1219.54 | 1227.41 | 1235.29 | 1243.16 | 1255.21 | 1260.11 | 1268.38 | 1276.65 | 1284.92 | 1292.87 | 1301.36 | 1309.84 | 1318.33 | 1326.48 | 1335.19 | 1343.9 | 1352.61 | 1360.97 | 1369.91 | 1378.84 | 1387.77 | 1396.36 | 1405.52 | 1414.69 | 1423.86 | 1432.66 | 1442.07 | 1451.47 | 1460.88 | 1469.91 | 1479.56 | 1489.21 | 1498.86 | 1508.13 | 1518.03 | 1527.93 | 1537.83 | 1547.34 | 1557.5 | 1567.66 | 1577.81 | 1587.57 | 1597.99 | 1608.41 | 1618.84 | 1628.85 | 1639.54 | 1650.23 | 1660.93 | 1671.2 | 1682.17 | 1693.14 | 1704.11 | 1714.65 | 1725.91 | 1737.16 | 1748.42 | 1759.23 | 1770.78 | 1782.33 | 1793.88 | 1804.97 | 1816.82 | 1828.67 | 1840.52 | 1851.9 | 1864.06 | 1876.21 | 1888.37 | 1900.05 | 1912.52 | 1925 | 1937.47 | 1949.45 | 1962.25 | 1975.04 | 1987.84 | 2000.14 | 2013.27 | 2026.4 | 2039.52 | 2052.14 | 2065.61 | 2079.08 | 2092.55 | 2105.5 | 2119.32 | 2133.14 | 2146.96 | 2160.24 | 2174.42 | 2188.6 | 2202.78 | 2216.41 | 2230.96 | 2245.5 | 2260.05 | 2274.03 | 2288.96 | 2303.89 | 2318.81 | 2333.16 | 2348.47 | 2363.79 | 2379.1 | 2393.82 | 2409.53 | 2425.25 | 2440.96 | 2456.06 | 2472.18 | 2488.3 | 2504.42 | 2519.92 | 2536.46 | 2553 | 2569.54 | 2585.43 | 2602.41 | 2619.38 | 2636.35 | 2652.66 | 2670.07 | 2687.48 | 2704.89 | 2721.63 | 2739.49 | 2757.35 | 2775.22 | 2792.39 | 2810.72 | 2829.05 | 2847.38 | 2864.99 | 2883.8 | 2902.6 | 2921.41 | 2939.48 | 2958.77 | 2978.07 | 2997.36 | 3015.91 | 3035.7 | 3055.5 | 3075.3 | 3094.32 | 3114.63 | 3134.94 | 3155.25 | 3174.77 | 3195.61 | 3216.45 | 3237.29 | 3257.32 | 3278.7 | 3300.08 | 3321.46 | 3342.01 | 3363.94 | 3385.88 | 3407.82 | 3428.9 | 3451.41 | 3473.91 | 3496.42 | 3518.05 | 3541.14 | 3564.23 | 3587.33 | 3609.52 | 3633.21 | 3656.9 | 3680.6 | 3703.37 | 3727.68 | 3751.98 | 3776.29 | 3799.65 | 3824.59 | 3849.54 | 3874.48 | 3898.44 | 3924.03 | 3949.62 | 3975.21 | 3999.8 | 4026.06 | 4052.31 | 4078.57 | 4103.8 | 4130.74 | 4157.67 | 4184.61 | 4210.5 | 4238.14 | 4265.77 | 4293.41 | 4319.97 | 4348.33 | 4376.68 | 4405.04 | 4432.29 | 4461.38 | 4490.48 | 4519.57 | 4547.53 | 4577.38 | 4607.23 | 4637.08 | 4665.77 | 4696.39 | 4727.02 | 4757.64 | 4787.08 | 4818.5 | 4849.92 | 4881.34 | 4911.54 | 4943.78 | 4976.02 | 5008.26 | 5039.24 | 5072.32 | 5105.39 | 5138.47 | 5170.26 | 5204.2 | 5238.13 | 5272.07 | 5304.69 | 5339.51 | 5374.33 | 5409.15 | 5442.61 | 5478.33 | 5514.06 | 5549.78 | 5584.12 | 5620.77 | 5657.42 | 5694.08 | 5729.3 | 5766.91 | 5804.52 | 5842.12 | 5878.27 | 5916.85 | 5955.43 | 5994.02 | 6031.1 | 6070.69 | 6110.28 | 6149.86 | 6187.91 | 6228.53 | 6269.14 | 6309.76 | 6348.79 | 6390.47 | 6432.14 | 6473.81 | 6513.86 | 6556.62 | 6599.38 | 6642.13 | 6683.22 | 6727.09 | 6770.96 | 6814.83 | 6856.99 | 6902 | 6947.01 | 6992.01 | 7035.27 | 7081.45 | 7127.63 | 7173.81 | 7218.19 | 7265.57 | 7312.95 | 7360.33 | 7405.86 | 7454.47 | 7503.08 | 7551.69 | 7598.41 | 7648.29 | 7698.16 | 7748.04 | 7795.97 | 7847.14 | 7898.31 | 7949.49 | 7998.66 | 8051.17 | 8103.67 | 8156.17 | 8206.63 | 8260.5 | 8314.37 | 8368.23
[6 empty] | 10 | 06 | 10 | FISH & WILDLIFE FACILITIES | 5% | 272.96 | 276.04 | 284.61 | 287.69 | 293.79 | 300 | 309.83 | 312.44 | 317.17 | 318.26 | 327.74 | 327.83 | 327.53 | 329.77 | 336.78 | 337.58 | 337.59 | 341.9 | 345.41 | 344.61 | 344.74 | 346.93 | 349.22 | 347.84 | 347.27 | 349.61 | 349.34 | 349.75 | 350.28 | 352.65 | 356.54 | 359.07 | 362.38 | 367.09 | 370.86 | 371.49 | 374.97 | 379.49 | 382.47 | 382.81 | 382.1 | 385.48 | 388.93 | 389.01 | 391.31 | 393.28 | 396.94 | 395.33 | 398.09 | 402.68 | 403.56 | 403.94 | 409.21 | 419.09 | 417.86 | 421.18 | 427.15 | 429.69 | 432.59 | 434.12 | 438.14 | 444.64 | 447.98 | 447.96 | 447.8 | 452.65 | 457.78 | 459.09 | 461.23 | 466.4 | 468.57 | 468.4 | 469.97 | 474.07 | 474.38 | 472.57 | 474.86 | 480.31 | 487.47 | 483.86 | 487.08 | 489.21 | 489.75 | 489.55 | 490.33 | 491.91 | 496.69 | 497.31 | 499.28 | 508.67 | 514.07 | 513.82 | 514.15 | 516.87 | 520.35 | 525.69 | 534.75 | 558.9 | 571.55 | 586.56 | 593.35 | 597.76 | 600.97 | 608.18 | 624.32 | 630.14 | 636.39 | 645.47 | 649.01 | 668.79 | 674.11 | 671.55 | 675.58 | 693.72 | 722.13 | 719.86 | 698.29 | 686.42 | 689.95 | 691.34 | 696.93 | 707.21 | 712.33 | 711.42 | 718.73 | 732.94 | 740.7 | 740.08 | 744.72 | 749.69 | 749.6 | 749.46 | 758.43 | 764.29 | 764.9 | 766.75 | 774.03 | 779.64 | 785.65 | 786.93 | 792.02 | 788.66 | 793.12 | 788.51 | 790.9 | 795.09 | 807.3 | 804.64 | 811.91 | 823.16 | 831.76 | 834.07 | 833.09 | 846.58 | 860.94 | 867.95 | 873.73 | 878.35 | 881.63 | 877.83 | 880.38 | 883.42 | 890.83 | 904.43 | 925.56 | 974.85 | 1002.62 | 1025.12 | 1078.05 | 1100.62 | 1105.63 | 1100.49 | 1108.19 | 1122.28 | 1134.8 | 1132.27 | 1144.9 | 1147.14 | 1150.59 | 1151.26 | 1157.23 | 1175.1 | 1186.06 | 1193.77 | 1201.48 | 1209.19 | 1216.9 | 1228.69 | 1233.48 | 1241.58 | 1249.68 | 1257.77 | 1265.55 | 1273.86 | 1282.17 | 1290.48 | 1298.46 | 1306.98 | 1315.5 | 1324.03 | 1332.22 | 1340.96 | 1349.71 | 1358.45 | 1366.86 | 1375.83 | 1384.8 | 1393.77 | 1402.39 | 1411.6 | 1420.81 | 1430.01 | 1438.86 | 1448.3 | 1457.75 | 1467.19 | 1476.27 | 1485.96 | 1495.65 | 1505.34 | 1514.65 | 1524.59 | 1534.53 | 1544.48 | 1554.03 | 1564.23 | 1574.43 | 1584.63 | 1594.44 | 1604.9 | 1615.37 | 1625.83 | 1635.89 | 1646.63 | 1657.37 | 1668.1 | 1678.42 | 1689.44 | 1700.46 | 1711.48 | 1722.06 | 1733.37 | 1744.67 | 1755.97 | 1766.84 | 1778.43 | 1790.03 | 1801.63 | 1812.77 | 1824.67 | 1836.57 | 1848.47 | 1859.91 | 1872.12 | 1884.32 | 1896.53 | 1908.26 | 1920.79 | 1933.32 | 1945.84 | 1957.88 | 1970.73 | 1983.58 | 1996.43 | 2008.78 | 2021.97 | 2035.16 | 2048.34 | 2061.01 | 2074.54 | 2088.07 | 2101.6 | 2114.6 | 2128.48 | 2142.36 | 2156.24 | 2169.58 | 2183.82 | 2198.06 | 2212.3 | 2225.99 | 2240.6 | 2255.21 | 2269.82 | 2283.86 | 2298.85 | 2313.85 | 2328.84 | 2343.24 | 2358.62 | 2374.01 | 2389.39 | 2404.17 | 2419.95 | 2435.73 | 2451.51 | 2466.68 | 2482.87 | 2499.06 | 2515.25 | 2530.81 | 2547.42 | 2564.03 | 2580.65 | 2596.61 | 2613.65 | 2630.7 | 2647.74 | 2664.12 | 2681.61 | 2699.1 | 2716.58 | 2733.39 | 2751.33 | 2769.27 | 2787.22 | 2804.46 | 2822.87 | 2841.27 | 2859.68 | 2877.37 | 2896.26 | 2915.15 | 2934.04 | 2952.19 | 2971.56 | 2990.94 | 3010.32 | 3028.94 | 3048.82 | 3068.71 | 3088.59 | 3107.7 | 3128.09 | 3148.49 | 3168.89 | 3188.5 | 3209.42 | 3230.35 | 3251.28 | 3271.4 | 3292.87 | 3314.34 | 3335.82 | 3356.45 | 3378.48 | 3400.52 | 3422.55 | 3443.72 | 3466.32 | 3488.93 | 3511.53 | 3533.26 | 3556.45 | 3579.64 | 3602.83 | 3625.12 | 3648.92 | 3672.71 | 3696.51 | 3719.37 | 3743.79 | 3768.2 | 3792.62 | 3816.08 | 3841.13 | 3866.18 | 3891.22 | 3915.3 | 3941 | 3966.7 | 3992.4 | 4017.09 | 4043.46 | 4069.83 | 4096.2 | 4121.54 | 4148.59 | 4175.65 | 4202.7 | 4228.7 | 4256.46 | 4284.21 | 4311.97 | 4338.64 | 4367.12 | 4395.6 | 4424.08 | 4451.45 | 4480.67 | 4509.89 | 4539.11 | 4567.19 | 4597.17 | 4627.15 | 4657.12 | 4685.93 | 4716.69 | 4747.45 | 4778.21 | 4807.77 | 4839.33 | 4870.88 | 4902.44 | 4932.77 | 4965.15 | 4997.53 | 5029.91 | 5061.02 | 5094.24 | 5127.46 | 5160.68 | 5192.61 | 5226.69 | 5260.78 | 5294.86 | 5327.62 | 5362.59 | 5397.56 | 5432.53 | 5466.13 | 5502.01 | 5537.89 | 5573.77 | 5608.25 | 5645.07 | 5681.88 | 5718.69 | 5754.07 | 5791.84 | 5829.61 | 5867.38 | 5903.67 | 5942.43 | 5981.18 | 6019.93 | 6057.17 | 6096.93 | 6136.69 | 6176.45 | 6214.66 | 6255.45 | 6296.24 | 6337.04 | 6376.24 | 6418.09 | 6459.94 | 6501.8 | 6542.02 | 6584.96 | 6627.9 | 6670.85 | 6712.11 | 6756.17 | 6800.23 | 6844.29 | 6886.63 | 6931.83 | 6977.03 | 7022.24 | 7065.68 | 7112.06 | 7158.44 | 7204.82 | 7249.39 | 7296.97 | 7344.56 | 7392.14 | 7437.87 | 7486.69 | 7535.52 | 7584.34 | 7631.26 | 7681.35 | 7731.44 | 7781.53 | 7829.67 | 7881.06 | 7932.46 | 7983.85 | 8033.24 | 8085.97 | 8138.7 | 8191.43
| Paste the Web Address into browser for downloadable (.pdf) source of factors: |  |  |  |  | 11 | 07 | 11 | POWER PLANT | 10% | 254.91 | 261.92 | 271.8 | 276.78 | 282.49 | 290.3 | 299.66 | 305.47 | 309.82 | 312.2 | 318.6 | 318.44 | 319.76 | 322.14 | 326.42 | 328.13 | 329.23 | 331.22 | 336.05 | 336.13 | 335.55 | 336.98 | 338.59 | 338.98 | 339.42 | 341.68 | 342.4 | 343.89 | 344.84 | 346.64 | 350.24 | 352.88 | 355.43 | 359.77 | 362.57 | 365.95 | 370.58 | 375.63 | 379.26 | 380.68 | 382.72 | 385.98 | 390.04 | 392.37 | 395.96 | 398.37 | 400.46 | 401.16 | 403.39 | 406.1 | 407.68 | 408.81 | 411.75 | 415.92 | 417.3 | 419.18 | 422.2 | 424.51 | 426.7 | 429.08 | 432.79 | 437.55 | 440.85 | 442.1 | 441.89 | 444.43 | 446.64 | 447.38 | 447.1 | 450.74 | 453.52 | 455.29 | 457.05 | 458.84 | 460.27 | 459.69 | 461.41 | 464.12 | 467.99 | 467.98 | 469.5 | 472.63 | 473.85 | 474.95 | 476.65 | 478.03 | 481.14 | 482.73 | 483.76 | 489.01 | 493.68 | 493.88 | 494.64 | 496.8 | 499.15 | 502.53 | 508.32 | 524.12 | 534.82 | 545 | 550.58 | 555.21 | 557.62 | 565.16 | 578.01 | 583.39 | 591.74 | 602.27 | 605.88 | 621.78 | 628.04 | 628.54 | 635.04 | 648.1 | 672.38 | 676.86 | 660.73 | 657.37 | 660.93 | 664.75 | 670.51 | 677.22 | 683.75 | 684.61 | 690.66 | 702.31 | 709.32 | 709.88 | 713.57 | 717.4 | 717.04 | 718.99 | 722.83 | 725.97 | 728.72 | 730.08 | 735.33 | 738.7 | 743.11 | 744.66 | 746.47 | 743.2 | 745.99 | 743.39 | 741.76 | 745.13 | 752.67 | 751.99 | 756.08 | 760.68 | 766.03 | 768.15 | 771.29 | 779.8 | 789.39 | 796.24 | 800.68 | 804.9 | 808.46 | 808.21 | 811.48 | 812.05 | 814.58 | 820.49 | 833.37 | 865.7 | 899.04 | 926.74 | 968.78 | 996.24 | 1013.4 | 1015.93 | 1033.18 | 1045.85 | 1051.1 | 1055.21 | 1063.71 | 1068.22 | 1074.87 | 1075.37 | 1083.11 | 1104.34 | 1119.94 | 1127.22 | 1134.5 | 1141.78 | 1149.06 | 1160.19 | 1164.72 | 1172.37 | 1180.01 | 1187.66 | 1195.01 | 1202.85 | 1210.69 | 1218.54 | 1226.08 | 1234.12 | 1242.17 | 1250.22 | 1257.95 | 1266.21 | 1274.47 | 1282.73 | 1290.66 | 1299.13 | 1307.61 | 1316.08 | 1324.22 | 1332.91 | 1341.6 | 1350.3 | 1358.65 | 1367.57 | 1376.48 | 1385.4 | 1393.97 | 1403.12 | 1412.27 | 1421.42 | 1430.22 | 1439.6 | 1448.99 | 1458.38 | 1467.4 | 1477.03 | 1486.67 | 1496.3 | 1505.55 | 1515.44 | 1525.32 | 1535.2 | 1544.7 | 1554.84 | 1564.98 | 1575.12 | 1584.86 | 1595.26 | 1605.67 | 1616.07 | 1626.07 | 1636.74 | 1647.41 | 1658.09 | 1668.35 | 1679.3 | 1690.25 | 1701.2 | 1711.72 | 1722.96 | 1734.19 | 1745.43 | 1756.23 | 1767.76 | 1779.28 | 1790.81 | 1801.89 | 1813.72 | 1825.54 | 1837.37 | 1848.74 | 1860.87 | 1873.01 | 1885.14 | 1896.81 | 1909.26 | 1921.71 | 1934.16 | 1946.12 | 1958.9 | 1971.67 | 1984.45 | 1996.72 | 2009.83 | 2022.93 | 2036.04 | 2048.64 | 2062.08 | 2075.53 | 2088.98 | 2101.9 | 2115.7 | 2129.49 | 2143.29 | 2156.55 | 2170.71 | 2184.86 | 2199.02 | 2212.62 | 2227.14 | 2241.67 | 2256.19 | 2270.15 | 2285.05 | 2299.95 | 2314.85 | 2329.17 | 2344.46 | 2359.75 | 2375.04 | 2389.73 | 2405.42 | 2421.1 | 2436.79 | 2451.86 | 2467.96 | 2484.05 | 2500.15 | 2515.61 | 2532.13 | 2548.64 | 2565.15 | 2581.02 | 2597.96 | 2614.9 | 2631.84 | 2648.12 | 2665.51 | 2682.89 | 2700.27 | 2716.98 | 2734.81 | 2752.64 | 2770.48 | 2787.62 | 2805.92 | 2824.21 | 2842.51 | 2860.1 | 2878.87 | 2897.64 | 2916.42 | 2934.46 | 2953.72 | 2972.98 | 2992.24 | 3010.75 | 3030.52 | 3050.28 | 3070.04 | 3089.03 | 3109.31 | 3129.59 | 3149.86 | 3169.35 | 3190.15 | 3210.96 | 3231.76 | 3251.75 | 3273.1 | 3294.44 | 3315.79 | 3336.3 | 3358.2 | 3380.1 | 3402 | 3423.04 | 3445.51 | 3467.98 | 3490.45 | 3512.04 | 3535.09 | 3558.15 | 3581.2 | 3603.35 | 3627.01 | 3650.66 | 3674.31 | 3697.04 | 3721.31 | 3745.57 | 3769.84 | 3793.16 | 3818.06 | 3842.96 | 3867.86 | 3891.79 | 3917.33 | 3942.88 | 3968.42 | 3992.97 | 4019.18 | 4045.39 | 4071.6 | 4096.79 | 4123.68 | 4150.57 | 4177.46 | 4203.31 | 4230.9 | 4258.49 | 4286.08 | 4312.59 | 4340.9 | 4369.21 | 4397.52 | 4424.72 | 4453.76 | 4482.81 | 4511.85 | 4539.76 | 4569.56 | 4599.36 | 4629.16 | 4657.8 | 4688.37 | 4718.94 | 4749.52 | 4778.9 | 4810.27 | 4841.64 | 4873 | 4903.15 | 4935.33 | 4967.52 | 4999.7 | 5030.63 | 5063.65 | 5096.67 | 5129.69 | 5161.43 | 5195.31 | 5229.19 | 5263.07 | 5295.62 | 5330.39 | 5365.15 | 5399.91 | 5433.31 | 5468.98 | 5504.64 | 5540.3 | 5574.58 | 5611.17 | 5647.76 | 5684.35 | 5719.52 | 5757.06 | 5794.6 | 5832.14 | 5868.22 | 5906.74 | 5945.26 | 5983.78 | 6020.8 | 6060.32 | 6099.84 | 6139.36 | 6177.34 | 6217.89 | 6258.43 | 6298.98 | 6337.95 | 6379.55 | 6421.15 | 6462.76 | 6502.74 | 6545.42 | 6588.1 | 6630.79 | 6671.81 | 6715.6 | 6759.39 | 6803.19 | 6845.27 | 6890.21 | 6935.14 | 6980.07 | 7023.25 | 7069.35 | 7115.45 | 7161.55 | 7205.86 | 7253.15 | 7300.45 | 7347.75 | 7393.21 | 7441.74 | 7490.27 | 7538.79 | 7585.43 | 7635.22 | 7685.01 | 7734.8
| EM 1110-2-1304 CWCCIS | https://www.usace.army.mil/Cost-Engineering/cwccis/ |  |  |  | 12 | 08 | 12 | ROADS, RAILROADS & BRIDGES | 10% | 271.87 | 274.31 | 285.26 | 289.3 | 295.1 | 301.18 | 312.75 | 315.63 | 320.53 | 322.08 | 333.33 | 333.67 | 335.14 | 338.18 | 345.35 | 344.78 | 345.52 | 348.83 | 352.68 | 351.02 | 353.13 | 354.92 | 357.91 | 355.77 | 355.59 | 359.01 | 359.28 | 359.55 | 361.04 | 363.87 | 368.87 | 371.5 | 374.44 | 379.38 | 383.85 | 384.02 | 388.26 | 393.87 | 398.1 | 398.06 | 397.7 | 402.35 | 406.27 | 405.48 | 407.61 | 409.79 | 415.17 | 412.51 | 416.6 | 423.9 | 424.33 | 424.64 | 432.27 | 444.84 | 440.26 | 444.4 | 453.13 | 453.19 | 455.09 | 455.63 | 459.16 | 463.37 | 466.65 | 466.2 | 466.08 | 471.21 | 477.34 | 478.46 | 481.69 | 487.33 | 488.95 | 487 | 488.93 | 492.32 | 491.1 | 488.69 | 492.81 | 499.56 | 509.16 | 503.04 | 506.82 | 508.77 | 508.18 | 508.11 | 508.75 | 510.79 | 516.87 | 516.78 | 519.56 | 530.58 | 535.25 | 534.41 | 535.7 | 538.79 | 543.21 | 549.21 | 559.04 | 583.39 | 595.63 | 608.05 | 612.78 | 617.37 | 619.16 | 625.19 | 639.51 | 643.94 | 647.71 | 655.73 | 660.22 | 678.49 | 685.41 | 681.9 | 685.16 | 701.29 | 728.77 | 727.11 | 708.97 | 699.5 | 706.43 | 707.53 | 715.45 | 727.79 | 733.68 | 732.86 | 741.6 | 754.5 | 762.57 | 763.99 | 768.33 | 774.53 | 776.41 | 776.53 | 787.84 | 795.56 | 794.68 | 797.33 | 805.1 | 809.41 | 817.5 | 818.24 | 822.62 | 817.79 | 825.5 | 820.72 | 823.25 | 827.92 | 841.23 | 838.77 | 845.05 | 856.5 | 866.08 | 869.55 | 866.37 | 879.92 | 894.71 | 898.57 | 904.17 | 909.16 | 916.44 | 914.4 | 918.54 | 920.64 | 933.71 | 956.45 | 980.2 | 1032.05 | 1047.49 | 1059.94 | 1126.43 | 1143.58 | 1134.19 | 1127.52 | 1133.08 | 1146.67 | 1159.84 | 1155.72 | 1166.71 | 1170.71 | 1180.82 | 1185.09 | 1192.85 | 1210.71 | 1218.28 | 1226.2 | 1234.12 | 1242.04 | 1249.96 | 1262.07 | 1266.99 | 1275.31 | 1283.63 | 1291.94 | 1299.93 | 1308.47 | 1317 | 1325.53 | 1333.73 | 1342.49 | 1351.24 | 1360 | 1368.41 | 1377.39 | 1386.37 | 1395.36 | 1403.99 | 1413.2 | 1422.42 | 1431.64 | 1440.49 | 1449.95 | 1459.4 | 1468.86 | 1477.94 | 1487.65 | 1497.35 | 1507.05 | 1516.37 | 1526.32 | 1536.28 | 1546.23 | 1555.8 | 1566.01 | 1576.22 | 1586.43 | 1596.25 | 1606.72 | 1617.2 | 1627.68 | 1637.75 | 1648.5 | 1659.25 | 1670 | 1680.33 | 1691.36 | 1702.39 | 1713.42 | 1724.02 | 1735.34 | 1746.65 | 1757.97 | 1768.84 | 1780.45 | 1792.07 | 1803.68 | 1814.83 | 1826.75 | 1838.66 | 1850.57 | 1862.02 | 1874.24 | 1886.46 | 1898.69 | 1910.43 | 1922.97 | 1935.51 | 1948.05 | 1960.1 | 1972.97 | 1985.84 | 1998.7 | 2011.07 | 2024.27 | 2037.47 | 2050.67 | 2063.35 | 2076.9 | 2090.44 | 2103.99 | 2117 | 2130.9 | 2144.79 | 2158.69 | 2172.04 | 2186.3 | 2200.56 | 2214.81 | 2228.52 | 2243.14 | 2257.77 | 2272.4 | 2286.46 | 2301.47 | 2316.47 | 2331.48 | 2345.91 | 2361.3 | 2376.7 | 2392.1 | 2406.9 | 2422.7 | 2438.5 | 2454.3 | 2469.48 | 2485.69 | 2501.9 | 2518.11 | 2533.68 | 2550.32 | 2566.95 | 2583.58 | 2599.56 | 2616.62 | 2633.69 | 2650.75 | 2667.15 | 2684.66 | 2702.16 | 2719.67 | 2736.5 | 2754.46 | 2772.42 | 2790.38 | 2807.64 | 2826.07 | 2844.5 | 2862.93 | 2880.64 | 2899.55 | 2918.46 | 2937.37 | 2955.54 | 2974.94 | 2994.34 | 3013.74 | 3032.38 | 3052.29 | 3072.19 | 3092.1 | 3111.23 | 3131.65 | 3152.07 | 3172.49 | 3192.12 | 3213.07 | 3234.02 | 3254.98 | 3275.11 | 3296.61 | 3318.11 | 3339.61 | 3360.27 | 3382.32 | 3404.38 | 3426.44 | 3447.63 | 3470.26 | 3492.89 | 3515.52 | 3537.27 | 3560.49 | 3583.71 | 3606.93 | 3629.24 | 3653.06 | 3676.88 | 3700.71 | 3723.6 | 3748.04 | 3772.48 | 3796.93 | 3820.41 | 3845.49 | 3870.57 | 3895.65 | 3919.74 | 3945.47 | 3971.2 | 3996.93 | 4021.66 | 4048.06 | 4074.45 | 4100.85 | 4126.22 | 4153.31 | 4180.39 | 4207.47 | 4233.5 | 4261.29 | 4289.08 | 4316.87 | 4343.57 | 4372.08 | 4400.6 | 4429.11 | 4456.51 | 4485.76 | 4515.01 | 4544.26 | 4572.38 | 4602.39 | 4632.4 | 4662.41 | 4691.26 | 4722.05 | 4752.84 | 4783.64 | 4813.23 | 4844.82 | 4876.42 | 4908.01 | 4938.37 | 4970.79 | 5003.21 | 5035.62 | 5066.77 | 5100.03 | 5133.29 | 5166.55 | 5198.51 | 5232.63 | 5266.75 | 5300.88 | 5333.67 | 5368.68 | 5403.69 | 5438.7 | 5472.34 | 5508.26 | 5544.19 | 5580.11 | 5614.63 | 5651.48 | 5688.33 | 5725.19 | 5760.61 | 5798.42 | 5836.23 | 5874.04 | 5910.38 | 5949.18 | 5987.97 | 6026.77 | 6064.05 | 6103.86 | 6143.66 | 6183.46 | 6221.72 | 6262.56 | 6303.4 | 6344.23 | 6383.48 | 6425.38 | 6467.28 | 6509.18 | 6549.45 | 6592.44 | 6635.43 | 6678.42 | 6719.74 | 6763.85 | 6807.95 | 6852.06 | 6894.45 | 6939.71 | 6984.96 | 7030.22 | 7073.71 | 7120.14 | 7166.57 | 7213 | 7257.62 | 7305.26 | 7352.9 | 7400.54 | 7446.32 | 7495.2 | 7544.08 | 7592.95 | 7639.93 | 7690.07 | 7740.22 | 7790.37 | 7838.56 | 7890.02 | 7941.47 | 7992.92 | 8042.37 | 8095.16 | 8147.95 | 8200.74 | 8251.47 | 8305.63 | 8359.79 | 8413.96
| Table 1 FY2 | https://www.publications.usace.army.mil/USACE-Publications/Engineer-Circulars/ |  |  |  | 13 | 09 | 13 | CHANNELS & CANALS | 3% | 265.64 | 270.82 | 281.65 | 287.98 | 293.61 | 301.38 | 313.41 | 317.89 | 325.51 | 328.36 | 339.24 | 340.71 | 342.1 | 343.64 | 348.71 | 349.82 | 350.85 | 352.53 | 357.12 | 357.17 | 356.12 | 357.8 | 359.39 | 359.65 | 360.57 | 362.65 | 364.2 | 364.3 | 367.72 | 369.39 | 374.27 | 375.45 | 378.91 | 381.47 | 386.02 | 387.57 | 394.41 | 397.56 | 404.46 | 406 | 408.91 | 412.18 | 419.85 | 421.37 | 423.64 | 426.24 | 429.12 | 429.87 | 432.46 | 436.45 | 440.83 | 441.51 | 444.91 | 448.13 | 451.04 | 451.92 | 455.98 | 459.44 | 460.96 | 462.02 | 464.74 | 469.56 | 473.89 | 474.38 | 478.3 | 482.06 | 485.4 | 485.86 | 488.99 | 492.02 | 493.05 | 494.6 | 500.35 | 503.18 | 504.72 | 505.95 | 509.67 | 515.79 | 519.24 | 519.75 | 522.7 | 525.67 | 528.21 | 530.31 | 533.17 | 533.64 | 537.32 | 539.98 | 543.14 | 552.98 | 556.82 | 557.3 | 562.22 | 565.12 | 566.01 | 568.24 | 574.07 | 580.55 | 589.71 | 593.18 | 602.74 | 606.87 | 617.59 | 621.31 | 634.12 | 639.7 | 643.34 | 650.07 | 658.19 | 666.22 | 672.31 | 674.92 | 679 | 687.99 | 696.83 | 700.63 | 708.75 | 714.03 | 722.16 | 718.6 | 726.21 | 727.34 | 738.67 | 740.12 | 745.5 | 752.01 | 763.2 | 769.05 | 779.45 | 787.23 | 792.32 | 796.23 | 804.86 | 806.09 | 816.37 | 817.99 | 825.51 | 827.5 | 833.72 | 834.66 | 843.99 | 845.53 | 854.33 | 855.68 | 863.89 | 865.14 | 875.09 | 874.05 | 879.83 | 882.78 | 890.06 | 891.49 | 877.6 | 882.34 | 891.7 | 915.14 | 925.43 | 929.79 | 943.11 | 943.71 | 951.95 | 957.07 | 958.35 | 960.53 | 971.15 | 985.61 | 1007.96 | 1028.67 | 1044.05 | 1069.86 | 1082.35 | 1106.27 | 1139.18 | 1147.24 | 1170.38 | 1176.06 | 1196.36 | 1200.66 | 1217.99 | 1224.07 | 1235.68 | 1242.6 | 1248.83 | 1256.95 | 1265.06 | 1273.18 | 1281.3 | 1293.71 | 1298.76 | 1307.29 | 1315.81 | 1324.34 | 1332.53 | 1341.28 | 1350.02 | 1358.77 | 1367.18 | 1376.15 | 1385.13 | 1394.1 | 1402.72 | 1411.93 | 1421.14 | 1430.35 | 1439.19 | 1448.64 | 1458.09 | 1467.54 | 1476.61 | 1486.31 | 1496 | 1505.69 | 1515.01 | 1524.95 | 1534.89 | 1544.84 | 1554.4 | 1564.6 | 1574.8 | 1585 | 1594.81 | 1605.28 | 1615.75 | 1626.22 | 1636.28 | 1647.02 | 1657.76 | 1668.5 | 1678.82 | 1689.84 | 1700.86 | 1711.88 | 1722.47 | 1733.77 | 1745.08 | 1756.39 | 1767.25 | 1778.85 | 1790.45 | 1802.05 | 1813.2 | 1825.1 | 1837 | 1848.91 | 1860.34 | 1872.55 | 1884.77 | 1896.98 | 1908.71 | 1921.24 | 1933.77 | 1946.3 | 1958.34 | 1971.19 | 1984.05 | 1996.9 | 2009.26 | 2022.44 | 2035.63 | 2048.82 | 2061.5 | 2075.03 | 2088.56 | 2102.09 | 2115.1 | 2128.98 | 2142.86 | 2156.75 | 2170.09 | 2184.33 | 2198.58 | 2212.82 | 2226.51 | 2241.12 | 2255.74 | 2270.35 | 2284.4 | 2299.39 | 2314.39 | 2329.38 | 2343.79 | 2359.18 | 2374.56 | 2389.95 | 2404.73 | 2420.52 | 2436.3 | 2452.09 | 2467.26 | 2483.45 | 2499.65 | 2515.84 | 2531.4 | 2548.02 | 2564.64 | 2581.25 | 2597.22 | 2614.27 | 2631.32 | 2648.36 | 2664.75 | 2682.24 | 2699.73 | 2717.22 | 2734.03 | 2751.98 | 2769.92 | 2787.87 | 2805.12 | 2823.53 | 2841.94 | 2860.35 | 2878.05 | 2896.94 | 2915.83 | 2934.72 | 2952.88 | 2972.26 | 2991.64 | 3011.03 | 3029.65 | 3049.54 | 3069.43 | 3089.31 | 3108.42 | 3128.83 | 3149.23 | 3169.64 | 3189.24 | 3210.18 | 3231.11 | 3252.05 | 3272.16 | 3293.64 | 3315.12 | 3336.6 | 3357.24 | 3379.28 | 3401.31 | 3423.35 | 3444.53 | 3467.14 | 3489.75 | 3512.36 | 3534.09 | 3557.28 | 3580.48 | 3603.68 | 3625.97 | 3649.77 | 3673.57 | 3697.38 | 3720.25 | 3744.67 | 3769.09 | 3793.51 | 3816.97 | 3842.03 | 3867.08 | 3892.14 | 3916.22 | 3941.92 | 3967.63 | 3993.33 | 4018.04 | 4044.41 | 4070.79 | 4097.16 | 4122.51 | 4149.57 | 4176.63 | 4203.69 | 4229.69 | 4257.45 | 4285.22 | 4312.98 | 4339.66 | 4368.15 | 4396.63 | 4425.12 | 4452.49 | 4481.72 | 4510.95 | 4540.17 | 4568.26 | 4598.25 | 4628.23 | 4658.22 | 4687.03 | 4717.8 | 4748.57 | 4779.33 | 4808.9 | 4840.46 | 4872.03 | 4903.59 | 4933.93 | 4966.31 | 4998.7 | 5031.09 | 5062.21 | 5095.44 | 5128.67 | 5161.9 | 5193.83 | 5227.92 | 5262.01 | 5296.1 | 5328.87 | 5363.85 | 5398.82 | 5433.8 | 5467.42 | 5503.31 | 5539.19 | 5575.08 | 5609.57 | 5646.39 | 5683.21 | 5720.03 | 5755.42 | 5793.2 | 5830.98 | 5868.76 | 5905.06 | 5943.82 | 5982.58 | 6021.34 | 6058.59 | 6098.36 | 6138.13 | 6177.9 | 6216.12 | 6256.92 | 6297.72 | 6338.52 | 6377.73 | 6419.6 | 6461.46 | 6503.32 | 6543.56 | 6586.51 | 6629.46 | 6672.41 | 6713.69 | 6757.76 | 6801.83 | 6845.89 | 6888.24 | 6933.46 | 6978.67 | 7023.89 | 7067.34 | 7113.73 | 7160.12 | 7206.51 | 7251.09 | 7298.69 | 7346.28 | 7393.88 | 7439.62 | 7488.45 | 7537.28 | 7586.12 | 7633.05 | 7683.15 | 7733.25 | 7783.36 | 7831.51 | 7882.91 | 7934.32 | 7985.72 | 8035.13 | 8087.87 | 8140.61 | 8193.35 | 8244.04 | 8298.15 | 8352.27 | 8406.38 | 8458.38 | 8513.9 | 8569.43 | 8624.95
[6 empty] | 14 | 10 | 14 | BREAKWATER & SEAWALLS | 5% | 268.87 | 275.43 | 284.94 | 291.47 | 297.87 | 307 | 317.48 | 322.03 | 329.54 | 332.77 | 341.4 | 342.84 | 344.42 | 346.28 | 350.15 | 351.06 | 351.96 | 353.84 | 357.66 | 357.81 | 360.2 | 360.88 | 362.49 | 363.08 | 364.15 | 366.12 | 367.26 | 367.48 | 371.39 | 372.87 | 376.57 | 377.7 | 381.39 | 383.48 | 387.91 | 389.42 | 399.19 | 402.23 | 408.93 | 410.56 | 416.23 | 418.83 | 426.15 | 427.58 | 431.75 | 434.02 | 436.95 | 437.42 | 440.32 | 444.65 | 449.52 | 450.14 | 453.92 | 457.1 | 459.86 | 459.59 | 464.97 | 467.37 | 469.13 | 470.36 | 473.69 | 477.42 | 480.99 | 481.23 | 486.3 | 489.3 | 492.45 | 493.39 | 497.41 | 499.61 | 500.41 | 501.47 | 508.28 | 510.27 | 511.29 | 512.16 | 515.93 | 520.56 | 523.14 | 523.68 | 526.04 | 526.7 | 528.42 | 530.28 | 533 | 532.9 | 535.39 | 537.42 | 539.67 | 551.63 | 554.03 | 554.89 | 560.3 | 563.87 | 564.09 | 566.98 | 572.43 | 579.15 | 587.47 | 594.67 | 603.21 | 607.88 | 618.82 | 622.23 | 633.85 | 640.07 | 642.8 | 647.89 | 654.97 | 660.82 | 666.4 | 668.25 | 672.17 | 679.9 | 689.75 | 696.2 | 704.84 | 708.1 | 714.7 | 707.23 | 714.39 | 715.35 | 722.61 | 723.34 | 730.49 | 737.82 | 747.94 | 753.93 | 757.76 | 764.47 | 768.52 | 772.18 | 782 | 784.6 | 792.86 | 792.77 | 800.38 | 802.68 | 807.76 | 806.83 | 818.17 | 818.72 | 824.48 | 824.1 | 831.82 | 831.91 | 838.22 | 837.49 | 842.48 | 844.31 | 849.56 | 850.53 | 836.69 | 841.08 | 848.92 | 874.05 | 883.72 | 886.87 | 896.39 | 897.36 | 905 | 908.51 | 908.8 | 910.87 | 923.38 | 933.83 | 954.45 | 979.48 | 992.88 | 1022.1 | 1033.68 | 1059.88 | 1091.38 | 1099.18 | 1120.44 | 1123.69 | 1140.73 | 1144.23 | 1158.05 | 1161.24 | 1170.43 | 1178.55 | 1187.77 | 1195.49 | 1203.21 | 1210.93 | 1218.65 | 1230.46 | 1235.26 | 1243.37 | 1251.48 | 1259.59 | 1267.38 | 1275.7 | 1284.02 | 1292.34 | 1300.33 | 1308.87 | 1317.4 | 1325.94 | 1334.14 | 1342.9 | 1351.65 | 1360.41 | 1368.83 | 1377.81 | 1386.8 | 1395.78 | 1404.42 | 1413.64 | 1422.85 | 1432.07 | 1440.93 | 1450.39 | 1459.85 | 1469.31 | 1478.4 | 1488.1 | 1497.8 | 1507.51 | 1516.83 | 1526.79 | 1536.75 | 1546.7 | 1556.27 | 1566.49 | 1576.7 | 1586.92 | 1596.73 | 1607.22 | 1617.7 | 1628.18 | 1638.25 | 1649 | 1659.76 | 1670.51 | 1680.84 | 1691.88 | 1702.91 | 1713.94 | 1724.55 | 1735.87 | 1747.19 | 1758.51 | 1769.38 | 1781 | 1792.61 | 1804.23 | 1815.39 | 1827.3 | 1839.22 | 1851.14 | 1862.59 | 1874.81 | 1887.04 | 1899.27 | 1911.02 | 1923.56 | 1936.1 | 1948.65 | 1960.7 | 1973.57 | 1986.44 | 1999.31 | 2011.68 | 2024.88 | 2038.09 | 2051.29 | 2063.98 | 2077.53 | 2091.08 | 2104.63 | 2117.65 | 2131.55 | 2145.45 | 2159.35 | 2172.71 | 2186.97 | 2201.23 | 2215.49 | 2229.2 | 2243.83 | 2258.46 | 2273.09 | 2287.16 | 2302.17 | 2317.18 | 2332.19 | 2346.62 | 2362.03 | 2377.43 | 2392.83 | 2407.63 | 2423.44 | 2439.24 | 2455.05 | 2470.23 | 2486.45 | 2502.66 | 2518.88 | 2534.46 | 2551.09 | 2567.73 | 2584.37 | 2600.35 | 2617.42 | 2634.49 | 2651.56 | 2667.96 | 2685.48 | 2702.99 | 2720.5 | 2737.33 | 2755.3 | 2773.27 | 2791.23 | 2808.5 | 2826.94 | 2845.37 | 2863.81 | 2881.52 | 2900.44 | 2919.35 | 2938.27 | 2956.44 | 2975.85 | 2995.25 | 3014.66 | 3033.31 | 3053.22 | 3073.13 | 3093.04 | 3112.18 | 3132.6 | 3153.03 | 3173.46 | 3193.09 | 3214.05 | 3235.01 | 3255.97 | 3276.11 | 3297.62 | 3319.12 | 3340.63 | 3361.29 | 3383.35 | 3405.42 | 3427.48 | 3448.68 | 3471.32 | 3493.96 | 3516.6 | 3538.35 | 3561.58 | 3584.8 | 3608.03 | 3630.35 | 3654.18 | 3678.01 | 3701.84 | 3724.74 | 3749.19 | 3773.64 | 3798.08 | 3821.58 | 3846.66 | 3871.75 | 3896.83 | 3920.94 | 3946.68 | 3972.42 | 3998.15 | 4022.89 | 4049.29 | 4075.7 | 4102.1 | 4127.48 | 4154.57 | 4181.67 | 4208.76 | 4234.8 | 4262.59 | 4290.39 | 4318.19 | 4344.9 | 4373.42 | 4401.94 | 4430.46 | 4457.87 | 4487.13 | 4516.39 | 4545.65 | 4573.77 | 4603.79 | 4633.82 | 4663.84 | 4692.69 | 4723.49 | 4754.3 | 4785.1 | 4814.7 | 4846.3 | 4877.91 | 4909.51 | 4939.88 | 4972.31 | 5004.73 | 5037.16 | 5068.32 | 5101.59 | 5134.86 | 5168.12 | 5200.1 | 5234.23 | 5268.36 | 5302.5 | 5335.3 | 5370.32 | 5405.34 | 5440.36 | 5474.02 | 5509.95 | 5545.88 | 5581.81 | 5616.34 | 5653.21 | 5690.07 | 5726.94 | 5762.36 | 5800.19 | 5838.01 | 5875.84 | 5912.19 | 5950.99 | 5989.8 | 6028.61 | 6065.9 | 6105.72 | 6145.54 | 6185.35 | 6223.62 | 6264.47 | 6305.32 | 6346.17 | 6385.43 | 6427.34 | 6469.26 | 6511.17 | 6551.45 | 6594.46 | 6637.46 | 6680.46 | 6721.79 | 6765.91 | 6810.03 | 6854.15 | 6896.56 | 6941.83 | 6987.09 | 7032.36 | 7075.87 | 7122.31 | 7168.76 | 7215.2 | 7259.84 | 7307.49 | 7355.15 | 7402.8 | 7448.59 | 7497.49 | 7546.38 | 7595.27 | 7642.26 | 7692.42 | 7742.59 | 7792.75 | 7840.96 | 7892.43 | 7943.89 | 7995.36 | 8044.82 | 8097.63 | 8150.43 | 8203.24
[6 empty] | 15 | 11 | 15 | LEVEES & FLOODWALLS | 5% | 270.52 | 275.78 | 285.6 | 291.08 | 296.16 | 303.75 | 315.68 | 320.28 | 326.15 | 328.53 | 339.43 | 340.6 | 341.33 | 343.87 | 349.13 | 350.51 | 351.28 | 353.23 | 357.74 | 357.71 | 357.94 | 359.12 | 360.8 | 360.91 | 360.26 | 362.26 | 363.58 | 363.91 | 366.29 | 368.16 | 372.27 | 374.39 | 378.8 | 382.73 | 386.7 | 388.36 | 394.83 | 398.49 | 402.75 | 404 | 405.46 | 408.36 | 414.01 | 415.03 | 417.23 | 419.02 | 421.7 | 422.01 | 424.47 | 428.96 | 433.01 | 433.35 | 436.37 | 441.4 | 444.14 | 445.43 | 449.93 | 453.36 | 455.18 | 456.83 | 460.62 | 466.66 | 471.12 | 471.24 | 473.49 | 476.42 | 480.07 | 480.75 | 482.63 | 485.59 | 487.37 | 489.24 | 493.85 | 496.31 | 497.18 | 496.64 | 497.88 | 502.33 | 506.75 | 506.45 | 509.22 | 512.18 | 514.03 | 515.05 | 516.54 | 516.31 | 519.93 | 521.86 | 523.8 | 536.25 | 541.49 | 541.59 | 545.36 | 549.52 | 550.19 | 554.42 | 563.84 | 582.42 | 594.09 | 607.65 | 615.61 | 618 | 623.58 | 630.33 | 644.64 | 651.23 | 658.68 | 666.93 | 669.92 | 687.06 | 693.47 | 691.82 | 697.52 | 714.17 | 739.43 | 737.4 | 721.64 | 712.69 | 718.95 | 719.93 | 726.98 | 735.23 | 744.32 | 745.35 | 753.7 | 767.06 | 776.75 | 779.51 | 785.64 | 789.19 | 790.48 | 790.25 | 798.03 | 800.91 | 806.93 | 807.9 | 814.93 | 818.17 | 824.49 | 824.81 | 829.76 | 825.49 | 830.81 | 827.98 | 829 | 830.77 | 843.12 | 841.09 | 847.11 | 853.8 | 862.71 | 863.98 | 854.63 | 864.74 | 877.35 | 898.23 | 906.43 | 909.95 | 914.36 | 912.39 | 916.23 | 919.83 | 920.57 | 923.99 | 941.65 | 976.27 | 1011.76 | 1044.11 | 1071.77 | 1098.56 | 1110.59 | 1116.15 | 1132.2 | 1144.19 | 1163.12 | 1163.16 | 1174.39 | 1176.07 | 1180.16 | 1179.73 | 1182.83 | 1194.74 | 1206.96 | 1214.81 | 1222.65 | 1230.5 | 1238.34 | 1250.34 | 1255.22 | 1263.46 | 1271.7 | 1279.94 | 1287.86 | 1296.31 | 1304.76 | 1313.22 | 1321.34 | 1330.01 | 1338.69 | 1347.36 | 1355.69 | 1364.59 | 1373.49 | 1382.39 | 1390.94 | 1400.07 | 1409.2 | 1418.33 | 1427.11 | 1436.47 | 1445.84 | 1455.21 | 1464.21 | 1473.82 | 1483.43 | 1493.04 | 1502.28 | 1512.14 | 1522 | 1531.86 | 1541.34 | 1551.46 | 1561.57 | 1571.69 | 1581.42 | 1591.8 | 1602.18 | 1612.56 | 1622.53 | 1633.18 | 1643.83 | 1654.48 | 1664.72 | 1675.64 | 1686.57 | 1697.5 | 1708 | 1719.21 | 1730.42 | 1741.63 | 1752.41 | 1763.91 | 1775.41 | 1786.92 | 1797.97 | 1809.77 | 1821.57 | 1833.38 | 1844.72 | 1856.83 | 1868.94 | 1881.04 | 1892.68 | 1905.1 | 1917.53 | 1929.95 | 1941.89 | 1954.64 | 1967.38 | 1980.13 | 1992.38 | 2005.46 | 2018.54 | 2031.61 | 2044.18 | 2057.6 | 2071.02 | 2084.44 | 2097.33 | 2111.1 | 2124.86 | 2138.63 | 2151.86 | 2165.99 | 2180.11 | 2194.24 | 2207.81 | 2222.3 | 2236.79 | 2251.29 | 2265.21 | 2280.08 | 2294.95 | 2309.82 | 2324.11 | 2339.36 | 2354.62 | 2369.87 | 2384.53 | 2400.19 | 2415.84 | 2431.49 | 2446.53 | 2462.59 | 2478.65 | 2494.71 | 2510.14 | 2526.62 | 2543.1 | 2559.57 | 2575.41 | 2592.31 | 2609.22 | 2626.12 | 2642.37 | 2659.71 | 2677.06 | 2694.4 | 2711.07 | 2728.86 | 2746.66 | 2764.45 | 2781.56 | 2799.81 | 2818.07 | 2836.33 | 2853.88 | 2872.61 | 2891.34 | 2910.07 | 2928.08 | 2947.3 | 2966.52 | 2985.74 | 3004.21 | 3023.93 | 3043.65 | 3063.37 | 3082.32 | 3102.55 | 3122.78 | 3143.01 | 3162.46 | 3183.22 | 3203.97 | 3224.73 | 3244.68 | 3265.98 | 3287.28 | 3308.57 | 3329.04 | 3350.89 | 3372.75 | 3394.6 | 3415.6 | 3438.02 | 3460.44 | 3482.86 | 3504.4 | 3527.41 | 3550.41 | 3573.41 | 3595.52 | 3619.12 | 3642.72 | 3666.32 | 3689 | 3713.22 | 3737.43 | 3761.64 | 3784.92 | 3809.76 | 3834.6 | 3859.45 | 3883.32 | 3908.81 | 3934.3 | 3959.79 | 3984.29 | 4010.44 | 4036.59 | 4062.75 | 4087.88 | 4114.71 | 4141.55 | 4168.38 | 4194.17 | 4221.7 | 4249.23 | 4276.76 | 4303.21 | 4331.46 | 4359.71 | 4387.95 | 4415.1 | 4444.08 | 4473.06 | 4502.04 | 4529.89 | 4559.62 | 4589.36 | 4619.09 | 4647.67 | 4678.17 | 4708.68 | 4739.19 | 4768.51 | 4799.81 | 4831.11 | 4862.41 | 4892.49 | 4924.6 | 4956.72 | 4988.83 | 5019.69 | 5052.64 | 5085.59 | 5118.54 | 5150.2 | 5184.01 | 5217.82 | 5251.62 | 5284.11 | 5318.79 | 5353.48 | 5388.16 | 5421.5 | 5457.08 | 5492.67 | 5528.26 | 5562.46 | 5598.97 | 5635.48 | 5671.99 | 5707.08 | 5744.54 | 5782 | 5819.46 | 5855.46 | 5893.9 | 5932.33 | 5970.77 | 6007.71 | 6047.14 | 6086.57 | 6126.01 | 6163.91 | 6204.37 | 6244.83 | 6285.29 | 6324.17 | 6365.68 | 6407.19 | 6448.7 | 6488.6 | 6531.19 | 6573.78 | 6616.37 | 6657.3 | 6701 | 6744.7 | 6788.39 | 6830.39 | 6875.22 | 6920.06 | 6964.89 | 7007.98 | 7053.98 | 7099.98 | 7145.98 | 7190.19 | 7237.38 | 7284.58 | 7331.78 | 7377.13 | 7425.55 | 7473.98 | 7522.4 | 7568.94 | 7618.62 | 7668.3 | 7717.98 | 7765.73 | 7816.7 | 7867.68 | 7918.65 | 7967.64 | 8019.94 | 8072.24 | 8124.54 | 8174.8 | 8228.46 | 8282.12 | 8335.77
[6 empty] | 16 | 12 | 16 | NAVIGATION PORTS & HARBORS | 10% | 296.3 | 313.31 | 320.93 | 319.65 | 330.51 | 349.87 | 353.82 | 359.31 | 366.59 | 368.34 | 376.27 | 376.98 | 380.06 | 363.25 | 364.66 | 368.73 | 373.05 | 379.74 | 381.11 | 385.87 | 385.63 | 374.08 | 376.9 | 371.31 | 372.96 | 368.74 | 374.47 | 365.23 | 360.11 | 354.3 | 355.95 | 366.15 | 366.8 | 368.08 | 366.12 | 371.23 | 374.55 | 379.56 | 381.82 | 389.13 | 390.24 | 388.71 | 385.42 | 423.17 | 409.44 | 394.25 | 398.68 | 406.79 | 402.75 | 404.05 | 409.82 | 414.28 | 415.43 | 419.76 | 419.6 | 421.51 | 416.32 | 421.58 | 422.01 | 431 | 429.5 | 437.84 | 436.89 | 434.34 | 439.35 | 449.73 | 446.82 | 469.89 | 465.98 | 463.12 | 458.42 | 465.36 | 459.69 | 457.07 | 454.85 | 458.59 | 455.42 | 459.42 | 466.91 | 480.03 | 485.6 | 495.16 | 501.01 | 519.15 | 512.19 | 502.64 | 505.06 | 499.47 | 491.92 | 502.81 | 509.07 | 521.2 | 525.66 | 527.04 | 524.41 | 529.19 | 537.22 | 562.46 | 569.88 | 608.44 | 592.73 | 617.25 | 632.02 | 688.11 | 649.53 | 675.74 | 683.98 | 688.3 | 692.6 | 696.34 | 706.31 | 713.66 | 738.66 | 791.33 | 844.82 | 767.18 | 693.15 | 698.1 | 700.97 | 721.64 | 735.18 | 744.79 | 739.8 | 759.65 | 775.94 | 824.07 | 820.39 | 813.49 | 818.43 | 834.42 | 811.06 | 847.13 | 827.74 | 829.45 | 829.74 | 843.32 | 838.49 | 848.4 | 845.17 | 832.72 | 774.14 | 775.5 | 786.88 | 778.77 | 744.87 | 753.77 | 777.12 | 781.16 | 789.3 | 796.59 | 812.6 | 836.56 | 850.24 | 855.82 | 882.24 | 894.76 | 852.58 | 877.57 | 870.61 | 872.39 | 870.01 | 813.87 | 846.89 | 857.47 | 888.81 | 929.81 | 978.19 | 1023.54 | 1030.78 | 1149.59 | 1199.98 | 1225.37 | 1131.28 | 1095.47 | 1067.62 | 1126.29 | 1076.96 | 1121.83 | 1091.32 | 1079.98 | 1078.21 | 1071.37 | 1110 | 1117.22 | 1124.43 | 1131.65 | 1138.86 | 1149.89 | 1154.38 | 1161.96 | 1169.54 | 1177.11 | 1184.4 | 1192.17 | 1199.95 | 1207.72 | 1215.19 | 1223.17 | 1231.14 | 1239.12 | 1246.79 | 1254.97 | 1263.15 | 1271.34 | 1279.2 | 1287.6 | 1296 | 1304.39 | 1312.46 | 1321.08 | 1329.69 | 1338.31 | 1346.59 | 1355.42 | 1364.26 | 1373.1 | 1381.6 | 1390.67 | 1399.73 | 1408.8 | 1417.52 | 1426.82 | 1436.13 | 1445.43 | 1454.37 | 1463.92 | 1473.47 | 1483.01 | 1492.19 | 1501.98 | 1511.78 | 1521.57 | 1530.98 | 1541.03 | 1551.08 | 1561.13 | 1570.79 | 1581.1 | 1591.41 | 1601.72 | 1611.63 | 1622.21 | 1632.79 | 1643.37 | 1653.53 | 1664.39 | 1675.24 | 1686.09 | 1696.52 | 1707.66 | 1718.8 | 1729.93 | 1740.63 | 1752.06 | 1763.49 | 1774.91 | 1785.89 | 1797.61 | 1809.34 | 1821.06 | 1832.32 | 1844.35 | 1856.38 | 1868.41 | 1879.96 | 1892.3 | 1904.64 | 1916.98 | 1928.84 | 1941.5 | 1954.17 | 1966.83 | 1978.99 | 1991.98 | 2004.97 | 2017.96 | 2030.45 | 2043.77 | 2057.1 | 2070.43 | 2083.24 | 2096.91 | 2110.59 | 2124.26 | 2137.4 | 2151.43 | 2165.46 | 2179.49 | 2192.98 | 2207.37 | 2221.76 | 2236.16 | 2249.99 | 2264.76 | 2279.53 | 2294.3 | 2308.49 | 2323.65 | 2338.8 | 2353.95 | 2368.51 | 2384.06 | 2399.61 | 2415.15 | 2430.09 | 2446.05 | 2462 | 2477.95 | 2493.28 | 2509.64 | 2526.01 | 2542.37 | 2558.1 | 2574.89 | 2591.69 | 2608.48 | 2624.61 | 2641.84 | 2659.07 | 2676.3 | 2692.85 | 2710.53 | 2728.2 | 2745.88 | 2762.87 | 2781 | 2799.14 | 2817.27 | 2834.7 | 2853.31 | 2871.92 | 2890.52 | 2908.4 | 2927.49 | 2946.59 | 2965.68 | 2984.02 | 3003.61 | 3023.2 | 3042.78 | 3061.61 | 3081.7 | 3101.8 | 3121.9 | 3141.21 | 3161.83 | 3182.45 | 3203.07 | 3222.88 | 3244.04 | 3265.19 | 3286.35 | 3306.68 | 3328.38 | 3350.09 | 3371.79 | 3392.65 | 3414.92 | 3437.19 | 3459.46 | 3480.86 | 3503.71 | 3526.55 | 3549.4 | 3571.36 | 3594.8 | 3618.24 | 3641.69 | 3664.22 | 3688.27 | 3712.32 | 3736.37 | 3759.48 | 3784.16 | 3808.84 | 3833.52 | 3857.23 | 3882.55 | 3907.87 | 3933.19 | 3957.52 | 3983.5 | 4009.47 | 4035.45 | 4060.41 | 4087.07 | 4113.72 | 4140.37 | 4165.99 | 4193.33 | 4220.68 | 4248.02 | 4274.3 | 4302.36 | 4330.41 | 4358.47 | 4385.43 | 4414.22 | 4443 | 4471.79 | 4499.45 | 4528.99 | 4558.52 | 4588.06 | 4616.44 | 4646.74 | 4677.04 | 4707.35 | 4736.47 | 4767.56 | 4798.65 | 4829.74 | 4859.62 | 4891.51 | 4923.41 | 4955.31 | 4985.97 | 5018.69 | 5051.42 | 5084.15 | 5115.6 | 5149.18 | 5182.76 | 5216.34 | 5248.61 | 5283.06 | 5317.51 | 5351.96 | 5385.07 | 5420.42 | 5455.77 | 5491.11 | 5525.08 | 5561.35 | 5597.62 | 5633.88 | 5668.73 | 5705.94 | 5743.15 | 5780.36 | 5816.12 | 5854.3 | 5892.48 | 5930.65 | 5967.34 | 6006.51 | 6045.68 | 6084.85 | 6122.49 | 6162.68 | 6202.87 | 6243.06 | 6281.68 | 6322.91 | 6364.14 | 6405.37 | 6445 | 6487.3 | 6529.61 | 6571.91 | 6612.57 | 6655.97 | 6699.38 | 6742.78 | 6784.5 | 6829.03 | 6873.56 | 6918.1 | 6960.89 | 7006.58 | 7052.28 | 7097.97 | 7141.88 | 7188.76 | 7235.64 | 7282.51 | 7327.57 | 7375.66 | 7423.76 | 7471.86 | 7518.08 | 7567.43 | 7616.78 | 7666.13
[6 empty] | 17 | 13 | 17 | PUMPING PLANT | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1146.96 | 1137.95 | 1136.3 | 1165.27 | 1180.42 | 1188.09 | 1195.77 | 1203.44 | 1211.11 | 1222.84 | 1227.62 | 1235.68 | 1243.73 | 1251.79 | 1259.54 | 1267.8 | 1276.07 | 1284.34 | 1292.28 | 1300.77 | 1309.25 | 1317.73 | 1325.88 | 1334.59 | 1343.29 | 1351.99 | 1360.36 | 1369.29 | 1378.22 | 1387.14 | 1395.73 | 1404.89 | 1414.05 | 1423.21 | 1432.01 | 1441.41 | 1450.81 | 1460.21 | 1469.25 | 1478.89 | 1488.54 | 1498.18 | 1507.45 | 1517.34 | 1527.24 | 1537.13 | 1546.64 | 1556.79 | 1566.95 | 1577.1 | 1586.85 | 1597.27 | 1607.69 | 1618.1 | 1628.11 | 1638.8 | 1649.49 | 1660.17 | 1670.44 | 1681.41 | 1692.37 | 1703.34 | 1713.87 | 1725.12 | 1736.37 | 1747.62 | 1758.44 | 1769.98 | 1781.52 | 1793.06 | 1804.15 | 1816 | 1827.84 | 1839.68 | 1851.06 | 1863.21 | 1875.36 | 1887.51 | 1899.19 | 1911.66 | 1924.12 | 1936.59 | 1948.57 | 1961.36 | 1974.15 | 1986.94 | 1999.23 | 2012.35 | 2025.48 | 2038.6 | 2051.21 | 2064.68 | 2078.14 | 2091.6 | 2104.54 | 2118.36 | 2132.17 | 2145.99 | 2159.26 | 2173.43 | 2187.61 | 2201.78 | 2215.4 | 2229.94 | 2244.49 | 2259.03 | 2273 | 2287.92 | 2302.84 | 2317.76 | 2332.1 | 2347.41 | 2362.72 | 2378.02 | 2392.74 | 2408.44 | 2424.15 | 2439.85 | 2454.95 | 2471.06 | 2487.18 | 2503.29 | 2518.78 | 2535.31 | 2551.84 | 2568.37 | 2584.26 | 2601.23 | 2618.19 | 2635.15 | 2651.45 | 2668.86 | 2686.26 | 2703.67 | 2720.39 | 2738.25 | 2756.11 | 2773.96 | 2791.12 | 2809.44 | 2827.76 | 2846.08 | 2863.69 | 2882.49 | 2901.29 | 2920.08 | 2938.15 | 2957.43 | 2976.72 | 2996.01 | 3014.54 | 3034.33 | 3054.11 | 3073.9 | 3092.92 | 3113.22 | 3133.52 | 3153.82 | 3173.33 | 3194.16 | 3214.99 | 3235.82 | 3255.84 | 3277.21 | 3298.58 | 3319.95 | 3340.49 | 3362.42 | 3384.35 | 3406.27 | 3427.34 | 3449.84 | 3472.34 | 3494.84 | 3516.46 | 3539.54 | 3562.62 | 3585.7 | 3607.88 | 3631.57 | 3655.25 | 3678.93 | 3701.69 | 3725.99 | 3750.28 | 3774.58 | 3797.93 | 3822.86 | 3847.79 | 3872.72 | 3896.68 | 3922.26 | 3947.83 | 3973.41 | 3997.99 | 4024.23 | 4050.48 | 4076.72 | 4101.94 | 4128.86 | 4155.79 | 4182.71 | 4208.59 | 4236.22 | 4263.84 | 4291.47 | 4318.01 | 4346.36 | 4374.7 | 4403.04 | 4430.28 | 4459.36 | 4488.44 | 4517.52 | 4545.47 | 4575.31 | 4605.14 | 4634.98 | 4663.65 | 4694.26 | 4724.88 | 4755.49 | 4784.91 | 4816.31 | 4847.72 | 4879.13 | 4909.31 | 4941.54 | 4973.76 | 5005.99 | 5036.96 | 5070.02 | 5103.08 | 5136.14 | 5167.92 | 5201.84 | 5235.76 | 5269.68 | 5302.28 | 5337.09 | 5371.89 | 5406.7 | 5440.14 | 5475.85 | 5511.56 | 5547.27 | 5581.59 | 5618.22 | 5654.86 | 5691.5 | 5726.71 | 5764.3 | 5801.89 | 5839.48 | 5875.6 | 5914.17 | 5952.74 | 5991.3 | 6028.37 | 6067.94 | 6107.51 | 6147.08 | 6185.1 | 6225.7 | 6266.3 | 6306.9 | 6345.92 | 6387.57 | 6429.23 | 6470.88 | 6510.91 | 6553.65 | 6596.39 | 6639.12 | 6680.19 | 6724.04 | 6767.89 | 6811.74 | 6853.88 | 6898.87 | 6943.86 | 6988.85 | 7032.08 | 7078.24 | 7124.4 | 7170.56 | 7214.91 | 7262.27 | 7309.63 | 7356.99 | 7402.5 | 7451.09 | 7499.68 | 7548.27 | 7594.97 | 7644.82 | 7694.67 | 7744.53 | 7792.44 | 7843.59 | 7894.74 | 7945.89 | 7995.04 | 8047.52 | 8100 | 8152.48
| CWCCIS EM1110-2-1304 updates occur twice yearly on 31 March and 30 September. |  |  |  |  | 18 | 14 | 18 | RECREATION FACILITIES | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1146.96 | 1137.95 | 1136.3 | 1165.27 | 1180.42 | 1188.09 | 1195.77 | 1203.44 | 1211.11 | 1222.84 | 1227.62 | 1235.68 | 1243.73 | 1251.79 | 1259.54 | 1267.8 | 1276.07 | 1284.34 | 1292.28 | 1300.77 | 1309.25 | 1317.73 | 1325.88 | 1334.59 | 1343.29 | 1351.99 | 1360.36 | 1369.29 | 1378.22 | 1387.14 | 1395.73 | 1404.89 | 1414.05 | 1423.21 | 1432.01 | 1441.41 | 1450.81 | 1460.21 | 1469.25 | 1478.89 | 1488.54 | 1498.18 | 1507.45 | 1517.34 | 1527.24 | 1537.13 | 1546.64 | 1556.79 | 1566.95 | 1577.1 | 1586.85 | 1597.27 | 1607.69 | 1618.1 | 1628.11 | 1638.8 | 1649.49 | 1660.17 | 1670.44 | 1681.41 | 1692.37 | 1703.34 | 1713.87 | 1725.12 | 1736.37 | 1747.62 | 1758.44 | 1769.98 | 1781.52 | 1793.06 | 1804.15 | 1816 | 1827.84 | 1839.68 | 1851.06 | 1863.21 | 1875.36 | 1887.51 | 1899.19 | 1911.66 | 1924.12 | 1936.59 | 1948.57 | 1961.36 | 1974.15 | 1986.94 | 1999.23 | 2012.35 | 2025.48 | 2038.6 | 2051.21 | 2064.68 | 2078.14 | 2091.6 | 2104.54 | 2118.36 | 2132.17 | 2145.99 | 2159.26 | 2173.43 | 2187.61 | 2201.78 | 2215.4 | 2229.94 | 2244.49 | 2259.03 | 2273 | 2287.92 | 2302.84 | 2317.76 | 2332.1 | 2347.41 | 2362.72 | 2378.02 | 2392.74 | 2408.44 | 2424.15 | 2439.85 | 2454.95 | 2471.06 | 2487.18 | 2503.29 | 2518.78 | 2535.31 | 2551.84 | 2568.37 | 2584.26 | 2601.23 | 2618.19 | 2635.15 | 2651.45 | 2668.86 | 2686.26 | 2703.67 | 2720.39 | 2738.25 | 2756.11 | 2773.96 | 2791.12 | 2809.44 | 2827.76 | 2846.08 | 2863.69 | 2882.49 | 2901.29 | 2920.08 | 2938.15 | 2957.43 | 2976.72 | 2996.01 | 3014.54 | 3034.33 | 3054.11 | 3073.9 | 3092.92 | 3113.22 | 3133.52 | 3153.82 | 3173.33 | 3194.16 | 3214.99 | 3235.82 | 3255.84 | 3277.21 | 3298.58 | 3319.95 | 3340.49 | 3362.42 | 3384.35 | 3406.27 | 3427.34 | 3449.84 | 3472.34 | 3494.84 | 3516.46 | 3539.54 | 3562.62 | 3585.7 | 3607.88 | 3631.57 | 3655.25 | 3678.93 | 3701.69 | 3725.99 | 3750.28 | 3774.58 | 3797.93 | 3822.86 | 3847.79 | 3872.72 | 3896.68 | 3922.26 | 3947.83 | 3973.41 | 3997.99 | 4024.23 | 4050.48 | 4076.72 | 4101.94 | 4128.86 | 4155.79 | 4182.71 | 4208.59 | 4236.22 | 4263.84 | 4291.47 | 4318.01 | 4346.36 | 4374.7 | 4403.04 | 4430.28 | 4459.36 | 4488.44 | 4517.52 | 4545.47 | 4575.31 | 4605.14 | 4634.98 | 4663.65 | 4694.26 | 4724.88 | 4755.49 | 4784.91 | 4816.31 | 4847.72 | 4879.13 | 4909.31 | 4941.54 | 4973.76 | 5005.99 | 5036.96 | 5070.02 | 5103.08 | 5136.14 | 5167.92 | 5201.84 | 5235.76 | 5269.68 | 5302.28 | 5337.09 | 5371.89 | 5406.7 | 5440.14 | 5475.85 | 5511.56 | 5547.27 | 5581.59 | 5618.22 | 5654.86 | 5691.5 | 5726.71 | 5764.3 | 5801.89 | 5839.48 | 5875.6 | 5914.17 | 5952.74 | 5991.3 | 6028.37 | 6067.94 | 6107.51 | 6147.08 | 6185.1 | 6225.7 | 6266.3 | 6306.9 | 6345.92 | 6387.57 | 6429.23 | 6470.88 | 6510.91 | 6553.65 | 6596.39 | 6639.12 | 6680.19 | 6724.04 | 6767.89 | 6811.74 | 6853.88 | 6898.87 | 6943.86 | 6988.85 | 7032.08 | 7078.24 | 7124.4 | 7170.56 | 7214.91 | 7262.27 | 7309.63 | 7356.99 | 7402.5 | 7451.09 | 7499.68 | 7548.27 | 7594.97 | 7644.82 | 7694.67 | 7744.53 | 7792.44 | 7843.59 | 7894.74 | 7945.89 | 7995.04 | 8047.52 | 8100 | 8152.48
| Feature codes 02 to 20 and Composite index reflect the indices in the 28 October 2025 EM1110-2-1304 CWCCIS |  |  |  |  | 19 | 15 | 19 | FLOODWAY CONTROL & DIVERSION STRUCTURE | 2% | 272.96 | 276.04 | 284.61 | 287.69 | 293.79 | 300 | 309.83 | 312.44 | 317.17 | 318.26 | 327.74 | 327.83 | 327.53 | 329.77 | 336.78 | 337.58 | 337.59 | 341.9 | 345.41 | 344.61 | 344.74 | 346.93 | 349.22 | 347.84 | 347.27 | 349.61 | 349.34 | 349.75 | 350.28 | 352.65 | 356.54 | 359.07 | 362.38 | 367.09 | 370.86 | 371.49 | 374.97 | 379.49 | 382.47 | 382.81 | 382.1 | 385.48 | 388.93 | 389.01 | 391.31 | 393.28 | 396.94 | 395.33 | 398.09 | 402.68 | 403.56 | 403.94 | 409.21 | 419.09 | 417.86 | 421.18 | 427.15 | 429.69 | 432.59 | 434.12 | 438.14 | 444.64 | 447.98 | 447.96 | 447.8 | 452.65 | 457.78 | 459.09 | 461.23 | 466.4 | 468.57 | 468.4 | 469.97 | 474.07 | 474.38 | 472.57 | 474.86 | 480.31 | 487.47 | 483.86 | 487.08 | 489.21 | 489.75 | 489.55 | 490.33 | 491.91 | 496.69 | 497.31 | 499.28 | 508.67 | 514.07 | 513.82 | 514.15 | 516.87 | 520.35 | 525.69 | 534.75 | 558.9 | 571.55 | 586.56 | 593.35 | 597.76 | 600.97 | 608.18 | 624.32 | 630.14 | 636.39 | 645.47 | 649.01 | 668.79 | 674.11 | 671.55 | 675.58 | 693.72 | 722.13 | 719.86 | 698.29 | 686.42 | 689.95 | 691.34 | 696.93 | 707.21 | 712.33 | 711.42 | 718.73 | 732.94 | 740.7 | 740.08 | 744.72 | 749.69 | 749.6 | 749.46 | 758.43 | 764.29 | 764.9 | 766.75 | 774.03 | 779.64 | 785.65 | 786.93 | 792.02 | 788.66 | 793.12 | 788.51 | 790.9 | 795.09 | 807.3 | 804.64 | 811.91 | 823.16 | 831.76 | 834.07 | 833.09 | 846.58 | 860.94 | 867.95 | 873.73 | 878.35 | 881.63 | 877.83 | 880.38 | 883.42 | 890.83 | 904.43 | 925.56 | 974.85 | 1002.62 | 1025.12 | 1078.05 | 1100.62 | 1105.63 | 1100.49 | 1108.19 | 1122.28 | 1134.8 | 1132.27 | 1144.9 | 1147.14 | 1150.59 | 1151.26 | 1157.23 | 1175.1 | 1186.06 | 1193.77 | 1201.48 | 1209.19 | 1216.9 | 1228.69 | 1233.48 | 1241.58 | 1249.68 | 1257.77 | 1265.55 | 1273.86 | 1282.17 | 1290.48 | 1298.46 | 1306.98 | 1315.5 | 1324.03 | 1332.22 | 1340.96 | 1349.71 | 1358.45 | 1366.86 | 1375.83 | 1384.8 | 1393.77 | 1402.39 | 1411.6 | 1420.81 | 1430.01 | 1438.86 | 1448.3 | 1457.75 | 1467.19 | 1476.27 | 1485.96 | 1495.65 | 1505.34 | 1514.65 | 1524.59 | 1534.53 | 1544.48 | 1554.03 | 1564.23 | 1574.43 | 1584.63 | 1594.44 | 1604.9 | 1615.37 | 1625.83 | 1635.89 | 1646.63 | 1657.37 | 1668.1 | 1678.42 | 1689.44 | 1700.46 | 1711.48 | 1722.06 | 1733.37 | 1744.67 | 1755.97 | 1766.84 | 1778.43 | 1790.03 | 1801.63 | 1812.77 | 1824.67 | 1836.57 | 1848.47 | 1859.91 | 1872.12 | 1884.32 | 1896.53 | 1908.26 | 1920.79 | 1933.32 | 1945.84 | 1957.88 | 1970.73 | 1983.58 | 1996.43 | 2008.78 | 2021.97 | 2035.16 | 2048.34 | 2061.01 | 2074.54 | 2088.07 | 2101.6 | 2114.6 | 2128.48 | 2142.36 | 2156.24 | 2169.58 | 2183.82 | 2198.06 | 2212.3 | 2225.99 | 2240.6 | 2255.21 | 2269.82 | 2283.86 | 2298.85 | 2313.85 | 2328.84 | 2343.24 | 2358.62 | 2374.01 | 2389.39 | 2404.17 | 2419.95 | 2435.73 | 2451.51 | 2466.68 | 2482.87 | 2499.06 | 2515.25 | 2530.81 | 2547.42 | 2564.03 | 2580.65 | 2596.61 | 2613.65 | 2630.7 | 2647.74 | 2664.12 | 2681.61 | 2699.1 | 2716.58 | 2733.39 | 2751.33 | 2769.27 | 2787.22 | 2804.46 | 2822.87 | 2841.27 | 2859.68 | 2877.37 | 2896.26 | 2915.15 | 2934.04 | 2952.19 | 2971.56 | 2990.94 | 3010.32 | 3028.94 | 3048.82 | 3068.71 | 3088.59 | 3107.7 | 3128.09 | 3148.49 | 3168.89 | 3188.5 | 3209.42 | 3230.35 | 3251.28 | 3271.4 | 3292.87 | 3314.34 | 3335.82 | 3356.45 | 3378.48 | 3400.52 | 3422.55 | 3443.72 | 3466.32 | 3488.93 | 3511.53 | 3533.26 | 3556.45 | 3579.64 | 3602.83 | 3625.12 | 3648.92 | 3672.71 | 3696.51 | 3719.37 | 3743.79 | 3768.2 | 3792.62 | 3816.08 | 3841.13 | 3866.18 | 3891.22 | 3915.3 | 3941 | 3966.7 | 3992.4 | 4017.09 | 4043.46 | 4069.83 | 4096.2 | 4121.54 | 4148.59 | 4175.65 | 4202.7 | 4228.7 | 4256.46 | 4284.21 | 4311.97 | 4338.64 | 4367.12 | 4395.6 | 4424.08 | 4451.45 | 4480.67 | 4509.89 | 4539.11 | 4567.19 | 4597.17 | 4627.15 | 4657.12 | 4685.93 | 4716.69 | 4747.45 | 4778.21 | 4807.77 | 4839.33 | 4870.88 | 4902.44 | 4932.77 | 4965.15 | 4997.53 | 5029.91 | 5061.02 | 5094.24 | 5127.46 | 5160.68 | 5192.61 | 5226.69 | 5260.78 | 5294.86 | 5327.62 | 5362.59 | 5397.56 | 5432.53 | 5466.13 | 5502.01 | 5537.89 | 5573.77 | 5608.25 | 5645.07 | 5681.88 | 5718.69 | 5754.07 | 5791.84 | 5829.61 | 5867.38 | 5903.67 | 5942.43 | 5981.18 | 6019.93 | 6057.17 | 6096.93 | 6136.69 | 6176.45 | 6214.66 | 6255.45 | 6296.24 | 6337.04 | 6376.24 | 6418.09 | 6459.94 | 6501.8 | 6542.02 | 6584.96 | 6627.9 | 6670.85 | 6712.11 | 6756.17 | 6800.23 | 6844.29 | 6886.63 | 6931.83 | 6977.03 | 7022.24 | 7065.68 | 7112.06 | 7158.44 | 7204.82 | 7249.39 | 7296.97 | 7344.56 | 7392.14 | 7437.87 | 7486.69 | 7535.52 | 7584.34 | 7631.26 | 7681.35 | 7731.44 | 7781.53 | 7829.67 | 7881.06 | 7932.46 | 7983.85 | 8033.24 | 8085.97 | 8138.7 | 8191.43
[6 empty] | 20 | 16 | 20 | BANK STABILIZATION | 2% | 252.82 | 257.63 | 266.45 | 273.32 | 279.15 | 286.12 | 295.88 | 299.36 | 305.34 | 308.27 | 318.02 | 320.08 | 321.52 | 322.52 | 327.18 | 327.81 | 329.24 | 331.83 | 336.53 | 336.61 | 339.5 | 342.69 | 344.67 | 344.96 | 346.37 | 349.19 | 351.15 | 351.23 | 354.5 | 357.36 | 360.96 | 362.01 | 365.31 | 368.11 | 370.12 | 371.45 | 376.09 | 379.56 | 383.04 | 384.58 | 386.68 | 391.12 | 394.94 | 396.05 | 398.72 | 402.16 | 404.24 | 405.03 | 406.86 | 411.41 | 414.73 | 415.36 | 419.18 | 423.02 | 424.66 | 427.08 | 430.35 | 433.67 | 435.18 | 436.35 | 439.89 | 444.59 | 449.63 | 450.08 | 453.16 | 456.47 | 459.29 | 459.9 | 462.5 | 464.94 | 466.65 | 467.64 | 472.31 | 476.13 | 478.33 | 479.14 | 483.67 | 488.48 | 492.81 | 493.47 | 496.2 | 500.74 | 503.53 | 505.51 | 508.86 | 511.15 | 515.13 | 516.86 | 519.9 | 530.24 | 534.49 | 534.58 | 538.56 | 542.73 | 544.59 | 547.71 | 553.65 | 561.04 | 568.83 | 574.2 | 584.95 | 591.3 | 599.32 | 603.93 | 619.29 | 627.39 | 632.75 | 642.25 | 654.93 | 666.89 | 672.89 | 678.39 | 685.5 | 693.62 | 705.31 | 710.77 | 718.39 | 722.75 | 726.93 | 725.05 | 731.87 | 734.65 | 743.86 | 745.72 | 751.63 | 757.16 | 765.44 | 765.87 | 771.7 | 779.14 | 784.52 | 784.53 | 790.84 | 793.64 | 801.54 | 805.25 | 812.74 | 817.68 | 824.94 | 825.65 | 833.88 | 837.55 | 844.72 | 846.91 | 856.95 | 861.3 | 871.24 | 868.28 | 878.14 | 883.04 | 892.9 | 894.64 | 893.48 | 901.37 | 910.43 | 923.01 | 934.16 | 939 | 954.24 | 953.88 | 965.11 | 971.43 | 975.81 | 977.64 | 991.62 | 1008.67 | 1030.08 | 1043.86 | 1071.74 | 1095.93 | 1117.78 | 1131.29 | 1167.74 | 1179.48 | 1195.89 | 1204.26 | 1233.62 | 1241.69 | 1257.17 | 1267.32 | 1293.7 | 1302.83 | 1312.96 | 1321.49 | 1330.03 | 1338.56 | 1347.1 | 1360.15 | 1365.46 | 1374.42 | 1383.38 | 1392.35 | 1400.96 | 1410.16 | 1419.35 | 1428.55 | 1437.38 | 1446.82 | 1456.25 | 1465.69 | 1474.76 | 1484.44 | 1494.12 | 1503.8 | 1513.1 | 1523.03 | 1532.96 | 1542.9 | 1552.44 | 1562.63 | 1572.82 | 1583.01 | 1592.8 | 1603.26 | 1613.71 | 1624.17 | 1634.22 | 1644.94 | 1655.67 | 1666.4 | 1676.71 | 1687.71 | 1698.72 | 1709.72 | 1720.3 | 1731.59 | 1742.89 | 1754.18 | 1765.03 | 1776.61 | 1788.2 | 1799.79 | 1810.92 | 1822.81 | 1834.69 | 1846.58 | 1858 | 1870.2 | 1882.4 | 1894.59 | 1906.31 | 1918.82 | 1931.34 | 1943.85 | 1955.88 | 1968.71 | 1981.55 | 1994.39 | 2006.73 | 2019.9 | 2033.07 | 2046.25 | 2058.9 | 2072.42 | 2085.93 | 2099.45 | 2112.44 | 2126.3 | 2140.17 | 2154.03 | 2167.36 | 2181.58 | 2195.81 | 2210.04 | 2223.71 | 2238.31 | 2252.9 | 2267.5 | 2281.53 | 2296.5 | 2311.48 | 2326.45 | 2340.85 | 2356.21 | 2371.58 | 2386.94 | 2401.71 | 2417.47 | 2433.24 | 2449 | 2464.15 | 2480.33 | 2496.5 | 2512.68 | 2528.22 | 2544.82 | 2561.41 | 2578.01 | 2593.95 | 2610.98 | 2628.01 | 2645.03 | 2661.4 | 2678.87 | 2696.34 | 2713.8 | 2730.59 | 2748.52 | 2766.44 | 2784.36 | 2801.59 | 2819.98 | 2838.37 | 2856.76 | 2874.43 | 2893.3 | 2912.17 | 2931.03 | 2949.16 | 2968.52 | 2987.88 | 3007.24 | 3025.84 | 3045.7 | 3065.57 | 3085.43 | 3104.52 | 3124.89 | 3145.27 | 3165.65 | 3185.23 | 3206.14 | 3227.05 | 3247.96 | 3268.05 | 3289.5 | 3310.95 | 3332.4 | 3353.02 | 3375.03 | 3397.04 | 3419.05 | 3440.2 | 3462.78 | 3485.36 | 3507.94 | 3529.64 | 3552.81 | 3575.98 | 3599.15 | 3621.41 | 3645.18 | 3668.95 | 3692.72 | 3715.57 | 3739.96 | 3764.35 | 3788.74 | 3812.17 | 3837.2 | 3862.22 | 3887.24 | 3911.29 | 3936.96 | 3962.64 | 3988.31 | 4012.98 | 4039.32 | 4065.67 | 4092.01 | 4117.32 | 4144.35 | 4171.37 | 4198.4 | 4224.37 | 4252.1 | 4279.83 | 4307.56 | 4334.21 | 4362.65 | 4391.1 | 4419.55 | 4446.89 | 4476.08 | 4505.27 | 4534.46 | 4562.51 | 4592.46 | 4622.41 | 4652.36 | 4681.14 | 4711.87 | 4742.59 | 4773.32 | 4802.85 | 4834.37 | 4865.9 | 4897.43 | 4927.72 | 4960.07 | 4992.41 | 5024.76 | 5055.84 | 5089.03 | 5122.22 | 5155.4 | 5187.3 | 5221.35 | 5255.39 | 5289.44 | 5322.17 | 5357.1 | 5392.03 | 5426.97 | 5460.54 | 5496.38 | 5532.23 | 5568.07 | 5602.52 | 5639.29 | 5676.07 | 5712.84 | 5748.18 | 5785.91 | 5823.64 | 5861.37 | 5897.63 | 5936.35 | 5975.06 | 6013.77 | 6050.97 | 6090.69 | 6130.41 | 6170.13 | 6208.3 | 6249.05 | 6289.8 | 6330.55 | 6369.71 | 6411.52 | 6453.33 | 6495.15 | 6535.33 | 6578.22 | 6621.12 | 6664.02 | 6705.24 | 6749.26 | 6793.27 | 6837.28 | 6879.58 | 6924.74 | 6969.9 | 7015.05 | 7058.45 | 7104.78 | 7151.11 | 7197.44 | 7241.97 | 7289.51 | 7337.04 | 7384.58 | 7430.26 | 7479.03 | 7527.81 | 7576.58 | 7623.45 | 7673.49 | 7723.53 | 7773.57 | 7821.66 | 7873 | 7924.34 | 7975.68 | 8025.02 | 8077.7 | 8130.37 | 8183.05 | 8233.67 | 8287.72 | 8341.76 | 8395.81 | 8447.75 | 8503.2 | 8558.65 | 8614.1 | 8667.39 | 8724.28 | 8781.17 | 8838.07 | 8892.74 | 8951.11 | 9009.48 | 9067.86
[6 empty] | 21 | 17 | 21 | BEACH REPLENISHMENT | 2% | 262.51 | 266.77 | 278.85 | 284.04 | 287.68 | 293.48 | 307.19 | 311.48 | 317.47 | 319.47 | 334.99 | 336.48 | 338.31 | 339.12 | 345.4 | 346.48 | 347.61 | 348.8 | 354.71 | 354.44 | 356.26 | 357.84 | 360.19 | 360.68 | 361.64 | 364.59 | 366.87 | 366.99 | 370.06 | 371.75 | 376.2 | 377.19 | 380.01 | 382.4 | 385.05 | 386.6 | 394.09 | 397.39 | 402.05 | 404.39 | 408.11 | 411.77 | 417.43 | 418.79 | 421.46 | 424.52 | 427.62 | 429.07 | 431.08 | 437.09 | 443.07 | 443.82 | 446.08 | 450.52 | 454.06 | 454.39 | 457.05 | 460.68 | 462.35 | 463.56 | 465.83 | 471.98 | 479.09 | 479.43 | 482.58 | 486.02 | 489.99 | 490.51 | 492.64 | 494.85 | 496.49 | 498.23 | 503.53 | 506.24 | 508.4 | 510.21 | 514.77 | 520.48 | 525.81 | 526.51 | 527.91 | 531.22 | 534.34 | 537.36 | 540.77 | 539.82 | 544.75 | 547.51 | 550.76 | 568.85 | 574.22 | 574.58 | 580.2 | 585.05 | 585.18 | 588.23 | 593.35 | 597.42 | 605.82 | 610.94 | 619.98 | 626.28 | 635.25 | 639.56 | 650.69 | 658.21 | 661.81 | 669.01 | 676.88 | 686.56 | 696 | 698.14 | 700.69 | 705.47 | 713.5 | 717.74 | 727.05 | 730.99 | 740.35 | 741.15 | 747.83 | 748.86 | 765.59 | 766.53 | 771.39 | 778.88 | 787.89 | 789.66 | 795.15 | 798.73 | 806.02 | 807.05 | 812.95 | 815.76 | 828.49 | 829.61 | 834.45 | 837.27 | 845.68 | 846.05 | 852.65 | 855.4 | 864.56 | 866.46 | 871.59 | 874.2 | 886.42 | 885.91 | 890.36 | 893.94 | 906.3 | 907.51 | 897.47 | 901.83 | 911.64 | 928.49 | 936.64 | 941.4 | 958.55 | 959.67 | 965.66 | 969.51 | 972.29 | 974.95 | 983.87 | 1000.49 | 1022.6 | 1039.2 | 1050.41 | 1070.45 | 1082.54 | 1103.2 | 1129.38 | 1137.36 | 1163.63 | 1170.63 | 1185.37 | 1191.31 | 1203.51 | 1212.39 | 1225.77 | 1231.09 | 1237.86 | 1245.91 | 1253.95 | 1262 | 1270.04 | 1282.35 | 1287.35 | 1295.81 | 1304.26 | 1312.71 | 1320.83 | 1329.5 | 1338.17 | 1346.84 | 1355.17 | 1364.06 | 1372.96 | 1381.85 | 1390.4 | 1399.53 | 1408.66 | 1417.78 | 1426.55 | 1435.92 | 1445.28 | 1454.64 | 1463.64 | 1473.25 | 1482.86 | 1492.46 | 1501.7 | 1511.55 | 1521.41 | 1531.27 | 1540.74 | 1550.85 | 1560.97 | 1571.08 | 1580.8 | 1591.18 | 1601.55 | 1611.93 | 1621.9 | 1632.55 | 1643.19 | 1653.84 | 1664.07 | 1674.99 | 1685.92 | 1696.84 | 1707.34 | 1718.54 | 1729.75 | 1740.96 | 1751.73 | 1763.23 | 1774.72 | 1786.22 | 1797.27 | 1809.07 | 1820.87 | 1832.66 | 1844 | 1856.11 | 1868.21 | 1880.31 | 1891.95 | 1904.36 | 1916.78 | 1929.2 | 1941.14 | 1953.88 | 1966.62 | 1979.36 | 1991.61 | 2004.68 | 2017.75 | 2030.82 | 2043.39 | 2056.8 | 2070.21 | 2083.63 | 2096.52 | 2110.28 | 2124.04 | 2137.8 | 2151.03 | 2165.14 | 2179.26 | 2193.38 | 2206.95 | 2221.44 | 2235.92 | 2250.41 | 2264.33 | 2279.2 | 2294.06 | 2308.92 | 2323.21 | 2338.45 | 2353.7 | 2368.95 | 2383.61 | 2399.25 | 2414.9 | 2430.55 | 2445.58 | 2461.64 | 2477.69 | 2493.74 | 2509.17 | 2525.64 | 2542.11 | 2558.58 | 2574.41 | 2591.3 | 2608.2 | 2625.1 | 2641.34 | 2658.68 | 2676.02 | 2693.35 | 2710.02 | 2727.8 | 2745.59 | 2763.38 | 2780.48 | 2798.73 | 2816.98 | 2835.23 | 2852.77 | 2871.49 | 2890.22 | 2908.94 | 2926.94 | 2946.15 | 2965.36 | 2984.58 | 3003.04 | 3022.75 | 3042.46 | 3062.18 | 3081.12 | 3101.34 | 3121.57 | 3141.79 | 3161.23 | 3181.98 | 3202.73 | 3223.48 | 3243.42 | 3264.71 | 3286 | 3307.29 | 3327.75 | 3349.59 | 3371.44 | 3393.28 | 3414.27 | 3436.68 | 3459.09 | 3481.5 | 3503.04 | 3526.04 | 3549.03 | 3572.02 | 3594.12 | 3617.71 | 3641.3 | 3664.9 | 3687.57 | 3711.77 | 3735.98 | 3760.18 | 3783.45 | 3808.28 | 3833.11 | 3857.95 | 3881.81 | 3907.29 | 3932.78 | 3958.26 | 3982.74 | 4008.88 | 4035.03 | 4061.17 | 4086.29 | 4113.12 | 4139.94 | 4166.76 | 4192.54 | 4220.06 | 4247.58 | 4275.1 | 4301.54 | 4329.78 | 4358.01 | 4386.25 | 4413.38 | 4442.35 | 4471.32 | 4500.29 | 4528.13 | 4557.85 | 4587.58 | 4617.3 | 4645.86 | 4676.36 | 4706.85 | 4737.35 | 4766.65 | 4797.94 | 4829.23 | 4860.52 | 4890.59 | 4922.69 | 4954.79 | 4986.89 | 5017.74 | 5050.68 | 5083.62 | 5116.55 | 5148.2 | 5182 | 5215.79 | 5249.58 | 5282.06 | 5316.73 | 5351.4 | 5386.07 | 5419.39 | 5454.96 | 5490.54 | 5526.11 | 5560.3 | 5596.79 | 5633.29 | 5669.79 | 5704.86 | 5742.31 | 5779.76 | 5817.2 | 5853.19 | 5891.61 | 5930.03 | 5968.45 | 6005.37 | 6044.79 | 6084.21 | 6123.63 | 6161.51 | 6201.96 | 6242.4 | 6282.84 | 6321.71 | 6363.21 | 6404.7 | 6446.2 | 6486.08 | 6528.65 | 6571.22 | 6613.8 | 6654.71 | 6698.4 | 6742.08 | 6785.76 | 6827.74 | 6872.55 | 6917.37 | 6962.19 | 7005.26 | 7051.24 | 7097.22 | 7143.2 | 7187.39 | 7234.57 | 7281.75 | 7328.93 | 7374.27 | 7422.67 | 7471.08 | 7519.48 | 7566 | 7615.66 | 7665.32 | 7714.99 | 7762.71 | 7813.67 | 7864.62 | 7915.58 | 7964.54 | 8016.82 | 8069.1 | 8121.38 | 8171.62 | 8225.26 | 8278.9 | 8332.54 | 8384.08 | 8439.12 | 8494.15 | 8549.18
| The 30 and 31 feature codes can be based on the updating factors from Table 1 in |  |  |  |  | 22 | 18 | 22 | CULTURAL RESOURCE PRESERVATION | 2% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1146.96 | 1137.95 | 1136.3 | 1165.27 | 1180.42 | 1188.09 | 1195.77 | 1203.44 | 1211.11 | 1222.84 | 1227.62 | 1235.68 | 1243.73 | 1251.79 | 1259.54 | 1267.8 | 1276.07 | 1284.34 | 1292.28 | 1300.77 | 1309.25 | 1317.73 | 1325.88 | 1334.59 | 1343.29 | 1351.99 | 1360.36 | 1369.29 | 1378.22 | 1387.14 | 1395.73 | 1404.89 | 1414.05 | 1423.21 | 1432.01 | 1441.41 | 1450.81 | 1460.21 | 1469.25 | 1478.89 | 1488.54 | 1498.18 | 1507.45 | 1517.34 | 1527.24 | 1537.13 | 1546.64 | 1556.79 | 1566.95 | 1577.1 | 1586.85 | 1597.27 | 1607.69 | 1618.1 | 1628.11 | 1638.8 | 1649.49 | 1660.17 | 1670.44 | 1681.41 | 1692.37 | 1703.34 | 1713.87 | 1725.12 | 1736.37 | 1747.62 | 1758.44 | 1769.98 | 1781.52 | 1793.06 | 1804.15 | 1816 | 1827.84 | 1839.68 | 1851.06 | 1863.21 | 1875.36 | 1887.51 | 1899.19 | 1911.66 | 1924.12 | 1936.59 | 1948.57 | 1961.36 | 1974.15 | 1986.94 | 1999.23 | 2012.35 | 2025.48 | 2038.6 | 2051.21 | 2064.68 | 2078.14 | 2091.6 | 2104.54 | 2118.36 | 2132.17 | 2145.99 | 2159.26 | 2173.43 | 2187.61 | 2201.78 | 2215.4 | 2229.94 | 2244.49 | 2259.03 | 2273 | 2287.92 | 2302.84 | 2317.76 | 2332.1 | 2347.41 | 2362.72 | 2378.02 | 2392.74 | 2408.44 | 2424.15 | 2439.85 | 2454.95 | 2471.06 | 2487.18 | 2503.29 | 2518.78 | 2535.31 | 2551.84 | 2568.37 | 2584.26 | 2601.23 | 2618.19 | 2635.15 | 2651.45 | 2668.86 | 2686.26 | 2703.67 | 2720.39 | 2738.25 | 2756.11 | 2773.96 | 2791.12 | 2809.44 | 2827.76 | 2846.08 | 2863.69 | 2882.49 | 2901.29 | 2920.08 | 2938.15 | 2957.43 | 2976.72 | 2996.01 | 3014.54 | 3034.33 | 3054.11 | 3073.9 | 3092.92 | 3113.22 | 3133.52 | 3153.82 | 3173.33 | 3194.16 | 3214.99 | 3235.82 | 3255.84 | 3277.21 | 3298.58 | 3319.95 | 3340.49 | 3362.42 | 3384.35 | 3406.27 | 3427.34 | 3449.84 | 3472.34 | 3494.84 | 3516.46 | 3539.54 | 3562.62 | 3585.7 | 3607.88 | 3631.57 | 3655.25 | 3678.93 | 3701.69 | 3725.99 | 3750.28 | 3774.58 | 3797.93 | 3822.86 | 3847.79 | 3872.72 | 3896.68 | 3922.26 | 3947.83 | 3973.41 | 3997.99 | 4024.23 | 4050.48 | 4076.72 | 4101.94 | 4128.86 | 4155.79 | 4182.71 | 4208.59 | 4236.22 | 4263.84 | 4291.47 | 4318.01 | 4346.36 | 4374.7 | 4403.04 | 4430.28 | 4459.36 | 4488.44 | 4517.52 | 4545.47 | 4575.31 | 4605.14 | 4634.98 | 4663.65 | 4694.26 | 4724.88 | 4755.49 | 4784.91 | 4816.31 | 4847.72 | 4879.13 | 4909.31 | 4941.54 | 4973.76 | 5005.99 | 5036.96 | 5070.02 | 5103.08 | 5136.14 | 5167.92 | 5201.84 | 5235.76 | 5269.68 | 5302.28 | 5337.09 | 5371.89 | 5406.7 | 5440.14 | 5475.85 | 5511.56 | 5547.27 | 5581.59 | 5618.22 | 5654.86 | 5691.5 | 5726.71 | 5764.3 | 5801.89 | 5839.48 | 5875.6 | 5914.17 | 5952.74 | 5991.3 | 6028.37 | 6067.94 | 6107.51 | 6147.08 | 6185.1 | 6225.7 | 6266.3 | 6306.9 | 6345.92 | 6387.57 | 6429.23 | 6470.88 | 6510.91 | 6553.65 | 6596.39 | 6639.12 | 6680.19 | 6724.04 | 6767.89 | 6811.74 | 6853.88 | 6898.87 | 6943.86 | 6988.85 | 7032.08 | 7078.24 | 7124.4 | 7170.56 | 7214.91 | 7262.27 | 7309.63 | 7356.99 | 7402.5 | 7451.09 | 7499.68 | 7548.27 | 7594.97 | 7644.82 | 7694.67 | 7744.53 | 7792.44 | 7843.59 | 7894.74 | 7945.89 | 7995.04 | 8047.52 | 8100 | 8152.48
| Table 1 FY27 Program Cost Estiimate Updating Rates 31 March 2025 |  |  |  |  | 23 | 19 | 23 | BUILDINGS, GROUNDS & UTILITIES | 5% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 459.51 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1146.96 | 1137.95 | 1136.3 | 1165.27 | 1180.42 | 1188.09 | 1195.77 | 1203.44 | 1211.11 | 1222.84 | 1227.62 | 1235.68 | 1243.73 | 1251.79 | 1259.54 | 1267.8 | 1276.07 | 1284.34 | 1292.28 | 1300.77 | 1309.25 | 1317.73 | 1325.88 | 1334.59 | 1343.29 | 1351.99 | 1360.36 | 1369.29 | 1378.22 | 1387.14 | 1395.73 | 1404.89 | 1414.05 | 1423.21 | 1432.01 | 1441.41 | 1450.81 | 1460.21 | 1469.25 | 1478.89 | 1488.54 | 1498.18 | 1507.45 | 1517.34 | 1527.24 | 1537.13 | 1546.64 | 1556.79 | 1566.95 | 1577.1 | 1586.85 | 1597.27 | 1607.69 | 1618.1 | 1628.11 | 1638.8 | 1649.49 | 1660.17 | 1670.44 | 1681.41 | 1692.37 | 1703.34 | 1713.87 | 1725.12 | 1736.37 | 1747.62 | 1758.44 | 1769.98 | 1781.52 | 1793.06 | 1804.15 | 1816 | 1827.84 | 1839.68 | 1851.06 | 1863.21 | 1875.36 | 1887.51 | 1899.19 | 1911.66 | 1924.12 | 1936.59 | 1948.57 | 1961.36 | 1974.15 | 1986.94 | 1999.23 | 2012.35 | 2025.48 | 2038.6 | 2051.21 | 2064.68 | 2078.14 | 2091.6 | 2104.54 | 2118.36 | 2132.17 | 2145.99 | 2159.26 | 2173.43 | 2187.61 | 2201.78 | 2215.4 | 2229.94 | 2244.49 | 2259.03 | 2273 | 2287.92 | 2302.84 | 2317.76 | 2332.1 | 2347.41 | 2362.72 | 2378.02 | 2392.74 | 2408.44 | 2424.15 | 2439.85 | 2454.95 | 2471.06 | 2487.18 | 2503.29 | 2518.78 | 2535.31 | 2551.84 | 2568.37 | 2584.26 | 2601.23 | 2618.19 | 2635.15 | 2651.45 | 2668.86 | 2686.26 | 2703.67 | 2720.39 | 2738.25 | 2756.11 | 2773.96 | 2791.12 | 2809.44 | 2827.76 | 2846.08 | 2863.69 | 2882.49 | 2901.29 | 2920.08 | 2938.15 | 2957.43 | 2976.72 | 2996.01 | 3014.54 | 3034.33 | 3054.11 | 3073.9 | 3092.92 | 3113.22 | 3133.52 | 3153.82 | 3173.33 | 3194.16 | 3214.99 | 3235.82 | 3255.84 | 3277.21 | 3298.58 | 3319.95 | 3340.49 | 3362.42 | 3384.35 | 3406.27 | 3427.34 | 3449.84 | 3472.34 | 3494.84 | 3516.46 | 3539.54 | 3562.62 | 3585.7 | 3607.88 | 3631.57 | 3655.25 | 3678.93 | 3701.69 | 3725.99 | 3750.28 | 3774.58 | 3797.93 | 3822.86 | 3847.79 | 3872.72 | 3896.68 | 3922.26 | 3947.83 | 3973.41 | 3997.99 | 4024.23 | 4050.48 | 4076.72 | 4101.94 | 4128.86 | 4155.79 | 4182.71 | 4208.59 | 4236.22 | 4263.84 | 4291.47 | 4318.01 | 4346.36 | 4374.7 | 4403.04 | 4430.28 | 4459.36 | 4488.44 | 4517.52 | 4545.47 | 4575.31 | 4605.14 | 4634.98 | 4663.65 | 4694.26 | 4724.88 | 4755.49 | 4784.91 | 4816.31 | 4847.72 | 4879.13 | 4909.31 | 4941.54 | 4973.76 | 5005.99 | 5036.96 | 5070.02 | 5103.08 | 5136.14 | 5167.92 | 5201.84 | 5235.76 | 5269.68 | 5302.28 | 5337.09 | 5371.89 | 5406.7 | 5440.14 | 5475.85 | 5511.56 | 5547.27 | 5581.59 | 5618.22 | 5654.86 | 5691.5 | 5726.71 | 5764.3 | 5801.89 | 5839.48 | 5875.6 | 5914.17 | 5952.74 | 5991.3 | 6028.37 | 6067.94 | 6107.51 | 6147.08 | 6185.1 | 6225.7 | 6266.3 | 6306.9 | 6345.92 | 6387.57 | 6429.23 | 6470.88 | 6510.91 | 6553.65 | 6596.39 | 6639.12 | 6680.19 | 6724.04 | 6767.89 | 6811.74 | 6853.88 | 6898.87 | 6943.86 | 6988.85 | 7032.08 | 7078.24 | 7124.4 | 7170.56 | 7214.91 | 7262.27 | 7309.63 | 7356.99 | 7402.5 | 7451.09 | 7499.68 | 7548.27 | 7594.97 | 7644.82 | 7694.67 | 7744.53 | 7792.44 | 7843.59 | 7894.74 | 7945.89 | 7995.04 | 8047.52 | 8100 | 8152.48
[5 empty] | Select | 24 | 20 | 24 | PERMANENT OPERATING EQUIPMENT | 2% | 269.79 | 273.86 | 281.34 | 285.41 | 291.55 | 298.07 | 308.21 | 311.18 | 314.92 | 316.12 | 324.53 | 324.95 | 325.26 | 328.39 | 333.91 | 335.74 | 336.79 | 340 | 343.84 | 343.63 | 344.18 | 345.83 | 347.56 | 346.91 | 345.43 | 347.52 | 347.92 | 348.46 | 349.49 | 351.39 | 354.69 | 357.81 | 362.28 | 368.41 | 372.76 | 374.35 | 378.56 | 383.86 | 385.02 | 385.11 | 383.69 | 386 | 388.53 | 388.78 | 390.85 | 391.74 | 394.01 | 392.82 | 395.72 | 399.85 | 400.53 | 400.17 | 403.93 | 411.62 | 411.97 | 415.02 | 421.19 | 423.94 | 426.49 | 428.02 | 433.65 | 440 | 442.92 | 442.3 | 441.66 | 444.01 | 447.85 | 448.8 | 450.05 | 454.32 | 457.23 | 458.34 | 469.97 | 461.72 | 460.32 | 456.04 | 455.05 | 458.29 | 465.05 | 462.25 | 466.3 | 468.39 | 469.29 | 468.22 | 468.84 | 470.57 | 474.22 | 475.09 | 476.18 | 485.23 | 492.07 | 491.16 | 491.18 | 495.32 | 498.09 | 505 | 520.69 | 557.62 | 576.08 | 600.71 | 605.19 | 603.75 | 600.77 | 612.17 | 632.03 | 638.5 | 649.88 | 661.67 | 658.14 | 689.31 | 692.87 | 687.19 | 696.7 | 725.23 | 774.76 | 768.74 | 715.95 | 691.26 | 694.39 | 697.18 | 705.25 | 722.76 | 728.03 | 727.14 | 738.68 | 759.69 | 768.44 | 768.35 | 770.37 | 772.58 | 767.66 | 766.57 | 773.09 | 778.6 | 776.77 | 777.31 | 785.64 | 789.93 | 795.77 | 795 | 797.68 | 784.02 | 786.63 | 776.94 | 773.31 | 777.31 | 791.51 | 787.71 | 794.57 | 807.59 | 816.18 | 817.39 | 818.05 | 834.7 | 850.29 | 864.3 | 870.05 | 872.7 | 864.06 | 857.91 | 858.42 | 860.31 | 863.19 | 874.18 | 905.63 | 973.75 | 1024.86 | 1069.68 | 1129.16 | 1162.67 | 1169.55 | 1143.96 | 1140.31 | 1159.64 | 1167.06 | 1158.56 | 1163.25 | 1158.12 | 1146.96 | 1137.95 | 1136.3 | 1165.27 | 1180.42 | 1188.09 | 1195.77 | 1203.44 | 1211.11 | 1222.84 | 1227.62 | 1235.68 | 1243.73 | 1251.79 | 1259.54 | 1267.8 | 1276.07 | 1284.34 | 1292.28 | 1300.77 | 1309.25 | 1317.73 | 1325.88 | 1334.59 | 1343.29 | 1351.99 | 1360.36 | 1369.29 | 1378.22 | 1387.14 | 1395.73 | 1404.89 | 1414.05 | 1423.21 | 1432.01 | 1441.41 | 1450.81 | 1460.21 | 1469.25 | 1478.89 | 1488.54 | 1498.18 | 1507.45 | 1517.34 | 1527.24 | 1537.13 | 1546.64 | 1556.79 | 1566.95 | 1577.1 | 1586.85 | 1597.27 | 1607.69 | 1618.1 | 1628.11 | 1638.8 | 1649.49 | 1660.17 | 1670.44 | 1681.41 | 1692.37 | 1703.34 | 1713.87 | 1725.12 | 1736.37 | 1747.62 | 1758.44 | 1769.98 | 1781.52 | 1793.06 | 1804.15 | 1816 | 1827.84 | 1839.68 | 1851.06 | 1863.21 | 1875.36 | 1887.51 | 1899.19 | 1911.66 | 1924.12 | 1936.59 | 1948.57 | 1961.36 | 1974.15 | 1986.94 | 1999.23 | 2012.35 | 2025.48 | 2038.6 | 2051.21 | 2064.68 | 2078.14 | 2091.6 | 2104.54 | 2118.36 | 2132.17 | 2145.99 | 2159.26 | 2173.43 | 2187.61 | 2201.78 | 2215.4 | 2229.94 | 2244.49 | 2259.03 | 2273 | 2287.92 | 2302.84 | 2317.76 | 2332.1 | 2347.41 | 2362.72 | 2378.02 | 2392.74 | 2408.44 | 2424.15 | 2439.85 | 2454.95 | 2471.06 | 2487.18 | 2503.29 | 2518.78 | 2535.31 | 2551.84 | 2568.37 | 2584.26 | 2601.23 | 2618.19 | 2635.15 | 2651.45 | 2668.86 | 2686.26 | 2703.67 | 2720.39 | 2738.25 | 2756.11 | 2773.96 | 2791.12 | 2809.44 | 2827.76 | 2846.08 | 2863.69 | 2882.49 | 2901.29 | 2920.08 | 2938.15 | 2957.43 | 2976.72 | 2996.01 | 3014.54 | 3034.33 | 3054.11 | 3073.9 | 3092.92 | 3113.22 | 3133.52 | 3153.82 | 3173.33 | 3194.16 | 3214.99 | 3235.82 | 3255.84 | 3277.21 | 3298.58 | 3319.95 | 3340.49 | 3362.42 | 3384.35 | 3406.27 | 3427.34 | 3449.84 | 3472.34 | 3494.84 | 3516.46 | 3539.54 | 3562.62 | 3585.7 | 3607.88 | 3631.57 | 3655.25 | 3678.93 | 3701.69 | 3725.99 | 3750.28 | 3774.58 | 3797.93 | 3822.86 | 3847.79 | 3872.72 | 3896.68 | 3922.26 | 3947.83 | 3973.41 | 3997.99 | 4024.23 | 4050.48 | 4076.72 | 4101.94 | 4128.86 | 4155.79 | 4182.71 | 4208.59 | 4236.22 | 4263.84 | 4291.47 | 4318.01 | 4346.36 | 4374.7 | 4403.04 | 4430.28 | 4459.36 | 4488.44 | 4517.52 | 4545.47 | 4575.31 | 4605.14 | 4634.98 | 4663.65 | 4694.26 | 4724.88 | 4755.49 | 4784.91 | 4816.31 | 4847.72 | 4879.13 | 4909.31 | 4941.54 | 4973.76 | 5005.99 | 5036.96 | 5070.02 | 5103.08 | 5136.14 | 5167.92 | 5201.84 | 5235.76 | 5269.68 | 5302.28 | 5337.09 | 5371.89 | 5406.7 | 5440.14 | 5475.85 | 5511.56 | 5547.27 | 5581.59 | 5618.22 | 5654.86 | 5691.5 | 5726.71 | 5764.3 | 5801.89 | 5839.48 | 5875.6 | 5914.17 | 5952.74 | 5991.3 | 6028.37 | 6067.94 | 6107.51 | 6147.08 | 6185.1 | 6225.7 | 6266.3 | 6306.9 | 6345.92 | 6387.57 | 6429.23 | 6470.88 | 6510.91 | 6553.65 | 6596.39 | 6639.12 | 6680.19 | 6724.04 | 6767.89 | 6811.74 | 6853.88 | 6898.87 | 6943.86 | 6988.85 | 7032.08 | 7078.24 | 7124.4 | 7170.56 | 7214.91 | 7262.27 | 7309.63 | 7356.99 | 7402.5 | 7451.09 | 7499.68 | 7548.27 | 7594.97 | 7644.82 | 7694.67 | 7744.53 | 7792.44 | 7843.59 | 7894.74 | 7945.89 | 7995.04 | 8047.52 | 8100 | 8152.48
[5 empty] | Class | 25 | ALL | 25 | COMPOSITE INDEX (WEIGHTED AVERAGE) | 100% | 270.89 | 276.33 | 285.85 | 289.76 | 295.87 | 303.91 | 314.31 | 318.24 | 323.45 | 325.24 | 335.09 | 335.72 | 336.75 | 337.22 | 342.77 | 344.12 | 345.25 | 348.43 | 352.39 | 352.45 | 353.23 | 353.64 | 355.73 | 354.66 | 354.6 | 356.25 | 357.4 | 356.91 | 357.75 | 359.01 | 362.94 | 366.08 | 369.3 | 373.44 | 376.76 | 378.56 | 383.22 | 387.78 | 391.19 | 392.55 | 393.28 | 396.19 | 399.75 | 404.15 | 405.07 | 405.25 | 408.48 | 408.68 | 410.77 | 414.89 | 417.22 | 418.01 | 422.05 | 428.85 | 429.04 | 431.4 | 435.65 | 438.47 | 440.77 | 442.92 | 446.34 | 452.21 | 455.44 | 455.24 | 456.46 | 460.75 | 464.13 | 467.28 | 468.6 | 471.96 | 473.39 | 474.74 | 476.72 | 478.83 | 478.86 | 478.01 | 479.74 | 484.42 | 490.61 | 490.05 | 493.28 | 496.38 | 498.13 | 500.48 | 501.17 | 501.33 | 505.47 | 506.11 | 507.18 | 516.82 | 522.4 | 523.44 | 525.26 | 528.3 | 530.64 | 535.59 | 544.89 | 566.51 | 578.67 | 595.09 | 599.22 | 604.49 | 608.79 | 620.94 | 630.43 | 638.08 | 644.95 | 654.19 | 657.49 | 674.89 | 681.29 | 680.42 | 687.9 | 708.36 | 738.89 | 731.03 | 705.87 | 697.73 | 702.67 | 705.72 | 713.39 | 722.89 | 729.23 | 731.19 | 739.86 | 756.92 | 764.34 | 764.82 | 769.23 | 775.01 | 773.35 | 777.41 | 782.27 | 786.67 | 789.56 | 792.07 | 797.85 | 802.53 | 808.31 | 807.52 | 805.97 | 801.94 | 808.19 | 803.77 | 801.82 | 805.71 | 818.83 | 817.3 | 823.47 | 831.91 | 841.4 | 845.51 | 844.49 | 855.27 | 869.33 | 881.15 | 882.69 | 888.93 | 892.31 | 890.36 | 893.31 | 890.14 | 897.67 | 907.64 | 928.78 | 971.54 | 1005.06 | 1033.84 | 1073.97 | 1108.73 | 1120.16 | 1120.76 | 1121.67 | 1130.44 | 1138.98 | 1144.03 | 1149.32 | 1155.42 | 1157.94 | 1157.2 | 1162.49 | 1178.02 | 1192.24 | 1199.99 | 1207.74 | 1215.49 | 1223.24 | 1235.09 | 1239.91 | 1248.05 | 1256.19 | 1264.33 | 1272.15 | 1280.5 | 1288.85 | 1297.2 | 1305.23 | 1313.79 | 1322.36 | 1330.93 | 1339.16 | 1347.95 | 1356.74 | 1365.53 | 1373.98 | 1383 | 1392.02 | 1401.04 | 1409.7 | 1418.96 | 1428.21 | 1437.46 | 1446.36 | 1455.85 | 1465.34 | 1474.84 | 1483.96 | 1493.7 | 1503.44 | 1513.18 | 1522.54 | 1532.54 | 1542.53 | 1552.53 | 1562.13 | 1572.38 | 1582.64 | 1592.89 | 1602.75 | 1613.27 | 1623.79 | 1634.31 | 1644.42 | 1655.21 | 1666 | 1676.8 | 1687.17 | 1698.25 | 1709.32 | 1720.4 | 1731.04 | 1742.4 | 1753.76 | 1765.13 | 1776.05 | 1787.7 | 1799.36 | 1811.02 | 1822.22 | 1834.18 | 1846.14 | 1858.11 | 1869.6 | 1881.87 | 1894.14 | 1906.42 | 1918.21 | 1930.8 | 1943.39 | 1955.98 | 1968.08 | 1981 | 1993.92 | 2006.84 | 2019.25 | 2032.51 | 2045.76 | 2059.02 | 2071.75 | 2085.35 | 2098.95 | 2112.55 | 2125.62 | 2139.57 | 2153.52 | 2167.48 | 2180.89 | 2195.2 | 2209.52 | 2223.83 | 2237.59 | 2252.28 | 2266.96 | 2281.65 | 2295.77 | 2310.84 | 2325.9 | 2340.97 | 2355.46 | 2370.92 | 2386.38 | 2401.84 | 2416.7 | 2432.56 | 2448.42 | 2464.29 | 2479.53 | 2495.81 | 2512.08 | 2528.36 | 2544 | 2560.7 | 2577.4 | 2594.1 | 2610.14 | 2627.28 | 2644.41 | 2661.54 | 2678.01 | 2695.59 | 2713.16 | 2730.74 | 2747.64 | 2765.67 | 2783.71 | 2801.74 | 2819.07 | 2837.58 | 2856.08 | 2874.59 | 2892.37 | 2911.36 | 2930.34 | 2949.33 | 2967.57 | 2987.05 | 3006.53 | 3026.01 | 3044.73 | 3064.71 | 3084.7 | 3104.69 | 3123.89 | 3144.4 | 3164.9 | 3185.41 | 3205.11 | 3226.15 | 3247.19 | 3268.23 | 3288.45 | 3310.03 | 3331.62 | 3353.2 | 3373.95 | 3396.09 | 3418.24 | 3440.38 | 3461.67 | 3484.39 | 3507.11 | 3529.83 | 3551.67 | 3574.98 | 3598.3 | 3621.61 | 3644.01 | 3667.93 | 3691.85 | 3715.77 | 3738.76 | 3763.3 | 3787.84 | 3812.38 | 3835.97 | 3861.15 | 3886.33 | 3911.5 | 3935.7 | 3961.54 | 3987.37 | 4013.2 | 4038.03 | 4064.54 | 4091.04 | 4117.55 | 4143.02 | 4170.21 | 4197.41 | 4224.6 | 4250.74 | 4278.64 | 4306.54 | 4334.44 | 4361.26 | 4389.88 | 4418.51 | 4447.14 | 4474.65 | 4504.02 | 4533.39 | 4562.76 | 4590.99 | 4621.13 | 4651.26 | 4681.4 | 4710.36 | 4741.27 | 4772.19 | 4803.11 | 4832.82 | 4864.55 | 4896.27 | 4927.99 | 4958.48 | 4991.03 | 5023.57 | 5056.12 | 5087.4 | 5120.79 | 5154.19 | 5187.58 | 5219.67 | 5253.93 | 5288.19 | 5322.46 | 5355.38 | 5390.54 | 5425.69 | 5460.84 | 5494.62 | 5530.69 | 5566.76 | 5602.82 | 5637.48 | 5674.49 | 5711.49 | 5748.5 | 5784.06 | 5822.02 | 5859.99 | 5897.96 | 5934.44 | 5973.4 | 6012.35 | 6051.3 | 6088.74 | 6128.7 | 6168.67 | 6208.64 | 6247.05 | 6288.05 | 6329.06 | 6370.06 | 6409.47 | 6451.54 | 6493.61 | 6535.68 | 6576.11 | 6619.28 | 6662.45 | 6705.61 | 6747.09 | 6791.38 | 6835.67 | 6879.96 | 6922.52 | 6967.96 | 7013.4 | 7058.84 | 7102.5 | 7149.12 | 7195.75 | 7242.37 | 7287.17 | 7335 | 7382.83 | 7430.67 | 7476.64 | 7525.71 | 7574.79 | 7623.86 | 7671.03 | 7721.38 | 7771.73 | 7822.09 | 7870.47 | 7922.14 | 7973.8 | 8025.46 | 8075.11 | 8128.11 | 8181.12 | 8234.12 | 24468254.45
|  |  |  | Government Personnel | 1 | 26 | 30 | 26 | Planning Engineering and Design |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.0128 | 1.0255 | 1.0382 | 1.051 | 1.0607 | 1.0704 | 1.0802 | 1.0899 | 1.0983 | 1.1068 | 1.1152 | 1.1237 | 1.1324 | 1.1411 | 1.1498 | 1.1585 | 1.1675 | 1.1765 | 1.1854 | 1.1944 | 1.204 | 1.2135 | 1.2231 | 1.2326 | 1.2425 | 1.2524 | 1.2622 | 1.2721 | 1.2823 | 1.2924 | 1.3026 | 1.3128 | 1.3233 | 1.3338 | 1.3443 | 1.3548 | 1.366 | 1.3772 | 1.3883 | 1.3995 | 1.4107 | 1.4219 | 1.4331 | 1.4443 | 1.4559 | 1.4674 | 1.479 | 1.4905 | 1.5028 | 1.5151 | 1.5274 | 1.5397 | 1.552 | 1.5643 | 1.5767 | 1.589 | 1.6017 | 1.6144 | 1.6271 | 1.6398 | 1.6533 | 1.6669 | 1.6804 | 1.6939 | 1.7071 | 1.7202 | 1.7333 | 1.7464 | 1.76 | 1.7735 | 1.787 | 1.8006 | 1.8145 | 1.8285 | 1.8424 | 1.8564 | 1.8708 | 1.8852 | 1.8996 | 1.914 | 1.9288 | 1.9436 | 1.9584 | 1.9733 | 1.9896 | 2.0058 | 2.0221 | 2.0384 | 2.0547 | 2.071 | 2.0873 | 2.1036 | 2.1205 | 2.1373 | 2.1541 | 2.1709 | 2.1883 | 2.2057 | 2.223 | 2.2404 | 2.2583 | 2.2763 | 2.2942 | 2.3121 | 2.3306 | 2.3491 | 2.3676 | 2.3861 | 2.4052 | 2.4243 | 2.4434 | 2.4625 | 2.4822 | 2.5019 | 2.5216 | 2.5413 | 2.5616 | 2.5819 | 2.6022 | 2.6226 | 2.6436 | 2.6645 | 2.6855 | 2.7065 | 2.7281 | 2.7498 | 2.7714 | 2.7931 | 2.8154 | 2.8378 | 2.8601 | 2.8825 | 2.9055 | 2.9286 | 2.9517 | 2.9747 | 2.9985 | 3.0223 | 3.0461 | 3.0699 | 3.0945 | 3.119 | 3.1436 | 3.1681 | 3.1935 | 3.2188 | 3.2442 | 3.2695 | 3.2957 | 3.3218 | 3.348 | 3.3742 | 3.4011 | 3.4281 | 3.4551 | 3.4821 | 3.51 | 3.5378 | 3.5657 | 3.5936 | 3.6223 | 3.6511 | 3.6798 | 3.7085 | 3.7382 | 3.7679 | 3.7976 | 3.8272 | 3.8578 | 3.8885 | 3.9191 | 3.9497 | 3.9813 | 4.0129 | 4.0445 | 4.0761 | 4.1087 | 4.1413 | 4.1739 | 4.2065 | 4.2402 | 4.2738 | 4.3075 | 4.3411 | 4.3759 | 4.4106 | 4.4453 | 4.48 | 4.5159 | 4.5517 | 4.5876 | 4.6234 | 4.6604 | 4.6974 | 4.7344 | 4.7714 | 4.8095 | 4.8477 | 4.8859 | 4.924 | 4.9634 | 5.0028 | 5.0422 | 5.0816 | 5.1223 | 5.1629 | 5.2036 | 5.2442 | 5.2862 | 5.3281 | 5.3701 | 5.412 | 5.4553 | 5.4986 | 5.5419 | 5.5852 | 5.6299 | 5.6746 | 5.7193 | 5.7639 | 5.8101 | 5.8562 | 5.9023 | 5.9484 | 5.996 | 6.0436 | 6.0912 | 6.1387 | 6.1878 | 6.237 | 6.2861 | 6.3352 | 6.3859 | 6.4365 | 6.4872 | 6.5379 | 6.5902 | 6.6425 | 6.6948 | 6.7471 | 6.8011 | 6.8551 | 6.909 | 6.963 | 7.0187 | 7.0744 | 7.1301 | 7.1858 | 7.2433 | 7.3008 | 7.3583 | 7.4158 | 7.4751 | 7.5344 | 7.5938 | 7.6531 | 7.7143 | 7.7755 | 7.8368 | 7.898 | 7.9612 | 8.0244 | 8.0875 | 8.1507 | 8.2159 | 8.2811 | 8.3463 | 8.4116 | 8.4788 | 8.5461 | 8.6134 | 8.6807 | 8.7502 | 8.8196 | 8.8891 | 8.9585 | 9.0302 | 9.1018 | 9.1735 | 9.2452 | 9.3191 | 9.3931 | 9.4671 | 9.541 | 9.6173 | 9.6937 | 9.77 | 9.8463 | 9.9251 | 10.0039 | 10.0826 | 10.1614 | 10.2427 | 10.324 | 10.4053 | 10.4866 | 10.5705 | 10.6544 | 10.7383 | 10.8222 | 10.9087 | 10.9953 | 11.0819 | 11.1685 | 11.2578 | 11.3472 | 11.4365 | 11.5259 | 8.6444 | 5.7629
| Instructions for Feature Codes 30 and 31: In Cells F27 and F28 Enter the Table 1 class that is going to be used for the 30 and 31 accounts either class 1 or class 2. Inflation factors differ if work is to be performed by Government personnel or AE contractor. Class 1 is for government personnel and Class 2 is for everything else. Class 1 includes salary increases, step increases, health insurance, attrition rates, retirement, etc. Note: the Class 1 factor can be higher than the Class 2 factor, when the FEPCA formula is used by OMB to predict future raises, and this will affect the TPCS. In addition, EC11-2-XXX does not provide a historical index as it is only concerned with future projections. |  |  | Government Personnel | 1 | 27 | 31 | 27 | Construction Management |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1.0128 | 1.0255 | 1.0382 | 1.051 | 1.0607 | 1.0704 | 1.0802 | 1.0899 | 1.0983 | 1.1068 | 1.1152 | 1.1237 | 1.1324 | 1.1411 | 1.1498 | 1.1585 | 1.1675 | 1.1765 | 1.1854 | 1.1944 | 1.204 | 1.2135 | 1.2231 | 1.2326 | 1.2425 | 1.2524 | 1.2622 | 1.2721 | 1.2823 | 1.2924 | 1.3026 | 1.3128 | 1.3233 | 1.3338 | 1.3443 | 1.3548 | 1.366 | 1.3772 | 1.3883 | 1.3995 | 1.4107 | 1.4219 | 1.4331 | 1.4443 | 1.4559 | 1.4674 | 1.479 | 1.4905 | 1.5028 | 1.5151 | 1.5274 | 1.5397 | 1.552 | 1.5643 | 1.5767 | 1.589 | 1.6017 | 1.6144 | 1.6271 | 1.6398 | 1.6533 | 1.6669 | 1.6804 | 1.6939 | 1.7071 | 1.7202 | 1.7333 | 1.7464 | 1.76 | 1.7735 | 1.787 | 1.8006 | 1.8145 | 1.8285 | 1.8424 | 1.8564 | 1.8708 | 1.8852 | 1.8996 | 1.914 | 1.9288 | 1.9436 | 1.9584 | 1.9733 | 1.9896 | 2.0058 | 2.0221 | 2.0384 | 2.0547 | 2.071 | 2.0873 | 2.1036 | 2.1205 | 2.1373 | 2.1541 | 2.1709 | 2.1883 | 2.2057 | 2.223 | 2.2404 | 2.2583 | 2.2763 | 2.2942 | 2.3121 | 2.3306 | 2.3491 | 2.3676 | 2.3861 | 2.4052 | 2.4243 | 2.4434 | 2.4625 | 2.4822 | 2.5019 | 2.5216 | 2.5413 | 2.5616 | 2.5819 | 2.6022 | 2.6226 | 2.6436 | 2.6645 | 2.6855 | 2.7065 | 2.7281 | 2.7498 | 2.7714 | 2.7931 | 2.8154 | 2.8378 | 2.8601 | 2.8825 | 2.9055 | 2.9286 | 2.9517 | 2.9747 | 2.9985 | 3.0223 | 3.0461 | 3.0699 | 3.0945 | 3.119 | 3.1436 | 3.1681 | 3.1935 | 3.2188 | 3.2442 | 3.2695 | 3.2957 | 3.3218 | 3.348 | 3.3742 | 3.4011 | 3.4281 | 3.4551 | 3.4821 | 3.51 | 3.5378 | 3.5657 | 3.5936 | 3.6223 | 3.6511 | 3.6798 | 3.7085 | 3.7382 | 3.7679 | 3.7976 | 3.8272 | 3.8578 | 3.8885 | 3.9191 | 3.9497 | 3.9813 | 4.0129 | 4.0445 | 4.0761 | 4.1087 | 4.1413 | 4.1739 | 4.2065 | 4.2402 | 4.2738 | 4.3075 | 4.3411 | 4.3759 | 4.4106 | 4.4453 | 4.48 | 4.5159 | 4.5517 | 4.5876 | 4.6234 | 4.6604 | 4.6974 | 4.7344 | 4.7714 | 4.8095 | 4.8477 | 4.8859 | 4.924 | 4.9634 | 5.0028 | 5.0422 | 5.0816 | 5.1223 | 5.1629 | 5.2036 | 5.2442 | 5.2862 | 5.3281 | 5.3701 | 5.412 | 5.4553 | 5.4986 | 5.5419 | 5.5852 | 5.6299 | 5.6746 | 5.7193 | 5.7639 | 5.8101 | 5.8562 | 5.9023 | 5.9484 | 5.996 | 6.0436 | 6.0912 | 6.1387 | 6.1878 | 6.237 | 6.2861 | 6.3352 | 6.3859 | 6.4365 | 6.4872 | 6.5379 | 6.5902 | 6.6425 | 6.6948 | 6.7471 | 6.8011 | 6.8551 | 6.909 | 6.963 | 7.0187 | 7.0744 | 7.1301 | 7.1858 | 7.2433 | 7.3008 | 7.3583 | 7.4158 | 7.4751 | 7.5344 | 7.5938 | 7.6531 | 7.7143 | 7.7755 | 7.8368 | 7.898 | 7.9612 | 8.0244 | 8.0875 | 8.1507 | 8.2159 | 8.2811 | 8.3463 | 8.4116 | 8.4788 | 8.5461 | 8.6134 | 8.6807 | 8.7502 | 8.8196 | 8.8891 | 8.9585 | 9.0302 | 9.1018 | 9.1735 | 9.2452 | 9.3191 | 9.3931 | 9.4671 | 9.541 | 9.6173 | 9.6937 | 9.77 | 9.8463 | 9.9251 | 10.0039 | 10.0826 | 10.1614 | 10.2427 | 10.324 | 10.4053 | 10.4866 | 10.5705 | 10.6544 | 10.7383 | 10.8222 | 10.9087 | 10.9953 | 11.0819 | 11.1685 | 11.2578 | 11.3472 | 11.4365 | 11.5259 | 8.6444 | 5.7629
|  |  |  | 1 | Government Personnel |  |  |  | Table 1 FY27 Table 1 Class 1 Factors | 31 March 2025 | FY QTRS 1980Q2: 1; FY QTRS 1981Q2: 1; FY QTRS 1982Q2: 1; FY QTRS 1983Q2: 1; FY QTRS 1984Q2: 1; FY QTRS 1985Q2: 1; FY QTRS 1986Q2: 1; FY QTRS 1987Q2: 1; FY QTRS 1988Q2: 1; FY QTRS 1989Q2: 1; FY QTRS 1990Q2: 1; FY QTRS 1991Q2: 1; FY QTRS 1992Q2: 1; FY QTRS 1993Q2: 1; FY QTRS 1994Q2: 1; FY QTRS 1995Q2: 1; FY QTRS 1996Q2: 1; FY QTRS 1997Q2: 1; FY QTRS 1998Q2: 1; FY QTRS 1999Q2: 1; FY QTRS 2000Q2: 1; FY QTRS 2001Q2: 1; FY QTRS 2002Q2: 1; FY QTRS 2003Q2: 1; FY QTRS 2004Q2: 1; FY QTRS 2005Q2: 1; FY QTRS 2006Q2: 1; FY QTRS 2007Q2: 1; FY QTRS 2008Q2: 1; FY QTRS 2009Q2: 1; FY QTRS 2010Q2: 1; FY QTRS 2011Q2: 1; FY QTRS 2012Q2: 1; FY QTRS 2013Q2: 1; FY QTRS 2014Q2: 1; FY QTRS 2015Q2: 1; FY QTRS 2016Q2: 1; FY QTRS 2017Q2: 1; FY QTRS 2018Q2: 1; FY QTRS 2019Q2: 1; FY QTRS 2020Q2: 1; FY QTRS 2021Q2: 1; FY QTRS 2022Q2: 1; FY QTRS 2023Q2: 1; FY QTRS 2024Q2: 5.1%; FY QTRS 2025Q2: 3.7%; FY QTRS 2026Q2: 3.1%; FY QTRS 2027Q2: 3.1%; FY QTRS 2028Q2: 3.1%; FY QTRS 2029Q2: 3.2%; FY QTRS 2030Q2: 3.2%; FY QTRS 2031Q2: 3.2%; FY QTRS 2032Q2: 3.2%; FY QTRS 2033Q2: 3.3%; FY QTRS 2034Q2: 3.2%; FY QTRS 2035Q2: 3.2%; FY QTRS 2036Q2: 3.3%; FY QTRS 2037Q2: 3.2%; FY QTRS 2038Q2: 3.2%; FY QTRS 2039Q2: 3.3%; FY QTRS 2040Q2: 3.1%; FY QTRS 2041Q2: 3.1%; FY QTRS 2042Q2: 3.1%; FY QTRS 2043Q2: 3.1%; FY QTRS 2044Q2: 3.1%; FY QTRS 2045Q2: 3.3%; FY QTRS 2046Q2: 3.2%; FY QTRS 2047Q2: 3.2%; FY QTRS 2048Q2: 3.2%; FY QTRS 2049Q2: 3.2%; FY QTRS 2050Q2: 3.2%; FY QTRS 2051Q2: 3.2%; FY QTRS 2052Q2: 3.2%; FY QTRS 2053Q2: 3.2%; FY QTRS 2054Q2: 3.2%; FY QTRS 2055Q2: 3.2%; FY QTRS 2056Q2: 3.2%; FY QTRS 2057Q2: 3.2%; FY QTRS 2058Q2: 3.2%; FY QTRS 2059Q2: 3.2%; FY QTRS 2060Q2: 3.2%; FY QTRS 2061Q2: 3.2%; FY QTRS 2062Q2: 3.2%; FY QTRS 2063Q2: 3.2%; FY QTRS 2064Q2: 3.2%; FY QTRS 2065Q2: 3.2%; FY QTRS 2066Q2: 3.2%; FY QTRS 2067Q2: 3.2%; FY QTRS 2068Q2: 3.2%; FY QTRS 2069Q2: 3.2%; FY QTRS 2070Q2: 3.2%; FY QTRS 2071Q2: 3.2%; FY QTRS 2072Q2: 3.2%; FY QTRS 2073Q2: 3.2%; FY QTRS 2074Q2: 3.2%; FY QTRS 2075Q2: 3.2%; FY QTRS 2076Q2: 3.2%; FY QTRS 2077Q2: 3.2%; FY QTRS 2078Q2: 3.2%; FY QTRS 2079Q2: 3.2%; FY QTRS 2080Q2: 3.2%; FY QTRS 2081Q2: 3.2%; FY QTRS 2082Q2: 3.2%; FY QTRS 2083Q2: 3.2%; FY QTRS 2084Q2: 3.2%; FY QTRS 2085Q2: 3.2%; FY QTRS 2086Q2: 3.2%; FY QTRS 2087Q2: 3.2%; FY QTRS 2088Q2: 3.2%; FY QTRS 2089Q2: 3.2%; FY QTRS 2090Q2: 3.2%; FY QTRS 2091Q2: 3.2%; FY QTRS 2092Q2: 3.2%; FY QTRS 2093Q2: 3.2%; FY QTRS 2094Q2: 3.2%; FY QTRS 2095Q2: 3.2%; FY QTRS 2096Q2: 3.2%; FY QTRS 2097Q2: 3.2%; FY QTRS 2098Q2: 3.2%; FY QTRS 2099Q2: 3.2%; FY QTRS 2100Q2: 3.2%
|  |  |  | 2 | AE Contractor |  |  |  | Table 1 FY27 Table 1 Class 2 Factors | 31 March 2025 | FY QTRS 1980Q2: 1; FY QTRS 1981Q2: 1; FY QTRS 1982Q2: 1; FY QTRS 1983Q2: 1; FY QTRS 1984Q2: 1; FY QTRS 1985Q2: 1; FY QTRS 1986Q2: 1; FY QTRS 1987Q2: 1; FY QTRS 1988Q2: 1; FY QTRS 1989Q2: 1; FY QTRS 1990Q2: 1; FY QTRS 1991Q2: 1; FY QTRS 1992Q2: 1; FY QTRS 1993Q2: 1; FY QTRS 1994Q2: 1; FY QTRS 1995Q2: 1; FY QTRS 1996Q2: 1; FY QTRS 1997Q2: 1; FY QTRS 1998Q2: 1; FY QTRS 1999Q2: 1; FY QTRS 2000Q2: 1; FY QTRS 2001Q2: 1; FY QTRS 2002Q2: 1; FY QTRS 2003Q2: 1; FY QTRS 2004Q2: 1; FY QTRS 2005Q2: 1; FY QTRS 2006Q2: 1; FY QTRS 2007Q2: 1; FY QTRS 2008Q2: 1; FY QTRS 2009Q2: 1; FY QTRS 2010Q2: 1; FY QTRS 2011Q2: 1; FY QTRS 2012Q2: 1; FY QTRS 2013Q2: 1; FY QTRS 2014Q2: 1; FY QTRS 2015Q2: 1; FY QTRS 2016Q2: 1; FY QTRS 2017Q2: 1; FY QTRS 2018Q2: 1; FY QTRS 2019Q2: 1; FY QTRS 2020Q2: 1; FY QTRS 2021Q2: 1; FY QTRS 2022Q2: 1; FY QTRS 2023Q2: 1; FY QTRS 2024Q2: 3%; FY QTRS 2025Q2: 2.6%; FY QTRS 2026Q2: 2.6%; FY QTRS 2027Q2: 2.6%; FY QTRS 2028Q2: 2.6%; FY QTRS 2029Q2: 2.6%; FY QTRS 2030Q2: 2.6%; FY QTRS 2031Q2: 2.6%; FY QTRS 2032Q2: 2.6%; FY QTRS 2033Q2: 2.6%; FY QTRS 2034Q2: 2.6%; FY QTRS 2035Q2: 2.6%; FY QTRS 2036Q2: 2.6%; FY QTRS 2037Q2: 2.6%; FY QTRS 2038Q2: 2.6%; FY QTRS 2039Q2: 2.6%; FY QTRS 2040Q2: 2.6%; FY QTRS 2041Q2: 2.6%; FY QTRS 2042Q2: 2.6%; FY QTRS 2043Q2: 2.6%; FY QTRS 2044Q2: 2.6%; FY QTRS 2045Q2: 2.6%; FY QTRS 2046Q2: 2.6%; FY QTRS 2047Q2: 2.6%; FY QTRS 2048Q2: 2.6%; FY QTRS 2049Q2: 2.6%; FY QTRS 2050Q2: 2.6%; FY QTRS 2051Q2: 2.6%; FY QTRS 2052Q2: 2.6%; FY QTRS 2053Q2: 2.6%; FY QTRS 2054Q2: 2.6%; FY QTRS 2055Q2: 2.6%; FY QTRS 2056Q2: 2.6%; FY QTRS 2057Q2: 2.6%; FY QTRS 2058Q2: 2.6%; FY QTRS 2059Q2: 2.6%; FY QTRS 2060Q2: 2.6%; FY QTRS 2061Q2: 2.6%; FY QTRS 2062Q2: 2.6%; FY QTRS 2063Q2: 2.6%; FY QTRS 2064Q2: 2.6%; FY QTRS 2065Q2: 2.6%; FY QTRS 2066Q2: 2.6%; FY QTRS 2067Q2: 2.6%; FY QTRS 2068Q2: 2.6%; FY QTRS 2069Q2: 2.6%; FY QTRS 2070Q2: 2.6%; FY QTRS 2071Q2: 2.6%; FY QTRS 2072Q2: 2.6%; FY QTRS 2073Q2: 2.6%; FY QTRS 2074Q2: 2.6%; FY QTRS 2075Q2: 2.6%; FY QTRS 2076Q2: 2.6%; FY QTRS 2077Q2: 2.6%; FY QTRS 2078Q2: 2.6%; FY QTRS 2079Q2: 2.6%; FY QTRS 2080Q2: 2.6%; FY QTRS 2081Q2: 2.6%; FY QTRS 2082Q2: 2.6%; FY QTRS 2083Q2: 2.6%; FY QTRS 2084Q2: 2.6%; FY QTRS 2085Q2: 2.6%; FY QTRS 2086Q2: 2.6%; FY QTRS 2087Q2: 2.6%; FY QTRS 2088Q2: 2.6%; FY QTRS 2089Q2: 2.6%; FY QTRS 2090Q2: 2.6%; FY QTRS 2091Q2: 2.6%; FY QTRS 2092Q2: 2.6%; FY QTRS 2093Q2: 2.6%; FY QTRS 2094Q2: 2.6%; FY QTRS 2095Q2: 2.6%; FY QTRS 2096Q2: 2.6%; FY QTRS 2097Q2: 2.6%; FY QTRS 2098Q2: 2.6%; FY QTRS 2099Q2: 2.6%; FY QTRS 2100Q2: 2.6%
Enter "updating factor" 1 and 2 for previous year, current year, and projected years. Historical years, change to 1.00.
Note on J30: Table 1 Factors are yearly factors for inflating costs to future values and do not include historical rates. Rates will be shown in the first calendar year quarter. Values will be changed to 1.00 for quarters where CWCCIS has a historical basis.
Note on J31: Table 1 Factors are yearly factors for inflating costs to future values and do not include historical rates. Rates will be shown in the first calendar year quarter. Values will be changed to 1.00 for quarters where CWCCIS has a historical basis.

## Midpoint Calculator
Feature | 07 POWER PLANT |  |  |  |  | NOT USED |  | Days
| Month | Day | Year | CWCCIS | 1 | 02 RELOCATIONS | January | 31
Construction Start | 10 | 12 | 2024 | 2025Q1 | 2 | 03 RESERVOIRS | February | 28.25 | Use this sheet to determine the midpoint of construction.
Construction End | 3 | 12 | 2030 | 2030Q2 | 3 | 04 DAMS | March | 31
Midpoint | 6 | 27 | 2027 | 2027Q3 | 4 | 05 LOCKS | April | 30 | Cells with gray fill and blue text are input cells.
Feature | NOT USED |  |  |  | 5 | 06 FISH & WILDLIFE FACILITIES | May | 31
| Month | Day | Year | CWCCIS | 6 | 07 POWER PLANT | June | 30 | Cells with yellow fill are output cells.
Construction Start | 1 | 1 | 2000 | 2000Q2 | 7 | 08 ROADS, RAILROADS & BRIDGES | July | 31
Construction End | 1 | 1 | 2001 | 2001Q2 | 8 | 09 CHANNELS & CANALS | August | 31
Midpoint | 7 | 2 | 2000 | 2000Q4 | 9 | 10 BREAKWATER & SEAWALLS | September | 30
Feature | NOT USED |  |  |  | 10 | 11 LEVEES & FLOODWALLS | October | 31
| Month | Day | Year | CWCCIS | 11 | 12 NAVIGATION PORTS & HARBORS | Novermber | 30
Construction Start | 1 | 1 | 2000 | 2000Q2 | 12 | 13 PUMPING PLANT | December | 31
Construction End | 1 | 1 | 2001 | 2001Q2 |  | 14 RECREATION FACILITIES
Midpoint | 7 | 2 | 2000 | 2000Q4 |  | 15 FLOODWAY CONTROL & DIVERSION STRUCTURE
Feature | NOT USED |  |  |  |  | 16 BANK STABILIZATION
| Month | Day | Year | CWCCIS |  | 17 BEACH REPLENISHMENT
Construction Start | 1 | 1 | 2000 | 2000Q2 |  | 18 CULTURAL RESOURCE PRESERVATION
Construction End | 1 | 1 | 2001 | 2001Q2 |  | 19 BUILDINGS, GROUNDS & UTILITIES
Midpoint | 7 | 2 | 2000 | 2000Q4 |  | 20 PERMANENT OPERATING EQUIPMENT
Feature | NOT USED |  |  |  |  | 30 Planning Engineering and Design
| Month | Day | Year | CWCCIS |  | 31 Construction Management
Construction Start | 1 | 1 | 2000 | 2000Q2
Construction End | 1 | 1 | 2001 | 2001Q2
Midpoint | 7 | 2 | 2000 | 2000Q4
Feature | NOT USED
| Month | Day | Year | CWCCIS
Construction Start | 1 | 1 | 2000 | 2000Q2
Construction End | 1 | 1 | 2001 | 2001Q2
Midpoint | 7 | 2 | 2000 | 2000Q4
Feature | NOT USED
| Month | Day | Year | CWCCIS
Construction Start | 1 | 1 | 2000 | 2000Q2
Construction End | 1 | 1 | 2001 | 2001Q2
Midpoint | 7 | 2 | 2000 | 2000Q4