## Documents
ESTIMATE PRODUCTS |  |  |  |  | Review for decision document estimates, Feasibility estimates thru IGE
Project Title & Location: |  |  |  |  | Test Title | REVIEW COMMENTS
Project Review Phase: |  |  |  |  | document phase related to design, report, estimate
Product Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
KEY DOCUMENTS SUPPORTING ATR AND COMMENTS
ER 1105-2-100, Planning Guidance Notebook.
ER 1110-2-1150, Engineering and Design for Civil Works Projects.
ER 1110-1-1300, Cost Engineering Policy and General Requirements.
ER 1110-2-1302, Civil Works Cost Engineering.
EM 1110-2-1304, Civil Works Construction Cost Index System (CWCCIS).
ETL 1110-2-573, Construction Cost Estimating Guide for Civil Works.
Cost Dx Website: http://www.nww.usace.army.mil/html/OFFICES/Ed/C/default.asp
Y | N | N/P | N/A |  | REVIEW CATEGORIES
|  |  |  | DOC | DOCUMENTS PROVIDED FOR ATR
|  |  |  | DOC 1 | Report: As a minimum, the Main Report, the Engineering Appendix, Cost Appendix.
|  |  |  | DOC 2 | Scoping documents such as drawings, presentations, photos.
|  |  |  | DOC 3 | Supporting Detailed Estimates in MCACES MII and CEDEP dredge estimates in electronic format.
|  |  |  | DOC 4 | Construction Schedule.
|  |  |  | DOC 5 | Total Project Schedule, all Features (PED, Acquisiton, and Construction).
|  |  |  | DOC 6 | Cost and Schedule Risk Analysis (>$40M) or basis for contingency when <$40M.
|  |  |  | DOC 7 | CSRA Report documenting the process.
|  |  |  | DOC 8 | Total Project Cost Summary (TPCS).
|  |  |  | DOC 9 | Record of DQC - District Quality Control.
|  |  |  | DOC 10 | Quantity Take-offs (details and summary).
|  |  |  | SC | SCOPING DOCUMENTS
|  |  |  | SC 1 | Scoping documents are adequately developed to the design phase in accordance with ER 1110-2-1150, presenting the Main Report, plan formulation and recommended plan, related scope and cost appendixes, risk analyses, etc.
|  |  |  | SC 2 | Adequate scoping documents have been provided to convey a thorugh and confident understanding of the project scope.
|  |  |  | SC 2 | The scoping documents are accurately portrayed within the estimates.
|  |  |  | SC 3 | Reviewer is confident of scope captured within the estimate, schedule and risk review.

## Estimate
Project Title & Location: |  |  |  |  | Test Title | REVIEW COMMENTS
Project Review Phase: |  |  |  |  | document phase related to design, report, estimate
Product Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES
PROJECT NOTES - (General Construction Details and Narrative)
|  |  |  | NOTE | Basis of Cost Estimate Notes | REVIEW COMMENTS
|  |  |  | NOTE 1 | Project and Top Folder notes notes present a clear understanding and scope definition.
|  |  |  | NOTE 2 | Scope presented in the project notes is consistent with the scope of the documents for the corresponding plan.
|  |  |  | NOTE 3 | Major project construction features clearly identified in the estimate subfolders.
|  |  |  | NOTE 4 | Top Folder notes clarify major assumptions such as acquisition strategy, expected bid competition, prime and subcontractor assignments, major cost quotes, major construction processes, construction phasing and/or sequencing.
|  |  |  | NOTE 5 | Top Folder notes address significant or high-risk cost items in the project scope.
|  |  |  | NOTE 6 | Notes are adequate to convey project scope and estimate assumptions.
[5 empty] | Construction Estimate Notes on Critical Costs | REVIEW COMMENTS
|  |  |  | NOTE 8 | General assumptions noted in the project notes and whether they seem reasonable.
|  |  |  | NOTE 9 | Folder notes provide basis of estimate related to assumptions, quotes, and historical data?
|  |  |  | NOTE 10 | Site and project access considered and presented in the notes.
|  |  |  | NOTE 11 | Critical material sources identified and supported by research.
|  |  |  | NOTE 12 | Unusual construction conditions considered and documented (e.g., studies, geotechnical data, borrow sources, water and water diversion, and weather).
|  |  |  | NOTE 13 | Unique construction techniques considered, documented and reasonable.
|  |  |  | NOTE 14 | Environmental concerns addressed impacting construction activities.
|  |  |  | NOTE 15 | Acquisition Plan identified and matches the estimate structure.
|  |  |  | NOTE 16 | Subcontracting plan and subcontract crafts identified.
|  |  |  | NOTE 17 | Effective dates for pricing labor, equipment, and material are current.
|  |  |  | EST | GENERAL ESTIMATE LAYOUT - Title Structure (Work Breakdown Structure)
|  |  |  | EST 1 | Estimate developed in proper Work Breakdown Structure (WBS) format in accordance with all guidelines (ETL 1110-2-573).
|  |  |  | EST 2 | Folder title structure and the descriptions adequate to determine what is being estimated.
|  |  |  | EST 3 | WBS adequately reflects all project scope
|  |  |  | EST 4 | Prime and subcontractor assignments appear reasonable.
|  |  |  | EST 5 | Major Folder quantity units and unit proces appear reasonable.
|  |  |  | EST 6 | Major folders developed to support a coherent construction schedule development.
|  |  |  | EST 7 | Major construction features supported by quantity take-offs and appear reasonable.
CONSTRUCTION ESTIMATE DETAILS
|  |  |  | MISC | Miscellaneous Estimate Details | REVIEW COMMENTS
|  |  |  | MISC 1 | Estimate covers the many minor cost items, that together, can add significantly to the project.
|  |  |  | MISC 2 | Costs include any potential Hazardous, Toxic, and Radioactive Waste (HTRW) concerns.
|  |  |  | MISC 3 | Limited use of generic Cost Book unit prices for critical cost items that could undermine the total cost accuracy.
|  |  |  | MISC 4 | Limted use of Lump Sum, Each or Allowance items that do not accurately convey scope or pricing.
|  |  |  | MISC 5 | Limited use of over-ridden unit or detailed costs that results in lost confidence and greater risks.
|  |  |  | LAB | Labor | REVIEW COMMENTS
|  |  |  | LAB 1 | Current labor rates used that match the estimate date and location where the work is occurring.
|  |  |  | LAB 2 | Actual labor rates determined to be reasonable, considering the type of work and other site factors.
|  |  |  | LAB 3 | Overtime application appears justified, reasonable and logical for major work items.
|  |  |  | LAB 4 | If overtime is used, the direct cost markup factors correctly entered and applied.
|  |  |  | LAB 5 | Application of Payroll Tax and Insurance (PT&I) for the selected Contractors: State Unemployment Insurance (SUI) based on the state in which the work is occurring vs. using the AVG default.
|  |  |  | LAB 6 | Under PT&I for Workmen’s Compensation Insurance (WCI), was the selected Contractor Class based on the actual work to be performed vs. using the default for Concrete Work?
|  |  |  | LAB 7 | Labor rates take into consideration potential labor shortages and includes any necessary subsistence or per diem for critical labor elements.
|  |  |  | LAB 8 | Labor consideration made in mobilization and demobilization efforts.
|  |  |  | LAB 9 | Correct labor rates used for Building, Heavy, Highway, Residential.
|  |  |  | LAB 10 | Marine Work – Work performed on or over navigable waterways addresses Longshoreman and Harbor Workers Act insurance, if required by the state.
|  |  |  | LAB 11 | Dredging – Labor rate database updated to reflect the latest wage rates available for dredging work at the location.
|  |  |  | LAB 12 | Dredging – Labor rates appear reasonable, based on the location and type of plant performing the work.
|  |  |  | EQ | Equipment | REVIEW COMMENTS
|  |  |  | EQ 1 | Correct regional equipment rates used for the location where the work is occurring.
|  |  |  | EQ 2 | Database updated to reflect the latest fuel prices for the work site.
|  |  |  | EQ 3 | Critical equipment choices, size and rates appear reasonable, considering work type and site conditions.
|  |  |  | EQ 4 | Rates for Average, Difficult, Severe or Standby are correctly applied and justified within the notes.
|  |  |  | EQ 5 | Standby rates used, in order to ensure that Ownership Costs for equipment were covered for the normal 40 hour work week.
|  |  |  | EQ 6 | Standby rates included for equipment mobilization and demobilization.
|  |  |  | EQ 7 | Rental rates used for equipment not normally owned by the selected contractor. Were operating costs for rented equipment included?
|  |  |  | EQ 8 | If warranted, were other factors (such as the Cost of Money) updated to reflect current conditions?
|  |  |  | EQ 9 | Dredging – Based on the actual site conditions, quantities, disposal areas, and schedule: was the selected dredge plant determined to be appropriate for the contract at hand?
|  |  |  | EQ 10 | Dredging - Appropriate dredge, dredge size and number of dredges reasonable for the work.
|  |  |  | EQ 11 | Dredging – Dredge plant costs based on the current CEDEP database.
|  |  |  | EQ 12 | Dredging - Was the dredge plant database, contained in CEDEP, reviewed and were plant costs determined to be reasonable based on the proposed work?
|  |  |  | EQ 13 | Dredging – Include costs for dredge plant during periods of standby or non-working hours and weather impacts.
|  |  |  | CP | Crews & Productivity | REVIEW COMMENTS
|  |  |  | CP 1 | Critical crew composition and productivity appear reasonable for the major work items.
|  |  |  | CP 2 | Productivity efficiencies or inefficiencies considered and explained.
|  |  |  | CP 3 | Critical project productivity rates appear reasonable. Notes describe logic.
|  |  |  | CP 4 | Heavy equipment crews include the supporting labor and equipment necessary to perform the task at the selected productivity.
|  |  |  | CP 5 | For large earthwork projects, crew assemblies and productivities for excavation, load, haul, placement, compaction and disposal correlate.
|  |  |  | CP 6 | Dredging – crew productivity and any applied efficiency factors adequately justified in the estimate.
|  |  |  | MAT | Materials | REVIEW COMMENTS
|  |  |  | MAT 1 | Major quantities supported by a quantity take-off document.
|  |  |  | MAT 2 | Major, critical or volatile materials and quantities identified at the detail level.
|  |  |  | MAT 3 | Estimate correctly includes State Sales Tax or Gross Receipts Tax to materials and supplies purchased for the contract.
|  |  |  | MAT 4 | Estimate notes identify the source of major material quotes, with source, name and date of quote (escalation concern).
|  |  |  | MAT 5 | Estimate makes adjustments for loss due to handling, placement, cutting, transportation, contamination, etc. Notes document adjustments.
|  |  |  | MAT 6 | Earthwork quantities indentified based on BCY for excavated material, LCY for hauled material, ECY for placed material.
|  |  |  | MAT 7 | Earthwork quantities make reasonable adjustments between BCY, LCY and ECY.
|  |  |  | MAT 8 | Line item note description for material purchase indicates if shipping is included for major items.
|  |  |  | MOB | Mobilization - Preparatory Work, Demobilization – Cleanup | REVIEW COMMENTS
|  |  |  | MOB 1 | Mobilization and demobilization costs are detailed or appropriate.
|  |  |  | MOB 2 | Total mobilization and demobilization cost appear reasonable.
|  |  |  | MOB 3 | Multiple mobilizations considered for longer projects impacted by weather or environmental restrictions.
|  |  |  | MOB 4 | Dredge work: Estimate includes preparation of dredge attendant plant for transfer, the cost to move all plant and equipment return of tug or towing vessel, and preparation of the plant to start work.
|  |  |  | MOB 5 | Dredge Work: Project and estimate clearly include a construction support site.
|  |  |  | MOB 6 | Dredge Work: Estimate includes all costs to secure machinery and equipment for storage.
|  |  |  | MOB 7 | Dredging - Pipeline mobilization, assembly and relocation for surface and underwater appropriately considered.
|  |  |  | SUB | Subcontracting | REVIEW COMMENTS
|  |  |  | SUB 1 | Subcontractor assignments and markups reasonable for the tasks assigned.
|  |  |  | SUB 2 | Estimate identifies subcontract quotes and addresses markup applications with the quotes.
|  |  |  | SUB 3 | Appropriate consideration has been made in addressing multi-tier subcontracting for specialty items.
|  |  |  | PR | Prime Contractor | REVIEW COMMENTS
|  |  |  | PR 1 | Prime contractor(s) has been aptly assigned with reasonable markups.
|  |  |  | PR 2 | Are appropriate taxes included or excluded as may be required?
|  |  |  | PR 3 | Field office overhead reasonable for this project?
|  |  |  | PR 4 | Field Office Overhead includes mobilization if not identified elsewhere.
|  |  |  | PR 5 | Home office overhead appears reasonable for the type of prime contractor specialty.
|  |  |  | PR 6 | Profit appears reasonable and based on the weighted guideline method or justified by other means.
|  |  |  | PR 7 | Bond appears reasonable.

## Schedule
Project Title & Location: |  |  |  |  | Test Title | REVIEW COMMENTS
Project Review Phase: |  |  |  |  | document phase related to design, report, estimate
Product Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES
|  |  |  | SCH | SCHEDULES
|  |  |  | CS | Construction Schedule | REVIEW COMMENTS
|  |  |  | CS 1 | Reflects the estimate and identifies critical aspects of the project scope and construction activities.
|  |  |  | CS 2 | Key milestones are depicted.
|  |  |  | CS 3 | Reflects reasonable logic of activities performed.
|  |  |  | CS 4 | Indicates a likely critical path.
|  |  |  | CS 5 | Reflects the estimate productivities for critical path items.
|  |  |  | CS 6 | Presents sequential and parallel activities where reasonable.
|  |  |  | CS 7 | Makes distinction between single shift, and double shift.
|  |  |  | CS 8 | Takes into consideration overtime where applicable.
|  |  |  | CS 9 | Depicts critical or time-sensitive orders or procurements.
|  |  |  | CS 10 | Considers weather issues, environmental restrictions, winter construction.
|  |  |  | CS 11 | Considers project ramp up, mobilization and demobilization.
|  |  |  | PS | Project Schedule | REVIEW COMMENTS
|  |  |  | PS 1 | The Project Schedule in the decision document report includes all FEATURE activities; i.e. review and approval, planning, engineering and design, procurement, construction, close-out and turn-over.
|  |  |  | PS 2 | The project schedule clearly presents reasonable dates to determine inflation based on escalation indexes, i.e., the activity beginning date or the activity midpoint?

## CSRA-Contingency
Project Title & Location: |  |  |  |  | Test Title | REVIEW COMMENTS
Project Review Phase: |  |  |  |  | document phase related to design, report, estimate
Product Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES
RISK-BASED CONTINGENCY
|  |  |  | CSRA | Formal Cost and Schedule Risk Analysis (CSRA for >$40M) | REVIEW COMMENTS
|  |  |  | CSRA 1 | CSRA structure and process follows the Cost Dx guidance.
|  |  |  | CSRA 2 | CSRA model provided in electronic format using Excel and Crystal Ball softwares.
|  |  |  | CSRA 3 | CSRA Report follows Cost Dx template.
|  |  |  | CSRA 4 | CSRA considers total cost and total schedule, all features.
|  |  |  | CSRA 5 | Risk Register developed by major PDT members for all project Features.
|  |  |  | CSRA 6 | Organizational and PM risks considered.
|  |  |  | CSRA 7 | Contract Acquisition risks considered.
|  |  |  | CSRA 8 | Technical risks considered.
|  |  |  | CSRA 9 | Scope quality and detail addressed.
|  |  |  | CSRA 10 | Lands and Damages and Relocations considered.
|  |  |  | CSRA 11 | Regualtory and Environmental risks considered.
|  |  |  | CSRA 12 | Construction risks considered.
|  |  |  | CSRA 13 | Estimate and schedule accuracy risks considered.
|  |  |  | CSRA 14 | Volatile pricing and extreme escalation considered.
|  |  |  | CSRA 15 | Material availability and transport considered.
|  |  |  | CSRA 16 | External risks: funding, stakeholders, labor, weather, opposition, bidding competition considered.
|  |  |  | CSRA 17 | Does the CSRA consider opportunities such as VE and alternatives?
|  |  |  | CSRA 18 | Risk register tracks logically from Concerns, PDT Discussions, Likelihood and Impacts to a reflective Risk Level.
|  |  |  | CSRA 19 | Risk model considers any risk duplications and correlations between cost and schedule risk events?
|  |  |  | CSRA 20 | Risk event correlations have been minimized.
|  |  |  | CSRA 21 | CSRA model includes the moderate and high risks.
|  |  |  | CSRA 22 | CSRA considers both internal and external risks.
|  |  |  | CSRA 23 | CSRA supported by market research and documented assumptions.
|  |  |  | CSRA 24 | CSRA results traceable back to the PDT Risk Events.
|  |  |  | CSRA 25 | CSRA model variance distributions appear reasonable w/ backup assumptions.
|  |  |  | CSRA 26 | Contingency value based upon an 80% confidence level.
|  |  |  | CSRA 27 | Contingencies appear reasonable based on project complexity and ATR findings.
|  |  |  | RB | Risk Based Contingency Development for <$40M | REVIEW COMMENTS
|  |  |  | RB 1 | Supported by a studied development per major Feature (not just a value w/o basis).
|  |  |  | RB 2 | Developed as a weighted aggregate of major construction features.
|  |  |  | RB 3 | Considers other factors other than just technical design and construction (see CSRA above).
|  |  |  | RB 4 | Considers external risk potentials (see CSRA External Risks above)
|  |  |  | CV | Contingency Value | REVIEW COMMENTS
|  |  |  | CV 1 | Rates appear reasonable for each major Feature item?
|  |  |  | CV 2 | Overall rate appears reasonable based on reviewers knowledge of project scope and estimates.

## TPCS
Project Title & Location: |  |  |  |  | Test Title | REVIEW COMMENTS
Project Review Phase: |  |  |  |  | document phase related to design, report, estimate
Product Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES
|  |  |  | TPCS | TOTAL PROJECT COST SUMMARY in Current Dollars (first column set)
|  |  |  | TPCS 1 | Proper TPCS format (ETL 1110-2-573).
|  |  |  | TPCS 2 | Price level date shown is consistent with the estimate preparation date.
|  |  |  | TPCS 3 | All project-related Civil Works WBS Features depicted.
|  |  |  | TPCS 4 | Base costs reflects the esitmate development in current dollars.
|  |  |  | TPCS 5 | Summary page roll up supported by sub-project calculations.
|  |  |  | TPCS 6 | Costs reasonable for PED (30 Feature). Note: percentages are sometimes used to develop these costs.
|  |  |  | TPCS 7 | 30 Feature clearly includes costs for PM, P&E, E&D, Reviews & VE, Contracting, reprographics, EDC, Planning during construction.
|  |  |  | TPCS 8 | Costs reasonable for Construction Management (31 Feature Code). Note: percentages are sometimes used to develop these costs.
|  |  |  | TPCS 9 | Contingencies shown separately for each Feature.
|  |  |  | TPCS 10 | Contingency rates match the risk based contingency results (commonly the 80 percent confidence level).
TOTAL PROJECT COST SUMMARY in Current Dollars (second column set)
|  |  |  | TPCS 11 | Depicts budget year for decision document funding request.
|  |  |  | TPCS 12 | Includes escalation from estimate date to budget year: EM 1110-2-1304, Civil Works Construction Cost Index System (CWCCIS).
|  |  |  | TPCS 13 | Captures total project cost for all Featrures to budget year.
TOTAL PROJECT COST Inflated to Fully Funded Estimate (third column set)
|  |  |  | TPCS 14 | Escalation dates and rates shown for each inflated Feature.
|  |  |  | TPCS 15 | Escalation dates consistent with the project schedule.
|  |  |  | TPCS 16 | Escalation based on price indexes from the current CWCCIS, EM 1110-2-1304 and correctly applied.
|  |  |  | TPCS 17 | Section 902 Limit ONLY; If lands and damages are inflated, is the escalation for inflation based on the Consumer Price Index? (ref. ER 1105-2-100, Determining Section 902 Limit)
TOTAL PROJECT COST SUMMARY - Federal and Non-Federal Costs
|  |  |  | TPCS 18 | Federal and non-Federal cost share percentages shown.
|  |  |  | TPCS 19 | Project cost share percent consistent with the Cost Sharing Agreement?
|  |  |  | TPCS 20 | If applicable, is the cost/value of non-Federal in-kind services shown?
|  |  |  | TPCS 21 | Cost shares calculated correctly.
|  |  |  | TPCS 22 | Signature blocks for PM, Cost Chief, Real Estate Chief (ER 1110-2-1302)

## Reports
Project Title & Location: |  |  |  |  | Test Title | REVIEW COMMENTS
Project Review Phase: |  |  |  |  | document phase related to design, report, estimate
Product Date: |  |  |  |  | 2009-08-13
Reviewer Name & Phone: |  |  |  |  | John Doe 1-800-555-1234
Review Date: |  |  |  |  | 2009-08-28
Y | N | N/P | N/A |  | REVIEW CATEGORIES
REPORTS - Basic Information for Reviewer – Scope and Form
|  |  |  | MR | Draft Main Report, General | REVIEW COMMENTS
|  |  |  | MR 1 | Complete report document provided for ATR. As a minimum: Main Report, Engineering Appendix, Cost Appendix, cost tables and project schedule.
|  |  |  | MR 2 | Package meets the requirements within ER 1105-2-100, Exhibit G of the Planning Guidance Notebook?
|  |  |  | MR 3 | Executive Summary clearly presents the “Total Project Cost” (TPC) inflated through the project schedule. The TPC at the time the project is authorized by Congress becomes the Baseline Cost Estimate (BCE). The BCE is subject to cost limits of Section 902 Water Resources Development Act of 1986. (ER 1105-2-100)
|  |  |  | MR 4 | Reported costs for all project Features included in the TPC and reflect the estimating products.
|  |  |  | MR 5 | Report indicates the Total Project Schedule or duration (ER 1110-2-1150).
|  |  |  | MR 6 | Both required costs (budget constant dollars and fully funded) presented in the Executive Summary.
|  |  |  | MR 7 | Report makes distinction between the Federal and Non-Federal dollars.
[5 empty] | Comparative Construction Cost Estimates | REVIEW COMMENTS
|  |  |  | MR 8 | Presents the various estimate scopes, technical/design data, method of construction, and assumptions used for developing the comparative estimates included and described (ER 1110-2-1302).
|  |  |  | MR 9 | Comparative cost estimates developed at the same price level.
|  |  |  | MR 10 | TPC of each comparative estimate accurately used in the economic analysis comparisons, such as costs and benefits at the same price level (ER 1105-2-100).
|  |  |  | MR 11 | Contingencies adequate for each alternative in consideration for the alternative risks/complexity.
[5 empty] | Cost Engineering Appendix | REVIEW COMMENTS
|  |  |  | CA 1 | Summarizes the scope of the supporting documents and describes the basis of the estimate, such as method of construction, major assumptions and cost data resources used to cost the major cost elements (ER 1110-2-1302).
|  |  |  | CA 2 | Summarizes the uncertainties associated with major cost items (ER 1105-2-100, appendix E).
|  |  |  | CA 3 | Summarizes the cost risk and resulting contingency development for the recommended plan construction cost estimate. A risk analysis report is required for any project estimated to greater than $40M.
|  |  |  | CA 4 | Describes the development of the Plan construction schedule.
|  |  |  | CA 5 | Summarizes and describes the basis and development of TPC. For example, the source and basis of engineering and design (E&D) (Feature 30), construction management (Feature 31), other pertinent feature costs, the price level of the constant dollar estimates (preparation date and program year date), and basis of cost indexes for inflating the project costs (inflated dollar basis) through the project schedule.