## Instructions
Instructions:
General note: | Blue text indicates items to be populated by the user.
Black text indicates items not to be altered by the user.
PDT Involvement Worksheet:
1. Fill in the appropriate team members names and office. The list is an example and is subject to change per project.
2. Input meeting date.
Input & Calculations Worksheet:
1. Per ER 1110-1-1300, 26 Mar 93, Section 9.d.(3): "…The cost engineer has the responsibility for application of contingencies to properly weight the uncertainties associated with each major construction cost item or feature in coordination with input with other members of the project development team." Therefore, the cost engineer shall be responsible for developing this worksheet.
2. Enter the Project Name in cell C2.
3. Enter the Project Development Stage in cell C3.
4. Enter the Total Construction Contract Cost in cell D6.
5. Create the Potential Risk Areas list based on appropriately selected items from the estimate's Work Breakdown Structure (WBS). Note that the 12th item (Remaining Items) in the list accounts for all WBS items not specifically selected for analysis. This value is calculated automatically by taking the total Contract Cost and subtracting the sum of the 11 previous Items. Up to 11 Items can be entered on the appropriate numbered lines without changing the formulas and structure of this workbook. Items 12, 13 and 14 are constants and are not to be modified.
4. Select the appropriate WBS number and description from the pull down menu in column B. Note that there is no pull down tab for the Remaining Items since it likely includes items from multiple WBS items. Note that the pull down tabs for Planning, Engineering, & Design and Construction Management are from the 30 & 31 accounts only.
5. Enter the corresponding Contract Cost for the WBS Items.
Risk Register Worksheet:
The Risk Register lists each Risk Element in the blue row. Each Potential Risk Area will be listed for each Risk Element in column B:D.
A number in column A is designated to reflect each Risk Element.
1. Enter the Concerns for each Potential Risk Area for each Risk Element in column E:K.
2. Enter the PDT Discussions & Conclusions for each Potential Risk Area for each Risk Element in column L:P.
3. Select the Likelihood from the pull down menu in column Q:R.
4. Select the Impact for the pull down menu in column S:T.
WBS Risk Matrix Worksheet:
No action is needed on this worksheet. All values self-populate. The WBS Risk Matrix serves as a summary.
CWWBS Worksheet:
This worksheet is for reference only.
Input & Calculations Worksheet:
1. Return to this worksheet to see the calculated results. No other input is needed on this sheet. All calculations occur from input values from other worksheets.
2. The Total Weighted Construction Contingency will be located in cell F26. This is the value to apply to the entire Construction Contract Cost.
3. The contingency rates for the 30 and 31 accounts are located in cell F27 and F28 respectively.

## Definitions
| Term | Definition
Terminology | Risk Analysis ER 1110-2-1302, 15 Sep 08, page 19 | a. Cost risk analysis is the process of identifying and measuring the cost impact of project uncertainties on the estimated TPC. It shall be accomplished as a joint analysis between the cost engineer and the designers or appropriate PDT members that have specific knowledge and expertise on all possible project risks. (1) PDTs are required to prepare a formal cost risk analysis for all decision documents requiring Congressional authorization for projects exceeding $40 million (TPC)(see appendix B). Where cost risk analysis is required, it is anticipated that the cost risk analysis will be performed once the recommended plan is identified prior to the alternative formulation briefing milestone.
| Typical Risk Elements | Factors that can introduce risk to items listed in the Selected Work Breakdown Structure Items. The ones listed are the most typical for Civil Works Projects. These Risk Elements should be reviewed and established for each project.
| Potential Risk Areas | These are items from the estimate's Work Breakdown Structure, either broad or detailed, that are believed to contain some risk. The cost estimator defines the Work Breakdown Structure. It is recommended that the PDT select the appropriate Selected Work Breakdown Structure Items and considers all Features. Focus should be placed on the items with the significant risks. Appropriately identifying the Selected Work Breakdown Structure Items will lead to a more confident development of contingency.
Typical Risk Elements | Project Scope | • Project accomplish intent? • Level of detail in design? • Investigations remain to finalize design? • Designer confidence in scope of work? • What are assumptions made? • Opportunities for scope to change (materials, details, etc.) during design?
| Acquisition Strategy | • Established contracting plan - unclear? • Accelerated schedule or harsh weather schedule? • 8a - Small Business contractor likely? • Affect on subcontracting? • Design-build?
| Construction Complexity | • Project constructible? • Unique methods of construction? • Special construction equipment?
| Volatile Commodities | • Materials or equipment subject to fluctuation?
| Quantities | • Level of confidence in the quantities? • Possibility for increase in quantities? • Appropriate method used to calculate quantities? • Enough information to calculate the quantities? • Calculated quantities check between designer and cost estimator?
| Fabrication & Project Installed Equipment | • Unusual parts, material or equipment be manufactured and/or installed? • Confidence in supplier's ability to produce equipment? • Confidence in contractor's ability to install equipment?
| Cost Estimating Method | • Reliability of quotes or Cost Book? • Assumptions made and affect on cost estimate? • Confidence of crews and production rates? • Site accessibility, delays? • Prime & Subcontractors appropriately identified? • Markups reasonable?
| External Project Risks | • Political influences and affect on project? • Adverse weather affect project? • What can impact project schedule? • Changes to project schedule affect quality?

## PDT Involvement
Abbreviated Risk Analysis
XYZ Project
?? Estimate Level
| Meeting Date: |  | DATE
PDT Members |  | (Typical Recommended)
| Project Management: |  | NAME
| Study Manager: |  | NAME
| Contracting: |  | NAME
| Real Estate: |  | NAME
| Relocations: |  | NAME
| Engineering & Design: |  | NAME
| Cost Engineering: |  | NAME
| Construction: |  | NAME
| Operations: |  | NAME

## Input & Calculations
Abbreviated Risk Analysis
| Project (less than $40M): | XYZ Project
| Project Development Stage: | ?? Estimate Level
|  | Total Construction Contract Cost = | 12
| WBS | Potential Risk Areas | Contract Cost |  | % Contingency | $ Contingency | Total
1 | 02 RELOCATIONS | Item Name | 1 |  | 0% | 0 | 1
2 |  | Item Name | 1 |  | 0% | 0 | 1
3 | 04 01 MAIN DAM | Item Name | 1 |  | 0% | 0 | 1
4 |  | Item Name | 1 |  | 0% | 0 | 1
5 | 06 03 WILDLIFE FACILITIES AND SANCTUARIES | Item Name | 1 |  | 0% | 0 | 1
6 |  | Item Name | 1 |  | 0% | 0 | 1
7 | 07 05 TAILRACE | Item Name | 1 |  | 0% | 0 | 1 | 02 RELOCATIONS
8 | 08 ROADS, RAILROADS, AND BRIDGES | Item Name | 1 |  | 0% | 0 | 1 | 02 01 ROADS, Construction Activities
9 | 09 CHANNELS AND CANALS (Except Navigation Ports and Harbors) | Item Name | 1 |  | 0% | 0 | 1 | 02 02 RAILROADS, Construction Activities
10 | 14 RECREATION FACILITIES | Item Name | 1 |  | 0% | 0 | 1 | 02 03 CEMETERIES, UTILITIES, AND STRUCTURES, Construction Activities
11 |  | Item Name | 1 |  | 0% | 0 | 1 | 03 RESERVOIRS
12 |  | Remaining Construction Items | 1 | 9.091% | 0% | 0 | 1 | 04 DAMS
13 | 30 PLANNING, ENGINEERING, AND DESIGN | Planning, Engineering, & Design | 0 |  | 0% | 0 | 0 | 04 01 MAIN DAM
14 | 31 CONSTRUCTION MANAGEMENT | Construction Management | 0 |  | 0% | 0 | 0 | 04 02 SPILLWAY
04 03 OUTLET WORKS
|  | Totals | [5 empty] | 04 04 POWER INTAKE WORKS
|  | Total Construction Estimate | 12 |  | 0% | 0 | 12 | 04 05 AUXILIARY DAMS
|  | Total Planning, Engineering & Design | 0 |  | 0% | 0 | 0 | 04 06 MUNICIPAL AND INDUSTRIAL WATER DELIVERY FACILITIES
|  | Total Construction Management | 0 |  | 0% | 0 | 0 | 05 LOCKS
|  | Total | 12 |  |  | 0 | 12 | 06 FISH AND WILDLIFE FACILITIES
06 01 FISH FACILITIES AT DAMS
06 02 FISH HATCHERY, (Including Trapping and Release Facilities)
06 03 WILDLIFE FACILITIES AND SANCTUARIES
07 POWER PLANT
07 01 POWERHOUSE
07 02 TURBINES AND GENERATORS
07 03 ACCESSORY ELECTRICAL EQUIPMENT
07 04 MISCELLANEOUS POWER PLANT EQUIPMENT
07 05 TAILRACE
07 06 SWITCHYARD
08 ROADS, RAILROADS, AND BRIDGES
08 01 ROADS
08 02 RAILROADS
09 CHANNELS AND CANALS (Except Navigation Ports and Harbors)
09 01 CHANNELS
09 02 CANALS
10 BREAKWATERS AND SEAWALLS
11 LEVEES AND FLOODWALLS
11 01 LEVEES
11 02 FLOODWALLS
12 NAVIGATION, PORTS AND HARBORS
12 01 PORTS
12 02 HARBORS
13 PUMPING PLANT
14 RECREATION FACILITIES
15 FLOODWAY CONTROL AND DIVERSION STRUCTURES
16 BANK STABILIZATION
17 BEACH REPLENISHMENT
18 CULTURAL RESOURCE PRESERVATION
19 BUILDINGS, GROUNDS, AND UTILITIES
20 PERMANENT OPERATING EQUIPMENT
30 PLANNING, ENGINEERING, AND DESIGN
30 11 PROJECT COOPERATION AGREEMENT
30 12 PROJECT MANAGEMENT PLAN
30 18 GENERAL REEVALUATION REPORT (GRR)
30 19 LIMITED REEVALUATION REPORT (LRR)
30 20 PROJECT DESIGN MEMORANDUM
30 21 FEATURE DESIGN MEMORANDUM
30 23 CONSTRUCTION CONTRACT(S) DOCUMENTS
30 24 VALUE ENGINEERING ANALYSIS DOCUMENTS
30 25 PROJECT OR FUNCTIONAL ELEMENT CLOSEOUT
30 26 PROGRAMS AND PROJECT MANAGEMENT DOCUMENTS
31 CONSTRUCTION MANAGEMENT
31 12 PROJECT MANAGEMENT PLAN
31 23 CONSTRUCTION CONTRACT(S) DOCUMENTS
31 26 PROGRAMS AND PROJECT MANAGEMENT DOCUMENTS
32 HAZARDOUS AND TOXIC WASTE
32 01 MOB, DEMOB & PREPARATORY WORK
32 02 SYSTEMS STARTUP/OPERATIONS/MAINTENANCE
32 03 INSTITUTIONAL ACTIONS
32 04 SURFACE WATER CONTROL
32 05 COLLECTION & INJECTION OF GROUND WATER
32 06 COLLECTION & DISPOSAL OF WASTES
32 07 CONTAIN & RESTORE CONTAMINATED GROUND WATER
32 08 CONTAINMENT FOR WASTES
32 10 TREAT-WASTES/CONTAMINATED SOIL & WATER
32 11 AIR POLLUTION AND LANDFILL GAS CONTROL
32 12 INNOVATIVE TECHNOLOGIES
32 13 SUPPORTING FACILITIES
32 14 PRIME CONTRACTOR'S INDIRECT COST

## Risk Register
XYZ Project
?? Estimate Level | [7 empty] | Risk Level
Abbreviated Risk Analysis
[6 empty] | Very Likely | 2 | 3 | 4 | 5 | 5
|  |  | Meeting Date: | DATE |  | Likely | 1 | 2 | 4 | 5 | 5
[6 empty] | Unlikely | 0 | 1 | 3 | 3 | 4
[6 empty] | Very Unlikely | 0 | 0 | 1 | 2 | 4
[7 empty] | Negligible | Marginal | Significant | Critical | Crisis
Risk Element | Potential Risk Areas | Concerns |  |  | PDT Discussions & Conclusions (Include logic & justification for choice of Likelihood & Impact) |  | Likelihood |  | Impact |  | Risk Level | Pull Down Menus
[12 empty] | WBS Item |  |  |  |  | Likelihood |  | Impact
Project Scope | [11 empty] | Item Name |  |  |  |  | Very LIKELY |  | Negligible
PS-1 | Item Name | Insert concern(s) here. |  |  | Insert discussions and conclusions here. Include logic and justification for choice of Likelihood & Impact. |  | Very Unlikely |  | Negligible |  | 0 | Item Name |  |  |  |  | LIKELY |  | Marginal
PS-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name |  |  |  |  | Unlikely |  | Significant
PS-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name |  |  |  |  | Very Unlikely |  | Critical
PS-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name | [6 empty] | Crisis
PS-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name
PS-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name
PS-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name
PS-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name
PS-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name
PS-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Item Name
PS-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Remaining Construction Items
PS-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Planning, Engineering, & Design
PS-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0 | Construction Management
PS-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0
Acquisition Strategy
AS-1 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 |  | Very Likely | 2 | 3 | 4 | 5 | 5
AS-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 |  | Likely | 1 | 2 | 4 | 5 | 5
AS-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 |  | Unlikely | 0 | 1 | 3 | 3 | 4
AS-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 |  | Very Unlikely | 0 | 0 | 1 | 2 | 4
AS-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0 |  |  | Negligible | Marginal | Significant | Critical | Crisis
AS-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0
AS-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0
Construction Complexity
CC-1 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0
CC-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0
Volatile Commodities
VC-1 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0
VC-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0
Quantities
Q-1 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0
Q-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0
Fabrication & Project Installed Equipment
FI-1 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0
FI-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0
Cost Estimating Method
CE-1 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0
CE-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0
External Project Risks
EX-1 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-2 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-3 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-4 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-5 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-6 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-7 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-8 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-9 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-10 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-11 | Item Name | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-12 | Remaining Construction Items | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-13 | Planning, Engineering, & Design | [5 empty] | Very Unlikely |  | Negligible |  | 0
EX-14 | Construction Management | [5 empty] | Very Unlikely |  | Negligible |  | 0

## WBS Risk Matrix
XYZ Project
?? Estimate Level
Abbreviated Risk Analysis
Potential Risk Areas
|  |  | Item Name | Item Name | Item Name | Item Name | Item Name | Item Name | Item Name | Item Name | Item Name | Item Name | Item Name | Remaining Construction Items | Planning, Engineering, & Design | Construction Management
Typical Risk Elements | Project Scope |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Acquisition Strategy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction Complexity |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Volatile Commodities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Quantities |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fabrication & Project Installed Equipment |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Cost Estimating Method |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| External Project Risks |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Weighted Summation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Weighted % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[11 empty] | Risk Level | Weight
[11 empty] | 0 | 0
[11 empty] | 1 | 1
[11 empty] | 2 | 2
[11 empty] | 3 | 3
[11 empty] | 4 | 4
[11 empty] | 5 | 6

## CWWBS
Civil Works Work Breakdown Structure | (CWWBS)
Reference ETL 110-2-573 03 Sep 08, Table 2-1.
01 LANDS AND DAMAGES
01 18 GENERAL REVALUATION REPORT (GRR)
01 19 LIMITED REVALUATION REPORT (LRR)
01 20 PROJECT DESIGN MEMORANDUM
01 21 FEATURE DESIGN MEMORANDUM
01 23 CONSTRUCTION CONTRACT(S) DOCUMENTS
02 RELOCATIONS
02 01 ROADS, Construction Activities
02 02 RAILROADS, Construction Activities
02 03 CEMETERIES, UTILITIES, AND STRUCTURES, Construction Activities
03 RESERVOIRS
04 DAMS
04 01 MAIN DAM
04 02 SPILLWAY
04 03 OUTLET WORKS
04 04 POWER INTAKE WORKS
04 05 AUXILIARY DAMS
04 06 MUNICIPAL AND INDUSTRIAL WATER DELIVERY FACILITIES
05 LOCKS
06 FISH AND WILDLIFE FACILITIES
06 01 FISH FACILITIES AT DAMS
06 02 FISH HATCHERY, (Including Trapping and Release Facilities)
06 03 WILDLIFE FACILITIES AND SANCTUARIES
07 POWER PLANT
07 01 POWERHOUSE
07 02 TURBINES AND GENERATORS
07 03 ACCESSORY ELECTRICAL EQUIPMENT
07 04 MISCELLANEOUS POWER PLANT EQUIPMENT
07 05 TAILRACE
07 06 SWITCHYARD
08 ROADS, RAILROADS, AND BRIDGES
08 01 ROADS
08 02 RAILROADS
09 CHANNELS AND CANALS (Except Navigation Ports and Harbors)
09 01 CHANNELS
09 02 CANALS
10 BREAKWATERS AND SEAWALLS
11 LEVEES AND FLOODWALLS
11 01 LEVEES
11 02 FLOODWALLS
12 NAVIGATION, PORTS AND HARBORS
12 01 PORTS
12 02 HARBORS
13 PUMPING PLANT
14 RECREATION FACILITIES
15 FLOODWAY CONTROL AND DIVERSION STRUCTURES
16 BANK STABILIZATION
17 BEACH REPLENISHMENT
18 CULTURAL RESOURCE PRESERVATION
19 BUILDINGS, GROUNDS, AND UTILITIES
20 PERMANENT OPERATING EQUIPMENT
30 PLANNING, ENGINEERING, AND DESIGN
30 11 PROJECT COOPERATION AGREEMENT
30 12 PROJECT MANAGEMENT PLAN
30 18 GENERAL REEVALUATION REPORT (GRR)
30 19 LIMITED REEVALUATION REPORT (LRR)
30 20 PROJECT DESIGN MEMORANDUM
30 21 FEATURE DESIGN MEMORANDUM
30 23 CONSTRUCTION CONTRACT(S) DOCUMENTS
30 24 VALUE ENGINEERING ANALYSIS DOCUMENTS
30 25 PROJECT OR FUNCTIONAL ELEMENT CLOSEOUT
30 26 PROGRAMS AND PROJECT MANAGEMENT DOCUMENTS
31 CONSTRUCTION MANAGEMENT
31 12 PROJECT MANAGEMENT PLAN
31 23 CONSTRUCTION CONTRACT(S) DOCUMENTS
31 26 PROGRAMS AND PROJECT MANAGEMENT DOCUMENTS
32 HAZARDOUS AND TOXIC WASTE
32 01 MOB, DEMOB & PREPARATORY WORK
32 02 SYSTEMS STARTUP/OPERATIONS/MAINTENANCE
32 03 INSTITUTIONAL ACTIONS
32 04 SURFACE WATER CONTROL
32 05 COLLECTION & INJECTION OF GROUND WATER
32 06 COLLECTION & DISPOSAL OF WASTES
32 07 CONTAIN & RESTORE CONTAMINATED GROUND WATER
32 08 CONTAINMENT FOR WASTES
32 10 TREAT-WASTES/CONTAMINATED SOIL & WATER
32 11 AIR POLLUTION AND LANDFILL GAS CONTROL
32 12 INNOVATIVE TECHNOLOGIES
32 13 SUPPORTING FACILITIES
32 14 PRIME CONTRACTOR'S INDIRECT COST